## Export
SAP Link | Financial Year | Plant Section | MRSB Type | Capital Allocation | Notification No | Notification Name | FLOC | Asset Class | Program | Program 2 | Scope Subset | Scope Quantity | Scope Unit | FY Estimate | System | Start Station | End Station | Notif: Linear Length | Notif: Length Unit | Notif: Marker St | Notif: Dist.St.Mrk. | Notif: Marker End | Notif: Dist.End Mrk. | Notif: Dist.Mrk.Unit | Rail Quantity | Sleeper Quantity | Rail KM | Track KM | Start KM | End KM | Latest Renewal Date | Road | Rail | Proposed Design | Renewal Design | Future Condition | Location Criticality | Performance Impact | Criticality Index | CRA Modifier | CRA Index | PCR Number | Baseline date | RIG Submission Date | RIG Table Category | Design Category | DURATION-Likelihood of Change | TIME-Likelihood of Change | SCOPE-Likelihood of Change | COST-Likelihood of Change | Notif. Mani System Status Description | FULL_USER_STATUS | FY23 IN / OUT | Notif. Required End Date | Description
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093508&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093508 | Access Point DESIGN | AP100723 | CIVIL | ACCESS POINTS | RENEWAL | DESIGN | 1 | SITE | 30000 | Blackwater | BOONAL | BLACKWATER | 0 | KM | BW03ML187 | 0.5629 | BW03ML187 | 0.5629 | KM |  |  | 187.565 | 187.565 | 187.565 | 187.565 | 2023-06-30 |  |  | BESPOKE DESIGN | BESPOKE DESIGN |  |  | 0.5 | 0.1 | 1 | 100 | 5342 | 2024-06-30 |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20231125 | 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default this design flows to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed renewal out to FY26. 31 March- PCR 5342, moved to FY23 for design and construction in FY25. Locality map was added. No condition assessment and detail design is available. Detail design to be completed and submitted to TMR for approval. There is short stacking issues at this crossing. So road also to be upgraded to include slip lanes etc.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093520&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093520 | *Access Point DESIGN | AP100724 | CIVIL | ACCESS POINTS | UPGRADE | DESIGN | 1 | SITE | 30000 | Blackwater | BLACKWATER | SAGITARIUS | 0 | KM | BW03ML189 | 0.6169 | BW03ML189 | 0.6169 | KM |  |  |  |  | 189.617 | 189.617 | 2025-06-30 | CAPRICORN HIGHWAY |  | BESPOKE DESIGN | BESPOKE DESIGN |  |  | 0.5 | 0.1 | 1 | 100 | 5342 | 2024-06-30 |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240923 | 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default this design flows to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed renewal out to FY26. 31 MARCH - PCR 5342, MOVED TO FY23 DESIGN FOR BETTER DESIGN AND PLANNING FOR CONSTRUCTION IN FY25. Detail design to be completed and to be sent to TMR for approval with the form F5083.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093509&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093509 | Access Point DESIGN | AP100722 | CIVIL | ACCESS POINTS | UPGRADE | DESIGN | 1 | SITE | 30000 | Blackwater | BOONAL | BLACKWATER | 0 | KM | BW46YR189 | 0.4 | BW46YR189 | 0.4 | KM |  |  | 189.4 | 189.4 | 189.4 | 189.4 | 2025-06-30 |  |  | BESPOKE DESIGN | BESPOKE DESIGN |  |  | 0.5 | 0.1 | 1 | 100 | 5342 | 2024-06-30 |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240523 | 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default this design flows to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed renewal out to FY26. PCR 5342- MOVED TO FY23 DESIGN FOR BETTER DESIGN AND PLANNING. CONSTRUCTION IS IN FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051939&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000051939 | Corridor Access Points Renewal/Upgrade | GA | CIVIL | ACCESS POINTS | UPGRADE | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 4.5 |  |  |  | 22.5 |  | 2021-03-31 | 2021-10-05 | Access Points & Rds | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:01:26 AUSQLD Tracy Holmes (R870040) * No design complete
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068825&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068825 | Access Roads Reactive | BW | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 375000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Access Points & Rds | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068826&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068826 | Access Roads Reactive | GA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 305000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Access Points & Rds | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068901&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068901 | Access Roads Reactive | MA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 175000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Access Points & Rds | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068828&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068828 | Access Roads Reactive | NL | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 235000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Access Points & Rds | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052464&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052464 | C01 BW ALDOGA UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.746 | KM | 809540 | Blackwater | ALDOGA | ALDOGA | 1.7459 | KM | BW01ML553 | 0.4109 | BW01ML555 | 0.19 | KM |  |  |  |  | 553.411 | 555.19 | 2023-06-30 | UP |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:53:43 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 19.10.2021 Tim Griffin (r878533) Adjust km's to align with u/c completed in FY20 (Finish moved from 555km696m to 555.190km).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126465&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000126465 | C14 U/C ALDOGA Up 553.411km. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.746 | KM | 809540 | Blackwater | ALDOGA | ALDOGA | 0.094 | KM | BW01ML553 | 0.4109 | BW01ML553 | 0.505 | KM |  |  |  |  | 553.411 | 555.19 | 2023-06-30 | UP |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification in process | NWSC | FY23 IN | 20240919 | * 26.09.2023 - LVL 1 Approved ALEY R889072 31.03.2021 18:53:43 AUSQLD Tracy Holmes (R870040) Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 19.10.2021 Tim Griffin (r878533) Adjust km's to align with u/c completed in FY20 (Finish moved from 555km696m to 555.190km). End km adjusted to be before the turnout at 553.505km. Residual Scope from RM902 - 553.411 - 553.600 New Notification raised due to 2000052464 not completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074473&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074473 | C01 BW ALDOGA DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.043 | KM | 947300 | Blackwater | ALDOGA | ALDOGA | 2.043 | KM | BW02ML553 | 0.7369 | BW02ML555 | 0.8159 | KM |  |  |  |  | 553.737 | 555.816 | 2023-06-30 | DN |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:31:12 AUSQLD Tracy Holmes (R870040) * Turnouts at * 31.03.2021 18:43:29 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:50 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074448&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074448 | C01 BW MT LARCOM DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.472 | KM | 1609854 | Blackwater | ALDOGA | MT LARCOM | 3.4719 | KM | BW02ML559 | 0.7239 | BW02ML563 | 0.2 | KM |  |  |  |  | 559.724 | 563.2 | 2023-06-30 | DN |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 31.03.2021 18:43:32 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052479&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052479 | C01 BLACKWATER U/C. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.898 | KM | 880020 | Blackwater | AMBROSE | RAGLAN | 1.8979 | KM | BW02ML575 | 0.9 | BW02ML577 | 0.8 | KM |  |  |  |  | 575.9 | 577.8 | 2022-06-30 |  |  |  |  | 3 | 4.9 |  |  |  | 14.7 | 5676 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20240630 | End km adjusted to not go into turnout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052480&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052480 | C01 BLACKWATER U/C. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.105 | KM | 976002 | Blackwater | AMBROSE | RAGLAN | 2.1049 | KM | BW02ML579 | 0.8 | BW02ML581 | 0.9 | KM |  |  |  |  | 579.8 | 581.9 | 2022-06-30 | DOWN |  |  |  | 3.5 | 4.9 |  |  |  | 14.35 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052472&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052472 | C01 BW MIDGEE UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.338 | KM | 620405 | Blackwater | ARCHER | MIDGEE | 1.338 | KM | BW01ML617 | 0.466 | BW01ML618 | 0.8 | KM |  |  |  |  | 617.466 | 618.8 | 2023-06-30 | UP |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:53:56 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 19.10.2021 Tim Griffin (r878533) Mainline high production RM902 u/c segmented by Bridge point asset on NCL and linked to notification 2000086041.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074456&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074456 | C01 BW MIDGEE DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.04 | KM | 482228 | Blackwater | ARCHER | MIDGEE | 1.04 | KM | BW02ML617 | 0.765 | BW02ML618 | 0.8 | KM |  |  |  |  | 617.765 | 618.8 | 2023-06-30 | DN |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20250630 | * 22.03.2021 10:27:01 AUSQLD Tracy Holmes (R870040) * just outside is BOB'S CREEK AT 618.850KM * 31.03.2021 18:43:44 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:47 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086032&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000086032 | C01 BW MIDGEE DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.402 | KM | 186399 | Blackwater | ARCHER | MIDGEE | 0.402 | KM | BW02ML618 | 0.9 | BW02ML619 | 0.2999 | KM |  |  |  |  | 618.9 | 619.3 | 2023-06-30 | DOWN |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20250630 | 19.10.2021 Tim Griffin (r878533) High production ballast u/c segemented for Bobs Creek point asset, linked to notification 2000074456.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086041&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000086041 | C01 BLACKWATER ML UC | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.403 | KM | 186863 | Blackwater | ARCHER | MIDGEE | 0.403 | KM | BW01ML618 | 0.9 | BW01ML619 | 0.2999 | KM |  |  |  |  | 618.9 | 619.3 | 2023-06-30 | UP |  |  |  | 4 |  |  |  |  | 16 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) Mainline high production RM902 u/c segmented due to bridge point asset and linked to notification 2000052472.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074537&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074537 | C01 GA HATFEILD UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.755 | KM | 1277394 | Goonyella | BLACK MOUNTAIN | HATFIELD | 2.7549 | KM | GA02ML42 | 0.5999 | GA02ML45 | 0.3539 | KM |  |  |  |  | 42.6 | 45.354 | 2023-06-30 | UP |  |  |  | 4.5 | 4.4 | 3 | 4 | 1 | 19.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | HIGH | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:45:20 AUSQLD Tracy Holmes (R870040) * Continue from FY22 scope and coordinate with BM TO 8C/D and 12A/B and cut all the way through to clean section up * 12.04.2021 16:23:12 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Renewal reduced to 40.116km to 43.000km (Up Rd) at Black Mountain for FY23 (Check prior to Aug2021 Phase II access workshop),as investigating substituting doing 43.000km -45.354km in FY21 due to Notification 2000055883 not being undertaken due to Closure restrictions with NCL traffic (as advise by Jane Livingston in April 2021). Reduce from 40.200 to 41.100km and skip section u/c in FY18 and join 42.600km to 45.354km, linked to notification 20000859XX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074585&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074585 | C01 GA BLAIR ATHOL. | GA-05ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.099 | KM | 973266 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 2.099 | KM | GA05ML108 | 0.2999 | GA05ML110 | 0.4 | KM |  |  |  |  | 108.3 | 110.4 | 2023-06-30 | BLOOP |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:57:18 AUSQLD Tracy Holmes (R870040) * Highly fouled and Rough track. * 31.03.2021 18:44:27 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:30 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074508&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074508 | C01 GA BALOOK DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.426 | KM | 661162 | Goonyella | BOLINGBROKE | BALOOK | 1.4259 | KM | GA01ML64 | 0.4799 | GA01ML65 | 0.908 | KM |  |  |  |  | 64.48 | 65.908 | 2023-06-30 | DN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:38:28 AUSQLD Tracy Holmes (R870040) * 64.480 end of bridge has near D7 twists * 31.03.2021 18:44:39 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:00 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * 19.10.2021 Tim Griffin (r878533) High production mainline ballast u/c segmented, linked to notification 2000085980. Critical section and high tonnage usage.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085980&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085980 | C01 GA BALOOK DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.353 | KM | 627314 | Goonyella | BOLINGBROKE | BALOOK | 1.3529 | KM | GA01ML65 | 0.9499 | GA01ML67 | 0.2999 | KM |  |  |  |  | 65.95 | 67.3 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) High production mainline ballast u/c segmented and linked to notification 2000074508.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074515&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074515 | C01 GA MINDI DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 6.743 | KM | 3126600 | Goonyella | BRAESIDE | MINDI | 6.743 | KM | GA01ML110 | 0.1749 | GA01ML116 | 0.92 | KM |  |  |  |  | 110.175 | 116.92 | 2023-06-30 | DN |  |  |  | 4 | 4.4 | 2 | 4 | 1 | 16 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:39:32 AUSQLD Tracy Holmes (R870040) * High fouling, top near D7, moderate twists. 2km section; 5km section 112.92 - 116.92 - FY24 section. (Maybe able to separate into 2km section with the remainder in Fy25) * 12.04.2021 16:23:04 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074589&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074589 | C01 NL ALMOOLA. | NL-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.218 | KM | 564717 | Newlands | BRIABA | ALMOOLA | 1.2179 | KM | NL03ML64 | 0.8319 | NL03ML66 | 0.05 | KM |  |  |  |  | 64.832 | 66.05 | 2023-06-30 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:58:33 AUSQLD Tracy Holmes (R870040) * Highly to severely fouled, geometry okay, a bit rough * 31.03.2021 18:45:43 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:33 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk Melissa Durnsford 13/07/2022: PCR # 5413 Created to transfer the notification over to be executed by the C14 product code. Change Board decision due 19/07/2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074588&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074588 | C01 NL ALMOOLA | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.45 | KM | 208656 | Newlands | BRIABA | ALMOOLA | 0.45 | KM | NL01ML71 | 0.4 | NL01ML71 | 0.8499 | KM |  |  |  |  | 71.4 | 71.85 | 2025-06-30 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Outstanding notification | RRIG INIF | FY23 IN | 20250630 | * 22.03.2021 10:57:56 AUSQLD Tracy Holmes (R870040) * Highly fouled after 71.4, top okay, cut out at points * 31.03.2021 18:45:53 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:31 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk Melissa Durnsford 13/07/2022: PCR # 5414 created to transfer notification over to be executed under the C14 product code. Change Board decision due on 19/07/2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074592&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074592 | C01 NL COLLINSVILLE. | NL-06PL | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.797 | KM | 369553 | Newlands | COLLINSVILLE | COLLINSVILLE | 0.797 | KM | NL06PL75 | 0.6029 | NL06PL76 | 0.4 | KM |  |  |  |  | 75.603 | 76.4 | 2023-06-30 |  |  |  |  | 4 | 2.5 |  |  |  | 10 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:59:09 AUSQLD Tracy Holmes (R870040) * Highly fouled, geometry a bit rough * 31.03.2021 18:46:10 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:34 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk Melissa Durnsford 13/07/2022: PCR # 5415 created to transfer notification to C14. Change Board Decision Due on 19/07/2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000106160&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000106160 | C01 NL MACNAUGHTON JCT.* | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.55 | KM | 533186 | Newlands | COLLINSVILLE | MACNAUGHTON JCT | 0.55 | KM | NL01ML76 | 0.6019 | NL01ML77 | 0.1499 | KM |  |  |  |  | 76.602 | 77.15 | 2023-06-30 |  |  |  |  | 4 | 2.5 |  |  |  | 10 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Outstanding notification | NWSC | FY23 IN | 20240511 | 22.03.2021 10:58:33 AUSQLD Tracy Holmes (R870040) Highly fouled, geometry fairly rough, cut through crossing and signals, out at pts unless also scoped 12.04.2021 16:23:33 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk Melissa Durnsford 13/07/2022: PCR Required to split into two following engineering review. 76.602km to 77.150km <(>&<)> 77.250km to 77.740km. Will reduce Newlands RIG Approved Scope by 100m due to turnout and level crossing. Lachlan Crow 13/10/2022 Split notification from 2000074590 as per PCR 5417. Reprioritised by Patrick Sanderson *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074590&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074590 | C01 NL MACNAUGHTON JCT. | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.5 | KM | 533186 | Newlands | COLLINSVILLE | MACNAUGHTON JCT | 0.5 | KM | NL01ML77 | 0.25 | NL01ML77 | 0.75 | KM |  |  |  |  | 77.25 | 77.75 | 2023-06-30 |  |  |  |  | 4 | 2.5 |  |  |  | 10 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:58:33 AUSQLD Tracy Holmes (R870040) * Highly fouled, geometry fairly rough, cut through crossing and signals, out at pts unless also scoped * 12.04.2021 16:23:33 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk Melissa Durnsford 13/07/2022: PCR Required to split into two following engineering review. 76.602km to 77.150km <(>&<)> 77.250km to 77.740km. Will reduce Newlands RIG Approved Scope by 100m due to turnout and level crossing. Lachlan Crow 13/10/2022: Split notification (2000106160) has now been created as per PCR 5417.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074562&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074562 | C01 GA COPPABELLA. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.755 | KM | 1277394 | Goonyella | COPPABELLA | COPPABELLA | 2.7549 | KM | GA03ML1 | 0.05 | GA03ML3 | 0.8469 | KM |  |  |  |  | 1.05 | 3.847 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 10:51:46 AUSQLD Tracy Holmes (R870040) * Ballast defect and rough geometry, highly fouled * 31.03.2021 18:46:35 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:21 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000117793&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000117793 | C01 GA COPPABELLA. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.755 | KM | 1277394 | Goonyella | COPPABELLA | COPPABELLA | 153.918 | KM | GA03ML1 | 0.005 | GA03ML154 | 0.9979 | KM |  |  |  |  | 1.05 | 3.847 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC | FY23 IN | 20231031 | 22.03.2021 10:51:46 AUSQLD Tracy Holmes (R870040) Ballast defect and rough geometry, highly fouled 31.03.2021 18:46:35 AUSQLD Tracy Holmes (R870040) to overall program low risk 12.04.2021 16:23:21 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074483&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074483 | C01 BW WALLAROO UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.592 | KM | 1665542 | Blackwater | DUARINGA | WALLAROO | 3.592 | KM | BW04ML105 | 0.6999 | BW04ML109 | 0.25 | KM |  |  |  |  | 105.7 | 109.25 | 2023-06-30 | UP |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:47:35 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074450&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074450 | C01 BW YAN YAN. | BW-08ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.775 | KM | 1286668 | Blackwater | FAIRHILL | YAN YAN | 2.7749 | KM | BW08ML47 | 0.1 | BW08ML49 | 0.878 | KM |  |  |  |  | 47.1 | 49.878 | 2023-06-30 | MAIN |  |  |  | 4 | 1.1 | 2 | 3 | 1 | 10 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:25:52 AUSQLD Tracy Holmes (R870040) * INCLUDES TURNOUT 12A/B FOR YAN YAN PASSING LOOP (bw-15pl) BUT STOPS BEFORE NEXT TURNOUT INTO YAN YAN PASSING LOOP * 12.04.2021 16:22:46 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074570&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074570 | C01 GA OAKY CREEK | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.481 | KM | 1614027 | Goonyella | GERMAN CREEK | OAKY CREEK | 3.4809 | KM | GA03ML132 | 0.0539 | GA03ML135 | 0.539 | KM |  |  |  |  | 132.054 | 135.539 | 2023-06-30 | MAIN |  |  |  | 4 | 1.1 |  |  |  | 4.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:53:58 AUSQLD Tracy Holmes (R870040) * Highly fouled, geometry good, dip near 134.25 only, fouling starts just before next section * 12.04.2021 16:23:24 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074571&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074571 | C01 GA OAKY CREEK | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.715 | KM | 331485 | Goonyella | GERMAN CREEK | OAKY CREEK | 0.7149 | KM | GA03ML136 | 0.2999 | GA03ML137 | 0.012 | KM |  |  |  |  | 136.3 | 137.012 | 2023-06-30 | MAIN |  |  |  | 4 | 1.1 |  |  |  | 4.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:54:04 AUSQLD Tracy Holmes (R870040) * Cut through level crossing and bridge ends, severely to highly fouled with moderate twist and top * 12.04.2021 16:23:25 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Actual undercut 345m due to bridge in the middle of the notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074503&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074503 | C01 GA BOLINGBROKE DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.917 | KM | 888876 | Goonyella | HATFIELD | BOLINGBROKE | 1.917 | KM | GA01ML50 | 0.5999 | GA01ML52 | 0.5 | KM |  |  |  |  | 50.6 | 52.58 | 2023-06-30 | DN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:37:34 AUSQLD Tracy Holmes (R870040) * Hatfield 12CD (in Fy22 T/O UC Program - 49.935) needs undercutting through signal to signal, otherwise low fouling until lx at 50.8 which needs to be cut * 12.04.2021 16:23:00 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074506&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074506 | C01 GA BOLINGBROKE DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.001 | KM | 464098 | Goonyella | HATFIELD | BOLINGBROKE | 1.0009 | KM | GA01ML55 | 0.925 | GA01ML56 | 0.925 | KM |  |  |  |  | 55.925 | 56.925 | 2023-06-30 | DN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:38:05 AUSQLD Tracy Holmes (R870040) * Fouling considerably high, top not too bad except at 56.4 * 31.03.2021 18:48:25 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:57 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074502&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074502 | C01 GA HATFEILD DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.204 | KM | 558225 | Goonyella | HATFIELD | HATFIELD | 1.2039 | KM | GA01ML47 | 0.4969 | GA01ML48 | 0.6999 | KM |  |  |  |  | 47.497 | 48.7 | 2023-06-30 | DN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:37:29 AUSQLD Tracy Holmes (R870040) * Cut from Hatfield 8AB (TO000449 - 47.443km) through signal, then continue. Geometry fairly rough. * 12.04.2021 16:22:59 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074563&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074563 | C01 GA INGSDON | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.426 | KM | 661162 | Goonyella | INGSDON | INGSDON | 1.4259 | KM | GA03ML10 | 0.9849 | GA03ML12 | 0.4 | KM |  |  |  |  | 10.985 | 12.4 | 2023-06-30 | UP |  |  |  | 4 | 2.8 |  |  |  | 11.2 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:52:16 AUSQLD Tracy Holmes (R870040) * Cut in after turnout Ingsdon 7A/B, cut through signal, all highly to severely fouled, top okay, ballast defect at high km end. Tie into Fy22 scope. * 12.04.2021 16:23:21 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085923&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085923 | C01 GA INGSDON | GA-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.231 | KM | 570791 | Goonyella | INGSDON | INGSDON | 1.231 | KM | GA04ML11 | 0.2999 | GA04ML12 | 0.5 | KM |  |  |  |  | 11.3 | 12.5 | 2023-06-30 | DOWN |  |  |  | 4 | 2.8 |  |  |  | 11.2 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) High production mainline RM902 u/c linked to notification 2000074577 due to point asset t/o interface.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074488&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074488 | C01 GA JILALAN DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.331 | KM | 1080794 | Goonyella | JILALAN | JILALAN | 2.3309 | KM | GA01ML17 | 0.636 | GA01ML19 | 0.9699 | KM |  |  |  |  | 17.636 | 19.97 | 2023-06-30 | DN |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:35:05 AUSQLD Tracy Holmes (R870040) * From turnout JB48AB to signal on severely fouled, geometry moderate. Turnouts heavily fouled at D1 <(>&<)> D7 limits need undercutting * 12.04.2021 16:22:54 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * 19.10.2021 Tim Griffin(r878533) Mainline high production u/c RM902 segmented and linked to notification 20000859XX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085976&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085976 | C01 GA JILALAN DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.23 | KM | 1033962 | Goonyella | JILALAN | JILALAN | 2.2299 | KM | GA01ML20 | 0.26 | GA01ML22 | 0.4879 | KM |  |  |  |  | 20.26 | 22.488 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20250630 | 19.10.2021 Tim Griffin (r878533) Mainline high production u/c RM902 and linked to notification 2000074488 due to segmentation. Wily ck at 21.540km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074493&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074493 | C01 GA YUKAN DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.176 | KM | 1008969 | Goonyella | JILALAN | YUKAN | 2.176 | KM | GA01ML25 | 0.462 | GA01ML27 | 0.635 | KM |  |  |  |  | 25.462 | 27.635 | 2023-06-30 | DN |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:35:41 AUSQLD Tracy Holmes (R870040) * 23.54 to 24.253 appears to be missed in FY21, SPM says 23.54 to 25.61, BCD program in FY21 from 24.253 to 25.614 - all completed * 12.04.2021 16:22:55 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * upon Luke Brownsey recommendation and Tim Griffin approval 2 July 2021.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074460&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074460 | C01 BW WARREN DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.66 | KM | 769664 | Blackwater | KABRA | WARREN | 1.6599 | KM | BW03ML21 | 0.45 | BW03ML23 | 0.1059 | KM |  |  |  |  | 21.45 | 23.106 | 2023-06-30 | DN |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:49:30 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074453&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074453 | C01 BW STARLEE. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.39 | KM | 1571878 | Blackwater | MEMOOLOO | STARLEE | 3.39 | KM | BW06ML57 | 0.4 | BW06ML60 | 0.8 | KM |  |  |  |  | 57.4 | 60.8 | 2023-06-30 | MAIN |  |  |  | 4 | 2.3 |  |  |  | 9.2 | 5678 | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20260630 | * 31.03.2021 18:50:09 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074454&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074454 | C01 BW STARLEE. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.627 | KM | 1218043 | Blackwater | MEMOOLOO | STARLEE | 2.6269 | KM | BW06ML69 | 0.45 | BW06ML72 | 0.0779 | KM |  |  |  |  | 69.45 | 72.078 | 2023-06-30 | MAIN |  |  |  | 4 | 2.3 |  |  |  | 9.2 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:50:11 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074569&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074569 | C01 GA BUNDOORA. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.745 | KM | 809123 | Goonyella | MIDDLEMOUNT JCT | BUNDOORA | 1.745 | KM | GA03ML125 | 0.5809 | GA03ML127 | 0.324 | KM |  |  |  |  | 125.581 | 127.324 | 2023-06-30 | MAIN |  |  |  | 4 | 1.4 |  |  |  | 5.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:53:33 AUSQLD Tracy Holmes (R870040) * Highly fouled, geometry okay apart from level crossing which is near D7 top; * 12.04.2021 16:23:23 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074600&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074600 | C01 GA SOUTH WALKER DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.718 | KM | 1260238 | Goonyella | MINDI | SOUTH WALKER | 2.7179 | KM | GA01ML123 | 0.047 | GA01ML125 | 0.757 | KM |  |  |  |  | 123.047 | 125.757 | 2023-06-30 | DN |  |  |  | 4 | 4.7 |  |  |  | 18.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:01:11 AUSQLD Tracy Holmes (R870040) * Severely Fouled - Top is okay. * 31.03.2021 18:50:28 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:35 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074565&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074565 | C01 GA PEAK DOWNS. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.042 | KM | 946790 | Goonyella | PEAK DOWNS | PEAK DOWNS | 2.0419 | KM | GA03ML43 | 0.655 | GA03ML45 | 0.684 | KM |  |  |  |  | 43.655 | 45.684 | 2023-06-30 | MAIN |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:52:30 AUSQLD Tracy Holmes (R870040) * Mud hole and ballast defect mid section, rough top, highly fouled * 31.03.2021 18:51:07 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:22 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * * Not sure why this has come to me for approval
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074595&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074595 | C01 BW MARMOR UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.002 | KM | 464608 | Blackwater | RAGLAN | MARMOR | 1.002 | KM | BW01ML591 | 0.5 | BW01ML592 | 0.5 | KM |  |  |  |  | 591.5 | 592.5 | 2023-06-30 | UP |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:59:45 AUSQLD Tracy Holmes (R870040) * Track Geometry Car Recordings * 31.03.2021 18:51:22 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:34 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074476&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074476 | C01 BW BURNGROVE DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.65 | KM | 765027 | Blackwater | RANGAL | BURNGROVE | 1.6499 | KM | BW03ML198 | 0.333 | BW03ML199 | 0.9819 | KM |  |  |  |  | 198.333 | 199.982 | 2023-06-30 | MAIN |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Outstanding notification | RRIG INIF | FY23 IN | 20250630 | * 22.03.2021 10:32:09 AUSQLD Tracy Holmes (R870040) * INCLUDES BURNGROVE CK @ 200.07KM * 31.03.2021 18:51:23 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:52 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074365&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074365 | C01 BW TIKARDI | BW-05ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 4.904 | KM | 2273845 | Blackwater | RANGAL | TIKARDI | 4.9039 | KM | BW05ML0 | 0.05 | BW05ML4 | 0.9579 | KM |  |  |  |  | 0.05 | 4.958 | 2023-06-30 | MAIN |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 09:32:44 AUSQLD Tracy Holmes (R870040) * from turnout 10A/B is 0.073km * 31.03.2021 18:53:57 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:44 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Replaced by 2000115975 due to SAP error unable to rectify
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115975&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000115975 | C01 BW TIKARDI | BW-05ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 4.904 | KM | 2273845 | Blackwater | RANGAL | TIKARDI | 20.5289 | KM | BW05ML0 | 0 | BW05ML20 | 0.458 | KM |  |  |  |  | 0.05 | 4.958 | 2023-06-30 | MAIN |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC | FY23 IN | 20230927 | 22.03.2021 09:32:44 AUSQLD Tracy Holmes (R870040) from turnout 10A/B is 0.073km 31.03.2021 18:53:57 AUSQLD Tracy Holmes (R870040) to overall program low risk 12.04.2021 16:22:44 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk Inplace of 2000074365 due to SAP error unable to rectify
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074475&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074475 | C01 BW BURNGROVE DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.967 | KM | 1375741 | Blackwater | SAGITTARIUS | BURNGROVE | 2.967 | KM | BW03ML192 | 0.0729 | BW03ML195 | 0.021 | KM |  |  |  |  | 192.073 | 195.021 | 2023-06-30 | DN |  |  |  | 4 | 2.9 |  |  |  | 11.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:32:02 AUSQLD Tracy Holmes (R870040) * INCLUDES TURNOUT 11A/B @195.280KM * 31.03.2021 18:51:48 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:51 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085752&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085752 | C01 BW RANGAL UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.027 | KM | 476154 | Blackwater | SAGITTARIUS | RANGAL | 1.0269 | KM |  | 0 |  | 0 | [5 empty] | 194 | 195.021 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.2 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20250630 | 15.10.2021 Tim Griffin (r878533) Continuation of FY22 works done from BW04ML (191.865 - 194.000) in FY22 due (notification 2000074474) to Single Dragon and carryover to FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083579&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083579 | C01 BW STANWELL BALOON EXIT | BW-04BL | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.001 | KM | 927779 | Blackwater | STANWELL BALLOON EXIT | STANWELL BALLOON EXIT | 2.0009 | KM | BW04BL1 | 0.9 | BW04BL3 | 0.9 | KM |  |  |  |  | 1.9 | 3.9 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | 14.09.2021 Tim Griffin (r878533) Stanwell balloon exit road undercut in conjunction with TLM relay during April2023 IP Closure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074593&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074593 | C01 BW ROLLESTON. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 4 | KM | 1854724 | Blackwater | STARLEE | ROLLESTON | 4 | KM | BW06ML83 | 0 | BW06ML87 | 0 | KM |  |  |  |  | 83 | 87 | 2023-06-30 | MAIN |  |  |  | 4 | 2.3 |  |  |  | 9.2 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:50:14 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074387&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074387 | C01 BW BOORGOON | BW-05ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.434 | KM | 1128599 | Blackwater | TIKARDI | BOORGOON | 2.434 | KM | BW05ML6 | 0.9559 | BW05ML9 | 0.39 | KM |  |  |  |  | 6.956 | 9.39 | 2023-06-30 | MAIN |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | SCPR INIF | FY23 IN | 20230630 | * 31.03.2021 18:51:50 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074464&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074464 | C01 BW TRYPHINNIA DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 4.934 | KM | 2287802 | Blackwater | WALLAROO | TRYPHINNIA | 4.934 | KM | BW03ML123 | 0.392 | BW03ML128 | 0.32 | KM |  |  |  |  | 123.392 | 128.32 | 2023-06-30 | DN |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:28:39 AUSQLD Tracy Holmes (R870040) * INCLUDES TURNOUT 12C/D @ 128.372KM FOR EASTERN CROSSOVER FOR TRYPHINNIA * 31.03.2021 18:52:44 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:49 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075319&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075319 | C01 BW WINDAH UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.648 | KM | 1691508 | Blackwater | WESTWOOD | WINDAH | 3.648 | KM | BW04ML51 | 0.5 | BW04ML55 | 0.1429 | KM |  |  |  |  | 51.5 | 55.143 | 2022-09-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | HIGH | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 14:27:04 AUSQLD Jane Livingston (R111275) * MISSED SCOPE FROM FY21 WESTWOOD - WINDAH NOTIFICATION #2000055787 - ORIGINALLY FROM 48.204 TO 54.32 HOWEVER 52.070 - 54.32 COULD NOT BE COMPLETED. NEEDS TO BE COMPLETED EARLY FY23
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075401&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075401 | C01 BW WESTWOOD UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 3.017 | KM | 1398879 | Blackwater | WYCARBAH | WESTWOOD | 3.0169 | KM | BW04ML39 | 0.9949 | BW04ML43 | 0.0109 | KM |  |  |  |  | 39.995 | 43.011 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 14:51:57 AUSQLD Jane Livingston (R111275) * NEW NOTIFICATION FOR MISSED WORK IN FY21 BALLAST UNDERCUTTING NOT NO. 2000055856 WYCARBAH - WESTWOOD UP. ORIGINAL SCOPE 37.497 - 44.615KM. MISSED SECTIONS IS 39.997 - 44.615KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074481&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074481 | C01 BW WESTWOOD UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 2.76 | KM | 1279713 | Blackwater | WYCARBAH | WESTWOOD | 2.7599 | KM | BW04ML43 | 0.111 | BW04ML45 | 0.8729 | KM |  |  |  |  | 43.111 | 45.873 | 2023-06-30 | UP |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:33:16 AUSQLD Tracy Holmes (R870040) * EASTERN END OF WESTWOOD. INCLUDES TURNOUT 12A/B @ 45.293KM WHICH CONNECTS BW-04ML TO BW-03PL * 12.04.2021 16:22:53 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074451&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074451 | C01 BW GREGORY | BW-08ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.787 | KM | 828551 | Blackwater | YANYAN | GREGORY | 1.7869 | KM | BW08ML52 | 0.2149 | BW08ML54 | 0 | KM |  |  |  |  | 52.215 | 54 | 2023-06-30 | MAIN |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20250630 | * 22.03.2021 10:26:08 AUSQLD Tracy Holmes (R870040) * BW-15ML CONNECTS BACK INTO BW-08ML AT 7C/D AT 52.160KM * 31.03.2021 18:53:17 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:22:46 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074471&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074471 | C01 BW YARWUN DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.769 | KM | 356570 | Blackwater | YARWUN | YARWUN | 0.769 | KM | BW02ML545 | 0.335 | BW02ML546 | 0.1 | KM |  |  |  |  | 545.335 | 546.1 | 2023-06-30 | DN |  |  |  | 4 | 4.9 |  |  |  | 19.6 |  | 2021-03-31 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 31.03.2021 18:53:28 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085904&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085904 | C01 BW YARWUN DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.545 | KM | 716340 | Blackwater | YARWUN | YARWUN | 1.5449 | KM | BW02ML546 | 0.5999 | BW02ML548 | 0.1469 | KM |  |  |  |  | 546.6 | 548.147 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) RM902 high production mainline u/c linked to notifications 2000074471 and 2000085901 (Boat Ck) on NCL, and interface with point asset Targinnie Road bridge BR101201.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085994&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085994 | C01 GA BLACK MOUNTAIN DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 0.604 | KM | 280016 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.6039 | KM | GA01ML32 | 0.5989 | GA01ML33 | 0.2 | KM |  |  |  |  | 32.599 | 33.2 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC | FY23 IN | 20250630 | 19.10.2021 Tim Griffin (r878533) Mainline high production u/c segmented and linked to notification 2000074497.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052356&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052356 | C01 GA BLACK MTN DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C01 | RENEWAL | 1.944 | KM | 901349 | Goonyella | YUKAN-BLACK MTN | YUKAN-BLACK MTN | 1.9439 | KM | GA01ML33 | 0.2 | GA01ML35 | 0.14 | KM |  |  |  |  | 33.2 | 35.14 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 15.4 | 4748 | 2020-03-06 | 2021-10-05 | Mainline Undercutting - C01 | HEAVY MAINTENANCE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20220630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074735&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074735 | BW C20 Unallocated | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | REACTIVE WORKS | 3.47 | KM | 2093190 | Blackwater |  |  | 3.47 | KM | BW01ML534 | 0.2909 | BW01ML537 | 0.76 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.5 |  |  |  | 14 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 18:53:57 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 03.10.2021 Tim Griffin (r878533) Initially was 5km Unscoped C14 u/c but with LEAD, STRAIGHT and DIVERGENT C14 for Turnout Point Assets totalling 1.53km Scope, there unscoped reduced to 3.47km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074736&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074736 | GA C20 Unallocated | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | REACTIVE WORKS | 4.376 | KM | 3016125 | Goonyella |  |  | 4.376 | KM | GA01ML8 | 0 | GA01ML12 | 0.3699 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.5 |  |  |  | 14 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 18:54:09 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 02/10/2021 Tim Griffin (r878533) 0.630km mainline assigned to C14 adjoin point t/o asset undercut, so reduce Unallocated to 4.370km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074737&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074737 | NL C20 Unallocated | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | REACTIVE WORKS | 1.29 | KM | 778160 | Newlands | ABBOT POINT | LEICHHARDT RANGE | 1.29 | KM | NL01ML0 | 0 | NL01ML1 | 0.272 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 2 |  |  |  | 8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 18:54:10 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 03.10.2021 Tim Griffin (r878533) C14 Unallocated scope reduced by 210m to allow mainline (LEAD and STRAIGHT + Divergent legs) of t/o undercut with C14 mainline.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074769&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074769 | MA C20 Unallocated | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | REACTIVE WORKS | 1.25 | KM | 754031 | Moura | GLADSTONE | MOURA MINE | 1.25 | KM | MA01ML2 | 0.4979 | MA01ML3 | 0.76 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 2 |  |  |  | 8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 18:54:10 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk 05.10.2021 Tim Griffin (r878533) C14 mainline u/c provision associated with Point Assets turnouts, thus reduce original allocation of 1.5km by 250m to now 1.25km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074513&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074513 | C14 GA WANDOO DOWN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.2 | KM | 120645 | Goonyella | BALOOK | WANDOO | 0.2 | KM | GA01ML80 | 0.45 | GA01ML80 | 0.65 | KM |  |  |  |  | 80.45 | 80.65 | 2023-06-30 | DN |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 10:39:18 AUSQLD Tracy Holmes (R870040) * Cut through crossing * 31.03.2021 18:43:57 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:03 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074543&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074543 | C14 GA WANDOO UP RD. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.295 | KM | 177891 | Goonyella | BALOOK | WANDOO | 0.2949 | KM | GA02ML81 | 0.6049 | GA02ML81 | 0.9 | KM |  |  |  |  | 81.605 | 81.9 | 2023-06-30 | UP |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 10:47:48 AUSQLD Tracy Holmes (R870040) * Planned up to crossing 5774 80.55 in FY21, needs doing after this point more than planned scope * 12.04.2021 16:23:14 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074591&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074591 | C14 NL BINBEE. | NL-05PL | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.35 | KM | 211068 | Newlands | BINBEE | BINBEE | 0.3499 | KM | NL05PL45 | 0.5999 | NL05PL45 | 0.9499 | KM |  |  |  |  | 45.6 | 45.95 | 2023-06-30 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:58:40 AUSQLD Tracy Holmes (R870040) * Severe fouling from 45.6 to 45.95 pts, near D7 top, points may need undercutting * 12.04.2021 16:23:33 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074523&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074523 | C14 GA CARBOROUGH DOWNS DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.698 | KM | 420990 | Goonyella | BROADLEA | CARBOROUGH DOWNS | 0.6979 | KM | GA01ML160 | 0.4 | GA01ML161 | 0.1 | KM |  |  |  |  | 160.4 | 161.1 | 2023-06-30 | DN |  |  |  | 4 | 2.5 |  |  |  | 10 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:41:47 AUSQLD Tracy Holmes (R870040) * Cut from signal at 160.4 to 161.1 signal * 31.03.2021 18:45:57 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:07 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074587&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074587 | C14 NL BUCKLEY. | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.4 | KM | 241290 | Newlands | BUCKLEY | ARMUNA | 0.4 | KM | NL01ML15 | 0.4 | NL01ML15 | 0.8 | KM |  |  |  |  | 15.4 | 15.8 | 2024-06-30 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:57:53 AUSQLD Tracy Holmes (R870040) * Highly fouled ballast after formation repair, rough track. Cut through level crossing * 12.04.2021 16:23:31 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074524&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074524 | C14 GA BURTON JNT DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.25 | KM | 150806 | Goonyella | CARBOROUGH DOWNS | BURTON JUNCTION | 0.25 | KM | GA01ML162 | 0.8499 | GA01ML163 | 0.1 | KM |  |  |  |  | 162.85 | 163.1 | 2023-06-30 | DN |  |  |  | 4 | 2.4 |  |  |  | 9.6 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:41:52 AUSQLD Tracy Holmes (R870040) * Fouled section with moderate top * 31.03.2021 18:46:09 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:07 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074578&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074578 | C14 GA DALRYMPLE BAY. | GA-05BA | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.25 | KM | 150806 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0.25 | KM | GA05BA0 | 0.05 | GA05BA0 | 0.2999 | KM |  |  |  |  | 0.05 | 0.3 | 2023-06-30 | BLOOP5 |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:55:44 AUSQLD Tracy Holmes (R870040) * Severely fouled, D1 twist at 0.05km otherwise good geometry until 0.6 to 0.7 which is near D7 top. * 12.04.2021 16:23:27 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * High production mainline RM902 u/c notification been segmented for point asset Bridge and Crew Pads and linked to notification 20000859XX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085915&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085915 | C14 GA DALY BAY BLOOPS. | GA-05BA | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.26 | KM | 156838 | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.26 | KM | GA05BA0 | 0.33 | GA05BA0 | 0.5899 | KM |  |  |  |  | 0.33 | 0.59 | 2023-06-30 | LOOPS |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) Notification linked to 2000074578 for high production mainline RM902 u/c .
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074463&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074463 | C14 BW AROONA DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.896 | KM | 540489 | Blackwater | EDUNGALBA | AROONA | 0.896 | KM | BW03ML87 | 0.676 | BW03ML88 | 0.5759 | KM |  |  |  |  | 87.676 | 88.576 | 2023-06-30 | DN |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 10:28:16 AUSQLD Tracy Holmes (R870040) * JUST AFTER TURNOUT MO/ER2 @ 84.773KM FOR BW-09SD AT WESTERN END OF EDUNGALBA AND INCLUDES WESTERN END TURNOUT OF BW-09ML (MO/ER1 @ 8 = 5.174KM) * 12.04.2021 16:22:49 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Agreed to split notification being 87.676km - 88.576km and linked to continuation of notification 2000085381.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085381&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085381 | C14 BW AROONA DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.686 | KM | 413812 | Blackwater | EDUNGALBA | AROONA | 0.686 | KM | BW03ML88 | 0.5759 | BW03ML89 | 0.265 | KM |  |  |  |  | 88.576 | 89.265 | 2022-06-30 | DN |  |  |  | 4 | 3.3 |  |  |  | 13.2 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074538&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074538 | C14 GA BOLINGBROKE UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.33 | KM | 199064 | Goonyella | HATFIELD | BOLINGBROKE | 0.33 | KM | GA02ML59 | 0.4 | GA02ML59 | 0.7299 | KM |  |  |  |  | 59.4 | 59.73 | 2023-06-30 | UP |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:46:37 AUSQLD Tracy Holmes (R870040) * Pick up gaps in scope from FY20 and FY22, shouldn't be pushed * 31.03.2021 18:48:27 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:13 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074577&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074577 | C14 GA INGSDON. | GA-04ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.235 | KM | 141697 | Goonyella | INGSDON | INGSDON | 0.2349 | KM | GA04ML10 | 0.9849 | GA04ML11 | 0.2399 | KM |  |  |  |  | 10.985 | 11.24 | 2023-06-30 | DOWN |  |  |  | 4 | 2.8 |  |  |  | 11.2 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 10:55:37 AUSQLD Tracy Holmes (R870040) * Severely fouled, Cut in after insdon 7cd, through crossing, out just before IN101A and back in straight after - D7 tops and near D7 twist. Tie into Fy21 Scope * 12.04.2021 16:23:27 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Notification segmented and linked to 2000085923 where cutout at 11.240km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052408&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052408 | C14 GA MINDI STH WALKER JNT. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.435 | KM | 262342 | Goonyella | MINDI-STH WALKER JCT | MINDI-STH WALKER JCT | 0.4349 | KM | GA02ML124 | 0.515 | GA02ML124 | 0.9499 | KM |  |  |  |  | 124.515 | 124.95 | 2022-06-30 |  |  |  |  | 3.5 | 4.3 |  |  |  | 15.23 | 4748 | 2020-03-06 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | Extended scope by 10m. PM Alex Gainsford and Tim Griffin 2 July 2021 review.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074554&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074554 | C14 GA MACARTHUR JCT UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.25 | KM | 150806 | Goonyella | TOOTOOLAH | MACARTHUR JCT | 0.25 | KM | GA02ML136 | 0.6999 | GA02ML136 | 0.9499 | KM |  |  |  |  | 136.7 | 136.95 | 2023-06-30 | UP |  |  |  | 4 | 4.7 |  |  |  | 18.8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:49:49 AUSQLD Tracy Holmes (R870040) * Ballast defect notification, top moderately rough and severely fouled, cut through to signal, LX also needs cutting * 12.04.2021 16:23:17 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074555&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074555 | C14 GA MACARTHER JNT UP RD. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.116 | KM | 69974 | Goonyella | TOOTOOLAH | MACARTHUR JCT | 0.116 | KM | GA02ML137 | 0.1 | GA02ML137 | 0.2159 | KM |  |  |  |  | 137.1 | 137.216 | 2023-06-30 | UP |  |  |  | 4 | 4.7 |  |  |  | 18.8 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 10:50:17 AUSQLD Tracy Holmes (R870040) * Ballast defect notification, top moderately rough and severely fouled, cut through to signal, LX also needs cutting * 12.04.2021 16:23:18 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * ENG review 18.01.2022 by R.Case Track is on TSR due to geometry defects through the crossing (D7 top and near D7 twist in October 2021 MMY038 run). For best results, please ensure crossing is cut through / removed, resurfaced and resinstated as part of the renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074514&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074514 | C14 GA WAITARA DOWN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.409 | KM | 246658 | Goonyella | WANDOO | WAITARA | 0.4089 | KM | GA01ML97 | 0.65 | GA01ML98 | 0.05 | KM |  |  |  |  | 97.65 | 98.05 | 2023-06-30 | DN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 10:39:22 AUSQLD Tracy Holmes (R870040) * Cut through crossing to signal. This will lead into the section undercutt in FY22 from 98.05 - 98.2km * 12.04.2021 16:23:03 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085901&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085901 | C14 BW YARWUN DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.23 | KM | 138741 | Blackwater | YARWUN | YARWUN | 0.23 | KM | BW02ML546 | 0.25 | BW02ML546 | 0.4799 | KM |  |  |  |  | 546.25 | 546.48 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | 19.10.2021 Tim Griffin (r878533) RM902 high production mainline u/c linked to notification 2000074471 (up to Boat Ck bridge BR101304) with bridge point asset 546.130 - 546.210km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084552&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084552 | C13 ADJACENT C14 ML STR MT LARCOM 9AB. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | ALDOGA | MT LARCOM | 0.05 | KM | BW01ML566 | 0.5 | BW01ML566 | 0.55 | KM |  |  |  |  | 566.5 | 566.55 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT mainline u/c for Point Asset t/o 1in12 Mt Larcom 9AB (FLOC TO 000902) linked to notification 2000074658.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084584&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084584 | C13 ADJACENT C14 ML LEAD ANNADALE 12A | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Moura | ANNADALE | EARLSFIELD | 0.05 | KM | MA01ML119 | 0.51 | MA01ML119 | 0.56 | KM |  |  |  |  | 119.51 | 119.56 |  | SINGLE |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated with Point Asset t/o undercut 1in12 Annadale 12A (FLOC TO 000935) and linked to notification 2000074617.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084568&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084568 | C13 ADJACENT C14 DIVERGENT ANNADALE 12A. | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.02 | KM | 12064 | Moura | ANNADALE | EARLSFIELD | 0.02 | KM | MA01ML119 | 0.633 | MA01ML119 | 0.653 | KM |  |  |  |  | 119.633 | 119.653 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg ballast u/c for Point Asset t/o 1in12 Annadale 12A (FLOC TO 000935) linked to notification 2000074617.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084542&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084542 | C13 ADJACENT C14 ML LEAD BAJOOL 11CD. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BAJOOL | ARCHER | 0.05 | KM | BW01ML603 | 0.524 | BW01ML603 | 0.5739 | KM |  |  |  |  | 603.524 | 603.574 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline turnout (C14) for Point Asset t/o undercutting (FLOC TO 000837) and associated notification reference 2000074620.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084601&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084601 | C13 ADJACENT C14 DIVERGENT BAJOOL 11CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | BAJOOL | ARCHER | 0.025 | KM | BW01ML603 | 0.662 | BW01ML603 | 0.687 | KM |  |  |  |  | 603.662 | 603.687 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg of Point Asset t/o 1in16 Bajool 11CD (FLOC TO 000837) and linked to notification 2000074620.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084543&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084543 | C13 ADJACENT C14 ML STR BAJOOL 11CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BAJOOL | ARCHER | 0.05 | KM | BW01ML603 | 0.662 | BW01ML603 | 0.7119 | KM |  |  |  |  | 603.662 | 603.712 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut for Point Asset t/o 1in16 Bajool 11CD (FLOC TO 000837) reference notification 2000074620.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084544&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084544 | C13 ADJACENT C14 ML LEAD BAJOOL 7AB. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BAJOOL | ARCHER | 0.05 | KM | BW01ML606 | 0.383 | BW01ML606 | 0.4329 | KM |  |  |  |  | 606.383 | 606.433 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated to Point Asset t/o 1in16 Bajool 7AB (FLOC 000835) and associated notification reference 2000074621)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084563&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084563 | C13 ADJACENT C14 DIVERGENT BAJOOL7AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | BAJOOL | ARCHER | 0.025 | KM | BW01ML606 | 0.521 | BW01ML606 | 0.546 | KM |  |  |  |  | 606.521 | 606.546 | 2023-06-30 | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg of ballast u/c for Point Asset t/o 1in16 Bajool 7AB (FLOC TO 000835) and linked to notification 2000074621.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084545&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084545 | C13 ADJACENT C14 ML STR BAJOOL 7AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BAJOOL | ARCHER | 0.05 | KM | BW01ML606 | 0.521 | BW01ML606 | 0.5709 | KM |  |  |  |  | 606.521 | 606.571 | 2023-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) Straight mainline undercut into Point Asset t/o Bajool 7AB 1in16 (FLOC TO 000835) for notification reference 2000074621.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084621&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084621 | C13 ADJACENT C14 ML LEAD BINBEE 7AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Newlands | BINBEE | BINBEE | 0.05 | KM | NL01ML44 | 0.393 | NL01ML44 | 0.443 | KM |  |  |  |  | 44.393 | 44.443 |  | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.04.2021 Tim Griffin (r878533) LEAD mainline ballast u/c associated with Point Asset t/o 1in16 Binbee 7AB (FLOC TO 000167) and linked to notification 2000080288.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084623&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084623 | C13 ADJACENT C14 ML DIVERGENT BINBEE 7AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Newlands | BINBEE | BINBEE | 0.025 | KM | NL01ML44 | 0.523 | NL01ML44 | 0.548 | KM |  |  |  |  | 44.523 | 44.548 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg of t/o associated with Point Asset 1in16 t/o Binbee 7AB (FLOC TO 000167) and linked to notification 2000080288. Start at NL01ML44.523km and finish NL01ML44.548km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084622&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084622 | C13 ADJACENT C14 ML STR BINBEE 7AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.058 | KM | 34987 | Newlands | BINBEE | BINBEE | 0.058 | KM | NL01ML44 | 0.523 | NL01ML44 | 0.5809 | KM |  |  |  |  | 44.523 | 44.581 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) STRAIGHT leg on mainline ballast u/c for Point Asset t/o 1in16 Binbee 7AB (FLOC TO 000167) linked to notification 2000080288).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084624&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084624 | C13 ADJACENT C14 ML LEAD BINBEE 12AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.035 | KM | 21112 | Newlands | BINBEE | BINBEE | 0.035 | KM | NL01ML46 | 0.19 | NL01ML46 | 0.225 | KM |  |  |  |  | 46.19 | 46.225 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) LEAD mainline ballast u/c associated with Point Asset t/o 1in16 Binbee 12AB (FLOC to 000175) linked to notification 2000080289.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084626&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084626 | C13 ADJACENT C14 ML DIVERGENT BINBEE12AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Newlands | BINBEE | BINBEE | 0.025 | KM | NL01ML46 | 0.2929 | NL01ML46 | 0.318 | KM |  |  |  |  | 46.293 | 46.318 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) DIVERGENT leg of Point Asset t/o 1in16 Binbee 12AB (FLOC TO 000175) linked to notification 2000080289.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084625&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084625 | C13 ADJACENT C14 ML STR BINBEE 12AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Newlands | BINBEE | BINBEE | 0.05 | KM | NL01ML46 | 0.2929 | NL01ML46 | 0.343 | KM |  |  |  |  | 46.293 | 46.343 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim griffin (r878533) STRAIGHT mainline leg on ballast u/c associated with t/o 1in16 Binbee 12AB (FLOC TO 000175) notification linked 2000080289.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084499&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084499 | C13 ADJACENT C14 ML Dn RD LEAD BOONAL8AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BLUFF | BOONAL | 0.05 | KM | BW03ML181 | 0.1239 | BW03ML181 | 0.1739 | KM |  |  |  |  | 181.124 | 181.174 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) C14 LEAD ML undercut for 1in16 Boonal 8AB t/o (FLOC TO 000649) and point asset notification 2000074607. M Durnsford Updated Description and functional location - this notification should be for the Down Road to Lead into Boonal 8AB
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084522&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084522 | C13 ADJACENT C14 ML Up RD STR BOONAL 8AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BLUFF | BOONAL | 0.05 | KM | BW03ML181 | 0.262 | BW03ML181 | 0.3119 | KM |  |  |  |  | 181.262 | 181.312 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) C14 STAIGHT Leg mainline undercut for 1in16 Boonal 8AB t/o (FLOC 000 649) and relative to t/o Point Asset undercut notification 2000074607.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084523&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084523 | C13 ADJACENT C14 ML UpRD LEAD BOONAL 7CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BLUFF | BOONAL | 0.05 | KM | BW03ML181 | 0.4189 | BW03ML181 | 0.4689 | KM |  |  |  |  | 181.419 | 181.469 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline u/c for T/O 1in16 Boonal 7CD (FLOC TO 000648) relative to turnout Point Asset and notification 2000074608.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084528&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084528 | C13 ADJACENT C14 ML Up RD STR BOONAL 7CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BLUFF | BOONAL | 0.05 | KM | BW03ML181 | 0.557 | BW03ML181 | 0.6069 | KM |  |  |  |  | 181.557 | 181.607 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) Mainline C14 STRAIGHT Leg of 1in16 t/o (FLOC TO 000648) and linked to Point Asset u/c turnout notification 2000074608.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084515&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084515 | C13 ADJACENT C14 ML LEAD BOONAL11AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BOONAL | BOONAL | 0.05 | KM | BW03ML178 | 0.0589 | BW03ML178 | 0.1089 | KM |  |  |  |  | 178.059 | 178.109 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) Adjoing C14 ML undercut on lead to 1in16 t/o Boonal 11AB (FLOC TO 000650) and C13 notification 2000074606.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084573&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084573 | C13 ADJACENT C14 DIVERGENT BOONAL 11AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | BOONAL | BOONAL | 0.025 | KM | BW03ML178 | 0.197 | BW03ML178 | 0.222 | KM |  |  |  |  | 178.197 | 178.222 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent leg of ballast undercut for Point Asset 1in16 t/o Boonal 11AB (FLOC TO 000650)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084498&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084498 | C13 ADJACENT C14 ML STR BOONAL 11AB. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | BOONAL | BOONAL | 0.05 | KM | BW03ML178 | 0.197 | BW03ML178 | 0.2469 | KM |  |  |  |  | 178.197 | 178.247 | 2023-06-30 | DOWN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) C14 mainline undercut straight leg of 1in16 turnout (FLOC TO 000650) reference to C13 t/ u/c notification 2000074606.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084574&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084574 | C13 ADJACENT C14 DIVERGENT BOONAL 8AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | BOONAL | BOONAL | 0.025 | KM | BW03ML181 | 0.262 | BW03ML181 | 0.2869 | KM |  |  |  |  | 181.262 | 181.287 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent leg undercut from Point Asset 1in16 t/o Boonal 8AB (FLOC TO 000649).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084575&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084575 | C13 ADJACENT C14 DIVERGENT BOONAL 7CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | BOONAL | BOONAL | 0.025 | KM | BW03ML181 | 0.557 | BW03ML181 | 0.5819 | KM |  |  |  |  | 181.557 | 181.582 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent leg undercut associated with Point Asset t/o 1in16 Boonal 7CD FLOC (TO 000648).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084508&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084508 | C13 ADJACENT C14 ML LEAD DALY BAY 11CD | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | DALY BAY | DALY BAY | 0.05 | KM | GA02BA7 | 0.915 | GA02BA7 | 0.9649 | KM |  |  |  |  | 7.915 | 7.965 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) LEAD mainline undercut assocaited with Point Asset t/o Daly Bay 11CD 1in16 balloon arrival (FLOC TO 000500) and linked to notification 2000074631.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084580&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084580 | C13 ADJACENT C14 ML LEAD DALY BAY 12AB | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | DALY BAY | DALY BAY | 0.05 | KM | GA02BA8 | 0.0089 | GA02BA8 | 0.0589 | KM |  |  |  |  | 8.009 | 8.059 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated with Point Asset t/o 1in25 Daly Day 12AB (FLOC TO 000501) and lined to notification 2000074632.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084509&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084509 | C13 ADJACENT C14 ML STR DALY BAY 11CD | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | DALY BAY | DALY BAY | 0.05 | KM | GA02BA8 | 0.0529 | GA02BA8 | 0.1029 | KM |  |  |  |  | 8.053 | 8.103 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o 1in16 Daly Day balloon arrival 11CD (FLOC TO 000500) and linked to notification 2000074631.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084581&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084581 | C13 ADJACENT C14 ML STR DALY BAY 12AB | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | DALY BAY | DALY BAY | 0.05 | KM | GA02BA8 | 0.171 | GA02BA8 | 0.221 | KM |  |  |  |  | 8.171 | 8.221 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline undercut associated with Point Asset t/o 1in25 Daly Bay 12AB (FLOC TO 000501) linked to notification 2000074632.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084566&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084566 | C13 ADJACENT C14 DIVERGENT DALY BAY 12AB | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | DALY BAY BA | DALY BAY BA | 0.05 | KM | GA02BA8 | 0.171 | GA02BA8 | 0.221 | KM |  |  |  |  | 8.171 | 8.221 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r8788533) Divergent leg of ballast u/c for Point Asset 1in25 Point Asset Daly Bay 12AB (FLOC TO 000501) linked to notification 2000074632.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084565&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084565 | C13 ADJACENT C14 DIVERGENT DALY BAY 11CD | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Goonyella | DALY BAY BALLOON ARRIVAL | DALY BAY BALLOON ARRIVAL | 0.025 | KM | GA02BA8 | 0.0529 | GA02BA8 | 0.0779 | KM |  |  |  |  | 8.053 | 8.078 | 2023-06-30 | BALLOON ARRIVAL |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg ballast u/c for Point Asset t/o 1in16 Daly Bay 11CD (FLOC TO 000500) linked to notifcation 2000074631.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084518&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084518 | C13 ADJACENT C14 ML STR UMOLO 12CD | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | DINGO | UMOLO | 0.05 | KM | BW04ML148 | 0.7039 | BW04ML148 | 0.754 | KM |  |  |  |  | 148.704 | 148.754 | 2023-06-30 | DN |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o 1in16 Umolo 12CD (FLOC 000590) linked to notification 2000074655.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084585&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084585 | C13 ADJACENT C14 ML STR ANNADALE 12A | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Moura | EARLSFIELD | ANNADALE | 0.05 | KM | MA01ML119 | 0.633 | MA01ML119 | 0.683 | KM |  |  |  |  | 119.633 | 119.683 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o 1in12 Annadale 12A (FLOC TO 000935) and linked to notification 2000074617.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084597&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084597 | C13 ADJACENT C14 DIVERGENT PEAK DNS 8AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.024 | KM | 14477 | Goonyella | HARROW | PEAK DOWNS | 0.024 | KM | GA03ML43 | 0.7179 | GA03ML43 | 0.7419 | KM |  |  |  |  | 43.718 | 43.742 | [5 empty] | 4 | 1.8 |  |  |  | 7.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg ballast u/c for Point Asset 1in16 t/o Peak Downs 8AB FLOC (TO 000387) linked to notification 2000074647.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084582&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084582 | C13 ADJACENT C14 ML LEAD SARAJI 12AB | GA-07PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | HARROW | SARAJI | 0.05 | KM | GA07PL67 | 0.4769 | GA07PL67 | 0.527 | KM |  |  |  |  | 67.487 | 67.527 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.8 |  |  |  | 7.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated with Point Asset 1in16 t/o Saraji 12AB (FLOC TO 000394) as linked to notification 2000074648.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084583&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084583 | C13 ADJACENT C14 ML STR SARAJI 12AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | HARROW | SARAJI | 0.05 | KM | GA03ML67 | 0.6149 | GA03ML67 | 0.665 | KM |  |  |  |  | 67.615 | 67.665 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.8 |  |  |  | 7.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o 1in16 Saraji 12AB (FLOC TO 000394) and lined to notification 2000074648.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084577&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084577 | C13 ADJACENT C14 DIVERGENT KABRA 107CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | KABRA | KABRA | 0.05 | KM | BW03ML21 | 0.132 | BW03ML21 | 0.1819 | KM |  |  |  |  | 21.132 | 21.182 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent ballast undercut associated with Point Asset t/o 1in25 Kabra 107CD (FLOC TO 000740).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084529&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084529 | C13 ADJACENT C14 ML LEAD KABRA 107CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | KABRA | STANWELL | 0.05 | KM | BW03ML20 | 0.9699 | BW03ML21 | 0.02 | KM |  |  |  |  | 20.97 | 21.02 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification in process | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) C14 mainline LEAD undercut into 1in25 t/o FLOC (TO 000740) Point Asset linked to notification 2000074610.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084530&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084530 | C13 ADJACENT C14 ML STR KABRA 107CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | KABRA | STANWELL | 0.05 | KM | BW03ML21 | 0.132 | BW03ML21 | 0.1819 | KM |  |  |  |  | 21.132 | 21.182 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut for associated 1in25 Kabra 107CD turnout (FLOC TO 000740) and Point Asset t/o notification 2000074610.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084564&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084564 | C13 ADJACENT C14 DIVERGENT KINROLA 11AB | BW-06ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | KINROLA | KINROLA JCT | 0.025 | KM | BW06ML0 | 0.1 | BW06ML0 | 0.125 | KM |  |  |  |  | 0.1 | 0.125 | 2023-06-30 | LOOP |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg ballast undercut of Point Asset t/o 1in16 Kinrole 11AB (FLOC TO 000819) linked to notification 2000074657.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084556&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084556 | C13 ADJACENT C14 ML STR KINROLA 11AB | BW-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | KINROLA JCT | KINROLA | 0.05 | KM | BW05ML0 | 0.1 | BW05ML0 | 0.1499 | KM |  |  |  |  | 0.1 | 0.15 | [5 empty] | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline undercut linkage to t/o Point Asset 1in16 KINROLA 11AB associated notification 2000074657.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084555&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084555 | C13 ADJACENT C14 ML LEAD KINROLA 11AB. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | KINROLA JCT | KINROLA | 0.05 | KM | BW06ML14 | 0.9619 | BW06ML15 | 0.012 | KM |  |  |  |  | 14.962 | 15.012 | 2023-06-30 |  |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification in process | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut linked to Point Asset t/o 1in16 Kinrola 11AB (FLOC TO 000819) linkage to notification 2000074657.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084627&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084627 | C13 ADJACENT C14 ML LEAD PEAK DNS 7AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.05 | KM | GA03ML43 | 0.54 | GA03ML43 | 0.5899 | KM |  |  |  |  | 43.54 | 43.59 | 2023-06-30 |  |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 05.10.2021 Tim griffin (r878533) LEAD mainline ballast u/c associated with Point Asset t/o 1in16 Peak Downs 7AB (FLOC TO 000388) and linked to notification 2000074646.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084596&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084596 | C13 ADJACENT C14 DIVERGENT PEAK DNS 7AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.027 | KM | 16226 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0269 | KM | GA03ML43 | 0.676 | GA03ML43 | 0.7029 | KM |  |  |  |  | 43.678 | 43.703 | 2023-06-30 |  |  |  |  | 4 | 1.8 |  |  |  | 7.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) Divergent leg ballast u/c for Point Asset 1in16 t/o Peak Down 7AB into Passing loop (05-PL) FLOC (TO 000388) linked to notification 2000074646.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084598&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084598 | C13 ADJACENT C14 ML LEAD STIRRAT 12A. | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Moura | STIRRAT | STIRRAT | 0.05 | KM | MA01ML38 | 0.2949 | MA01ML38 | 0.3449 | KM |  |  |  |  | 38.295 | 38.345 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.3 |  |  |  | 5.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim griffin (r878533) LEAD mainline u/c for Point Asset t/o 1in12 Stirrat 12A FLOC (TO 000961) linked to notification 2000080264.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084620&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084620 | C13 ADJACENT C14 DIVERGENT STIRRAT 12A | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.02 | KM | 12064 | Moura | STIRRAT | STIRRAT | 0.02 | KM | MA01ML38 | 0.4349 | MA01ML38 | 0.455 | KM |  |  |  |  | 38.435 | 38.455 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.3 |  |  |  | 5.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533)(TO 000961) linked to notification 2000080264. Divergent leg of ballast u/c to Point Asset t/o 1in12 Stirrat FLOC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084599&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084599 | C13 ADJACENT C14 ML STR STIRRAT 12A | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Moura | STIRRAT | STIRRAT | 0.05 | KM | MA01ML38 | 0.4349 | MA01ML38 | 0.4849 | KM |  |  |  |  | 38.435 | 38.485 | 2023-06-30 | SINGLE |  |  |  | 4 | 1.3 |  |  |  | 5.2 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 03.10.2021 Tim Griffin (r878533) STRAIGHT leg of Point Asset t/o 1in12 Stirrat 12A (FLOC TO 000961) linked to notification 2000080264.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084536&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084536 | C13 ADJACENT C14 ML LEAD TRYPHINIA 12CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | TRYPHINIA | DINGO | 0.05 | KM | BW03ML128 | 0.3119 | BW03ML128 | 0.3619 | KM |  |  |  |  | 128.312 | 128.362 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut to Point Asset t/o 1in16 Tryphinia 12CD (FLOC TO 000691) associated with notification 2000074615.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084537&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084537 | C13 ADJACENT C14 ML STR TRYPHINIA 12CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | TRYPHINIA | DINGO | 0.05 | KM | BW03ML128 | 0.45 | BW03ML128 | 0.5 | KM |  |  |  |  | 128.45 | 128.5 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o Tryphinia 12CD 1in16 (FLOC TO 000691) and associated notification 2000074615.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084591&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084591 | C13 ADJACENT C14 DIVERGENT TRYPHINIA 12C | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | TRYPHINIA | TRYPHINIA | 0.025 | KM | BW03ML128 | 0.45 | BW03ML128 | 0.4749 | KM |  |  |  |  | 128.45 | 128.475 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent leg ballast undercut (at least 50%) associated with Point Asset t/o 1in16 Tryphinia 12CD (FLOC TO 000691).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084531&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084531 | C13 ADJACENT C14 ML LEAD WYCARBAH 11CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | WARREN | WYCARBAH | 0.05 | KM | BW03ML36 | 0.0309 | BW03ML36 | 0.081 | KM |  |  |  |  | 36.031 | 36.081 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.07.2021 Tim Griffin (r878533) LEAD mainline undercut for Point Asset t/o 1in16 Wycarbah 11CD with reference linkage to notification 2000074611.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084534&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084534 | C13 ADJACENT C14 ML LEAD WYCARBAH 12AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | WARREN | WYCARBAH | 0.05 | KM | BW03ML36 | 0.047 | BW03ML36 | 0.097 | KM |  |  |  |  | 36.047 | 36.097 | 2023-06-30 |  |  |  |  | 4 |  |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin LEAD mainline undercut into 1in16 Wycarbah 12AB relative to Point Asset t/o (FLOC TO 000671) and reference notification 2000074612.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084533&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084533 | C13 ADJACENT C14 ML STR WYCARBAH 11CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | WARREN | WYCARBAH | 0.05 | KM | BW03ML36 | 0.169 | BW03ML36 | 0.219 | KM |  |  |  |  | 36.169 | 36.219 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline undercut associated with t/o 1in16 Wycarbah 11CD (FLOC TO 000672) and Point Asset notification 2000074611.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084535&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084535 | C13 ADJACENT C14 ML STR WYCARBAH 12AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Blackwater | WARREN | WYCARBAH | 0.05 | KM | BW03ML36 | 0.1849 | BW03ML36 | 0.2349 | KM |  |  |  |  | 36.185 | 36.235 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 16.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut for Point Asset 1in16 Wycarbah 12AB (FLOC TO 000671) and associated notification 2000074612.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084549&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084549 | C13 ADJACENT C14 ML LEAD PEAK DNS 8AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | WINCHESTER | PEAK DOWNS | 0.05 | KM | GA03ML43 | 0.5899 | GA03ML43 | 0.64 | KM |  |  |  |  | 43.59 | 43.64 | 2023-06-30 | SINGLE |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut linked to Point Asset t/o 1in16 Peak Downs 8AB (FLOC TO 000387) associated notification 2000074747.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084548&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084548 | C13 ADJACENT C14 ML LEAD PEAK DNS 7AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.055 | KM | 33177 | Goonyella | WINCHESTER | PEAK DOWNS | 0.055 | KM | GA03ML43 | 0.678 | GA03ML43 | 0.7329 | KM |  |  |  |  | 43.678 | 43.733 | 2023-06-30 | SINGLE |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut linked to Point Asset t/o 1in16 Peak Downs (FLOC TO 000388) reference to notification 2000074646.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084560&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084560 | C13 ADJACENT C14 ML STR PEAK DNS 8AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 30161 | Goonyella | WINCHESTER | PEAK DOWNS | 0.05 | KM | GA03ML43 | 0.7129 | GA03ML43 | 0.763 | KM |  |  |  |  | 43.713 | 43.763 | 2023-06-30 | SIGNLE |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline undercut linked to Point Asset t/o 1in16 Peak Downs 8AB and linkage to notification 2000074647.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084579&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084579 | C13 ADJACENT C14 DIVERGENT WYCARBAH 11CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | WYCARBAH | WYCARBAH | 0.025 | KM | BW03ML36 | 0.169 | BW03ML36 | 0.194 | KM |  |  |  |  | 36.169 | 36.194 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r878533) Divergent leg ballast undercut associated with Point Asset 1in16 t/o Wycarbah 11CD (FLOC TO 000672).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084590&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084590 | C13 ADJACENT C14 DIVERGENT WYCARBAH 12AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 15080 | Blackwater | WYCARBAH | WYCARBAH | 0.025 | KM | BW03ML36 | 0.1849 | BW03ML36 | 0.2099 | KM |  |  |  |  | 36.185 | 36.21 | [5 empty] | 4 | 3.35 |  |  |  | 13.4 |  |  | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | 02.10.2021 Tim Griffin (r875535) Divergent leg of ballast undercutting for Point Asset t/o 1in16 Wycarbah 12AB (FLOC TO 000671)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074485&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000074485 | C01-BU-GA-DALY JCT-10.733km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE | RENEWAL | 1.154 | KM | 571476 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 1.1539 | KM | GA01ML10 | 0.2899 | GA01ML11 | 0.45 | KM |  |  |  |  | 10.29 | 11.45 | 2023-06-30 | DN |  |  |  | 4 | 4.6 |  |  |  | 18.4 | 5376 | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | SCPR INIF |  | 20210918 | * 22.03.2021 10:34:35 AUSQLD Tracy Holmes (R870040) * Top defects D7 around 10.6 <(>&<)> 10.8. Was in FY20 from 10.815 to 11.115 but scope not completed. Ties into FY20 Scope. * 12.04.2021 16:22:54 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Replan Comments: 60%+ for 90% of scope, geometry is often near D7. High priority. There may be a FY24 notification already existing, preferrably moved into FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074529&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000074529 | C01-BU-GA-DALY JCT-10.330km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE | RENEWAL | 0.32 | KM | 166248 | Goonyella | DALRYMPLE BAY JUNCTION | PRAGUELANDS | 0.32 | KM | GA02ML10 | 0.33 | GA02ML10 | 0.65 | KM |  |  |  |  | 10.33 | 10.65 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 | 5379 | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | SCPR INIF |  | 20210918 | * 22.03.2021 10:43:36 AUSQLD Tracy Holmes (R870040) * Roughest section is planned in FY21, the remainder will need to be undercut at some point, top isn't too bad so could go to FY24 * 12.04.2021 16:23:09 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Replan Comments: Multiple D7 tops.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074530&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000074530 | C01-BU-GA-DALY JCT-12.436km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE | RENEWAL | 0.349 | KM | 644729 | Goonyella | DALRYMPLE BAY JUNCTION | PRAGUELANDS | 1.1559 | KM | GA02ML13 | 0.2149 | GA02ML14 | 0.3549 | KM |  |  |  |  | 13.215 | 13.564 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 | 5380 | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | SCPR INIF |  | 20230529 | * 22.03.2021 10:43:45 AUSQLD Tracy Holmes (R870040) * Capture where Fy21 scope finishes to end of section, fouled and rough top. Extremely fouled, cut through lubricator and signal and all the way upto to Pragueland 8C/D @ the 14.455km. Turnout PS 8/D is undercut in Fy22 * 12.04.2021 16:23:10 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052381&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052381 | C01-BU-GA-SW-140.300km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE | RENEWAL | 0.85 | KM | 447003 | Goonyella | MACARTHUR JCT-COPPABELLA | MACARTHUR JCT-COPPABELLA | 0.8499 | KM | GA01ML140 | 0.2999 | GA01ML141 | 0.1499 | KM |  |  |  |  | 140.3 | 141.15 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.1 | 5418 | 2020-03-06 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: 90% of scope is above 60%. Geometry in late 2021 is okay.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084167&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000084167 | C01-BU-GA-DALY JCT-10.650km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.42 | KM |  | Goonyella |  |  | 0.4129 | KM | GA02ML10 | 0.65 | GA02ML11 | 0.07 | KM |  |  |  |  | 10.65 | 11.07 | 2022-06-30 |  |  |  |  | 3.5 | [5 empty] | 5385 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20220919 | FY22 Residual Scope Replan Comments: Okay Track Geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052360&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052360 | C01-BU-GA-BLACK MOUNTAIN-43.015km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.585 | KM | 140456 | Goonyella | BLACK MTN-HATFIELD | BLACK MTN-HATFIELD | 0.5849 | KM | GA01ML43 | 0.0149 | GA01ML43 | 0.5999 | KM |  |  |  |  | 43.015 | 43.6 | 2022-06-30 |  |  |  |  | 3 | 4.6 |  |  |  | 15 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | SCPR |  | 20250630 | FY22 Residual Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052361&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052361 | C01-BU-GA-BLACK MOUNTAIN-43.600km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.789 | KM | 313354 | Goonyella | BLACK MTN-HATFIELD | BLACK MTN-HATFIELD | 0.789 | KM | GA01ML43 | 0.5999 | GA01ML44 | 0.387 | KM |  |  |  |  | 43.6 | 44.387 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 17.5 | 5362 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20221002 | FY22 Residual Scope Replan Comments: Replan for FY23 Q1; change board approval to extend July IP to 60hours
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052362&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052362 | C01-BU-GA-BLACK MOUNTAIN-44.387km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.463 | KM | 684233 | Goonyella | BLACK MTN-HATFIELD | BLACK MTN-HATFIELD | 1.463 | KM | GA01ML44 | 0.387 | GA01ML45 | 0.8499 | KM |  |  |  |  | 44.387 | 45.85 | 2022-06-30 |  |  |  |  | 3 | 4.6 |  |  |  | 15 | 5361 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: Replan for FY23 Q1; change board approval to extend July IP to 60hours
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052461&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052461 | C01-BU-BW-SW-542.600km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.677 | KM | 795076 | Blackwater | CALLEMONDAH-ROCKLANDS UP RD |  | 1.677 | KM | BW01ML542 | 0.5999 | BW01ML544 | 0.2999 | KM |  |  |  |  | 542.6 | 544.3 | 2022-06-30 |  |  |  |  | 3.5 | 4.9 |  |  |  | 14.4 | 5377 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20221013 | FY22 Residual Scope Replan Comments: Moderately rough with some D7 and near D7. Mostly 40-60% with the rest 60%+. On TSR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052462&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052462 | C01-BU-BW-SW-544.300km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.802 | KM | 784769 | Blackwater | CALLEMONDAH-ROCKLANDS UP RD |  | 1.802 | KM | BW01ML544 | 0.2999 | BW01ML546 | 0.1 | KM |  |  |  |  | 544.3 | 546.1 | 2022-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 | 5378 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20230630 | FY22 Residual Scope Replan Comments: Moderately rough with some D7 and near D7. Mostly 40-60% with the rest 60%+. On TSR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052382&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052382 | C01-BU-GA-COPPABELLA-153.100km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.03 | KM | 395250 | Goonyella | COPPABELLA-BROADLEA | COPPABELLA-BROADLEA | 0.6999 | KM | GA01ML153 | 0.2999 | GA01ML154 | 0 | KM |  |  |  |  | 153.1 | 154.13 | 2022-06-30 |  |  |  |  | 3 | 4.6 |  |  |  | 7.5 | 5419 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: 60%+ at unsealed level crossings, 30-40% over culvert, otherwise 20-30%. Near D7 tops at crossings. Culvert may not be deliverable with C14, in which case it may suit C01.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052335&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052335 | C01-BU-GA-DALY JCT-12.250km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.127 | KM | 657107 | Goonyella | DALY JCT-PRAGUELANDS | DALY JCT-PRAGUELANDS | 2.1269 | KM | GA01ML12 | 0.25 | GA01ML14 | 0.3649 | KM |  |  |  |  | 12.25 | 14.365 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.1 | 5375 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: 60%+ for approx 60% of scope, remainder is 30-40% and 40-60%. Geometry is often near D7. High priority. There may be a FY24 notification already existing, preferrably moved into FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102817&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000102817 | CO1 GOONYELLA U/C | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.85 | KM | 447003 | Goonyella | MACARTHUR JCT-COPPABELLA | MACARTHUR JCT-COPPABELLA | 0.8499 | KM | GA01ML140 | 0.2999 | GA01ML141 | 0.1499 | KM |  |  |  |  | 140.3 | 141.15 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.1 |  | 2020-03-06 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | NWSC |  | 20230630 | Adjusted Start and Finish markers distance (Same overall length of 850m) to save cutin and cutout impacts. Tim Griffin 2 July 2021
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052438&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052438 | C01-BU-BW-WESTWOOD-49.000km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0 | KM | 0 | Blackwater | ROCKLANDS-NOGOA DN RD |  | 1.298 | KM | BW03ML49 | 0 | BW03ML50 | 0.2999 | KM |  |  |  |  | 49 | 50.3 | 2022-06-30 |  |  |  |  | 3 | 4.5 |  |  |  | 10.05 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20240630 | FY22 Residual Scope Replan Comments: About 25% of the scope is 60%+, with the remainder a mix of category 3-5. One D7 and near D7 defects. FY22 element - IV.00831.E.A.BW.20.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052415&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052415 | C01-BU-GA-WINCHESTER-34.851km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.998 | KM | 1382153 | Goonyella | WINCHESTER-PEAK DOWNS | WINCHESTER-PEAK DOWNS | 2.998 | KM | GA03ML34 | 0.8509 | GA03ML37 | 0.8499 | KM |  |  |  |  | 34.851 | 37.85 | 2022-06-30 |  |  |  |  | 3 | 2.4 |  |  |  | 3 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: High fouling, mosting in the 40-60% range. Geometry is fairy good to fair with a moderately rough section from approx 36km - 37km and at level crossings. High fouling suggests mid-term reliability impacts. FY24 reasonable outcome if planning in FY23 cannot be done without considerable impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052416&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052416 | C01-BU-GA-WINCHESTER-37.850km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.148 | KM | 537846 | Goonyella | WINCHESTER-PEAK DOWNS | WINCHESTER-PEAK DOWNS | 1.1479 | KM | GA03ML37 | 0.8499 | GA03ML39 | 0 | KM |  |  |  |  | 37.85 | 39 | 2022-06-30 |  |  |  |  | 3.5 | 1 |  |  |  | 3.5 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: High fouling, mosting in the 40-60% range. Geometry is fairy good to fair with a moderately rough section from approx 36km - 37km and at level crossings. High fouling suggests mid-term reliability impacts. FY24 reasonable outcome if planning in FY23 cannot be done without considerable impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052417&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052417 | C01-BU-GA-WINCHESTER-42.270km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.461 | KM | 680960 | Goonyella | WINCHESTER-PEAK DOWNS | WINCHESTER-PEAK DOWNS | 1.461 | KM | GA03ML41 | 0 | GA03ML42 | 0.456 | KM |  |  |  |  | 41 | 42.456 | 2022-06-30 |  |  |  |  | 3.5 | 1 |  |  |  | 3.5 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: High fouling, mosting in the 40-60% range. Geometry is fairy good to fair with a moderately rough section from approx 36km - 37km and at level crossings. High fouling suggests mid-term reliability impacts. FY24 reasonable outcome if planning in FY23 cannot be done without considerable impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104430&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000104430 | C14-BU-BW-RAGLAN-584.780km-DOWN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.12 | KM | 539523 | Blackwater | CALLEMONDAH-ROCKLANDS DN RD |  | 0.1199 | KM | BW02ML584 | 0.78 | BW02ML584 | 0.9 | KM |  |  |  |  | 584.78 | 584.9 | 2022-06-30 | DN |  |  |  | 3 | 4.9 |  |  |  | 12.3 | 5386 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC |  | 20230908 | "FY22 Residual Scope Replan Comments: Option to do whole scope of C01, or 360m of C14, depending on resources. C14 likely to be the preferred option" Refer to notification 2000052481 and the FY22 Residual Scoping Sheet saved in Microsoft Teams
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104431&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000104431 | C14-BU-BW-EPALA-585.120km-DOWN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.24 | KM | 539523 | Blackwater | CALLEMONDAH-ROCKLANDS DN RD |  | 0.2399 | KM | BW02ML585 | 0.1199 | BW02ML585 | 0.3599 | KM |  |  |  |  | 585.12 | 585.36 | 2022-06-30 | DN |  |  |  | 3 | 4.9 |  |  |  | 12.3 | 5386 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC |  | 20230908 | "FY22 Residual Scope Replan Comments: Option to do whole scope of C01, or 360m of C14, depending on resources. C14 likely to be the preferred option" Reference to 2000052481
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085868&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085868 | C14-BU-GA-DALY BAYS-0.330km-BALLOON | GA-04BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.32 | KM | 582800 | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 1.2569 | KM | GA04BA0 | 0.33 | GA04BA1 | 0.5869 | KM |  |  |  |  | 0.33 | 0.65 |  | LOOP 4 |  |  |  | 4 | 2.3 |  |  |  | 9.2 | 5427 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20250630 | 19.10.2021 Tim Griffin (r878533) High production mainline RM902 u/c linked to notification 2000074576 due to point asset segmentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052398&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052398 | C14-BU-GA-PRAGUELANDS-21.500km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.45 | KM | 0 | Goonyella | JILALAN | JILALAN | 0.3499 | KM | GA02ML21 | 0.5999 | GA02ML21 | 0.9499 | KM |  |  |  |  | 21.5 | 21.95 | 2025-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.8 | 5389 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | SCPR |  | 20220630 | Adjusted start km to 21.500km giving overall length of 450m as per PM Alex Gainsford advice. Tim Griffin 2 July 2021. MD; Adjusted LInear Data to tie into 52397 being executed in FY22 PCR to be completed FY22 Residual Scope Replan Comments: Bridge (willy ck) in scope from 21.510-21.580 with splays <(>&<)> centre guard rails, will need to be completed as a roll out
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112836&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000112836 | C14-BU-GA-PRAGUELANDS-21.500km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.45 | KM | 0 | Goonyella | JILALAN | JILALAN | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM |  |  |  |  | 21.5 | 21.95 | 2025-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.8 | 5389 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC |  | 20230630 | Adjusted start km to 21.500km giving overall length of 450m as per PM Alex Gainsford advice. Tim Griffin 2 July 2021. MD; Adjusted LInear Data to tie into 52397 being executed in FY22 PCR to be completed FY22 Residual Scope Replan Comments: Bridge (willy ck) in scope from 21.510-21.580 with splays <(>&<)> centre guard rails, will need to be completed as a roll out
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052375&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052375 | C14-BU-GA-MINDI-126.850km-DOWN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0 | KM | 0 | Goonyella | MINDI-STH WALKER JCT | MINDI-STH WALKER JCT | 0.3449 | KM | GA01ML126 | 0.8499 | GA01ML127 | 0.2 | KM |  |  |  |  | 126.85 | 127.2 | 2023-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 4.2 | 5381 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20240630 | FY22 Residual Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074568&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074568 | C14-BU-GA-NORWICH PARK-115.150km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.352 | KM | 182872 | Goonyella | NORWICH PARK | MIDDLEMOUNT JCT | 0.3519 | KM | GA03ML115 | 0.1499 | GA03ML115 | 0.502 | KM |  |  |  |  | 115.15 | 115.502 | 2023-06-30 | MAIN |  |  |  | 4 | 1.5 |  |  |  | 6 |  | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | SCPR INIF |  | 20210918 | * 22.03.2021 10:53:28 AUSQLD Tracy Holmes (R870040) * Severely fouled before turnout and at D7, cut through turnout * 31.03.2021 18:50:52 AUSQLD Tracy Holmes (R870040) to overall program low risk * 12.04.2021 16:23:23 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Replan Comments: Requires replanning - High priority (FY22-FY23) severely fouled - includes AT site and level crossing - geometry poor from 115.350-115.500 inc. level crossing at D7 top. C14 fix on fail?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052435&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052435 | C01-BU-BW-WYCARBAH-38.250km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.549 | KM | 0 | Blackwater | ROCKLANDS-NOGOA DN RD |  | 0.549 | KM | BW03ML37 | 0.6999 | BW03ML38 | 0.25 | KM |  |  |  |  | 37.6 | 38.25 | 2023-06-30 |  |  |  |  | 3.5 | 4.5 |  |  |  | 11.73 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | SCPR |  | 20230630 | FY22 Residual Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052378&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052378 | C14-BU-GA-TOOTOOLAH-135.437km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0 | KM | 0 | Goonyella | TOOTOOLAH | MACARTHUR JCT | 0.2429 | KM | GA01ML135 | 0.4369 | GA01ML135 | 0.68 | KM |  |  |  |  | 135.437 | 135.68 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 4.2 | 5673 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | FY22 Residual Scope Replan Comments: Combine Adjoining scope from 10.330-10.650. Cutting adjacent to track which impacts machine access for C14
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102761&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000102761 | C14-BU-BW-WALTON-168.240km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.7 | KM | 286971 | Blackwater | WALTON | BLUFF | 0.46 | KM | BW04ML168 | 0.2399 | BW04ML168 | 0.6999 | KM |  |  |  |  | 168.24 | 168.7 | 2023-06-30 | UP | [10 empty] | 2022-06-30 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Notification completed | NWSC |  | 20230630 | Lachlan Crow 19/08/2022 (R888582) Residual scope missed from FY22 C01 Project (2000052458) being captured by the FY23 C14 Program.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074596&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000074596 | C14-BU-BW-WARREN-30.237km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 3.45 | KM | 941082 | Blackwater | WARREN | WYCARBAH | 3.45 | KM | BW03ML28 | 0.329 | BW03ML31 | 0.771 | KM |  |  |  |  | 28.329 | 31.771 | 2023-06-30 | DN |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20220630 | * 31.03.2021 18:53:02 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk * Approved based upon NLT approval of Q3 & Q4 FY22 brought forward * scope. Tim Griffin 2/1/2/2021
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052418&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052418 | C01-BU-GA-WINCHESTER-42.456km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.144 | KM | 86067 | Goonyella | WINCHESTER-PEAK DOWNS | WINCHESTER-PEAK DOWNS | 0.1439 | KM | GA03ML42 | 0.456 | GA03ML42 | 0.5999 | KM |  |  |  |  | 42.456 | 42.6 | 2022-06-30 |  |  |  |  | 3.5 | 2.1 |  |  |  | 7.35 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | SCPR |  | 20220630 | FY22 Residual Scope Replan Comments: High fouling, mostly in the 40-60% range. Geometry is fairy good to fair with a moderately rough section from approx 36km - 37km and at level crossings. High fouling suggests mid-term reliability impacts. FY24 reasonable outcome if planning in FY23 cannot be done without considerable impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052401&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000052401 | C14-BU-GA-YUKAN-32.379km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.221 | KM | 445299 | Goonyella | YUKAN-BLACK MTN | YUKAN-BLACK MTN | 1.5629 | KM | GA02ML32 | 0.379 | GA02ML33 | 0.9399 | KM |  |  |  |  | 32.379 | 32.6 | 2022-06-30 | UP |  |  |  | 3.5 | 4.6 |  |  |  | 15.4 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | SCPR |  | 20220630 | Sat 30.10.2021 Tim Griffin (r878533) Ammended notification due to FY22 Q3 <(>&<)> Q4 adjustments. See attcahed file / email details. FY22 Residual Scope Replan Comments: Requires crossing (unsealed, private) cut through
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113635&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000113635 | C14-BU-GA-YUKAN-32.379km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.221 | KM | 445299 | Goonyella | YUKAN-BLACK MTN | YUKAN-BLACK MTN | 0.1799 | KM | GA02ML32 | 0.5999 | GA02ML32 | 0.78 | KM |  |  |  |  | 32.379 | 32.6 | 2022-06-30 | UP |  |  |  | 3.5 | 4.6 |  |  |  | 15.4 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC |  | 20240225 | Residual Scope from C01 902 Original Notification 2000052401
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083678&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083678 | C13 BLACKWATER T/O UNALLOCATED | BW-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT | REACTIVE WORKS | 1 | TURNOUT | 141505 | Blackwater |  |  | 0 | KM | BW01ML534 | 0 | BW01ML534 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 14.25 |  |  | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | 15.09.2021 Tim Griffin (r878533) Reinstatement of C13 turnout reactive undercut for Blackwater System. 03.11.2022 Melissa Durnsford Rocklands 10AB was executed in October 2022 as the one Fix on Fail Turnout undercut for FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052223&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052223 | C13 GOONYELLA T/O Unallocated | GA-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT | REACTIVE WORKS | 1 | TURNOUT | 141505 | Goonyella |  |  | 0 | KM | GA01ML8 | 0 | GA01ML8 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3 | 3.5 |  |  |  | 10.5 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 24.02.2020 09:57:13 AUSQLD Allan Gough (R873345) * Allocation from NetOps Asset Maintenance N7 notifications during FY22 for up to 23 turnout undercuts, as per page 44 of RIG submission. * 12.04.2021 16:20:55 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052225&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052225 | C13 NEWLANDS T/O Unallocated | NL-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT | REACTIVE WORKS | 1 | TURNOUT | 141505 | Newlands |  |  | 0 | KM | NL01ML0 | 0 | NL01ML0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.5 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 24.02.2020 10:04:18 AUSQLD Allan Gough (R873345) * Allocation from NetOps Asset Maintenance N7 notifications during FY22 for up to 2 turnout undercuts, as per page 58 of RIG submission. * 12.04.2021 16:20:56 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074617&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074617 | C13 MOURA T/O 12A ANNANDALE. | TO000935 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Moura | ANNANDALE | ANNANDALE | 0.0379 | KM | MA01ML119 | 0.5699 | MA01ML119 | 0.6079 | KM |  |  |  |  | 119.57 | 119.57 | 2023-06-30 |  |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:54:36 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074620&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074620 | C13 BLACKWATER T/O 11C/D BAJOOL. | TO000837 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | BAJOOL | BAJOOL | 0.049 | KM | BW01ML603 | 0.5839 | BW01ML603 | 0.633 | KM |  |  |  |  | 603.591 | 603.662 | 2023-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 31.03.2021 18:54:49 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074621&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074621 | C13 BLACKWATER T/O 7A/B BAJOOL. | TO000835 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | BAJOOL | BAJOOL | 0.021 | KM | BW01ML606 | 0.443 | BW01ML606 | 0.464 | KM |  |  |  |  | 606.441 | 606.521 | 2023-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 31.03.2021 18:54:49 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000055922&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000055922 | C13 GOONYELLA T/O 8A/B BALOOK. | TO000212 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.4789 | GA01ML74 | 0.4789 | KM |  |  |  |  | 74.479 | 74.557 | 2023-06-30 |  |  |  |  | 3 | 4.8 |  |  |  | 14.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 27.04.2020 10:51:01 AUSQLD Peter Rayner (R003851) * Balook 8AB * 23.02.2021 10:57:31 AUSQLD William Schuh (R878634) * * PCR 4820 - defer to FY23 to align with FY21 planned scope . Monitor condition * 12.04.2021 16:21:01 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080288&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000080288 | C13 NEWLANDS T/O 7A/B BINBEE. | TO000167 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Newlands | BINBEE | BINBEE | 0.0459 | KM | NL01ML44 | 0.453 | NL01ML44 | 0.4989 | KM |  |  |  |  | 44.453 | 44.453 |  | NL-01ML |  |  |  | 3.5 | 1.7 |  |  |  | 5.95 |  |  | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080289&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000080289 | C13 NEWLANDS T/O 12A/B BINBEE BE. | TO000175 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Newlands | BINBEE | BINBEE | 0.047 | KM | NL01ML46 | 0.2129 | NL01ML46 | 0.166 | KM |  |  |  |  | 46.215 | 46.215 |  | NL-01ML |  |  |  | 3.5 | 1.7 |  |  |  | 5.95 |  |  | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051454&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000051454 | C13 GOONYELLA T/O 8A/B BLACK MTN. | TO000447 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.049 | KM | GA01ML40 | 0.797 | GA01ML40 | 0.8459 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:54:23 AUSQLD Tracy Holmes (R870040) * Still to complete walkouts, need to identify bridges, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to overall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074638&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074638 | C13 GOONYELLA T/O 8C/D BLACK MTN. | TO000332 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.0459 | KM | GA02ML40 | 0.897 | GA02ML40 | 0.8509 | KM |  |  |  |  | 40.896 | 40.975 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:11:31 AUSQLD Tracy Holmes (R870040) * Needs to be completed with ML U/C in FY23 * 12.04.2021 16:23:40 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074639&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074639 | C13 GONYELLA T/O 12A/B BLACK MTN. | TO000331 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.0459 | KM | GA02ML40 | 0.919 | GA02ML40 | 0.9649 | KM |  |  |  |  | 40.918 | 40.997 | 2023-06-30 |  |  |  |  | 3 | 5 |  |  |  | 15 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:12:03 AUSQLD Tracy Holmes (R870040) * Needs to be completed with ML U/C in FY23 * 12.04.2021 16:23:42 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074606&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074606 | C13 BLACKWATER T/O 11A/B BOONAL. | TO000650 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | BOONAL | BOONAL | 0.05 | KM | BW03ML178 | 0.1189 | BW03ML178 | 0.169 | KM |  |  |  |  | 178.12 | 178.197 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:55:03 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074607&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074607 | C13 BLACKWATER T/O 8A/B BOONAL. | TO000649 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | BOONAL | BOONAL | 0.0509 | KM | BW03ML181 | 0.1839 | BW03ML181 | 0.2349 | KM |  |  |  |  | 181.184 | 181.262 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:55:03 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074608&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074608 | C13 BLACKWATER T/O 7C/D BOONAL. | TO000648 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | BOONAL | BOONAL | 0.05 | KM | BW03ML181 | 0.4789 | BW03ML181 | 0.4289 | KM |  |  |  |  | 181.479 | 181.557 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:55:14 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074643&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074643 | C13 GOONYELLA T/O ER2.2B CBELLA. | TO000284 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | COPPABELLA | COPPABELLA | 0.032 | KM | GA02ML143 | 0.91 | GA02ML143 | 0.9419 | KM |  |  |  |  | 143.919 | 143.963 | 2023-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 11:12:46 AUSQLD Tracy Holmes (R870040) * Just at D7 top and D7 twist (Jan 21) * FY22 SPM 2000052409 144 - 144.4 so could join to it * 12.04.2021 16:23:43 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074644&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074644 | C13 GOONYELLA T/O 102B CBELLA. | TO000282 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | COPPABELLA | COPPABELLA | 0.0369 | KM | GA02ML144 | 0.501 | GA02ML144 | 0.464 | KM |  |  |  |  | 144.495 | 144.564 | 2023-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20210918 | * 22.03.2021 11:12:54 AUSQLD Tracy Holmes (R870040) * Just at D7 top and D7 twist (Jan 21) * FY22 SPM 2000052409 144 - 144.4 so could join to it * 12.04.2021 16:23:43 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074631&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074631 | C13 GOONYELLA T/O 11C/D DALY BAY. | TO000500 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0.048 | KM | GA02BA7 | 0.9749 | GA02BA7 | 0.927 | KM |  |  |  |  | 7.975 | 8.053 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:10:01 AUSQLD Tracy Holmes (R870040) * Near D7 top and twist (Jan 21) * 12.04.2021 16:23:38 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074632&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074632 | C13 GOONYELLA T/O 12A/B DALY BAY. | TO000501 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0.0719 | KM | GA02BA8 | 0.069 | GA02BA8 | 0.1409 | KM |  |  |  |  | 8.068 | 8.171 | 2023-06-30 |  |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:10:08 AUSQLD Tracy Holmes (R870040) * D7 twist, near D7 top (Jan 21) * 12.04.2021 16:23:39 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074633&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074633 | C13 GOONYELLA T/O 7A/B JILALAN. | TO000353 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | JILALAN | JILALAN | 0.032 | KM | GA02ML17 | 0.341 | GA02ML17 | 0.3729 | KM |  |  |  |  | 17.341 | 17.404 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:10:40 AUSQLD Tracy Holmes (R870040) * Needs to be completed with ML U/C in FY23 * 12.04.2021 16:23:39 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074622&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074622 | C13 GOONYELLA T/O 8C/D JILALAN. | TO000465 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | JILALAN | JILALAN | 0.032 | KM | GA01ML17 | 0.5669 | GA01ML17 | 0.535 | KM |  |  |  |  | 17.567 | 17.63 | 2023-06-30 | DN |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:08:01 AUSQLD Tracy Holmes (R870040) * D1 twist and D7 top, pair with adjacent 48AB (Jan 2021) * Completed in FY20 * 12.04.2021 16:23:37 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074634&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074634 | C13 GOONYELLA T/O 9A/B JILALAN. | TO000348 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | JILALAN | JILALAN | 0.033 | KM | GA02ML19 | 0.932 | GA02ML19 | 0.9649 | KM |  |  |  |  | 19.931 | 19.995 | 2023-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:10:43 AUSQLD Tracy Holmes (R870040) * D7 twist (Feb 21) * 12.04.2021 16:23:39 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074635&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074635 | C13 GOONYELLA T/O 10C/D JILALAN. | TO000347 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | JILALAN | JILALAN | 0.0359 | KM | GA02ML20 | 0.276 | GA02ML20 | 0.2399 | KM |  |  |  |  | 20.274 | 20.339 | 2023-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:10:47 AUSQLD Tracy Holmes (R870040) * D7 twist, near D7 top (Feb 21) * 12.04.2021 16:23:40 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074636&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074636 | C13 GOONYELLA T/O 11C/D JILALAN. | TO000346 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | JILALAN | JILALAN | 0.0359 | KM | GA02ML22 | 0.637 | GA02ML22 | 0.6009 | KM |  |  |  |  | 22.636 | 22.7 | 2023-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:11:22 AUSQLD Tracy Holmes (R870040) * Needs to be completed with ML U/C in FY23 * 12.04.2021 16:23:40 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074610&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074610 | C13 BLACKWATER T/O 107C/D KABRA. | TO000740 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | KABRA | KABRA | 0.0729 | KM | BW03ML21 | 0.0299 | BW03ML20 | 0.9569 | KM |  |  |  |  | 21.03 | 21.132 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:05 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074657&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074657 | C13 BLACKWATER T/O 11A/B KINROLA. | TO000819 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | KINROLA | KINROLA | 0.05 | KM | BW06ML0 | 0.0219 | BW06ML0 | 0.0719 | KM |  |  |  |  | 14.746 | 14.824 | 2023-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:07 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074658&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074658 | C13 BLACKWATER T/O 9A/B MT LARCOM. | TO000902 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | MT LARCOM | MT LARCOM | 0.0359 | KM | BW02ML566 | 0.4369 | BW02ML566 | 0.401 | KM |  |  |  |  | 564.537 | 564.5 | 2023-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:07 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074659&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074659 | C13 BLACKWATER T/O 7C/D MT LARCOM. | TO000903 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | MT LARCOM | MT LARCOM | 0.0509 | KM | BW02ML566 | 0.7219 | BW02ML566 | 0.773 | KM |  |  |  |  | 564.722 | 564.8 | 2023-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:17 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074646&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074646 | C13 GOONYELLA T/O 7A/B PEAK DNS. | TO000388 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0449 | KM | GA03ML43 | 0.5999 | GA03ML43 | 0.645 | KM |  |  |  |  | 43.597 | 43.678 | 2024-06-30 |  |  |  |  | 4.5 | 2.1 |  |  |  | 9.45 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC | FY23 IN | 20210918 | * 22.03.2021 11:13:28 AUSQLD Tracy Holmes (R870040) * Joins with PD8AB, if you do 1 do the other. Not highest priority. Near D7 top (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074647&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074647 | C13 GOONYELLA T/O 8A/B PEAK DNS. | TO000387 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0309 | KM | GA03ML43 | 0.65 | GA03ML43 | 0.681 | KM |  |  |  |  | 43.65 | 43.713 | 2024-06-30 |  |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC | FY23 IN | 20210918 | * 22.03.2021 11:13:35 AUSQLD Tracy Holmes (R870040) * Joins with PD7AB, if you do 1 do the other. Not highest priority. D7 twist and top (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074648&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074648 | C13 GOONYELLA T/O 12A/B SARAJI. | TO000394 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | SARAJI | SARAJI | 0.048 | KM | GA03ML67 | 0.537 | GA03ML67 | 0.4889 | KM |  |  |  |  | 67.535 | 67.615 | 2023-06-30 |  |  |  |  | 4 | 1.8 |  |  |  | 7.2 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:14:05 AUSQLD Tracy Holmes (R870040) * Pushed out fromm Fy23 to Fy24 * 12.04.2021 16:23:43 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074627&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074627 | C13 GOONYELLA T/O 7C/D SOUTH WALKER. | TO000249 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | SOUTH WALKER | SOUTH WALKER | 0.0709 | KM | GA01ML127 | 0.4 | GA01ML127 | 0.329 | KM |  |  |  |  | 127.4 | 127.502 | 2023-06-30 |  |  |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:09:18 AUSQLD Tracy Holmes (R870040) * Geometry moderately rough (Jan 21) * Pushed from FY21 BCD program due to resource and closure contraints (though not in SPM) to FY23 (28/01/2021) * 12.04.2021 16:23:38 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080264&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000080264 | C13 MOURA T/O 12A STIRRAT. | TO000961 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Moura | STIRRAT | STIRRAT | 0.0359 | KM | MA01ML39 | 0.395 | MA01ML39 | 0.4309 | KM |  |  |  |  | 39.388 | 39.424 |  | MA-01ML |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  |  | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074642&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074642 | C13 GOONYELLA T/O 8C/D TOOTOOLAH. | TO000301 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.047 | KM | GA02ML132 | 0.7109 | GA02ML132 | 0.664 | KM |  |  |  |  | 132.711 | 132.789 | 2023-06-30 |  |  |  |  | 4 | 4.7 |  |  |  | 18.8 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:12:41 AUSQLD Tracy Holmes (R870040) * Moderate top, twist okay (Feb 21) * Doing adjacent 12AB in FY22, connect to where this job finishes * 12.04.2021 16:23:42 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074615&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074615 | C13 BLACKWATER T/O 12C/D TRYPHINIA. | TO000691 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | TRYPHINNIA | TRYPHINNIA | 0.05 | KM | BW03ML128 | 0.3719 | BW03ML128 | 0.322 | KM |  |  |  |  | 128.372 | 128.45 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:31 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074654&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074654 | C13 BLACKWATER T/O 11A/B UMOLO. | TO000735 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | UMOLO | UMOLO | 0.0459 | KM | BW04ML148 | 0.4259 | BW04ML148 | 0.4719 | KM |  |  |  |  | 148.424 | 148.504 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:31 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074605&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074605 | C13 BLACKWATER T/O 11C/D UMOLO. | TO000734 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | UMOLO | UMOLO | 0.0439 | KM | BW03ML148 | 0.519 | BW03ML148 | 0.4749 | KM |  |  |  |  | 148.52 | 148.597 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:41 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074656&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074656 | C13 BLACKWATER T/O 12A/B UMOLO. | TO000580 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | UMOLO | UMOLO | 0.047 | KM | BW03ML148 | 0.53 | BW03ML148 | 0.5769 | KM |  |  |  |  | 148.53 | 148.608 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:42 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074655&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074655 | C13 BLACKWATER T/O 12C/D UMOLO. | TO000590 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | UMOLO | UMOLO | 0.0439 | KM | BW04ML148 | 0.626 | BW04ML148 | 0.5819 | KM |  |  |  |  | 148.625 | 148.704 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:42 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074626&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074626 | C13 GOONYELLA T/O 45B/C WAITARA. | TO000225 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | WAITARA | WAITARA | 0.0459 | KM | GA01ML106 | 0.4369 | GA01ML106 | 0.391 | KM |  |  |  |  | 106.427 | 106.515 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:08:48 AUSQLD Tracy Holmes (R870040) * D7 top, near D7 twist (Jan 2021) * 12.04.2021 16:23:38 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074641&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074641 | C13 GOONYELLA T/O 8C/D WANDOO. | TO000321 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | WANDOO | WANDOO | 0.048 | KM | GA02ML86 | 0.0369 | GA02ML85 | 0.9959 | KM |  |  |  |  | 86.037 | 86.115 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:12:11 AUSQLD Tracy Holmes (R870040) * Near D7 twist (Feb 21) * Was in FY20/21 but removed due to higher priorities * 12.04.2021 16:23:42 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074611&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074611 | C13 BLACKWATER T/O 11C/D WYCARBAH. | TO000672 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | WYCARBAH | WYCARBAH | 0.055 | KM | BW03ML36 | 0.0909 | BW03ML36 | 0.0359 | KM |  |  |  |  | 36.091 | 36.169 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:56:55 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074612&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074612 | C13 BLACKWATER T/O 12A/B WYCARBAH. | TO000671 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | WYCARBAH | WYCARBAH | 0.0459 | KM | BW03ML36 | 0.1069 | BW03ML36 | 0.1529 | KM |  |  |  |  | 36.111 | 36.185 | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:57:06 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074618&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074618 | C13 BLACKWATER T/O 11A/B YARWUN. | TO000895 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | YARWUN | YARWUN | 0.048 | KM | BW02ML545 | 0.279 | BW02ML545 | 0.231 | KM |  |  |  |  | 545.275 | 545.357 | 2023-06-30 |  |  |  |  | 4 | 4.9 |  |  |  | 19.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:57:08 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074619&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074619 | C13 BLACKWATER T/O 12C/D YARWUN. | TO000575 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | YARWUN | YARWUN | 0.047 | KM | BW02ML545 | 0.3029 | BW02ML545 | 0.3499 | KM |  |  |  |  | 545.303 | 545.381 | 2023-06-30 |  |  |  |  | 4 | 4.9 |  |  |  | 19.6 |  | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:57:08 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074624&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074624 | C13 GOONYELLA T/O 47A/B YUKAN. | TO000444 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Goonyella | YUKAN | YUKAN | 0.0369 | KM | GA01ML29 | 0.314 | GA01ML29 | 0.3509 | KM |  |  |  |  | 29.298 | 29.377 | 2023-06-30 |  |  |  |  | 4 | 4.8 |  |  |  | 19.2 | 5676 | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20240630 | * 22.03.2021 11:08:37 AUSQLD Tracy Holmes (R870040) * Near D7 top and twist (Jan 21) * On TSR early 2021, extremely fouled. Pushing to get in FY21 or FY22 * This looked pretty fouled on site. Needs to tie in to Fy23 ML UC * 12.04.2021 16:23:37 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104215&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000104215 | C13 Turnout B/U Memooloo 10 Pts | TO000823 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | KENMARE | MEMOOLOO | 0.032 | KM | BW06ML47 | 0.8639 | BW06ML47 | 0.8319 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 3.6 | 2.3 | 2 | 3.2 | 1 | 11.4 |  |  |  | Sleepers in Sleeper and Ballast Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044163&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044163 | Bridge Rollouts Renewal (Duckworth Ck). | BR100244-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 140 | METERS | 503883 | Blackwater | BLUFF | BOONAL | 0.14 | KM | BW04ML175 | 0.1799 | BW04ML175 | 0.32 | KM |  |  |  |  | 174.18 | 174.32 | 2023-06-30 | UP |  |  |  | 3.5 | 3.4 |  |  |  | 11.9 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:29:17 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. No Getech and assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044154&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044154 | BBR NL Pelican Creek 80.355-80.505KM. | BR300600-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 230 | METERS | 855581 | Newlands | COLLINSVILLE | SONOMA | 0.23 | KM | NL01ML80 | 0.315 | NL01ML80 | 0.545 | KM |  |  |  |  | 80.315 | 80.545 | 2023-06-30 | MAIN |  |  |  | 4 | 2.4 |  |  |  | 9.6 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:35:25 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. possession and may reduce. No Getech and assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044095&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044095 | Rollouts (Mackenzie O/Flow Lilley WHoles | BR101111-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 140 | METERS | 1200183 | Blackwater | CREW | MACKENZIE | 0.14 | KM | BW08ML19 | 0.78 | BW08ML19 | 0.92 | KM |  |  |  |  | 19.82 | 19.985 | 2023-06-30 | MAIN |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | MEDIUM |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230810 | * 31.03.2021 18:42:12 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. The actual scope is uncertain and dependant on engineering assessments of the adjoing abutments. An allocation has been made in time if the installation of relieving slabs are defined.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068154&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068154 | SR_BRIDGE WORKS_105.384_OH/HS/TB/BMF | BR100070-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 110 | METERS | 493303 | Blackwater | DUARINGA | WALLAROO | 0.11 | KM | BW03ML105 | 0.38 | BW03ML105 | 0.4899 | KM |  |  |  |  | 105.38 | 105.49 | 2023-06-30 | DOWN |  |  |  | 3.5 | 3 |  |  |  | 10.5 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:42:36 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044162&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044162 | Bridge Rollouts Renewal (Bells Ck). | BR400110-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 170 | METERS | 712061 | Moura | DUMGREE | MOUNT RAINBOW | 0.17 | KM | MA01ML100 | 0.8 | MA01ML100 | 0.9699 | KM |  |  |  |  | 100.8 | 100.97 | 2023-06-30 | MAIN |  |  |  | 4 | 1.3 |  |  |  | 5.2 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:42:41 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. No Getech and assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065324&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065324 | BBR Bolinbroke Creek UP 52.540-52.645KM. | BR200823-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 160 | METERS | 507728 | Goonyella | HATFIELD | BOLLINGBROKE | 0.16 | KM | GA02ML52 | 0.515 | GA02ML52 | 0.675 | KM |  |  |  |  | 52.515 | 52.675 | 2023-06-30 | DOWN |  |  |  | 3.5 | 4.2 |  |  |  | 14.7 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:42:54 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065329&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065329 | BBR GA Ingsdon North Ck 13.280-13.320KM. | BR200483-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 100 | METERS | 462723 | Goonyella | INGSDON | RED MOUNTAIN | 0.1 | KM | GA03ML13 | 0.2899 | GA03ML13 | 0.39 | KM |  |  |  |  | 13.29 | 13.39 | 2023-06-30 | SINGLE |  |  |  | 3.5 | 2.5 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230714 | * 31.03.2021 18:42:49 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. No Geotech so risk still exists have assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044155&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000044155 | BBR GA LVJ-SAJ Downs Ck 85.590-86.300KM. | BR200434-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 90 | METERS | 372143 | Goonyella | LAKE VERMONT | SARAJI | 0.0899 | KM | GA03ML85 | 0.5899 | GA03ML85 | 0.68 | KM |  |  |  |  | 85.59 | 85.68 | 2023-06-30 | MAIN |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:42:54 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043534&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043534 | Bridge Rollouts Renewal (Comet Rv Nth). | BR100925-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 50 | METERS | 234463 | Blackwater | MEMOOLOO | STARLEE | 0.05 | KM | BW06ML72 | 0.1049 | BW06ML72 | 0.1549 | KM |  |  |  |  | 72.105 | 72.155 | 2023-06-30 | MAIN |  |  |  | 3.5 | 2.3 |  |  |  | 8.1 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:43:06 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. No Getech and assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074682&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074682 | Bridge Rollouts Aldebaran Ck. | BR100916-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 114 | METERS | 594063 | Blackwater | MEMOOLOO | STARLEE | 0.114 | KM | BW06ML92 | 0.9599 | BW06ML93 | 0.19 | KM |  |  |  |  | 92.96 | 93.19 | 2023-06-30 | MAIN |  |  |  | 4 | 2.3 |  |  |  | 9.2 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 22.03.2021 11:37:32 AUSQLD Tracy Holmes (R870040) * Fouled with PVC>30 * 31.03.2021 18:43:17 AUSQLD Tracy Holmes (R870040) impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce. No Getech and assumed formation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065351&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065351 | BBR GA MII-TOT 125.74-125.84 Up (BEE CK) | BR200964-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 150 | METERS | 485623 | Goonyella | MINDI | TOOTOOLAH | 0.1499 | KM | GA02ML125 | 0.79 | GA02ML125 | 0.9399 | KM |  |  |  |  | 125.79 | 125.94 | 2023-06-30 | UP |  |  |  | 3.5 | 4.7 |  |  |  | 16.5 |  | 2021-03-31 | 2021-10-05 | Bridge Roll Out | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 18:43:12 AUSQLD Tracy Holmes (R870040) * Post walkout rating (willidentify formation requirements based on historical) BW MO High risk, GY NL Med Risk (Formation and curb raising impact on duration and cost curb raising after walkout formation historical). Rail replacement over bridges (defects closer to renewal date, walkout will review rail, sleeper formation also). Formation, sleeper, rail and curb raising scope will have a significant impact on BB clsoure duration and cost of job. Assumption will be higher for possession and may reduce.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084448&DY_MAB=X&~OKCODE=ONLI | FY23 |  | REACTIVE RENEWALS | COAL | 002000084448 | FENCING & CORRIDOR SECURITY REACTIVE | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 350000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  | 2021-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084446&DY_MAB=X&~OKCODE=ONLI | FY23 |  | REACTIVE RENEWALS | COAL | 002000084446 | FENCING & CORRIDOR SECURITY REACTIVE | GA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 375000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 4 | 3.8 |  |  |  | 15.2 |  |  | 2021-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051240&DY_MAB=X&~OKCODE=ONLI | FY23 |  | REACTIVE RENEWALS | COAL | 002000051240 | FENCING & CORRIDOR SECURITY REACTIVE | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 125000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2022-06-30 |  |  |  |  | 5 | 3.5 |  |  |  | 17.5 |  | 2020-03-06 | 2020-11-13 | Corridor Fencing and Security | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | NWSC |  | 20230630 | 30.05.2022 : Tim Griffin (r8788533) Fencing from 108.700km to 110.300km on Moura System approved by May Change Board. PCR 5352 of 17 May 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084449&DY_MAB=X&~OKCODE=ONLI | FY23 |  | REACTIVE RENEWALS | COAL | 002000084449 | FENCING & CORRIDOR SECURITY REACTIVE | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 225000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  |  | 2021-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084470&DY_MAB=X&~OKCODE=ONLI | FY23 |  | REACTIVE RENEWALS | COAL | 002000084470 | FENCING & CORRIDOR SECURITY REACTIVE | NL | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 225000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 2.7 |  |  |  | 10.8 |  |  | 2021-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103956&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000103956 | FY23 Renewal - Wallaby Lane Access Road | BW-03ML | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 1 | SITE |  | Blackwater | UMOLO | PARNABAL | 0.01 | KM | BW03ML155 | 0.935 | BW03ML155 | 0.9449 | KM |  |  |  |  | 155.935 | 155.945 | 2023-06-30 |  |  |  |  | 10 | 3.4 | 0.5 | 10 | 1 | 100 |  |  |  | Corridor Fencing and Security | [5 empty] | Notification in process | NWSC |  | 20230630 | Land Stabilisation <(>&<)> erosion control
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052730&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000052730 | C05-FR-GA-BROADLEA-163.119km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.714 | KM | 1555573 | Goonyella | BROADLEA | MALLAWA | 0.7139 | KM | GA01ML163 | 0.1189 | GA01ML163 | 0.8329 | KM |  |  |  |  | 163.119 | 163.833 | 2023-06-30 | DOWN |  |  |  | 3 | 4.6 |  |  |  | 13.8 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20241230 | * 31.03.2021 09:44:35 AUSQLD Jane Livingston (R111275) * 164km Test Pit - CBR 10 400 - 580mm depth and CBR 2.5 580 - 1200mm. Unsuitable 50%. * 12.04.2021 16:21:10 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * * 18.11.2021 Tim Griffin (r878533) See attached file in notification from NetOps Program Mgr Adrian Neubecker on 2/11/2021 updating allocation upon unsuitable and length extension to 714m (Initially 163km400m to 163km755m being 355m).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052754&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000052754 | C05-FR-NL-BUCKLEY-14.070km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.32 | KM | 595240 | Newlands | BUCKLEY | ARMUNA | 0.32 | KM | NL01ML14 | 0.07 | NL01ML14 | 0.39 | KM |  |  |  |  | 14.07 | 14.39 | 2024-06-30 | MAIN LINE |  |  |  | 3.25 | 2.5 | 2 | 3 | 1 | 9.8 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: Whistle board 15.258km; Culverts 15.130km <(>&<)> 15.200km; Bonds 15.502km for Level Crossing Bowen Developmental Road LX ID 3279 15.520km 15.000 - 15.161 Curve>1000m End Formation 10m from Bowen Developmental Road Level Crossing 01/02/2022 R888068 Ben Crozier - issue with start/end km in location tab. Updated location tab to reflect start/end km from linear data on notification tab. 09/03/2022 Tim Griffin (878533) - Linked to N7 : 2000091380 maintenance M3 notification of 2 Feb2022 where FoF from 13km900m to 14km010m planned for 19April2022 reactive formation renewal to remove 15 km/hr TSR and holding maintenance works until adjoining FY24 delivery in Q1 of FY24 (No later than 30 Sept 2023). See attachment for links and photos. 11.05.2022 Tim Griffin (r878533) Assume unsuitable to be 60% (Max of 900mm depth) due to black soil and historic geometry issues. 17.01.2023 ALEY (R889072) Scope extents updated from 14.010-14.225km to 14.070-14.390km as per with PCR # 5518 END COMMENT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075273&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075273 | C05-FR-BW-EPALA-577.300km | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 0.9 | KM | 1522744 | Blackwater | EPALA | RAGLAN | 0.896 | KM | BW02ML577 | 0.2999 | BW02ML578 | 0.2 | KM |  |  |  |  | 577.3 | 578.2 | 2023-06-30 | DOWN |  |  |  | 4 | 4.9 |  |  |  | 19.6 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:07:22 AUSQLD Jane Livingston (R111275) * Track Geometry Issues and repeat maintenance at this spot. Formation job at 570km - failed DCPs - ordered additional material - planned 600mm; completed 900mm formation. Bridge near it - Raglan Bridge (about 500m away); Access will be okay. Level Crossing at Epala. Access off the highway. 40% Unsuitable allowance. CBR 9.0 at Capping Layer. 300mm of ballast, 300mm of Capping and another 300mm. 16.01.23 ALEY R889072 FLOC ID corrected to BW-02ML (scope has been delivered in the July 22 BW IP closure), this change is to update records. Awaiting official approval from PCR # 5592. END COMMENT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092364&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000092364 | C05-FR-NL-KAILI-1165.880km | NC-03ML | CIVIL | FORMATION |  | RENEWAL | 0.161 | KM | 412160 | Newlands | KAILI | WATHANA | 0.161 | KM | NC03ML1165 | 0.88 | NC03ML1166 | 0.041 | KM |  |  |  |  | 1165.88 | 1166.041 | 2023-06-30 | MAIN LINE | [12 empty] | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification completed | NWSC | FY23 IN NON MRSB | 20230630 | 20/04/2023 Update to Location data inline with existing linear reference data
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052752&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052752 | C05-FR-NL-MCNAUGHTON JCT-79.260km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.65 | KM | 1487486 | Newlands | MCNAUGHTON JCT | SONOMA | 0.64 | KM | NL01ML79 | 0.26 | NL01ML79 | 0.9 | KM |  |  |  |  | 79.26 | 79.9 | 2023-06-30 | MAIN LINE |  |  |  | 3 | 2.5 |  |  |  | 7.5 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 10:03:47 AUSQLD Jane Livingston (R111275) * Level Crossing was refurbished in 2017; Clean Ballast. In a cutting with a subgrade that lets water through. Poor Drainage causing the Formation issues. 20% Unsuitable. * 12.04.2021 16:21:13 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068070&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068070 | C05-FR-BW-MIDGEE-631.900km | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 1015162 | Blackwater | MIDGEE | ROCKLANDS | 0.6019 | KM | BW02ML631 | 0.9 | BW02ML632 | 0.5 | KM |  |  |  |  | 631.9 | 632.5 | 2023-06-30 | DOWN |  |  |  | 3.5 | 4.2 |  |  |  | 14.7 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:09:01 AUSQLD Jane Livingston (R111275) * 2 Fix on fail formation jobs completed at beginning of July 2020. Clay seams and Rock through area. Attach DCPs and Photos from previous jobs. Holding of water and rocks at sites. Rock broke up with excavator. Access is okay, bit of a cutting down one end of job. 631.695km on NCL: CBR 25 500 -800mm Depth from previous job. 20% Unsuitable. * 12.04.2021 16:21:10 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075272&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075272 | C05-FR-BW-MIDGEE-631.900km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 1015162 | Blackwater | MIDGEE | ROCKLANDS | 0.6019 | KM | BW01ML631 | 0.9 | BW01ML632 | 0.5 | KM |  |  |  |  | 631.9 | 632.5 | 2023-06-30 | UP |  |  |  | 4 | 4.9 |  |  |  | 19.6 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:05:25 AUSQLD Jane Livingston (R111275) * 2 Fix on fail formation jobs completed at beginning of July 2020. Clay seams and rock through area. Attach DCPs and Photos from these previous jobs. Holding of water and rocks at sites. Rock broke up with excavator. Access is okay, bit of a cutting down one end of job. 631.695km on NCL: CBR 25 500 -800mm Depth from previous job. 20% Unsuitable.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052718&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000052718 | C05-FR-GA-MILLENNIUM-23.050km | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.65 | KM | 1596306 | Goonyella | MILLENNIUM | RED MOUNTAIN | 0.65 | KM | GA03ML23 | 0.05 | GA03ML23 | 0.6999 | KM |  |  |  |  | 23.05 | 23.7 | 2023-06-30 | MAIN LINE |  |  |  | 3 | 2.4 |  |  |  | 7.2 | 5220 | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:58:13 AUSQLD Jane Livingston (R111275) * Combined Notification No. 2000052718 and no. 2000052719 together and extend to be 23.050km to 23.700km GA-03ML - 30% unsuitable replacement; 22.977km CBR 3.0 @360 - 600mm; CBR 2.5 @ 600 - 900mm; 23.312km CBR 2.5 @ 600 -1250. * 12.04.2021 16:21:12 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075328&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000075328 | C05-FR-GA-MINDI-124.100km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.3 | KM | 914045 | Goonyella | MINDI | SOUTH WALKER | 0.2999 | KM | GA02ML124 | 0.1 | GA02ML124 | 0.4 | KM |  |  |  |  | 124.1 | 124.4 | 2023-06-30 | UP |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 10:17:30 AUSQLD Jane Livingston (R111275) * Test Pit at 124.12km - roadbase capping layer, geogrid and CBR 70 @ capping layer; CBR 2 at subgrade. Very fouled ballast. Struggles to hold up in the wet. We do have DCPs showing formation issues. 124.2km Test Pit - Mudholes, no capping layer, work completed on a previous section (124.120km) need to look for weld. CBR 4 @ 340 -890. Down Road - Gravelly capping layer - CBR 20 - CBR 8 at subgrade. 20% unsuitable. 22.12.2021 Tim Griffin (r8788533) - Shut to rail traffic on w/end of 18-19 Dec 2021 (See attached email and photo's) in attachment. 5.01.2022 Tim Griffin (r878533). N7 with D14 imposed on 30/12/2021 since mechanised resurfacing efforts of 28Dec (less than 48hrs) failed to hold leg, due to ballast fouling. Ballast u/c to be undertaken Jan2022 IP GYella Closure along with planned field side Shear Key repair at 124km237m since presently on weekly inspections and 15km/hr TSR. See attached email for details.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052721&DY_MAB=X&~OKCODE=ONLI | FY23 |  | BASELOAD | COAL | 002000052721 | C05-FR-GA-PEAK DOWNS-56.400km | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.7 | KM | 1719101 | Goonyella | PEAK DOWNS | HARROW | 0.6999 | KM | GA03ML56 | 0.4 | GA03ML57 | 0.1 | KM |  |  |  |  | 56.4 | 57.1 | 2023-06-30 | MAIN LINE |  |  |  | 3.5 | 2.4 |  |  |  | 8.4 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 10:01:13 AUSQLD Jane Livingston (R111275) * Test Pit at Moist Clay subgrade; CBR 4.5 at subgrade - consistent 4.5 CBR to 600mm depth therefore no capping layer. Poor drainage through area. 20% Unsuitable. * 12.04.2021 16:21:12 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052751&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052751 | C05-FR-NL-PRING-5.500km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.365 | KM | 835280 | Newlands | PRING | BUCKLEY | 0.3649 | KM | NL01ML5 | 0.5 | NL01ML5 | 0.8649 | KM |  |  |  |  | 5.5 | 5.865 | 2023-06-30 | MAIN LINE |  |  |  | 3.5 | 2.5 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 10:02:57 AUSQLD Jane Livingston (R111275) * Test Pit at the 6.4km: DCP results from last time is 5.816km - 5.986km - Not too bad at 5.816km end - 3blows at 600mm deep, increasing as going down. At the 5.985km, worse material. 50% unsuitable. Difficult access if wet. * 12.04.2021 16:21:12 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075274&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075274 | C05-FR-BW-WARREN-28.000km | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.217 | KM | 397947 | Blackwater | WARREN | WYCARBAH | 0.2169 | KM | BW03ML28 | 0 | BW03ML28 | 0.2169 | KM |  |  |  |  | 28 | 28.217 | 2023-06-30 | DOWN |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:14:43 AUSQLD Jane Livingston (R111275) * Originally Notification was 28km - 28.750km which includes a bridge. Formation at 31km in FY21. Bridge completed in Fy21 - split notifications into 2 - before and after bridge. Previous Geotech results fromm 29km on Down Rd - Rocky gravel capping at 900mm. CBR 13 at 910mm deep and CBR 2 at 900mm. If you go too deep you will hit the Moist Clay. Field Scope Check list of Bridge. Check job went passed splays. 30% Unsuitable Material * 31.03.2021 09:26:37 AUSQLD Jane Livingston (R111275) * Bridge is Kennedy creek. Bridge location including Splays is 28.217 - 28.309km. CBR 13 at 910mm deep and CBR 2 at 900mm. If you go too deep you will hit the Moist Clay. Field Scope Check list of Bridge. Check job went passed splays. 30% Unsuitable Material 31.03.2021 09:26:37 AUSQLD Jane Livingston (R111275) Bridge is Kennedy creek. Bridge location including Splays is 28.217 - 28.309km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075327&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075327 | C05-FR-BW-WARREN-28.309km | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.441 | KM | 808730 | Blackwater | WARREN | WYCARBAH | 0.441 | KM | BW03ML28 | 0.3089 | BW03ML28 | 0.75 | KM |  |  |  |  | 28.309 | 28.75 | 2023-06-30 | DOWN |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 09:32:28 AUSQLD Jane Livingston (R111275) * Originally Notification was 28km - 28.750km which includes a bridge. Formation at 31km in FY21. Bridge completed in Fy21 - split no = tifications into 2 - before and after bridge. Previous Geotech results fromm 29km on Down Rd - Rocky gravel capping at 900mm. CBR 13 at 910mm deep and CBR 2 at 900mm. If you go too deep you will hit the Moist Clay. Field Scope Check list of Bridge. Check job went passed splays. 30% Unsuitable Material. Bridge is Kennedy creek. Bridge location including Splays is 28.217 - 28.309km. tifications into 2 - before and after bridge. Previous Geotech results fromm 29km on Down Rd - Rocky gravel capping at 900mm. CBR 13 at 910mm deep and CBR 2 at 900mm. If you go too deep you will hit the Moist Clay. Field Scope Check list of Bridge. Check job went passed splays. 30% Unsuitable Material. Bridge is Kennedy creek. Bridge location including Splays is 28.217 - 28.309km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044383&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044383 | Formation C05 Reactive Works | BW | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2021-03-31 | 2021-10-05 | Formation Reactive | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | 21.02.2022 Tim Griffin (r878533) See attached email commitment for $35 ,000 FoF reactive formation for 10m in conjunction with Tryphinia Level Crossing renewal upgrade.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044312&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044312 | Formation C05 Reactive Works | GA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4.5 | 4.7 |  |  |  | 21.2 |  | 2021-03-31 | 2021-10-05 | Formation Reactive | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044384&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044384 | Formation C05 Reactive Works | MA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 775000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2021-03-31 | 2021-10-05 | Formation Reactive | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044385&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044385 | Formation C05 Reactive Works | NL | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 468500 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4.5 | 2 |  |  |  | 9 |  | 2021-03-31 | 2021-10-05 | Formation Reactive | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074772&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074772 | FORMATION GEOTECH DESIGN | BW | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 30000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 3.5 |  |  |  | 14 |  | 2021-03-31 | 2021-10-05 | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 23.03.2021 08:52:21 AUSQLD Jane Livingston (R111275) * THIS WORK IS FOR THE GEOTECHNICAL INVESTIGATION AND DESIGN FOR BRIDGE ROLLOUTS, LEVEL CROSSINGS AND FORMATION RENEWALS. * 12.04.2021 16:20:52 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074770&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074770 | FORMATION GEOTECH DESIGN | GA | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 30000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 23.03.2021 08:45:13 AUSQLD Jane Livingston (R111275) * THIS WORK IS FOR THE GEOTECHNICAL INVESTIGATION AND DESIGN FOR BRIDGE ROLLOUTS, LEVEL CROSSINGS AND FORMATION RENEWALS. * 12.04.2021 16:20:52 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074774&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074774 | FORMATION GEOTECH DESIGN | MA | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 20000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 1.5 |  |  |  | 6 |  | 2021-03-31 | 2021-10-05 | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 23.03.2021 09:05:30 AUSQLD Jane Livingston (R111275) * THIS WORK IS FOR THE GEOTECHNICAL INVESTIGATION AND DESIGN FOR BRIDGE ROLLOUTS, LEVEL CROSSINGS AND FORMATION RENEWALS. * 12.04.2021 16:20:53 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074773&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074773 | FORMATION GEOTECH DESIGN | NL | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 20000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 2.5 |  |  |  | 10 |  | 2021-03-31 | 2021-10-05 | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 23.03.2021 08:58:01 AUSQLD Jane Livingston (R111275) * THIS WORK IS FOR THE GEOTECHNICAL INVESTIGATION AND DESIGN FOR BRIDGE ROLLOUTS, LEVEL CROSSINGS AND FORMATION RENEWALS. * 12.04.2021 16:20:53 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074780&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074780 | FY23 CIVIL GPR RUN BLACKWATER | BW | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 624000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Ground Penetrating Radar | STRATEGIC | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 17:58:30 AUSQLD Jane Livingston (R111275) * INCLUDE SCREENABILITY IN THE SCOPE. APPROX KM BASED ON FY21 SCOPE = 954.068KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074777&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074777 | FY23 CIVIL GPR RUN GOONYELLA | GA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 590000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Ground Penetrating Radar | STRATEGIC | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 18:02:18 AUSQLD Jane Livingston (R111275) * INCLUDE SCREENABILITY IN THE SCOPE FOR FUTURE YEARS SCOPE HANDOVER. SCOPE BASED ON FY21 SUBMISSION IS 796.421KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079978&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079978 | Level Crossing Design | LX020210 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Blackwater | BLACKWATER | SAGITARIUS | 0 | KM | BW03ML189 | 0.6999 | BW03ML189 | 0.6999 | KM |  |  | 189.7 | 189.7 | 189.7 | 189.7 | 2025-06-30 | EMERGENCY ACCESS ROAD |  | AS PER NEW DESIGN | AS PER NEW DESIGN |  |  | 2 | 25 | 1 | 25 | 5758 | 2023-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240412 | Moved to FY23 for designing the site two years in advance. FY24 Design <(>&<)> depending on TMR design availability. Civil Design Team to progress. 20.03.2022 A new crossing to be designed and constructed. Considered as a strategic one. Future condition 10, Criticality Index 10, CRA Index 100.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079988&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079988 | FY23 Level Crossing Design | LX006951 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML42 | 0.4249 | BW06ML42 | 0.4249 | KM |  |  | 42.425 | 42.425 | 42.425 | 42.425 | 2025-06-30 | COMET ROLLESTON RD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3 | 3.2 | 2 | 3 | 1 | 9.8 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240517 | PCR 5338- moved to FY23 Design for FY25 latest construction date 26 March- amended condition assessment is provided. FY23 DESIGN for FY25 Delivery. Rail is as per the new formation extent
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079989&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079989 | FY23 Level Crossing Design | LX006952 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML53 | 0.0899 | BW06ML53 | 0.0899 | KM |  |  | 53.09 | 53.09 | 53.09 | 53.09 | 2025-06-30 | STRAUN ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 4.43 | 3.7 | 2 | 3 | 1 | 12.6 | 5758 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240517 | 29 March- PCR 5338, moved to FY23 for earlier design and construction in FY25. 26 March 2022- amended condition assessment is provided. FY23 DESIGN FOR FY25 DELIVERY. All supporting documents have been added in SPM. 20.03.2022 Condition assessment does not include rail and flangeway condition. The overall condition is 2.55 excluding. CRA Index was calculated based on OC 2.55. To be amended in the future when further updated OC is provided by inspectors.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083378&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083378 | FY23 Level Crossing Design | LX005558 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Blackwater | DUARINGA | WALLAROO | 0 | KM | BW03ML115 | 0.758 | BW03ML115 | 0.758 | KM |  |  | 115.758 | 115.758 | 115.758 | 115.758 | 2025-06-30 | WABBLER ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.3 | 3.35 | 2 | 4 | 1 | 13.2 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240426 | 29 March- PCR 5338, moved to FY23 Design for FY25 Renewal FY24 DESIGN for FY25 renewal. All supporting docs are added. Rail extent and formation extent are accordance with the new std. Standard design documents are added. Nearby Turnout ER1.2A is being renewed in April FY22 and extents of this renewal carry into extents of LX renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068861&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068861 | Level Crossing Design | LX005587 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Blackwater | EPALA | RAGLAN | 0 | KM | BW01ML579 | 0.8359 | BW01ML579 | 0.8359 | KM |  |  |  |  | 579.836 | 579.836 | 2023-06-30 | PARSONS CROSSING |  |  |  | 2.4 | 4.1 |  |  |  | 9.8 | 5707 | 2021-03-31 | 2021-10-05 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20240630 | * 22.03.2021 20:51:15 AUSQLD Sharbaree Biswas (R865006) * LINEAR DATA AND CRITICALITY ENTERED 22.03.2021 20:51:15 AUSQLD Sharbaree Biswas (R865006) LINEAR DATA AND CRITICALITY ENTERED
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088576&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000088576 | FY23 Level Crossing Design | LX007377 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Goonyella | HAY POINT BALLOON | HAY POINT BALLOON | 0 | KM | GA01BA3 | 0.1 | GA01BA3 | 0.1 | KM |  |  | 3.1 | 3.1 | 3.1 | 3.1 | 2025-06-30 | MAINTENANCE ACCESS ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.3 | 2.3 | 2 | 3 | 1 | 6.9 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20250207 | 29 March 2022- PCR 5338- moved to FY23 DESIGN for FY25 RENEWAL Truck pumping was observed. Severe rail defects in Loop 1 and 2 roads. Flangeways were installed but not maintained properly, gravel deposition into the flangeway gaps. Flangeway clips were installed incorrectly. Heavy duty insulators were observed, which are not allowed to be installed with flangeways. 20.03.2022 Overall condition is 1.8, which is near new, does not match with other supporting documents for renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088579&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000088579 | FY23 Level Crossing Design | LX003251 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Goonyella | MOOREVALE | INGSDON | 0 | KM | GA03ML10 | 0.935 | GA03ML10 | 0.935 | KM |  |  | 10.935 | 10.935 | 10.935 | 10.935 | 2025-06-30 | DAUNIA ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.4 | 2.4 | 2 | 3 | 1 | 7.2 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240531 | 29 March- PCR 5338, moved to FY23 DESIGN for FY25 RENEWAL Top <(>&<)> line issues (up direction down road), water pooling in S3-3 quadrant, 2007 rail down road up direction, IRS sign missing, line marking missing. Sharbaree Biswas comments on 15 March 2022: Condition assessment is not reflective and supportive to the other documents, GPR, track recording, site photos, rail history etc. Superintendent Engineering Civil is accountable to bring is adequate condition data.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067766&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000067766 | Level Crossings Reactive Works | BW | CIVIL | LEVEL CROSSINGS | C58 | REACTIVE WORKS | 1 | LUMPSUM | 340000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Level Crossing Other | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067767&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000067767 | Level Crossings Reactive Works | GA | CIVIL | LEVEL CROSSINGS | C58 | REACTIVE WORKS | 1 | LUMPSUM | 220000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Level Crossing Other | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067768&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000067768 | Level Crossings Reactive Works | MA | CIVIL | LEVEL CROSSINGS | C58 | REACTIVE WORKS | 1 | LUMPSUM | 70000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Level Crossing Other | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067769&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000067769 | Level Crossings Reactive Works | NL | CIVIL | LEVEL CROSSINGS | C58 | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Level Crossing Other | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068868&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068868 | FY23 Level Crossing Design | LX006022 | CIVIL | LEVEL CROSSINGS | DESIGN | DESIGN | 1 | SITE | 30000 | Moura | ANNANDALE | EARLSFIELD | 0 | KM | MA01ML125 | 0.2 | MA01ML125 | 0.2 | KM |  |  |  |  | 125.2 | 125.2 | 2025-06-30 | EARLSFIELD PIT ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.76 | 1.2 | 2 | 2.6 | 1 | 9.8 | 5338 |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20250228 | PCR 5338- moved to FY23 for completing the design two years in advance. 23 March 2022 - amended condition assessment is provided. 17 March- waiting on revised overall condition.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079987&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079987 | FY23 Level Crossing Design | LX003654 | CIVIL | LEVEL CROSSINGS | DESIGN | DESIGN | 1 | SITE | 30000 | Blackwater | GREGORY JUNCTION | OAKY CREEK | 0 | KM | BW08ML74 | 0.8289 | BW08ML74 | 0.8289 | KM |  |  | 74.829 | 74.829 | 74.829 | 74.829 | 2025-06-30 | OAKY CK MINE ACCESS RD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.5 | 2 | 2 | 2 | 1 | 5 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20240524 | 29 March -PCR 5338, moved to FY23 Design for FY25 renewal. No flangeways present- condition rating was 2.5, which should have been 4.5 (raising overall condition rating from 2.04 to 2.08). Site photos indicated top and line issues- the condition rating was 2.0. Condition assessment and other supporting docs do not quite match. Standard design documents have been added until the bespoke design is available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044043&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000044043 | 4989 Level Crossings Renewal | LX005159 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 500815 | Newlands | ABBOTT POINT ROAD |  | 0 | KM | NC03ML1166 | 0.08 | NC03ML1166 | 0.08 | KM |  |  |  |  | 1166.08 | 1166.08 | 2023-06-30 | ABBOTT POINT ROAD |  |  |  | 2.5 | 2.5 |  |  |  | 6.3 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN NON MRSB | 20230630 | * 19.03.2021 16:25:10 AUSQLD Sharbaree Biswas (R865006) * ID5159 Abbott Point Access Road has been requested to be renewed with track upgrade in FY23. Moving this to FY23. This is a critical crossing for the Abbott Point and it is complicated to organise two closures in two consecutive years, FY23 and FY24. * 12.04.2021 16:22:36 AUSQLD Jeremy Stevenson (R867415) * No design, geotech or BMF complete for this N4 - n eed to determine if it is std or bespoke design an * d if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve? * curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068841&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068841 | LEVEL CROSSING RENEWAL | LX003303 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 382291 | Newlands | ALMOOLA | MCNAUGHTAN | 0 | KM | NL01ML79 | 0.255 | NL01ML79 | 0.255 | KM |  |  |  |  | 79.255 | 79.255 | 2023-06-30 | CORDUROY CREEK RD |  |  |  | 2.1 | 2.4 |  |  |  | 5 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:05:43 AUSQLD Tracy Holmes (R870040) * No design, geotech or BMF complete for this N4 - need to determine if it is std or bespoke design and if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043428&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043428 | 3607 Level Crossings Renewal. | LX001776 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 813922 | Blackwater | BAJOOL | ARCHER | 0 | KM | BW01ML606 | 0.646 | BW01ML606 | 0.646 | KM |  |  |  |  | 606.65 | 606.65 | 2023-06-30 |  |  |  |  | 2.7 | 4.5 |  |  |  | 12.2 | 3662 | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:06:01 AUSQLD Tracy Holmes (R870040) * No design, geotech or BMF complete for this N4 - need to determine if it is std or bespoke design and if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044021&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044021 | 4967 Level Crossings Renewal. | LX006047 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 382291 | Moura | BELLDEEN | MOURA JCT | 0 | KM | MA01ML159 | 0.4989 | MA01ML159 | 0.4989 | KM |  |  |  |  | 159.5 | 159.5 | 2023-06-30 | SINGLE |  |  |  | 2.9 | 1.3 |  |  |  | 3.8 | 3662 | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:06:06 AUSQLD Tracy Holmes (R870040) * No design, geotech or BMF complete for this N4 - need to determine if it is std or bespoke design and if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044039&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044039 | 4985 Level Crossings Renewal. | LX005612 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 813922 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML173 | 0.2409 | BW03ML173 | 0.2409 | KM |  |  |  |  | 173.258 | 173.26 | 2023-06-30 | SUBSTATION ACCESS ROAD |  |  |  | 2.4 | 3.4 |  |  |  | 8.2 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:06:13 AUSQLD Tracy Holmes (R870040) * No design, geotech or BMF complete for this N4 - need to determine if it is std or bespoke design and if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044044&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044044 | 4990 L/Xing Renewal NL 87.250km ID 3310. | LX003310 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 382291 | Newlands | SONOMA MINE ACCESS RD |  | 0 | KM | NL01ML87 | 0.251 | NL01ML87 | 0.251 | KM |  |  |  |  | 87.25 | 87.25 | 2023-06-30 | SONOMA MINE ACCESS ROAD |  |  |  | 2.5 | 2.5 |  |  |  | 6.3 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF | FY23 IN | 20240630 | * 01.12.2020 11:05:06 AUSQLD Sharbaree Biswas (R865006) * RAP engineer and IM advised the crossing has higher priority over LX005159. * 01.12.2020 11:12:09 AUSQLD Sharbaree Biswas (R865006) make any changes. * 12.04.2021 16:21:40 AUSQLD Jeremy Stevenson (R867415) * No design, geotech or BMF complete for this N4 - n eed to determine if it is std or bespoke design an * d if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve? *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051903&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000051903 | Level Crossing Renewal. | LX005559 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 813922 | Blackwater | TRYPHINIA | GOOWARRA | 0 | KM | BW03ML123 | 0.342 | BW03ML123 | 0.342 | KM |  |  |  |  | 123.342 | 123.342 | 2023-06-30 | TRYPHINA ROAD |  |  |  | 2.6 | 3.4 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF | FY23 IN | 20240630 | * 18.02.2020 12:46:10 AUSQLD Sanjna Rajagopalan (R884639) * Bought into FY22 due to poor condition * 09.03.2020 11:24:19 AUSQLD Sharbaree Biswas (R865006) * Pushed to FY23 due to funding restriction. * 12.04.2021 16:22:26 AUSQLD Jeremy Stevenson (R867415) * No design, geotech or BMF complete for this N4 - n eed to determine if it is std or bespoke design an * d if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve? *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000047175&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000047175 | Level Crossings Signal Installation | LX005560 | CIVIL | LEVEL CROSSINGS | MAJOR UPGRADE SIGNAL | RENEWAL | 1 | SITE | 1679107 | Blackwater | GOOWARRA | DINGO | 0 | KM | BW03ML133 | 0.1809 | BW03ML133 | 0.1809 | KM |  |  |  |  | 133.187 | 133.187 | 2023-06-30 |  |  |  |  | 2.7 | 3.4 |  |  |  | 9.2 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 01.11.2019 11:55:50 AUSQLD Allan Gough (R873345) * ASSET Protection Required - including Boom Gates * * Upgrade to flashing lights and boom gates: Central - Mourindilla Road -Double (Blackwater System - 133.187km) * 15.01.2020 10:26:44 AUSQLD Sanjna Rajagopalan (R884639) * * Moved from FY21 to FY22 due to funding, with possibility of moving to FY23 * 09.03.2020 11:54:41 AUSQLD Sharbaree Biswas (R865006) * Moved into FY23 now.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073726&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073726 | Level Crossing Signal Installation- | LX005559 | CIVIL | LEVEL CROSSINGS | MAJOR UPGRADE SIGNAL | UPGRADE | 1 | SITE | 1679107 | Blackwater | TRYPHINIA | GOOWARRA | 0 | KM | BW03ML123 | 0.342 | BW03ML123 | 0.342 | KM |  |  |  |  | 123.342 | 123.342 | 2023-06-30 | TRYPHINIA ROAD |  |  |  | 2.6 | 3.4 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:05:51 AUSQLD Tracy Holmes (R870040) * No design, geotech or BMF complete for this N4 - need to determine if it is std or bespoke design and if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve?
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070850&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070850 | Rail Renewal. | CV006191 | CIVIL | RAIL |  | RENEWAL |  |  |  | Blackwater | TUNNEL | EDUNGALBA | 0.188 | KM | BW03ML76 | 0.537 | BW03ML76 | 0.7249 | KM |  |  |  |  | 76.536 | 77.725 | 2023-03-31 | DOWN | BOTH |  |  | 3 | 3.8 |  |  |  | 11.4 |  | 2021-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | SCPR | FY23 IN | 20230308 | * 18.03.2021 21:31:32 AUSQLD Sanjna Rajagopalan (R884639) * 2 curves in one scope so 2 shell notifications: * 2000070850 - this one has all qtys * * Re Rail only * 76.537km - 76.725km * BW 03ML - DOWN - both legs - 22 Rails total * renewal put forward due to high wearing location * FYQ2 or Q3 * 18.03.2021 21:40:10 AUSQLD Sanjna Rajagopalan (R884639) * 2000071149
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070703&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070703 | BW C17 UP ALDOGA 563.693-564.707 | CV005878 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Blackwater | ALDOGA | MOUNT LARCOM | 1.0389 | KM | BW01ML563 | 0.6929 | BW01ML564 | 0.7069 | KM |  |  |  |  | 563.693 | 564.707 | 2023-03-31 | UP | BOTH |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 20:21:36 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 20:13:51 AUSQLD Sanjna Rajagopalan (R884639) * PLEASE NOTE 3 CURVES IN ONE - SO TOTAL 3 SHELL NOTIFICATIONS FOR ONE SCOPE * * ALL THREE NOTIFICATION NUMBERS: * 2000071106 * 2000070703 * * Re Rail Only * Aldoga - Mount Larcom * 563.689km - 654.716km * UP Road - both rails - Total rails 19 * Renewal driven by Wear * FY23 Q1 Execution - SC so please put in early Q1 * 18.03.2021 20:19:28 AUSQLD Sanjna Rajagopalan (R884639) * cut out point TOS 11C/D * 19.03.2021 22:42:43 AUSQLD Sanjna Rajagopalan (R884639) * ALL 3 NOTIFICATION NUMBERS: * - 2000071106 - HAS ALL QTYS * - 2000070703 * - 2000070704 * Post walk out: 563.693 - 564.707
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070704&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070704 | BW C17 UP ALDOGA 563.693-564.707 | CV005880 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Blackwater | ALDOGA | MOUNT LARCOM | 1.0389 | KM | BW01ML563 | 0.6929 | BW01ML564 | 0.7069 | KM |  |  |  |  | 563.693 | 564.707 | 2023-03-31 | UP | BOTH |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 20:23:57 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 20:21:36 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 20:13:51 AUSQLD Sanjna Rajagopalan (R884639) * PLEASE NOTE 3 CURVES IN ONE - SO TOTAL 3 SHELL NOTIFICATIONS FOR ONE SCOPE * * ALL THREE NOTIFICATION NUMBERS: * 2000071106 * 2000070703 * 2000070704 * * Re Rail Only * Aldoga - Mount Larcom * 563.689km - 654.716km * UP Road - both rails - Total rails 19 * Renewal driven by Wear * FY23 Q1 Execution - SC so please put in early Q1 * 18.03.2021 20:19:28 AUSQLD Sanjna Rajagopalan (R884639) * cut out point TOS 11C/D * 19.03.2021 22:44:44 AUSQLD Sanjna Rajagopalan (R884639) * ALL 3 NOTIFICATION NUMBERS: * - 2000071106 - HAS ALL QTYS * - 2000070703 * - 2000070704 * Post walk out: 563.693 - 564.707
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071106&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071106 | BW C17 UP ALDOGA 563.693-564.707. | CV005877 | CIVIL | RAIL |  | RENEWAL | 2.052 | KM | 689479 | Blackwater | ALDOGA | MOUNT LARCOM | 1.0389 | KM | BW01ML563 | 0.6929 | BW01ML564 | 0.7069 | KM | 19 |  | 2.052 | 1.026 | 563.693 | 564.707 | 2023-03-31 | UP | BOTH |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 20:13:51 AUSQLD Sanjna Rajagopalan (R884639) * PLEASE NOTE 3 CURVES IN ONE - SO TOTAL 3 SHELL NOTIFICATIONS FOR ONE SCOPE * * ALL THREE NOTIFICATION NUMBERS: * 2000071106 * * * Re Rail Only * Aldoga - Mount Larcom * 563.689km - 654.716km * UP Road - both rails - Total rails 19 * Renewal driven by Wear * FY23 Q1 Execution - SC so please put in early Q1 * 18.03.2021 20:19:28 AUSQLD Sanjna Rajagopalan (R884639) * cut out point TOS 11C/D * 19.03.2021 22:41:05 AUSQLD Sanjna Rajagopalan (R884639) * ALL 3 NOTIFICATION NUMBERS: * - 2000071106 - HAS ALL QTYS * - 2000070703 * - 2000070704 * Latest renewal date updated to 31.12.2022 - post field measurements POST SITE WALKOUT: 563.693 - 564.707 - 19 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070881&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070881 | BW C17 DOWN ARCHER 614.62-615.43 | CV006505 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Blackwater | ARCHER | BAJOOL | 0.8659 | KM | BW02ML614 | 0.5649 | BW02ML615 | 0.4299 | KM |  |  |  |  | 614.565 | 615.43 | 2024-06-30 | DOWN | BOTH |  |  | 3.5 | 4.5 |  |  |  | 15.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 10:54:17 AUSQLD Sanjna Rajagopalan (R884639) * re rail * 2 curves = 2 notifications * 2000070880 - has all qtys * 2000070881 * * 614.620 - 615.431 * both legs - 15 rails total * Renewal driven by wear Post walkout: 614.565 - 615.430 - 16 rails Proposed additional 1 x rail to end in clear area and remove more SC rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070880&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070880 | BW C17 DOWN BAJOOL 614.565-615.43. | CV006504 | CIVIL | RAIL |  | RENEWAL | 1.728 | KM | 661469 | Blackwater | BAJOOL | ARCHER | 0.8659 | KM | BW02ML614 | 0.5649 | BW02ML615 | 0.4299 | KM | 16 |  | 1.728 | 0.865 | 614.565 | 615.43 | 2022-12-31 | DOWN | BOTH |  |  | 3.5 | 4.5 |  |  |  | 15.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 30.03.2021 10:42:06 AUSQLD Sanjna Rajagopalan (R884639) * re rail * 2 curves = 2 notifications * 2000070880 - has all qtys * * 614.620 - 615.431 * both legs - 15 rails total * Renewal driven by wear * Q4 Post walkout: 614.565 - 615.430 - 16 rails Proposed additional 1 x rail to end in clear area and remove more SC rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070960&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070960 | NL C17 BINBEE 50.425-51.25 | CV003434 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Newlands | BINBEE | BRIABA | 0.8239 | KM | NL01ML50 | 0.4249 | NL01ML51 | 0.25 | KM |  |  |  |  | 50.425 | 51.25 | 2023-03-31 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 18:53:17 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 18:46:40 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 3 CURVES = 3 NOTIFICATIONS: * - 2000070664 - this one has all the qtys * - 2000070667 * - 2000070960 * * 50.360km - 51.250km * NL - 01ML * BOTH RAILS - 8 RAILS TOTAL * Renewal driven by wear CHANGES AFTER SITE WALKOUTS: LEFT RAIL: 50.815 - 51.250 RIGHT RAIL - 50.425 - 50.803 8 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070667&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070667 | NL C17 SINGLE BINBEE 50.425-51.25 | CV003433 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Newlands | BINBEE | BRIABA | 0.8239 | KM | NL01ML50 | 0.4249 | NL01ML51 | 0.25 | KM |  |  |  |  | 50.425 | 51.25 | 2023-03-31 | SINGLE | BOTH |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 18:51:40 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 18:46:40 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 3 CURVES = 3 NOTIFICATIONS: * - 2000070664 - this one has all the qtys * - 2000070667 * * 50.360km - 51.250km * NL - 01ML * BOTH RAILS - 8 RAILS TOTAL * Renewal driven by wear * 19.03.2021 18:53:58 AUSQLD Sanjna Rajagopalan (R884639) * 3 CURVES = 3 NOTIFICATIONS: * - 2000070664 - this one has all the qtys * - 2000070667 * - 2000070960
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070664&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070664 | NL C17 SINGLE BINBEE 50.425-51.25. | CV003432 | CIVIL | RAIL |  | RENEWAL | 0.864 | KM | 464817 | Newlands | BINBEE | BRIABA | 0.8239 | KM | NL01ML50 | 0.4249 | NL01ML51 | 0.25 | KM | 8 |  | 0.864 | 0.825 | 50.425 | 51.25 | 2023-03-31 | SINGLE | BOTH |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 19.03.2021 18:46:40 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 3 CURVES = 3 NOTIFICATIONS: * - 2000070664 - this one has all the qtys * * 50.360km - 51.250km * NL - 01ML * BOTH RAILS - 8 RAILS TOTAL * Renewal driven by wear * 19.03.2021 18:54:41 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 3 CURVES = 3 NOTIFICATIONS: * - 2000070664 - this one has all the qtys * - 2000070667 * - 2000070960 CHANGES AFTER SITE WALKOUTS: LEFT RAIL: 50.815 - 51.250 - 0.435km RIGHT RAIL - 50.425 - 50.803 - 0.378km 8 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074693&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074693 | GA C17 UP BLACK MOUNTAIN 34.743-36.023. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.296 | KM | 539818 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 1.2649 | KM | GA02ML34 | 0.756 | GA02ML36 | 0.0189 | KM | 12 |  | 1.296 | 1.263 | 34.756 | 36.019 | 2022-12-31 | UP | CHECK SCOPE |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 12:24:22 AUSQLD Sanjna Rajagopalan (R884639) * Awaiting tech scope * * Left leg: 34.756 - 35.49 * Right leg:35.483- 36.019 * 12.04.2021 16:20:50 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071020&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071020 | GA C17 UP BLACK MOUNTAIN 42.857-43.613 | CV002920 | CIVIL | RAIL |  | RENEWAL | 0.972 | KM | 457996 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.756 | KM | GA02ML42 | 0.8569 | GA02ML43 | 0.6129 | KM | 9 |  | 0.972 | 0.756 | 42.857 | 43.613 | 2022-12-31 | UP | BOTH |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:41:12 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * BLACK MOUNTAIN * GA-02ML - UP42.857-43.613 BOTH LEGS * Total lengths of rail = 9 * FY23 Q2 * * 4 curves = 4 notifications * - 2000071020 - this has all qtys * 19.03.2021 21:55:52 AUSQLD Sanjna Rajagopalan (R884639) * 3 CURVES = 3 NOTIFICATIONS * * - 2000071020 - this has all qtys * - 2000070779 * - 2000070771 * LEFT: 42.857 - 43.613 = 7 RAILS RIGHT: 42.868 - 43.084 = 2 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071027&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071027 | GA C17 UP BLACK MOUNTAIN 41.391-41.9 | CV002912 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.515 | KM | GA02ML41 | 0.391 | GA02ML41 | 0.906 | KM |  |  |  |  | 41.391 | 41.9 | 2023-12-31 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20250701 | * 19.03.2021 15:44:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail Only * 2 Curves = 2 notifications: * * 2000070778 -this one has all qtys * 2000071027 * * 41.391 - 41.900 - UP 5.5 rails * cut in and cut outs are different for both legs * * cant review required on both curves * tie left rail into FY22 RRP starting 41.900km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070767&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070767 | GA C17 UP BLACK MOUNTAIN 44.518-45.058. | CV002931 | CIVIL | RAIL |  | RENEWAL | 1.08 | KM | 476069 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.545 | KM | GA02ML44 | 0.518 | GA02ML45 | 0.058 | KM | 10 |  | 1.08 | 0.54 | 44.518 | 45.058 | 2023-12-31 | UP | BOTH |  |  | 3 | 5 |  |  |  | 15 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 18:37:43 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail - ONE LEG ONLY * 44.518 - 45.058 * Black Mountail - Hatfield - UP * 5 rails * * renewal driven by rail wear * * RIGHT RAIL/ LOW LEG ONLY * Left Rail/ High Leg in next renewal cycle as per asset strategy Post Walk Out: Both legs are to be done as there is 5mm side wear on the Left Leg at the 44.722km - qty and estimate has been updated
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043655&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043655 | GA C17 DOWN BLACK MOUNTAIN 47.49-48.53. | GA-01ML | CIVIL | RAIL |  | RENEWAL | 2.08 | KM | 699673 | Goonyella | BLACK MOUNTAIN | HATFIELD | 1.0409 | KM | GA01ML47 | 0.4899 | GA01ML48 | 0.53 | KM | 19 | 0 | 2.08 | 1.04 | 47.49 | 48.53 | 2022-12-30 | DOWN | BOTH |  |  | 4 | 5 |  |  |  | 20 | 38 | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 13.08.2020 10:18:34 AUSQLD Milton Saha (R884640) * PUSHED TO FY23 Q2 DUE TO REVIEW BY MS AND AC 13.08.2020 * 23.03.2021 09:50:53 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL ONLY * HATFIELD - GA-01ML * 47.49 - 58.53 - DOWN - BOTH LEGS * 19 RAILS TOTAL * * 23.03.2021 09:52:48 AUSQLD Sanjna Rajagopalan (R884639) * 47.49 - 48.53
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070756&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070756 | GA C17 UP BOLINGBROKE 62.623-63.001. | CV002963 | CIVIL | RAIL |  | RENEWAL | 0.756 | KM | 401029 | Goonyella | BOLINGBROKE | BALOOK | 0.3599 | KM | GA02ML62 | 0.6229 | GA02ML63 | 0.001 | KM | 7 |  | 0.756 | 0.3745 | 62.623 | 63.001 | 2023-12-31 | UP | BOTH |  |  | 3 | 5 |  |  |  | 15 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 19:03:46 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * BOLINGBROKE - BALOOK * 62.623 - 63.001 - UP - BOTH LEGS * 7 RAILS TOTAL * * Occupational LX at 63.003km ID5763 no rubber flange way's fitted. * check cant excess, do both rails, double low leg wear * 12.04.2021 16:22:37 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070938&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070938 | GA C17 UP BOLINGBROKE 68.901-69.283. | CV002976 | CIVIL | RAIL |  | RENEWAL | 0.764 | KM | 401029 | Goonyella | BOLINGBROKE | BALOOK | 0.382 | KM | GA02ML68 | 0.901 | GA02ML69 | 0.2829 | KM | 7 |  | 0.764 | 0.378 | 68.901 | 69.283 | 2023-03-31 | UP | BOTH |  |  | 3 | 5 |  |  |  | 15 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 19:10:01 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * BOLINGBROKE - BALOOK - UP * 68.901 - 69.283 * BOTH LEGS - TOTAL 7 RAILS * Tail initiates 40m prior to spring. * 2000043645 FY21 RRP start 69.380km, will get next time CV002976 expires * 12.04.2021 16:22:38 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070758&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070758 | GA C17 UP BOLINGBROKE 70.199-73.15. | CV002980 | CIVIL | RAIL |  | RENEWAL | 5.902 | KM | 1689926 | Goonyella | BOLINGBROKE | BALOOK | 2.951 | KM | GA02ML70 | 0.199 | GA02ML73 | 0.1499 | KM | 55 |  | 5.902 | 2.951 | 70.199 | 73.15 | 2023-09-30 | UP | BOTH |  |  | 3 | 5 |  |  |  | 15 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 19.03.2021 19:18:10 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * BOLINGBROKE - BALOOK - UP * 70.199 - 72.062 - both legs * total 53 rails * * Tail initiates 40m prior to spring. * LX 5766 @ 70.341km, LX 5767 @ 71.100km, LX 5768 @ 71.523km, X 5769 @ 72.03km * Neutral section 71.228km to 71.276km * LX 5766 @ 70.341km, LX 5767 @ 71.100km, LX 5768 @ 71.523km, X 5769 @ 72.03km * Neutral section 71.228km to 71.276km Post site walkout notes: 70.199 - 73.150 = 55 rails Construction wanted to run to 150 as it allows for better location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070923&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070923 | GA C17 UP BRAESIDE 109.22-111.11 | CV003026 | CIVIL | RAIL |  | RENEWAL | 3.78 | KM | 1067521 | Goonyella | BRAESIDE | MINDI | 1.9059 | KM | GA02ML109 | 0.22 | GA02ML111 | 0.11 | KM | 35 |  | 3.78 | 1.89 | 109.22 | 111.11 | 2023-06-30 | UP | BOTH |  |  | 3 | 4.6 |  |  |  | 13.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 19:25:53 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 109.220 - 111.110 * UP * BOTH LEGS - TOTAL 39 RAILS * * Cutout will tie into Track Upgrade Starting at 11.090km, check cutout point after TU complete * Scope aligns with FY23 BBR at 109.760km * 12.04.2021 16:22:39 AUSQLD Jeremy Stevenson (R867415) * * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070961&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070961 | NL C17 DOWN BRIABA 58.61-59.09. | CV003450 | CIVIL | RAIL |  | RENEWAL | 0.96 | KM | 453127 | Newlands | BRIABA | ALMOOLA | 0.4799 | KM | NL03ML58 | 0.6099 | NL03ML59 | 0.0899 | KM | 9 |  | 0.96 | 0.48 | 58.61 | 59.09 | 2023-06-30 | DOWN | BOTH |  |  | 3.5 | 1.7 |  |  |  | 6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 16:55:46 AUSQLD Sanjna Rajagopalan (R884639) * re rail * * 58.610 - 59.090km * both legs = total 9 rails * Occupational level xing @58.810 - replace rail through crossing * equality 59km 995.722 = 59km * * Driven by wear * Q4 FY23 * 19.05.2021 11:16:00 AUSQLD Sanjna Rajagopalan (R884639) * DOWN ROAD
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070674&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070674 | NL C17 SINGLE COLLINSVILLE 72.835-73.12 | CV003489 | CIVIL | RAIL |  | RENEWAL | 0.54 | KM | 263763 | Newlands | COLLINSVILLE | MCNAUGHTON JCT | 0.2889 | KM | NL01ML72 | 0.8349 | NL01ML73 | 0.1229 | KM | 5 |  | 0.54 | 0.288 | 72.835 | 73.123 | 2023-06-30 | SINGLE | BOTH |  |  | 3.5 | 2.5 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 16:32:01 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * * 72.830 - 73.102 * Both Legs - 5 rails total * Please note equality 71km 1000.16 = 72km * Turnout Almoola #12A/B points at cut in Turnout Almoola #12A/B points at cut in Post Site Walkouts: 72.835 - 73.123 5 rails total Chnage captured in SharePoint Change Request #134
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070901&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070901 | BW C17 UP EDUNGALBA 94.093-94.597. | CV006231 | CIVIL | RAIL |  | RENEWAL | 0.972 | KM | 449589 | Blackwater | EDUNGALBA | AROONA | 0.504 | KM | BW04ML94 | 0.0929 | BW04ML94 | 0.5969 | KM | 9 |  | 0.972 | 0.51 | 94.093 | 94.597 | 2023-06-30 | UP | BOTH |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 18:38:23 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 94.195km - 94.627km * Edungalba - Aroona * Back of T/O 11 C/D wear * Both Legs - 8 rails Total * Back of T/O 11 C/D wear * Renewal Driven by Wear * Q1 or Q2 Execution * 12.04.2021 16:22:30 AUSQLD Jeremy Stevenson (R867415) * * * 94.093 - 94.597 9 rails Cut in point extended to remove high wear at cut in
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070695&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070695 | BW C17 UP EPALA 584-584.795. | CV005917 | CIVIL | RAIL |  | RENEWAL | 1.59 | KM | 625066 | Blackwater | EPALA | RAGLAN | 0.795 | KM | BW01ML584 | 0 | BW01ML584 | 0.795 | KM | 15 |  | 1.59 | 0.795 | 584 | 584.795 | 2022-09-30 | UP | BOTH |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 18.03.2021 20:36:42 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail only * Epala - Raglan * 584km - 584.703km * 2 curves - cannot find shell notification for first curve - CV005915 * UP road - Both legs - 13 rails total * Scope driven by rail wear * FY23 Q1 * * 6mm Back of T/O from 584.005 - T/O 11A/B - Cut in * Remove SC Rail BHP 1992 Post site walkout: 584km - 584.795km - 15 rails 1 additional rail to extend new rail from Raglan #11A/B all the way to TOS Raglan #ER1B"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070810&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070810 | MA C17 SINGLE FRY 80.985-82.83 | CV007014 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Moura | FRY | MOUNT RAINBOW | 1.8449 | KM | MA01ML80 | 0.9849 | MA01ML82 | 0.8299 | KM |  |  |  |  | 80.985 | 82.83 | 2022-09-30 | SINGLE | BOTH |  |  | 4 | 1.3 |  |  |  | 5.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 03:17:10 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 03:13:18 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * * 4 curves + 4 Notifications: * 2000070879 - this one has all qtys * 2000070810 * * Fry - Mount Rainbow * 81.010km - 82.792km * Single Line - Both rails - total of 33 rails * SC through here plus high wear * FY23 Q1 or Q2 * 19.03.2021 03:25:37 AUSQLD Sanjna Rajagopalan (R884639) * REST RELATING NOTIFICATION: * 2000071059 * 2000070811 expiry date changed to 30/09/2022 Post walkout: 80.985 - 82.830 - 34 rails Proposed on site to add 1 rail to cover further outside of springs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071059&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071059 | MA C17 SINGLE FRY 80.985-82.83 | CV007015 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Moura | FRY | MOUNT RAINBOW | 1.8449 | KM | MA01ML80 | 0.9849 | MA01ML82 | 0.8299 | KM |  |  |  |  | 80.985 | 82.83 | 2023-06-30 | SINGLE | BOTH |  |  | 4 | 1.3 |  |  |  | 5.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 03:19:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * * 4 curves + 4 Notifications: * 2000070879 - this one has all qtys * 2000070810 * 2000071059 * * Fry - Mount Rainbow * 81.010km - 82.792km * Single Line - Both rails - total of 33 rails * SC through here plus high wear * FY23 Q1 or Q2 * 19.03.2021 03:26:13 AUSQLD Sanjna Rajagopalan (R884639) * remaining relating notification: * 2000070811 Post walkout: 80.985 - 82.830 - 34 rails Proposed on site to add 1 rail to cover further outside of springs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070811&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070811 | MA C17 SINGLE FRY 80.985-82.83 | CV007016 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Moura | FRY | MOUNT RAINBOW | 1.8449 | KM | MA01ML80 | 0.9849 | MA01ML82 | 0.8299 | KM |  |  |  |  | 80.985 | 82.83 | 2023-06-30 | SINGLE | BOTH |  |  | 4 | 1.3 |  |  |  | 5.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 03:21:16 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 03:19:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * * 4 curves + 4 Notifications: * 2000070879 - this one has all qtys * 2000070810 * 2000071059 * 2000070811 * * Fry - Mount Rainbow * 81.010km - 82.792km * Single Line - Both rails - total of 33 rails * SC through here plus high wear * FY23 Q1 or Q2 Post walkout: 80.985 - 82.830 - 34 rails Proposed on site to add 1 rail to cover further outside of springs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070879&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070879 | MA C17 SINGLE FRY 80.985-82.83. | CV007013 | CIVIL | RAIL |  | RENEWAL | 3.69 | KM | 1083750 | Moura | FRY | MOUNT RAINBOW | 1.8449 | KM | MA01ML80 | 0.9849 | MA01ML82 | 0.8299 | KM | 34 |  | 3.69 | 1.845 | 80.985 | 82.83 | 2023-09-30 | SINGLE | BOTH |  |  | 4 | 1.3 |  |  |  | 5.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 19.03.2021 03:13:18 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * * 4 curves + 4 Notifications: * 2000070879 - this one has all qtys * * Fry - Mount Rainbow * 81.010km - 82.792km * Single Line - Both rails - total of 33 rails * SC through here plus high wear * FY23 Q1 or Q2 * 19.03.2021 03:24:12 AUSQLD Sanjna Rajagopalan (R884639) * * REST NOTIFICATIONS: * 2000070810 * 2000071059 * 2000070811 Post walkout: 80.985 - 82.830 - 34 rails Proposed on site to add 1 rail to cover further outside of springs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070861&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070861 | BW C17 DOWN GRANTLEIGH 68.89-69.538. | CV006167 | CIVIL | RAIL |  | RENEWAL | 1.296 | KM | 521982 | Blackwater | GRANTLEIGH | TUNNEL | 0.649 | KM | BW03ML68 | 0.89 | BW03ML69 | 0.538 | KM | 12 |  | 1.296 |  | 68.89 | 69.538 | 2023-12-31 | DOWN | BOTH |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20210630 | * 18.03.2021 16:11:39 AUSQLD Sanjna Rajagopalan (R884639) * Re rail * Grantleigh - Tunnel * 68.890 - 69.538 Down both legs 12 rails total * Driven by rail wear * Q2/Q3 * 12.04.2021 16:22:29 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070863&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070863 | BW C17 DOWN GRANTLEIGH 70.554-71.276. | CV006171 | CIVIL | RAIL |  | RENEWAL | 1.44 | KM | 570951 | Blackwater | GRANTLEIGH | TUNNEL | 0.7019 | KM | BW03ML70 | 0.554 | BW03ML71 | 0.276 | KM | 13 |  | 1.404 | 0.722 | 70.554 | 71.276 | 2023-09-30 | DOWN | BOTH |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 23:17:10 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail - Only * 70.583km - 70.907km * Down Road - Both Rails - total 6 rails * FY23 Q1 Execution - was originally pushed out of FY22 (Double of this scope - 2000044090) * SC - So cannot push any further than FY23 Q1 * Renewal is driven by scope * 12.04.2021 16:22:33 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * 70.554 - 71.276 - 13 rails "Agree to join in to FY22 scope at 71.276km to elminate the need to come back to this site for 370m that would otherwise be left out. Scope extents 70.554 - 71.276km"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070859&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070859 | BW C17 UP GRANTLEIGH 75.514-75.853. | CV006187 | CIVIL | RAIL |  | RENEWAL | 0.678 | KM | 417550 | Blackwater | GRANTLEIGH | TUNNEL | 0.339 | KM | BW04ML75 | 0.514 | BW04ML75 | 0.8529 | KM | 7 |  | 0.678 | 0.378 | 75.514 | 75.853 | 2023-06-30 | UP | BOTH |  |  | 3.5 | 3.4 |  |  |  | 11.9 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 16:23:56 AUSQLD Sanjna Rajagopalan (R884639) * Rail Renewal * 75.520km - 75.898km - UP BW 04ML - both rails * 7 rail total * Renewal driven by wear * Going from T/o 8D Tunnel to T/o 7A Tunnel * Q3/Q4 * 12.04.2021 16:22:30 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * 75.514km - 75.853km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043934&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043934 | GA C17 DOWN HATFIELD 49.927-50.263. | GA-01ML | CIVIL | RAIL |  | RENEWAL | 0.648 | KM | 378810 | Goonyella | HATFIELD | BOLINGBROKE | 0.3009 | KM | GA01ML49 | 0.93 | GA01ML50 | 0.26 | KM | 6 | 0 | 0.648 | 0.366 | 49.927 | 50.263 | 2024-06-30 | DOWN | BOTH |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 20.02.2020 11:49:23 AUSQLD Milton Saha (R884640) * Could be deferred if capitally challenged. * Rail wear. 800 radius curve. Expiry 02/26 * 22.03.2021 11:34:51 AUSQLD Sanjna Rajagopalan (R884639) * * Awaiting RAP Confirmation * 23.03.2021 09:55:01 AUSQLD Sanjna Rajagopalan (R884639) * Confirmed RAP - Just confirm Quarter allocation * 23.03.2021 10:08:13 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL ONLY * HATFIELD * 47.49 - 48.53 * DOWN ROAD - BOTH LEGS * TOTAL 19 RAILS *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043940&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043940 | GA C17 UP HATFIELD 52.876-54. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 2.248 | KM | 704388 | Goonyella | HATFIELD | BOLINGBROKE | 1.1029 | KM | GA02ML52 | 0.876 | GA02ML54 | 0 | KM | 21 |  | 2.248 | 1.123 | 52.876 | 54 | 2023-06-30 | UP | BOTH |  |  | 3.5 | 5 |  |  |  | 17.5 | 38 | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 20.02.2020 11:52:59 AUSQLD Milton Saha (R884640) * Rail wear + history of head shelling. * Rail wear. 805 radius curve. HH. Expiry 11/25 * 13.08.2020 11:53:42 AUSQLD Milton Saha (R884640) * Rail wear + history of head shelling. * Rail wear. 805 radius curve. HH. Expiry 11/25 * 23.03.2021 11:17:20 AUSQLD Sanjna Rajagopalan (R884639) * Confirmed and FY23 Q4 execution * * 31.03.2021 10:12:06 AUSQLD Sanjna Rajagopalan (R884639) * Equality 52km 1002.01m = 53km post / EQUALITY - =53km580 / Equality 53km 997.7m = 54km post * Changed from Track Upgrade to Re Rail, due to sleepers being completed as part of FY20 scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074354&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074354 | GA C17 COMMON LOOP HATFIELD COMMON LOOP | GA-01PL | CIVIL | RAIL |  | RENEWAL | 0.972 | KM | 459442 | Goonyella | HATFIELD COMMON LOOP | HATFIELD COMMON LOOP | 0.4859 | KM | GA01PL49 | 0.323 | GA01PL49 | 0.809 | KM | 9 |  | 0.972 | 0.486 | 49.323 | 49.809 | 2022-12-31 | COMMON LOOP | BOTH |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 20.03.2021 09:20:49 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * HATFIELD COMMON LOOP - GA 01PL * 49.323 - 49.809 * 9 RAILS TOTAL - DO BOTH LEGS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070730&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070730 | GA C17 UP HAY POINT 11.618-12.321. | CV002836 | CIVIL | RAIL |  | RENEWAL | 1.404 | KM | 561887 | Goonyella | HAY POINT | DALRYMPLE BAY | 0.7099 | KM | GA02ML11 | 0.6179 | GA02ML12 | 0.321 | KM | 13 |  | 1.404 | 0.702 | 11.618 | 12.321 | 2023-09-30 | UP | BOTH |  |  | 3 | 2.3 |  |  |  | 6.9 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230309 | * 19.03.2021 13:23:18 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL - ONLY * 11.618 - 12.321 * UP Road - Both Legs - Total Rail 13 rails * * Greaser at 11.612km * Cables at 11.914km and 11.968km * Track Magnets 11.960km and 12.099km * Cant review required for curve * JFE rail on Left Leg * * FY23 Q4 or FY24 Q1
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070726&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070726 | GA C17 CHECK TECH SCOPE JILALAN 21.955- | CV002864 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | JILALAN | YUKAN | 1.131 | KM | GA02ML21 | 0.9549 | GA02ML23 | 0.19 | KM |  |  |  |  | 21.955 | 23.19 | 2023-09-30 | CHECK TECH SCOPE |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 24.03.2021 12:13:25 AUSQLD Sanjna Rajagopalan (R884639) * 2 CURVES = 2 NOTIFICATIONS * * 2000070975 - CV002867 - HAS ALL QTYS - BOTH * 2000070726 - CV002864 - HIGH LEG * * RRP - 13.6 rails * > LR 21.955km-22.605km <(>&<)> 22.637km-23.190km * > RR 21.955km-22.605km * > TOS 11CD pts @ 22.636km * GIJ: * > 60kg 6 bolt @ 22.435 LR (Signal JB 73) - replace * > 60kg 6 bolt @ 22.436 RR (Signal JB 73) - replace * Comment: Driven by LL 22.664km wear Exp Aug 23 * > CV002867 rerail low leg due to table wear <(>&<)> high leg due to side wear * > CV002864 rerail low leg only - due to table wear * > cant review required for both curves * > New HD insulators required for CV002864 gauge side both rails - field side installed 2021 * > Reuse HD insulators on field side both rails CV002864 <(>&<)> both sides right rail CV002867
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070975&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070975 | GA C17 UP JILALAN 21.955-23.19. | CV002867 | CIVIL | RAIL |  | RENEWAL | 1.728 | KM | 654178 | Goonyella | JILALAN | YUKAN | 1.131 | KM | GA02ML21 | 0.9549 | GA02ML23 | 0.19 | KM | 16 |  | 1.728 | 1.995 | 21.955 | 23.19 | 2023-09-30 | UP | CHECK TECH SCOPE |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 13:45:00 AUSQLD Sanjna Rajagopalan (R884639) * Re - Rail - 2 Curves - 2 Notifications * - 2000070975 - this one has all the qtys * * 21.955 - 23.190 * up - Both Legs - 23 Rails Total * FY23 Q2 or FY24 Q1 * * Check Cant for both curves * New HD insulators required for CV002867 gauge side both rails - field side installed 2021 * Reuse HD insulators on field side both rails CV002867 & both sides left rail CV002864 (21.955km-22.430km) * 6 bolt GIJ @ 22.435km - 22.436km * Turnout 11 C/D PTS 60kg SNX 22.600km LLT 1 in 12 * 24.03.2021 11:41:10 AUSQLD Sanjna Rajagopalan (R884639) * * LEFT RAIL: 21.955 - 23.190 * Turnout 11 C/D PTS 60kg SNX 22.600km LLT 1 in 12 * Equality of 114m, 22.886km = 23.00km * 10 RAILS * * RIGHT RAIL: 21.955 - 22.605 * 6 RAILS * * * * 24.03.2021 12:18:43 AUSQLD Sanjna Rajagopalan (R884639) * 2000070975 - CV002867 - HAS ALL QTYS - BOTH * 2000070726 - CV002864 - HIGH LEG
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070697&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070697 | BW C17 UP MARMOR 597.751-599.171 | CV005933 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Blackwater | MARMOR | BAJOOL | 1.3609 | KM | BW01ML597 | 0.751 | BW01ML599 | 0.171 | KM |  |  |  |  | 597.751 | 599.171 | 2023-06-30 | UP | BOTH |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230308 | * 18.03.2021 21:02:59 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 20:56:34 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail only * 2 Curves so 2 shell notifications * 2000071100 - - this one has all Qtys * 2000070697 * * 597.820km - 599.171km * Marmor - Bajool * UP Road - both legs - 25 rails total * Re Rail driven by wear * FY23 Q2 - SC so dont allow to be pushed further without full assessment Post walkout: 597.751 - 599.171
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071100&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071100 | RRP BW C17 UP MARMOR 597.751-599.171. | CV005931 | CIVIL | RAIL |  | RENEWAL | 2.84 | KM | 880122 | Blackwater | MARMOR | BAJOOL | 1.3609 | KM | BW01ML597 | 0.751 | BW01ML599 | 0.171 | KM | 25 |  | 2.84 | 1.42 | 597.751 | 599.171 | 2022-12-31 | UP | BOTH |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 18.03.2021 20:56:34 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail only * 2 Curves so 2 shell notifications - this one has all Qtys: * 2000071100 * * 597.820km - 599.171km * Marmor - Bajool * UP Road - both legs - 25 rails total * Re Rail driven by wear * FY23 Q2 - SC so dont allow to be pushed further without full assessment * 19.03.2021 22:48:41 AUSQLD Sanjna Rajagopalan (R884639) * 2 CURVES = 2 NOTIFICATIONS * 2000071100 - HAS ALL QTYS * 2000070697 Post site walkout: 597.751km - 599.171km - 25 rails Start adjusted to take out excessive AT welds on tangent and SC rail (note these continue down the tangent further). No additional rail required as -57m equality not considered in original scope or on walkout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070715&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070715 | BW C17 UP MOUNT MILLER 542.542-543.073. | CV005672 | CIVIL | RAIL |  | RENEWAL | 1.062 | KM | 466136 | Blackwater | MOUNT MILLER | YARWUN | 0.526 | KM | BW01ML542 | 0.542 | BW01ML543 | 0.0729 | KM | 10 |  | 1.062 | 0.531 | 542.542 | 543.073 | 2024-12-31 | UP | BOTH |  |  | 3 | 3.8 |  |  |  | 11.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230523 | * 18.03.2021 19:03:22 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * Mount Miller - Yarwun * 542.532 - 543.126 * both Rails UP - 11 Rails Total * FY23 Q3/Q4 * * 60kg 6 bolt GIJ @ 542.675km - LL/right * + 60kg 6 bolt GIJ @ 542.872km - both rails * + T/O 8CD @ cut in Post site walkout: 542.542km - 543.073km - 10 rails Scope extents adjusted to joins rerail from FY20/21 on High Chainage side (cut out taper rails this end) FY21 rerail 543.071 - 544.348km. Tie into 543.071 Cut into back of Turnout
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070948&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070948 | BW C17 UP MOUNT MILLER 546.635-547.385. | CV005688 | CIVIL | RAIL |  | RENEWAL | 1.512 | KM | 611171 | Blackwater | MOUNT MILLER | YARWUN | 0.751 | KM | BW01ML546 | 0.635 | BW01ML547 | 0.385 | KM | 14 |  | 1.512 | 0.75 | 546.635 | 547.385 | 2022-10-31 | UP | BOTH |  |  | 4 | 3.8 |  |  |  | 15.2 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230308 | * 18.03.2021 19:20:38 AUSQLD Sanjna Rajagopalan (R884639) * 546.594 - 547.406 * Mount Miller - Yarwun * Up Road - Both rails - 15 rails total * Renewal Driven by Wear * FY23 - Q1 * Targini Bridge at Cut in end * 12.04.2021 16:22:31 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * 546.575 - 547.385 - 15 rails Move cut in point to stay clear of bridge as rail across bridge does not require rerail right now and can be done when BBR is completed. Changed extents to 546.635 - 547.385 - 14 rails (reason stated above)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063758&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000063758 | MA C17 SINGLE PARANA 522.903-523.436. | NC-02ML | CIVIL | RAIL |  | RENEWAL | 1.08 | KM | 460355 | Moura | PARANA | PARANA | 0.533 | KM | NC02ML522 | 0.903 | NC02ML523 | 0.4359 | KM | 10 |  | 1.08 | 0.533 | 522.903 | 523.436 | 2023-03-31 | SINGLE | BOTH |  |  | 4 | 2.4 |  |  |  | 9.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | HIGH | Notification completed | RRIG | FY23 IN NON MRSB | 20230630 | * 26.08.2020 11:10:37 AUSQLD Milton Saha (R884640) * 1. Rail Renewal FY21 Brought in * 2. Location: NC-02ML Parana 522.898 - 523.426 km * 3. Number of Rails: 9 * 4. Reason: Missed Rerail Found when doing Automated Rail Notifications Review. Also likely missed due to it being Transposed Rail and data unable to pick it up properly * 5. Current Condition: Near CETS and requires TANC to be completed by SR by end of September 2020 * 6. Latest Renewal Date: End of FY21 * 26.08.2020 12:27:02 AUSQLD Milton Saha (R884640) * 1. After conversation with District Engineer and RAP teams leader - Location will be: * A. TANC PLACED ON IT * B. LOCATIONS WITH BAD WEAR ARE TO BE PLUGGED * 3. THE REST OF THE CURVE SHALL BE RERAILED AT A LATER DATE. CURRENT THINKING IS FY23 POST SITE WALKOUT: 522.903 - 523.436 OK to move start point 5m to work in with turnout. 523.436km is in a curve but this was proposed during walkout Increase of 1 rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071054&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071054 | BW C17 UP/DOWN ROCKLANDS 632.44-0.191 | CV007528 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Blackwater | ROCKLANDS | ROCKLANDS | 0.191 | KM | BW03ML0 | 0 | BW03ML0 | 0.191 | KM |  |  |  |  | 632.44 | 0.191 | 2023-09-30 | UP/DOWN | BOTH |  |  | 4 | 4.5 |  |  |  | 18 | 5663 | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20250630 | * 30.03.2021 13:21:15 AUSQLD Sanjna Rajagopalan (R884639) * Re rail * * 3 Curves = 3 notifications * 2000070802 - has all qtys * 2000071054 * * * BW01ML - BW03ML * 632.440 - 0.191 * TOTAL 14 RAILS - both legs * + Cut out point LLB of Rocklands Road 8 points crossover * Please note located in system crossover location * Q1 Execution * 30.03.2021 13:25:45 AUSQLD Sanjna Rajagopalan (R884639) * 3 Curves = 3 notifications * 2000070802 - has all qtys * 2000071054 * 2000071041
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071041&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071041 | BW C17 UP/DOWN ROCKLANDS 632.44-0.191 | CV007893 | CIVIL | RAIL |  | RENEWAL | 0 | KM |  | Blackwater | ROCKLANDS | ROCKLANDS | 0.1229 | KM | BW01ML632 | 0.444 | BW01ML632 | 0.5669 | KM |  |  |  |  | 632.44 | 0.191 | 2023-09-30 | UP/DOWN | BOTH |  |  | 4 | 4.5 |  |  |  | 18 | 5663 | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20250630 | * 30.03.2021 13:24:08 AUSQLD Sanjna Rajagopalan (R884639) * Re rail * * 3 Curves = 3 notifications * 2000070802 - has all qtys * 2000071054 * 2000071041 * * BW01ML - BW03ML * 632.440 - 0.191 * TOTAL 14 RAILS - both legs * + Cut out point LLB of Rocklands Road 8 points crossover * Please note located in system crossover location * Q1 Execution
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070802&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070802 | BW C17 UP/DOWN ROCKLANDS 632.44-0.191. | CV007494 | CIVIL | RAIL |  | RENEWAL | 1.519 | KM | 628385 | Blackwater | ROCKLANDS | ROCKLANDS | 0.391 | KM | BW01ML632 | 0.5669 | BW01ML632 | 0.9579 | KM | 14 |  | 1.519 | 0.76 | 632.44 | 0.191 | 2023-09-30 | UP/DOWN | BOTH |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20250630 | * 30.03.2021 12:51:30 AUSQLD Sanjna Rajagopalan (R884639) * Re rail * * 3 Curves = 3 notifications * 2000070802 - has all qtys * * * * BW01ML - BW03ML * 632.440 - 0.191 * TOTAL 14 RAILS - both legs * + Cut out point LLB of Rocklands Road 8 points crossover * Please note located in system crossover location * Q1 Execution * * Re Rail driven by wear * 30.03.2021 13:26:00 AUSQLD Sanjna Rajagopalan (R884639) * 3 Curves = 3 notifications * 2000070802 - has all qtys * 2000071054 * 2000071041
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071052&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071052 | MA C17 SINGLE STOWE 27.299-28.469. | CV007186 | CIVIL | RAIL |  | RENEWAL | 2.34 | KM | 763576 | Moura | STOWE | GRAHAM | 1.1699 | KM | MA01ML27 | 0.2989 | MA01ML28 | 0.468 | KM | 22 |  | 2.376 | 1.17 | 27.299 | 28.469 | 2024-06-30 | SINGLE | BOTH |  |  | 3 | 1.3 |  |  |  | 3.9 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 19.03.2021 02:48:45 AUSQLD Sanjna Rajagopalan (R884639) * re rail only * 27.290km - 28.407 * Stowe - Graham * Renewal driven by wear combined with rail type - SC * MA - 01ML * Both legs - total 23 rails * FY23 - Q3 * 12.04.2021 16:22:34 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * CUT IN: 27.299 CUT OUT: 28.469
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071149&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071149 | BW C17 DOWN TUNNEL 76.536-77.725 | CV006192 | CIVIL | RAIL |  | RENEWAL | 2.376 | KM | 772175 | Blackwater | TUNNEL | EDUNGALBA | 0.9819 | KM | BW03ML76 | 0.537 | BW03ML77 | 0.7249 | KM | 22 |  | 2.376 | 1.188 | 76.536 | 77.725 | 2023-06-30 | DOWN | BOTH |  |  | 3 | 3.8 |  |  |  | 11.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230308 | * 18.03.2021 21:39:08 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 21:31:32 AUSQLD Sanjna Rajagopalan (R884639) * 2 curves in one scope so 2 shell notifications: * 2000070850 - this one has all qtys * 2000071149 * * Re Rail only * 76.537km - 76.725km * BW 03ML - DOWN - both legs - 22 Rails total * renewal put forward due to high wearing location * FYQ2 or Q3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070847&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070847 | BW C17 DOWN TUNNEL 86.855-87.179. | CV006213 | CIVIL | RAIL |  | RENEWAL | 0.648 | KM | 510700 | Blackwater | TUNNEL | EDUNGALBA | 0.3639 | KM | BW03ML86 | 0.8549 | BW03ML87 | 0.1789 | KM | 6 |  | 0.648 | 0.324 | 86.855 | 87.179 | 2022-09-30 | DOWN | BOTH |  |  | 3 | 3.8 |  |  |  | 11.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230308 | * 18.03.2021 23:44:27 AUSQLD Sanjna Rajagopalan (R884639) * 2 Curves - 2 notifications: * 2000070847 - this one has the qtys * * Re Rail * Tunnel - Edungalba * 86.820km - 87.880km * BW-03ML - DOWN - Both Rails - 20 Rails Total * Q3 FY22 * Renewal driven by wear * 18.03.2021 23:47:30 AUSQLD Sanjna Rajagopalan (R884639) * Shown in SPM as another N4 - 002000066544 * 18.03.2021 23:51:08 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 23:44:27 AUSQLD Sanjna Rajagopalan (R884639) * * 2000070848- second curve N4 * 25.03.2021 10:19:27 AUSQLD Sanjna Rajagopalan (R884639) * Double up deleted Latest renewal date Q1 FY23 - 30.09.2022 POST WALK OUT: Scope split over 2 notifications as tangent inbetween did not need to be renewed CUT IN: 86.855 CUT OUT: 87.179 6 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070848&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070848 | BW C17 DOWN TUNNEL 87.605-87.875 | CV006215 | CIVIL | RAIL |  | RENEWAL | 0.54 | KM | 219780 | Blackwater | TUNNEL | EDUNGALBA | 0.27 | KM | BW03ML87 | 0.6049 | BW03ML87 | 0.875 | KM | 5 |  | 0.54 | 0.27 | 87.605 | 87.875 | 2022-09-30 | DOWN | BOTH |  |  | 3 | 3.8 |  |  |  | 11.4 |  |  | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 18.03.2021 23:49:45 AUSQLD Sanjna Rajagopalan (R884639) * 18.03.2021 23:44:27 AUSQLD Sanjna Rajagopalan (R884639) * 2 Curves - 2 notifications: * 2000070847 - this one has the qtys * 2000070848 * * Shown in SPM as another N4 - 002000066544 * * Re Rail * Tunnel - Edungalba * 86.820km - 87.880km * BW-03ML - DOWN - Both Rails - 20 Rails Total * Q3 FY22 * Renewal driven by wear POST SITE WALKOUT: Only re railing both curves so splitting scope across 2 x notification for this one: CUT IN: 87.605 CUT OUT: 87.875 5 rails
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070942&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070942 | BW C17 DOWN YARWUN 553.083-553.568. | CV005714 | CIVIL | RAIL |  | RENEWAL | 0.864 | KM | 425187 | Blackwater | YARWUN | ALDOGA | 0.4849 | KM | BW02ML553 | 0.083 | BW02ML553 | 0.5679 | KM | 8 |  | 0.864 | 0.485 | 553.083 | 553.568 | 2023-09-30 | DOWN | BOTH |  |  | 4 | 4.1 |  |  |  | 16.4 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 18.03.2021 19:39:23 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail only * 553.700km - 553.569km * Yarwun - Aldoga * Down Road - Both rails - total 9 rails * Yarwun Aldoga * Renewal Driven by wear * Q2 FY23 * 12.04.2021 16:22:31 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * LEFT 553.083 - 553.568 - 4.5 Rails RIGHT 553.130 - 553.566 - 4 Rails 50m piece of rail on site - install this on lower chaingage on left leg, and utlise 8 rails for remainder of scope. Reducing scope from 9 rails to 8 rails
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066543&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000066543 | BW C17 UP YARWUN 554.069-555.159. | BW-01ML | CIVIL | RAIL |  | RENEWAL | 2.18 | KM | 719024 | Blackwater | YARWUN | ALDOGA | 1.0669 | KM | BW01ML554 | 0.069 | BW01ML555 | 0.159 | KM | 20 | 0 | 2.18 | 1.09 | 554.069 | 555.159 | 2024-03-31 | UP | BOTH |  |  | 3 | 4.1 |  |  |  | 12.3 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 21.10.2020 09:14:53 AUSQLD Milton Saha (R884640) * 1. Rail Renewal * 2. Callemondah - Rocklands Up BW-01ML * 3. 553.040 -555.125 km (39 Rails) * 4. Reason = Wear * 5. Construction to confirm exact limits closer to renewal date * 6. Type of sleeper and ballast condition to be confirmed during site walkout * 20.03.2021 09:25:49 AUSQLD Sanjna Rajagopalan (R884639) * In program FY22 - TU 553.550 - 554.07 - 10 RAILS + 650 SLEEPERS * FY23 CURRENTLY - RE RAIL - 553.04 - 553.509 - 9 RAILS - TRYING TO SO WITH FY22 TU * * LEFT OVER FOR THIS SCOPE - FY23 RE RAIL - 554.07 - 555.130 - 20 RAILS POST WALK OUTS: 554.069 - 555.159 - 20 RAILS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070972&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070972 | GA C17 DOWN YUKAN 36.371-39.178. | CV002889 | CIVIL | RAIL |  | RENEWAL | 5.616 | KM | 1595964 | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM | 52 |  | 5.616 | 2.808 | 36.371 | 39.178 | 2023-06-30 | DOWN | 52 |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20220630 | * 19.03.2021 20:39:20 AUSQLD Sanjna Rajagopalan (R884639) * RE RAIL * 36.371 - 39.178 * BOTH LEGS - 52 RAILS TOTAL * DOWN * 19.03.2021 20:50:37 AUSQLD Sanjna Rajagopalan (R884639) * 7 curves in this re rail = 7 notification: * - 2000070972 - this one has the qtys * 19.03.2021 21:34:56 AUSQLD Sanjna Rajagopalan (R884639) * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070722&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070722 | GA C17 DOWN YUKAN 36.371-39.178 | CV002890 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 20:58:00 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN * 19.03.2021 21:34:37 AUSQLD Sanjna Rajagopalan (R884639) * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070973&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070973 | GA C17 DOWN YUKAN 36.371-39.178 | CV002893 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 5 | 4.4 |  |  |  | 22 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:05:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN * 19.03.2021 21:33:43 AUSQLD Sanjna Rajagopalan (R884639) * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070781&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070781 | GA C17 DOWN YUKAN 36.371-39.178 | CV002894 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:08:58 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 21:05:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN * 19.03.2021 21:33:25 AUSQLD Sanjna Rajagopalan (R884639) * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071030&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071030 | GA C17 DOWN YUKAN 36.371-39.178 | CV002897 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 1.8109 | KM | GA01ML37 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:21:56 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 21:08:58 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 21:05:16 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN * 19.03.2021 21:32:55 AUSQLD Sanjna Rajagopalan (R884639) * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070783&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070783 | GA C17 DOWN YUKAN 36.371-39.178 | CV002898 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:26:19 AUSQLD Sanjna Rajagopalan (R884639) * * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN * 19.03.2021 21:32:21 AUSQLD Sanjna Rajagopalan (R884639) * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071032&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071032 | GA C17 DOWN YUKAN 36.371-39.178 | CV002901 | CIVIL | RAIL |  | RENEWAL |  | KM |  | Goonyella | YUKAN | BLACK MOUNTAIN | 2.817 | KM | GA01ML36 | 0.3709 | GA01ML39 | 0.1779 | KM |  |  |  |  | 36.371 | 39.178 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 21:30:21 AUSQLD Sanjna Rajagopalan (R884639) * 19.03.2021 21:26:19 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 7 curves = 7 notifications * * 2000070972 - this one has the qtys * 2000070722 * 2000070973 * 2000070781 * 2000071030 * 2000070783 * 2000071032 * * 36.371 - 39.178 * 52 rails * GA-01ML - DOWN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074694&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074694 | GA C17 UP YUKAN 36.793-39.108. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 4.63 | KM | 1338898 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.315 | KM | GA02ML38 | 0.792 | GA02ML39 | 0.111 | KM | 43 |  | 4.63 | 2.315 | 36.793 | 39.108 | 2022-09-30 | UP | BOTH |  |  | 4.5 | 4.4 |  |  |  | 19.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 12:38:37 AUSQLD Sanjna Rajagopalan (R884639) * Awaiting tech scope * 12.04.2021 16:20:51 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074695&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074695 | GA C17 UP YUKAN 39.39-39.5. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.22 | KM | 269207 | Goonyella | YUKAN | BLACK MOUNTAIN | 1.114 | KM | GA02ML38 | 0.389 | GA02ML39 | 0.507 | KM | 2 |  | 0.22 | 0.11 | 39.39 | 39.5 | 2023-09-30 | UP | BOTH |  |  | 4.5 | 4.4 |  |  |  | 19.8 |  | 2021-03-31 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 12:42:27 AUSQLD Sanjna Rajagopalan (R884639) * Awaiting tech scope * 12.04.2021 16:20:51 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070957&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070957 | C17 NL BRIABA 67.346 - 67.746 | CV003476 | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 364417 | Newlands | BRIABA | ALMOOLA | 0.4 | KM | NL03ML67 | 0.3459 | NL03ML67 | 0.7459 | KM | 8 |  | 0.864 | 0.4 | 67.346 | 37.746 | 2022-12-31 | DOWN | BOTH |  |  | 4 | 1.7 | 1 | 2.2 | 1 |  | 5411 |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20260630 | Connecting into 2000070957
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070958&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070958 | C17 NL DN 67.746-68.321KM. | CV003478 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 501073 | Newlands | BRIABAB | ALMOOLA | 0.5769 | KM | NL03ML67 | 0.7459 | NL03ML68 | 0.321 | KM | 11 |  | 1.188 | 0.577 | 67.746 | 68.321 | 2023-12-31 | DOWN | BOTH |  |  | 4 | 1.7 | 1 | 2.2 | 1 |  | 5411 |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20260630 | Connecting to 200070957 7.346 – 67.746 – CV3476 – 8 Rails – 2000070957 67.746 – 68.321 – CV3478 – 11 Rails – 2000070958
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058703&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000058703 | Rail Renewal. | CV005683 | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 158730 | Blackwater | MOUNT MILLER | YARWUN | 0.386 | KM | BW01ML544 | 0.3479 | BW01ML544 | 0.7339 | KM | 7 |  | 0.756 | 0.385 | 544.349 | 544.734 | 2023-06-30 | UP | BOTH |  |  | 4.4 | 4.1 | [7 empty] | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230630 | Approved by change board to complete inn FY23 - PCR 5236
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072050&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000072050 | NON COAL - KAILI | CV007307 | CIVIL | RAIL |  | RENEWAL | 0.247 | TRACK KM | 364268 | Newlands | KAILI | DURROBURRA | 0.2469 | KM | NC03ML1165 | 0.8499 | NC03ML1166 | 0.097 | KM | 5 | 635 | 0.54 | 0.247 | 1165.85 | 1166.097 | 2024-06-30 |  | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | SCPR |  | 20230630 | Moved to FY23 as per AIC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075264&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075264 | RAIL RENEWAL Fix on Fail | BW | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 1 | LUMPSUM | 315000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:39:56 AUSQLD Sanjna Rajagopalan (R884639) * FoF for Blackwater System
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075265&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075265 | RAIL RENEWAL Fix on Fail | GA | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 1 | LUMPSUM | 315000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:42:18 AUSQLD Sanjna Rajagopalan (R884639) * Fix on Fail for Goonyella System
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075266&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075266 | RAIL RENEWAL Fix on Fail | MA | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 1 | LUMPSUM | 35000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:45:13 AUSQLD Sanjna Rajagopalan (R884639) * Lumpsum for Fix on Fail for Moura
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075267&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075267 | RAIL RENEWAL Fix on Fail | NL | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 1 | LUMPSUM | 35000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:47:48 AUSQLD Sanjna Rajagopalan (R884639) * Lumpsum for Fix on Fail for Moura system
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073797&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073797 | BW C65 BLACKWATER SYSTEM - | BW | CIVIL | RAIL LUBRICATION | CONSTRUCT | REACTIVE WORKS | 1 | LUMPSUM | 40000 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 09.03.2021 18:46:41 AUSQLD Tracy Holmes (R870040) * Justification: Fix on fail for lubrication units. This funding is to be used for whole unit replacements, lubricator relocations, or anything considered to be beyond regular maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073853&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073853 | GA C65 GOONYELLA SYSTEM - | GA | CIVIL | RAIL LUBRICATION | CONSTRUCT | REACTIVE WORKS | 1 | LUMPSUM | 40000 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 09.03.2021 18:49:47 AUSQLD Tracy Holmes (R870040) * Justification: Fix on fail for lubrication units. This funding is to be used for whole unit replacements, lubricator relocations, or anything considered to be beyond regular maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073854&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073854 | MA C65 MOURA SYSTEM - | MA | CIVIL | RAIL LUBRICATION | CONSTRUCT | REACTIVE WORKS | 1 | LUMPSUM | 10000 | Moura | MOURA SYSTEM | MOURA SYSTEM | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 09.03.2021 19:04:36 AUSQLD Tracy Holmes (R870040) * Justification: Fix on fail for lubrication units. This funding is to be used for whole unit replacements, lubricator relocations, or anything considered to be beyond regular maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073819&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073819 | NL C65 NEWLANDS SYSTEM - | NL | CIVIL | RAIL LUBRICATION | CONSTRUCT | REACTIVE WORKS | 1 | LUMPSUM | 10000 | Newlands | NEWLANDS SYSTEM | NEWLANDS SYSTEM | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 09.03.2021 18:56:15 AUSQLD Tracy Holmes (R870040) * Justification: Fix on fail for lubrication units. This funding is to be used for whole unit replacements, lubricator relocations, or anything considered to be beyond regular maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044287&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044287 | GA C18 DOWN BALOOK 82.38-85.932. | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 5185 | SLEEPERS | 2201782 | Goonyella | BALOOK | WANDOO | 3.5539 | KM | GA01ML82 | 0.381 | GA01ML85 | 0.932 | KM | 0 | 5185 |  | 3.552 | 82.38 | 85.932 | 2023-06-30 | DOWN | NONE |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240630 | * 23.03.2021 13:50:42 AUSQLD Sanjna Rajagopalan (R884639) * Sleeper Renewal * Any time in FY23 * 82.381 - 85.932 * Existing 22T + 28T Fists * Ties in with TU from 81/733 - 83.381 * 5186 sleepers required total * 12.04.2021 16:20:54 AUSQLD Jeremy Stevenson (R867415) * Tech Scope attached * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044290&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044290 | BW C18 ENTRY BOORGOON 0.19-2.154. | BW-23ML | CIVIL | SLEEPERS |  | RENEWAL | 2867 | SLEEPERS | 1558081 | Blackwater | BOORGOON | BOORGOON | 1.979 | KM | BW23ML0 | 0.192 | BW23ML2 | 0.1539 | KM | 0 | 2867 |  | 1.964 | 0.19 | 2.154 | 2023-12-31 | ENTRY | NONE |  |  | 4 | 0.9 |  |  |  | 3.6 |  | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20231029 | * 19.03.2021 02:34:12 AUSQLD Sanjna Rajagopalan (R884639) * 0.192 - 2.154 (entry road - after 10AB points till loadout from IM works) - From 10AB points to back of TLO - sleeper upgrade only * 2865 sleepers * 19.03.2021 23:11:13 AUSQLD Sanjna Rajagopalan (R884639) * * LINKS TO BELOW: * 0.037 - 0.156 - track updgrade * * 4.085 - 4.165 - track updgrade * 19.03.2021 23:28:04 AUSQLD Sanjna Rajagopalan (R884639) * 0.037 -0.153km * 3 Rails * 183 Sleepers * * * Part 3 Notification 2000063031 - Boorgoon Exit Road (Back of 10A - Spring of 4.09km curve) * 4.090 - 4.165 km * 2 Rails * 117 Sleepers * 31.03.2021 09:05:28 AUSQLD Sanjna Rajagopalan (R884639) * 2 Rails * 117 Sleepers 117 Sleepers Central station communication by Geoff McMahon on 28/06/2022 '.....Kevin Please find enclosed the approved BMF data for your survey support of works planned for execution as follows • July BW Closure: 18/07/22 – 20/07/22 TU BW Boorgoon Balloon 0.033 - 0.158km Entry Road Both 3 Rails <(>&<)> 190 Slps SRC BW Boorgoon Balloon 0.191 - 0.356km Entry Road Both 3 PW Rails <(>&<)> 240 Slps SRC BW Boorgoon Balloon 4.085 - 4.160km Exit Road 120 Slps • Oct BW Closure: 27/10/22 – 01/11/22 SRC BW Boorgoon-Boorgoon 0.356 - 2.191km Entry Road 2864 Slprs TLM Neil <(>&<)> Terry As per Rinaldo's communication on the 12/5/22 "........Attached is a missing OHW adjustment summary consisting of 5 masts at the start of the balloon loop. There are no OHW changes relating to the BMF. However according to Wayne there are pre existing issues such as pan horn contact at BG/0/015 and SI issue. If time permit, please check the 500mm wire separation at the turnout. Adjust if necessary. Then check the setup for SI at BG/0/44. Note refer to previous COM for the other pages: Page 1-3. Note they have OHW modification required............." Regards Geoff....."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052763&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052763 | GA C18 UP BRAESIDE 107.868-108.68. | GA-02ML | CIVIL | SLEEPERS |  | RENEWAL | 1185 | SLEEPERS | 903481 | Goonyella | BRAESIDE | MINDI | 0.8199 | KM | GA02ML107 | 0.8679 | GA02ML108 | 0.68 | KM | 0 | 1185 |  | 0.812 | 107.868 | 108.68 | 2023-06-30 | UP | NONE |  |  | 3 | 4.6 |  |  |  | 13.8 |  | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 08:31:02 AUSQLD Milton Saha (R884640) * Braeside - Mindi 107.868 - 108.680 * Reason: 28T Fist * FY if budget available: FY22 * FY if cap restraint: FY23 * 12.04.2021 16:21:01 AUSQLD Jeremy Stevenson (R867415) * Tech Scope attached * * Kevin Please find enclosed the approved BMF data for your survey support of GA SRC Braeside - Mindi UP 107.868 - 108.68 planned for execution on the 19th August 2022 David, Hayley <(>&<)> Jason As per Rinaldo's communication on the 20/10/2021 "........The MINIMUM OHW work involve is minor adjustment on two structures. There is ample adjustment. HOWEVER, it will need a longer rego tube for both location. I'm hoping you already have these tubes already. Please let me know if you haven't. The work should be done after the track mod. Please post height and stagger after......" Regards Geoff
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111301&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000111301 | C18 BW MAIN BURNGROVE 260.080 - 261.598 | BW-03ML | CIVIL | SLEEPERS |  | RENEWAL | 2200 | SLEEPERS | 1427800 | Blackwater | BURNGROVE | NOGOA | 1.5169 | KM | BW03ML260 | 0.08 | BW03ML261 | 0.5979 | KM |  | 2200 |  | 1.517 | 260.08 | 261.598 | 2023-06-30 |  |  |  |  | 4 | 1.65 | 1 | 2.1 | 1 | 8.4 | 5828 | [8 empty] | Notification in process | NWSC |  | 20231231 | Non Coal Sleeper Renewal original scope was 260.08 - 263.15 approx. 4500 sleepers. Only partial scope was able to be competed - 260.080 - 261.598 approx. 2200 sleepers. Additonal sleepers will be completed in FY24 Change Captured in PCR 5828
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043678&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043678 | GA C18 3RD ROAD JILALAN 19.67-19.824. | GA-05YR | CIVIL | SLEEPERS |  | RENEWAL | 225 | SLEEPERS | 151547 | Goonyella | JILALAN | JILALAN | 0.1539 | KM | GA05YR19 | 0.67 | GA05YR19 | 0.8239 | KM | 0 | 225 |  | 0.154 | 19.67 | 19.824 | 2023-06-30 | 3RD ROAD | NONE |  |  | 3.5 | 1 |  |  |  | 4 |  | 2020-03-06 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 17.02.2020 15:07:42 AUSQLD Milton Saha (R884640) * Timber Sleepers which require upgrade * 22.02.2021 17:11:44 AUSQLD William Robertson (R863808) * Changed incorrect FLOC ID from GA-10YR to GA-05YR. Working on Jilalan 3rd Road * 08.06.2021 08:37:34 AUSQLD Katie Clark (R883621) * SRC from 19.670km - 19.824km Moved to FY23 - change biard decision Central Station communication 1128 from Geoff McMahon on 1/12/2021 Patrick ".....Please find enclosed the approved BMF data for your survey support of the planned execution of SRC GA Jilalan Old Yard 19.700km - 19.820km 3RD ROAD which has recently been rescheduled to 7/03/2023 Hayley <(>&<)> David As per Rinaldo's communication on the 29/8/21 ".....The BMF requires no OHW mod. Only post height and stagger......" Regards Geoff
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043356&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043356 | GA C18 5TH ROAD JILALAN 19.67-20.84. | GA-06YR | CIVIL | SLEEPERS |  | RENEWAL | 1722 | SLEEPERS | 1161205 | Goonyella | JILALAN | JILALAN | 1.1659 | KM | GA06YR19 | 0.66 | GA06YR20 | 0.8399 | KM | 0 | 1722 |  | 1.18 | 19.67 | 20.84 | 2023-06-30 | 5TH ROAD | NONE |  |  | 3.5 | 1 |  |  |  | 3.5 | 38 | 2020-03-06 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 17.02.2020 15:07:09 AUSQLD Milton Saha (R884640) * Timber Sleepers Requiring Upgrade * 04.08.2020 10:48:43 AUSQLD Milton Saha (R884640) * * Q1 Allocation as noted by the latest renewal date being 30.9.2021 * 22.01.2021 17:12:38 AUSQLD William Robertson (R863808) * Changes made: * - Increased End point from 19.824km to 20.780km * - Sleeper quantity increased from 540 sleepers to 1620 sleepers * - Increased cost from $327,240 to $994,680 * 08.06.2021 08:39:34 AUSQLD Katie Clark (R883621) * Increased scope - 19.660km to 20.840km Moved to FY23 as per change board decision 1723 sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043355&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043355 | GA C18 4 STRAIGHT JILALAN 21.07-21.971. | GA-06YR | CIVIL | SLEEPERS |  | RENEWAL | 1315 | SLEEPERS | 886649 | Goonyella | JILALAN | JILALAN | 0.901 | KM | GA06YR21 | 0.07 | GA06YR21 | 0.9709 | KM | 0 | 1315 |  | 0.901 | 21.07 | 21.971 | 2023-06-30 | 4 STRAIGHT | NONE |  |  | 3 | 1 |  |  |  | 3 |  | 2020-03-06 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 17.02.2020 15:06:41 AUSQLD Milton Saha (R884640) * Reason: Timber Sleepers requiring upgrade * 04.03.2021 09:27:55 AUSQLD William Robertson (R863808) * Changes made: * - FLOC ID updated from GA-10YR to GA-06YR to reflect correct road (No. 4 Straight track) * - Updated Start KM from 21.080km to 21.025km. New job length now 0.975km * - Increased number of sleepers from 475 to 1430. Original scope 1 in 3, now full sleeper replacement Moved to FY23 - change biard decision
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052766&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052766 | GA C18 UP WAITARA 106.872-107.73. | GA-02ML | CIVIL | SLEEPERS |  | RENEWAL | 1253 | SLEEPERS | 931955 | Goonyella | WAITARA | BRAESIDE | 0.8469 | KM | GA02ML106 | 0.8719 | GA02ML107 | 0.7299 | KM | 0 | 1253 |  | 0.858 | 106.872 | 107.73 | 2023-06-30 | UP | NONE |  |  | 3 | 4.6 |  |  |  | 13.8 |  | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 08:43:37 AUSQLD Milton Saha (R884640) * 28.02.2020 08:41:49 AUSQLD Milton Saha (R884640) * Waitara - Braeside 106.872 -107.730 * GA UP * Reason: 28T Fist Clip to be replaced * FY22 but if CAP challenge then FY23 * 30.03.2021 17:35:41 AUSQLD Sanjna Rajagopalan (R884639) * Ballast replacement required, condition of ballast at level xing @107.6km poor * 12.04.2021 16:21:02 AUSQLD Jeremy Stevenson (R867415) * * * Please find enclosed the approved BMF data for your survey support of SRC GA Waitara - Braeside 106.872km - 107.730km Down planned for execution on the 17th August 2022 David, Hayley <(>&<)> Jason As per Rinaldo's communication on the 27/02/2022 "........The BMF has no mods required. Just post height and stagger. The track notification is 2000052766. Construction is planned for 17th August 2022. Please liase with Aaron Low and track planner asap to ensure the OHW is part of the Operation Steps in the their WO and resource allocation. Attached is the OHW adjustment report......" Regards Geoff......" 2000052766 BMF Review SRC GA Waitara - Braeside 106.872km - 107.730km Up Central Station communication dated 2/08/2022 from Geoff McMahon "....Kev Please find enclosed the approved BMF data for your survey support of SRC Braeside - Mindi UP 107.868km - 108.680km 1186 Slprs TLM works planned for execution on the 17th Aug David <(>&<)> Hayley As per Rinaldo's earlier communication to you on the 29th July and this enclosed OHW adjustment summary "........There are only 2 onsite adjustment required onsite. They are located just at the end of the renewal works. Please ensure the work footprint 3 mast further outside the BMF area. One of them, removing the rake would help but I suggest you have a JLG there ready to adjust both of them. Midspan offset issue. ........." Regards Geoff......"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100038&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000100038 | GA C18 DOWN WAITARA 109.095 - 109.190 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 139 | SLEEPERS | 85902 | Goonyella | WAITARA | BRAESIDE | 0.095 | KM | GA01ML109 | 0.095 | GA01ML109 | 0.19 | KM |  | 139 |  | 0.095 | 109.095 | 109.19 | 2023-06-30 | DOWN |  |  |  | 3.5 | 4.4 | 1 | [6 empty] | Sleeper Renewal | [5 empty] | Notification completed | NWSC |  | 00000000 | Fist Clip Sleepers identified between nebo creek and cooper creek brige. Opportunity to replace these sleepers whilst girder upgrade works are being completed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075271&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075271 | BW C18 UP WALLAROO 119.28-122.5. | BW-04ML | CIVIL | SLEEPERS |  | RENEWAL | 4701 | SLEEPERS | 2035988 | Blackwater | WALLAROO | TRYPHINIA | 3.221 | KM | BW04ML119 | 0.28 | BW04ML122 | 0.5 | KM |  | 4701 |  | 3.22 | 119.28 | 122.5 | 2024-06-20 | UP |  |  |  | 3.5 | 3.4 |  |  |  | 11.7 | 5607 | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 30.03.2021 11:51:39 AUSQLD Sanjna Rajagopalan (R884639) * Sleeper Renewal * * 119.280 - 122.500 * total 4701 sleepers * renewal driven by derailment damage in sleepers * Q4 execution Notification put back in progress as requested by Adrian Neubecker 17.10.23
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067638&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000067638 | C38-SS-GA-BLACK MOUNTAIN-44.240KM | GA-01CR | CIVIL | SLOPE STABILITY | DESIGN | DESIGN | 1 | EACH | 75000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.08 | KM | GA01ML44 | 0.2399 | GA01ML44 | 0.32 | KM |  |  |  |  | 44.24 | 44.32 | 2022-09-30 |  |  |  |  | 4 | 4 | 3 | 4 | 15 | 16 |  | 2021-03-31 | 2021-10-05 | Formation - Other | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 11.11.2020 15:10:33 AUSQLD Timothy Griffin (R878533) * Carryover works provision from FY22 Slope Stability works at 41km Black Mountain. * 22.03.2021 15:19:55 AUSQLD Jane Livingston (R111275) * 22.03.2021 Changed from $650,000 to $200,000 for Investigation and Design of the next segment in the Slope Stability Strategy. * * 12.04.2021 16:21:59 AUSQLD Jeremy Stevenson (R867415) * No geotech or BMF design complete for this N4. * * 2022) to aid FY24 delivery MRSB N4 notification and commencement in July2023 (FY24). Agreed to reallocate portion of Design allocation for Rocklands Wedge cutting design in Blackwater System so that Black Mt now $75,000, after discussion with AM Leader Will Schuh on Thursday 12Aug2021 RAR to aid with Geotech Design and Delivery pipeline activities.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081954&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000081954 | ROCKLANDS WEDGE SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY | DESIGN | DESIGN | 1 | LUMPSUM | 125000 | Blackwater | ROCKLANDS | GRACEMERE | 0.1 | KM | BW03ML0 | 0.55 | BW03ML0 | 0.65 | KM |  |  |  |  | 0.55 | 0.65 | 2023-03-03 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | 16.08.2021 Tim Griffin (r878533) $125,000 Design and Cost Estimate for Rocklands Wedge slope stability on Blackwater System for Construction in FY24 or later, pending pipeline of Geovert works from Goonyella Black Mountain area and agreed to by AM Leader Will Schuh on 12Aug2021. 04.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY23 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070074&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000070074 | Structures Reactive Works | BW | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 0 | Blackwater | BW |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [9 empty] | 25 | 3541 | 2021-03-31 |  | Culvert Renewals | [5 empty] | Notification completed | SCPR | FY23 OUT | 20230630 | * 31.12.2020 08:19:50 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. reduced by 225000 due to BR101111 inclusion FY23 Reactive, no longer required as at 8/10/21 and removed based on budget constraints. Zeroed out and Closed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070073&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000070073 | Structures Reactive Works | GA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 0 | Goonyella | GA |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [9 empty] | 25 | 3541 | 2021-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR | FY23 OUT | 20230630 | * 31.12.2020 08:19:24 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. * 31.03.2021 09:35:42 AUSQLD Edward Brooks (R884255) * * Reduced to 0 due to inclusion of CU201128 culvert renewal. Reduced to 373 due to inclusion of design for CU201278. FY23 Reactive, no longer required as at 8/10/21 and removed based on budget constraints. Zeroed out and Closed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070075&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000070075 | Structures Reactive Works | MA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 0 | Moura | MA |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [9 empty] | 25 | 3541 | 2021-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR | FY23 OUT | 20211226 | * 31.12.2020 08:22:11 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. FY23 Reactive, no longer required as at 8/10/21 and removed based on budget constraints. Zeroed out and Closed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070076&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000070076 | Structures Reactive Works | NL | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 0 | Newlands | NL |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [9 empty] | 25 | 3541 | 2021-03-31 |  | Culvert Renewals | [5 empty] | Notification completed | SCPR | FY23 OUT | 20230630 | * 31.12.2020 08:25:50 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. * 04.01.2021 11:28:44 AUSQLD Edward Brooks (R884255) * Reduced to zero to allow for short span bridge at 6.640km can be included in renewal plan to improve efficiency with renewal of 6.7km short span bridge. FY23 Reactive works no longer required. Zeroed out and closed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043439&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043439 | Structures Renewal. | BR201054 | CIVIL | STRUCTURES | BRIDGE BEARING | DESIGN & RENEWAL | 1 | BRIDGES | 2259567 | Goonyella |  |  | 0.0919 | KM | GA01ML109 | 0.774 | GA01ML109 | 0.8659 | KM |  |  |  |  | 109.82 |  | 2023-06-30 | DN |  |  |  | 3.5 | 4.4 |  |  |  | 16.2 |  | 2021-03-31 | 2021-10-05 | Bridges Renewal | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 25.09.2020 18:13:10 AUSQLD Edward Brooks (R884255) * Defect: "Bridge Bearing issue Pier 1 Bearing 4 & Bearing 8, Pier 5 Bearing 5 * Propose: Remove and replace bearing pad, by jacking girders. * " * 31.12.2020 07:18:30 AUSQLD Edward Brooks (R884255) * Risk: High * Reason: Although not all the bearing pads are almost falling out, one is and if it falls out completely then we will have concrete on create interface which will damage the headstock or girder which then may need to be replaced altogether. To avoid this a bearing pad replacement will maintain the life of the girders and headstock. Any sort of concrete deterioration to the girder could result in a failure or girder which could occur with little warning which could have catastrophic impact to life and service in this region. Any incident like this would have the track closed for weeks or months with investigation and repairs, so this work is critical for operations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070137&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070137 | Structures Renewal | CU300259 | CIVIL | STRUCTURES | BRIDGE SHORT SPAN | DESIGN & RENEWAL | 1 | BRIDGES | 1450018 | Newlands | NL |  | 0.016 | KM | NL01ML6 | 0.633 | NL01ML6 | 0.649 | KM |  |  |  |  | 6.64 |  | 2023-06-30 |  |  |  |  | 3 | 1.7 |  |  |  | 5.1 |  | 2021-03-31 | 2021-10-05 | Bridges Renewal | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 04.01.2021 11:29:55 AUSQLD Edward Brooks (R884255) * Defect: Speed restriction, Under load capacity * Propose: Strengthening Required, design thickening at base slab and piers D<(>&<)>C works, also consider RCBC replacement. * Risk: Mod-High * Reason: This bridge should be completed at the same time as 6.7km to improve efficiency and potentially obtain some cost savings. This bridge is not in as bad condition as 6.7, however has been established as under capacity for shear in the deck slabs and under capacity in bending in the pier walls and in bending and shear in the base slab. This is the reason for the speed restrictions and need for this asset to be renewed. * 04.01.2021 11:33:40 AUSQLD Edward Brooks (R884255) * Based on BK comparison and height of 2.4m believe RCBC will be cheapest alternative.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065450&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065450 | Structures Renewal | CU300266 | CIVIL | STRUCTURES | BRIDGE SHORT SPAN | DESIGN & RENEWAL | 1 | BRIDGES | 1450018 | Newlands | NL |  | 0.0219 | KM | NL01ML6 | 0.6889 | NL01ML6 | 0.7109 | KM |  |  |  |  | 6.7 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  | 2021-03-31 | 2021-10-05 | Bridges Renewal | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 25.09.2020 18:41:43 AUSQLD Edward Brooks (R884255) * Defect: Speed restriction, Under load capacity * Propose: Strengthening Required, design thickening at base slab and piers D<(>&<)>C works, also consider RCBC replacement. * 31.12.2020 07:34:34 AUSQLD Edward Brooks (R884255) * Risk: High * Reason: Rail traffic is speed restricted in this area because of the under capacity short span bridges. These were meant to be strengthened or replaced by 2016, however remain an issue now and plan is to progressively replace them until speed restriction can be removed. This will improve traffic efficiency for customers. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065451&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065451 | Structures Renewal | BR300130 | CIVIL | STRUCTURES | BRIDGE SHORT SPAN | RENEWAL | 1 | BRIDGES | 1450018 | Newlands | NL |  | 0.0179 | KM | NL01ML11 | 0.3109 | NL01ML11 | 0.329 | KM |  |  |  |  | 11.32 |  | 2023-06-30 |  |  |  | 6/2400X1800 UNIBOX +1/900X300 | 3.5 | 1.7 |  |  |  | 6 |  | 2021-03-31 | 2021-10-05 | Bridges Renewal | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 25.09.2020 18:47:45 AUSQLD Edward Brooks (R884255) * Defect: Moderate Spalling and reinforcement exposed with moderate section loss in piers 2 and 4 * Propose: Strengthening or remove and replace with longer span bridge (1/15m est) or RCBC equivalent. * 31.12.2020 07:36:31 AUSQLD Edward Brooks (R884255) * Proposed: Looking at BK comparison, RCBC looks best option. * Risk: High * Reason: Rail traffic is speed restricted in this area because of the under capacity short span bridges. These were meant to be strengthened or replaced by 2016, however remain an issue now and plan is to progressively replace them until speed restriction can be removed. This will improve traffic efficiency for customers. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078778&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078778 | Structures Design & Renewal | BR101111 | CIVIL | STRUCTURES | BRIDGE_RELIEVING SLAB | DESIGN & RENEWAL | 1 | SITE | 244575 | Blackwater | BW-GG |  | 0.0769 | KM | BW08ML19 | 0.8139 | BW08ML19 | 0.891 | KM |  |  |  |  | 19.85 |  | 2023-06-30 |  |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  | 2021-10-05 | Bridges Renewal | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20230930 | Defect - Bridge embankment protection showing signs of undermining and drainage issues with sinking gabion baskets. No relieving slab present on bridge. Renewal - As part of the bridge rollout in FY23, install new relieving slab to improve transition and drainage away from abutment. Additional filling material likely to be required for during closure. Risk - Mod-High risk due to the top of rail alignment issues currently present and undermining of embankment protection. Until drainage issue resolved reoccurence of top of rail alignment issues will reoccur after heavy event. Also embankment supporting formation and track, may also be undermining increasing risk of rail, ballast and formation failures.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093964&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093964 | Structures Design | BR101453 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | DESIGN | 1 | SITE | 30000 | Blackwater | BW-NCL UP RD |  | 0.0459 | KM | BW01ML573 | 0.006 | BW01ML573 | 0.0519 | KM |  |  |  |  | 572.99 |  | 2024-06-30 |  |  | REPLACE REL SLAB & LHS HR |  |  |  | 4 | 0.1 | 1 | 100 | 5335 |  |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Notification completed | NWSC |  | 20230630 | Defect: Relieving slab failing on high chainage side, visible from abutment and install handrails on LHS. Confirm Proposed: Remove and Replace Relieving slabs both ends of the bridge and install handrails on LHS in Rollout Drawing: Risk: Mod-High Reason: Relieving slab has severe cracking in the ends of the abutment. Top alignment issues have also been observed which is causing faster deterioration of the ballast on the bridge. Higher maintenance costs until relieving slab resolved. the handrails are strategic scope for bridges on the CQCN.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082925&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082925 | Structures Design | BR300248 | CIVIL | STRUCTURES | BRIDGE-SHORT SPAN | DESIGN | 1 | SITE | 50000 | Newlands | NL |  | 0.021 | KM | NL01ML12 | 0.1849 | NL01ML12 | 0.2059 | KM |  |  |  |  | 12.2 |  | 2024-06-30 | [7 empty] | 0.1 |  | 100 | 119 |  | 2021-10-05 | Bridges Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Strategic as trying to remove long term speed restriction due to under capacity short span bridge. Business in above rail wanting to have these restrictions removed. Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082926&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082926 | Structures Design | BR300239 | CIVIL | STRUCTURES | BRIDGE-SHORT SPAN | DESIGN | 1 | SITE | 50000 | Newlands | NL |  | 0.021 | KM | NL01ML12 | 0.227 | NL01ML12 | 0.2479 | KM |  |  |  |  | 12.23 |  | 2024-06-30 | [7 empty] | 0.1 |  | 100 | 119 |  | 2021-10-05 | Bridges Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Strategic as trying to remove long term speed restriction due to under capacity short span bridge. Business in above rail wanting to have these restrictions removed. Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082927&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082927 | Structures Design | BR300238 | CIVIL | STRUCTURES | BRIDGE-SHORT SPAN | DESIGN | 1 | SITE | 50000 | Newlands | NL |  | 0.0109 | KM | NL01ML13 | 0.5 | NL01ML13 | 0.511 | KM |  |  |  |  | 13.51 |  | 2025-06-30 | [7 empty] | 0.1 |  | 100 | 119 |  | 2021-10-05 | Bridges Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Strategic as trying to remove long term speed restriction due to under capacity short span bridge. Business in above rail wanting to have these restrictions removed. Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082928&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082928 | Structures Design | BR300310 | CIVIL | STRUCTURES | BRIDGE-SHORT SPAN | DESIGN | 1 | SITE | 50000 | Newlands | NL |  | 0.014 | KM | NL01ML14 | 0.048 | NL01ML14 | 0.0619 | KM |  |  |  |  | 14.05 |  | 2025-06-30 | [7 empty] | 0.1 |  | 100 | 119 |  | 2021-10-05 | Bridges Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Strategic as trying to remove long term speed restriction due to under capacity short span bridge. Business in above rail wanting to have these restrictions removed. Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082917&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082917 | Structures Design | CU100909 | CIVIL | STRUCTURES | CMP - CONCRETE LINE | DESIGN | 1 | SITE | 37000 | Blackwater | BW-RM |  | 0 | KM | BW06ML51 | 0.1499 | BW06ML51 | 0.1499 | KM |  |  |  |  | 51.15 |  | 2025-06-30 |  |  |  |  | 3.5 | 2.3 |  |  |  | 8.1 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Corrosion in all inverts. Most severe in cells 6-9, 11, 14 <(>&<)> 15 Proposed: Concrete Line pending Hydro Check. Remove and replace would need to hold longer. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082632&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082632 | Structures Renewal | CU400303 | CIVIL | STRUCTURES | CMP GROUT & DIVERT | RENEWAL | 1 | SITE | 41485 | Moura |  |  | 0 | KM | MA01ML86 | 0.22 | MA01ML86 | 0.22 | KM |  |  |  |  | 86.22 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 8.1 | 118 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Regular silts up and does not function as a drain. Maintenance costs of cleaning annually and not required based on modelling. Proposed: Grout <(>&<)> Divert - Formalisation of existing longitudinal drain likely required. Grout existing structure and fill depression Risk: Moderate Reason: This work will help reduce significant maintenance costs in de-silting culverts after annual weather events. Also not required for flood immunity so better to remove them to svae ongoing costs of inspections and maintenance
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082633&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082633 | Structures Renewal | CU400325 | CIVIL | STRUCTURES | CMP GROUT & DIVERT | RENEWAL | 1 | SITE | 113757 | Moura |  |  | 0 | KM | MA01ML86 | 0.9699 | MA01ML86 | 0.9699 | KM |  |  |  |  | 86.97 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 8.1 | 118 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Regular silts up and does not function as a drain. Maintenance costs of cleaning annually and not required based on modelling. Proposed: Grout <(>&<)> Divert - Formalisation of existing longitudinal drain required. Filling culvert depression and scour protection to be considered. Note potential change in outfall catchment Risk: Moderate Reason: This work will help reduce significant maintenance costs in de-silting culverts after annual weather events. Also not required for flood immunity so better to remove them to svae ongoing costs of inspections and maintenance
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082937&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082937 | Structures Design | CU201240 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 37000 | Goonyella | GA-NG |  | 0 | KM | GA01ML10 | 0 | GA01ML10 | 0 | KM |  |  |  |  | 10 |  | 2024-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 16.1 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Moderate to severe corrosion corrosion through out invert of culvert. Proposed: CIPP LIne before worsens and if hydro suitable. Otherwise Remove and replace may need to be considered. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070069&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070069 | Structures Renewal | CU100088 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 120755 | Blackwater |  |  | 0 | KM | BW03ML79 | 0.5 | BW03ML79 | 0.5 | KM |  |  |  |  | 79.5 |  | 2023-06-30 |  |  |  |  | 3 | 3.8 |  |  |  | 11.3 | 5708 | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20231030 | * 30.12.2020 15:18:54 AUSQLD Edward Brooks (R884255) * Defect: Notification present, widening left severely corroded. * Proposed: Heaps of cover, CIPP lining 7m windening only as very costly and likely track closure to remove and replace. * Risk: Mod-High * Reason: Widening severely corroded and risk of collapse which will impact access rd above and wil stop drainage though this culvert and increase risk to track washout. * 12.04.2021 16:21:07 AUSQLD Jeremy Stevenson (R867415) * Design completed FY18, 39m widening * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070102&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070102 | Structures Renewal | CU200728 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 176230 | Goonyella | GA |  | 0 | KM | GA01ML67 | 0.9399 | GA01ML67 | 0.9399 | KM |  |  |  |  | 67.94 |  | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.12.2020 07:06:33 AUSQLD Edward Brooks (R884255) * Defect: Severe corrosion and hole in invert for 3m and moderate corrosion throughout. * Proposed: CIPP lining or remove and replace. * Risk: High * Reason: Large hole in culvert already and need renewal asap due to risk of CIPP no longer working if left longer. Also high risk of crushing. * 12.04.2021 16:21:13 AUSQLD Jeremy Stevenson (R867415) * FY22 (Aug) not discussed * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081440&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000081440 | Structures Design | CU200187 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 37100 | Goonyella | CAVAL RIDGE JCT | VILLAFRANCA | 0 | KM | GA05ML27 | 0.89 | GA05ML27 | 0.89 | KM |  |  |  |  | 27.89 |  | 2024-06-30 |  |  |  |  | 4 | 1.2 |  |  |  | 8.6 |  |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Structural crack in CMP increased from 0.3m to 3m in 2 years, corrosion throughout. Proposed: Concrete Lining pending hydro or Remove and replace with RCBC however approx 4m cover. Possible pipe jacking site as well. Risk: High Reason: Severe cracking in CMP increases risk of collapse corrosion appears to be coming from outside to inside which means section thickness and asociated strength of cmp severely compromised. Risk of collapse high and being 1.8m diameter likely to cause significant track impact.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070095&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070095 | Structures Renewal | CU200890 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 2361280 | Goonyella |  |  | 0 | KM | GA01ML20 | 0.9399 | GA01ML20 | 0.9399 | KM |  |  |  |  | 20.94 |  | 2023-06-30 |  |  |  |  | 3.5 | 4.7 |  |  |  | 16.5 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230828 | * 30.12.2020 16:56:38 AUSQLD Edward Brooks (R884255) * Defect: Severe corrosion above invert lining for approx 150m of culvert. Water leaking through walls. * Proposed: hydro check for concrete Lining option. Cover is 1500, so need to confirm if pumping * Risk: Mod-High * Reason: Risk of crushing the cmp at concrete invert intersection and corrosion on invert of CMP is high. Concrete lining now will avoid track closure in future and remove risk of track alignment and derailment issues.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082630&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082630 | Structures Renewal. | CU400346 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 416389 | Moura |  |  | 0 | KM | MA01ML84 | 0.4199 | MA01ML84 | 0.4199 | KM |  |  |  |  | 84.42 |  | 2024-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 7.7 | 118 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20230630 | Defect: Moderate to severe corrosion of invert through. Rocks inside culvert will need to be removed. Access difficult. Proposed: Concrete Line - Base of CMP is corroded propose to line - thickness of liner TBC but have assumed 250mm for purposes of hydraulic modelling. Large rock sitting on top of CMP obvert at inlet to be relocated to safe position which will not block the waterway. , continue to monitor this as it has potential to block CMP if dislodged Limited scope to do any works upstream due to access and terrain (large boulders) Risk: Moderate Reason: This is critical from the condition of the invert which is corroded which could lead to deformation and more difficult in linin the asset. A remove and replace of this asset will be extremely difficult and not efficientm so capturing this prior to severe deterioration is important for cost and duration of closure. This could be deferred to FY24 if required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082618&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082618 | Structures Renewal. | CU400335 | CIVIL | STRUCTURES | CMP-DROP STRUCTURE | RENEWAL | 1 | SITE | 264532 | Moura |  |  | 0 | KM | MA01ML81 | 0.7099 | MA01ML81 | 0.7099 | KM |  |  |  |  | 81.71 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.1 |  |  |  | 7.2 | 118 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20230831 | Defect: High risk of personal injury on inlet side as poorly visible. Severe scour on outlet side undermining outlet. Proposed:"Inlet Drop Structure Outlet Scour Protection - Possible options: Replace grate with raised steel grate Dig down concrete surround existing CMP and place concrete collar/riser on top with grate Remove current arrangement and install precast pit with riser and grate Additional rock or grouting of existing required at outlet" Risk: Mod-High Reason: High risk of staff injury due to poor visibility of of inlet grate. Risk of undermining outlet could worsen to extent where remove and replacement of culvert may be required which will be a significant cost impact or 3 to 4 times the current cost, including a track closure which is not require for currently proposed work.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082631&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082631 | Structures Renewal | CU400250 | CIVIL | STRUCTURES | CMP-OUTLET | RENEWAL | 1 | SITE | 220444 | Moura |  |  | 0 | KM | MA01ML84 | 0.81 | MA01ML84 | 0.81 | KM |  |  |  |  | 84.81 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 8.1 |  |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | Defect: Outlet scour severe undermining apron rock matress. Proposed: Outlet Scour Protection - Engineered solution required at outlet to prevent further scour and existing rock mattress being washed away. Stepped gabion, concrete batter chute, or insitu solution with dissipator required Access to both sides difficult Risk: Mod-High Reason: Severe undermining of outlet and if not complete now the risk will be the cost of replacing CMP may need to be factored into the work, including a track closure. Will also loose current rock mattress on outlet.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070109&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070109 | Structures Renewal | CU201022 | CIVIL | STRUCTURES | ELIMINATE | RENEWAL | 1 | SITE | 81926 | Goonyella | GA |  | 0 | KM | GA01ML158 | 0.0899 | GA01ML158 | 0.0899 | KM |  |  |  |  | 158.09 |  | 2023-06-30 |  |  |  |  | 3.5 | 2.5 |  |  |  | 8.8 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.12.2020 07:32:51 AUSQLD Edward Brooks (R884255) * Defect: moderate corrosion through all and cell 1 was recently blocked 100%. Cell 1 was cleaned and found to be collapsed and now grouted. * Proposed: Remove and replace RCBC 26m long * Risk: High * Reason: Cell 1 collapsed and has been grout filled. Risk that other two cells may do the same and may be corroding from outside to inside. This will have top of rail alignment issues and risk of derailment. With one cell grouted high risk of track washout in severe weather event * 12.04.2021 16:21:14 AUSQLD Jeremy Stevenson (R867415) * * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065452&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000065452 | Structures Renewal. | CU100480 | CIVIL | STRUCTURES | NON-MRSB RCBC | RENEWAL | 1 | SITE | 774985 | Blackwater | BURNGORVE NOGOA |  | 0 | KM | BW03ML243 | 0.3449 | BW03ML243 | 0.3449 | KM |  |  |  |  | 243.08 |  | 2023-06-30 |  |  |  |  | 3 | 1.7 |  |  |  | 5.1 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | RRIG INIF | FY23 IN NON MRSB | 20240630 | * 25.09.2020 19:13:13 AUSQLD Edward Brooks (R884255) * Defect: Found in study of 243.567km to require 2 cells to prevent afflux to TMR. * Propose: Remove and replace 2/1500x600 RCBC. Must be constructed with 243.567 * 30.12.2020 15:50:17 AUSQLD Edward Brooks (R884255) * Risk: High * Reason: Must be completed in conjunction with 243.567, or else Aurizon will be responsible for significant afflux to TMR highway. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043970&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000043970 | 4909 Structures Renewal | CU100378 | CIVIL | STRUCTURES | NON-MRSB RCBC-ELIMINATE | RENEWAL | 1 | SITE | 29043 | Blackwater | BURNGORVE NOGOA |  | 0 | KM | BW03ML243 | 0.5669 | BW03ML243 | 0.5669 | KM |  |  |  |  | 243.57 |  | 2023-06-30 |  |  |  |  | 4.5 | 1.7 |  |  |  | 7.4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN NON MRSB | 20240630 | * 25.09.2020 19:12:07 AUSQLD Edward Brooks (R884255) * Defect: Notification 2000029989 Ballast falling through LHS CIS Section. Collapsed * Propose: Eliminate and divert but must be completed with expansion of 243.080 to 2 cells to avoid TMR afflux * 30.12.2020 15:52:25 AUSQLD Edward Brooks (R884255) * Risk: High * Reason: Current ballast is falling through large crack in insitu section which will lead to top of rail alignment issues and then lead to derailments. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080946&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000080946 | Structures Design | CU100625 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37100 | Blackwater |  |  | 0 | KM | BW03ML181 | 0.2 | BW03ML181 | 0.2 | KM |  |  |  |  | 181.2 |  | 2025-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 16 |  |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Pumping and severe cracks throughout ceiling and legs of insitu section. Proposed: Remove and replace with RCBC. Risk: Mod-High Reason: Severe cracking in ceiling increases risk of collapse and pumping will make the structure deteriorate faster. Original Insitu culverts were intended for 15TAL and we are running 26.5TAL so all factors increase risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082461&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082461 | Structures Design | CU101368 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 39567 | Blackwater |  |  | 0 | KM | BW01ML596 | 0.2399 | BW01ML596 | 0.2399 | KM |  |  |  |  | 596.24 |  | 2023-06-30 |  |  |  |  | 3.5 | 4.1 |  |  |  | 15.9 |  |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Severe corrosion through CMP on outlet side. Unable to vac lean due to risk of damaging CMP. Proposed: Remove and Replace RCBC. Can inlet be raised or else drop chute may be required. Also a causeway required on access rd to direct council drain flow into new culvert. Risk: Mod-High Reason: Severe corrosion on outlet side is prevent cleaning silt due to risk of corrosion and loss of section thickness. Risk of collapse is mod-high and arch under track also deteriorated.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082934&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082934 | Structures Design | CU100123 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Blackwater | BW-CL |  | 0 | KM | BW03ML194 | 0.6199 | BW03ML194 | 0.6199 | KM |  |  |  |  | 194.62 |  | 2025-06-30 |  |  |  |  | 4 | 2.85 |  |  |  | 11 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: RHS insitu section Pumping under loaded training. Cracking in haunches. Proposed: Remove and Replace RCBC Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082936&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082936 | Structures Design | CU101607 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML626 | 0.39 | BW01ML626 | 0.39 | KM |  |  |  |  | 626.39 |  | 2025-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Cell 1, unit 1 - crack in leg. Cell 1 unit 7 sunk 25mm base slab failing. Cell 2 unit 7 sunk 25mm base slab failing. Cell 3 unit 7 sunk 50mm base slab failing. Proposed: Remove <(>&<)> Replace RCBC Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082635&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082635 | Structures Design | MA-01ML | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 38000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML80 | 0.2999 | MA01ML80 | 0.2999 | KM |  |  |  | 80.3 | 80.3 | 80.3 | 2025-06-30 | MA-01ML | [6 empty] | 0.1 |  | 100 | 118 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Overtpping of Rail and track washout at MA-80.300km, multiple washouts at this location historically. Proposed: Additional new Culverts - 2/1200x900mm RCBC Risk: Mod-High Reason: Significant flood risk at this locatio of 80.300 due to insufficient drainage through the track. Multiple washouts have occured at this location historically.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084073&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084073 | Structures Design | CU201083 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Goonyella | GA |  | 0 | KM | GA01ML98 | 0.8399 | GA01ML98 | 0.8399 | KM |  |  |  |  | 98.84 |  | 2025-06-30 |  |  |  |  | 3.5 | 4.7 |  |  |  | 16.1 | 131 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Propeed all cells unit8-14. Poor patching is starting to spall again. Loaded trains now running on DN rd which is not propped. FY16 design for 20% reduction concrete lining, but this is only 125m thick, confirm 200-250 thickness will work. Proposed: Concrete lIning FY16 recommendation, but need to confirm constructability due to 1200 height or Remove <(>&<)> Replace RCBC Risk: Mod-High Reason: Long term propped structures on units 8-14 and now all repairs are failing again and other section of culvert is spalling. Main section of goonyella line which is speed restriction or closure occured would impact many customer services.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093103&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093103 | Structures Design | CU201297 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 38000 | Goonyella | GA-HP |  | 0.01 | KM | GA01BD0 | 0.4359 | GA01BD0 | 0.446 | KM |  |  |  |  | 0.42 |  | 2026-06-30 |  |  |  |  | 4 | 2.3 |  |  |  | 14.5 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | NWSC |  | 20230630 | Defect: Sereve spalling in ceiling of units with exposed reinforcement. Currently propped to make safe. Incorrectly called up as Bridge, when in fact 2 Cell RCBC Culvert. Proposed: Remove and replace with RCBC Drawing: Risk: High Reason: Culvert is in poor condition with section of reinforcement severely corroded and exposed. Propping has been installed to make safe however need for replacement is urgent as risk of collapse is high in these poor units.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083115&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083115 | Structures Design | CU200413 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Goonyella | GA-OC |  | 0 | KM | GA03ML16 | 0.4199 | GA03ML16 | 0.4199 | KM |  |  |  |  | 16.42 |  | 2024-06-30 |  |  |  |  | 4.5 | 2.8 |  |  |  | 12.6 | 121 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: units misaligned, ballasting falling through joints and undermining sleeper stability. Speed restriction required. Temporary rings or hdpe required until renewal Proposed: Remove and Replace RCBC Pipe through culvert owned by Daunia Quarry, to be contacted prior to renewal Risk: High Reason: Track stability has been compromised in this location with edge of sleeper exposed from falling ballast into culvert. temporary measures dramatically reduce the capacity of the waterway and increase the risk of track washout during weather event. All these put above rail operation at high risk of disruptions.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080311&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000080311 | Structures Design | CU201298 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37100 | Goonyella | GA-PD |  | 0 | KM | GA17ML45 | 0.3599 | GA17ML45 | 0.3599 | KM |  |  |  |  | 45.36 |  | 2024-06-30 |  |  |  |  | 4.5 | 1.2 |  |  |  | 5.4 |  |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: FLOOR INVERT CORROSION. and hole formed between access rd and track suggesting severe corrosion. Proposed: Remove and replace with RCBC. Mine pipe through cell is not live and can be removed during construction, confirmed by PD Mine 26/7/21. Risk: Mod-High Reason: not immediate risk, but coming closer to FY24, this culvert will be in risk of scouring and track impacts to movement in the pipes. Also if we do not catch this cmp now it will require a track closure to remove and replace. Plan now is for it to be CIPP lined.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084072&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084072 | Structures Design | CU400456 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Moura | MA |  | 0 | KM | MA01ML60 | 0.8199 | MA01ML60 | 0.8199 | KM |  |  |  |  | 60.82 |  | 2024-06-30 |  |  |  |  | 4 | 1.1 |  |  |  | 14.2 | 131 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Longitudinal cracks in base and haunch cracking in cells 2 and 3. D7 track defect constantly occuring on this asset, making it higher priority to get replaced. FY19 Stirrat-Clarje flood study Proposed: Remove and Replace RCBC as subgrade appears to be compromised as base slab failed. Risk: High Reason: Track stability has been an issue for local districts team and ATIS is stating a D7 defect each run and therefore this is a priority piece of work to get renewed as soon as possible. High risk of customer impacts if this scope is deferred.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082634&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082634 | Structures Design | CU400449 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 38000 | Moura | MA |  | 0 | KM | MA01ML86 | 0.78 | MA01ML86 | 0.78 | KM |  |  |  |  | 86.78 |  | 2025-06-30 |  |  |  |  | 3.5 | 1.1 |  |  |  | 7.2 | 118 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Washout risk and inadequate cover. Proposed: Remove and Replace RCBC - Proposed diversion results in overtopping of rail and thus is deemed unacceptable. Currently has insufficient cover, if Aurizon wishes to remove and replace 900 x 600mm RCBC required Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082909&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082909 | Structures Design | CU300115 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 37000 | Newlands | NL |  | 0 | KM | NL01ML62 | 0.1799 | NL01ML62 | 0.1799 | KM |  |  |  |  | 62.18 |  | 2025-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: CULVERTS ENTIRE CRACKED Proposed: Remove and replace with large RCBC or RCP. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070089&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070089 | Structures Renewal. | CU400503 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 401150 | Moura |  |  | 0 | KM | MA03ML1 | 0.4899 | MA03ML1 | 0.4899 | KM |  |  |  |  | 1.49 |  | 2023-06-30 |  |  |  | 3/1200 X 900 RCBC | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20230630 | * 30.12.2020 16:10:23 AUSQLD Edward Brooks (R884255) * Defect: moderate to severe spalling in ceiling in every unit and span. * Proposed: Remove and replace, can CIPP lining be considered for this size box? * Risk: Mod-High * Reason: moderate to severe spalling in majority of the unit in the ceiling with exposed reinf in most. Risk is that deterioration may speed up similar to cell 2 and a possible collapse fo the unit which may cause a derailment. a derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070063&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070063 | Structures Renewal. | CU100193 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 525872 | Blackwater |  |  | 0 | KM | BW03ML15 | 0.01 | BW03ML15 | 0.01 | KM |  |  |  | 15.01 | 15.01 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 14:36:50 AUSQLD Edward Brooks (R884255) * Defect: cell 3 <(>&<)> 5 unit 6 severe cracking * Proposed: CIPP lining or remove and replace. * Risk: Mod-High * Reason: Cracking in the ceiling and sides of the RCP are structural cracks and risk of collapse is moderate to high. If collapses it will be remove and replace requiring track closure, CIPP will not require closure and cost less. * 12.04.2021 16:21:05 AUSQLD Jeremy Stevenson (R867415) * Design FY22 (Early wks package, exp is a CIPP lini ng to be confirmed not confirmed till design. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044240&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044240 | Structures Renewal | CU201002 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 608677 | Goonyella |  |  | 0 | KM | GA01ML24 | 0.3119 | GA01ML24 | 0.3119 | KM |  |  |  |  | 24.27 |  | 2023-06-30 |  |  |  |  | 3.5 | 5 |  |  |  | 17.5 |  | 2019-07-15 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG | FY23 IN | 20230630 | Delayed from FY20->FY21 due to COVID DElayed from FY21->FY23 due to QR restructions on closures on NCL. Now tentaively agreed fro October 2022 60hr closure in FY23. Defect - Severe Spalling in ceiling of unis 5 <(>&<)> 8. Reinforcement exposed and corroded. Dropped approx 25mm Renewal - Drawing AUR-Q-0772-4011. Remove and Replace 3/1800x900 RCBC 17.3m Long
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070064&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070064 | Structures Renewal. | CU100236 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 422907 | Blackwater |  |  | 0 | KM | BW03ML36 | 0.7199 | BW03ML36 | 0.7199 | KM |  |  |  |  | 36.72 |  | 2023-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 11.7 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 14:50:06 AUSQLD Edward Brooks (R884255) * Defect: LHS is failing, crushed box unit and severely cracked base slab. * Proposed: Relocation of culvert 20m increasing chainage. 3/1200x450 RCBC. Grout old culvert * Risk: High * Reason: Severely crack base slab will lead to track alignment issues and risk of derailment, and LHS sinking needs to be rectified as soon as possible to ensure track washout does not occur from reduced drain capacity. * 12.04.2021 16:21:06 AUSQLD Jeremy Stevenson (R867415) * * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070065&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070065 | Structures Renewal. | CU100498 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 510213 | Blackwater |  |  | 0 | KM | BW03ML69 | 0.55 | BW03ML69 | 0.55 | KM |  |  |  |  | 69.55 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 14:57:04 AUSQLD Edward Brooks (R884255) * Defect: Crcaked @ 3,9<(>&<)>12 oclock and disformed shape vertically. Cracks may be allowing movement * Proposed: Grout up or CIPP lining if possible. * Risk: High * Reason: Severe cacking in ceiling of RCP high risk of collapse and risk of track misalignment and increased risk of derailment. * 12.04.2021 16:21:06 AUSQLD Jeremy Stevenson (R867415) * FY22 Design (Aug) awaiting design to confirm scope is CIPP 13m may change CIPP to Grout. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082619&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082619 | Structures Renewal | CU400312 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 370114 | Moura |  |  | 0 | KM | MA01ML82 | 0.0299 | MA01ML82 | 0.0299 | KM |  |  |  |  | 82.03 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 8.1 | 118 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Damaged on rhs. Moderate corrosion in invert. Inadequate cover over CMP. Proposed: "Remove and replace - Diversion checked however ToR immunity not achieved with diversion therefore diversion not acceptable solution. Remove and replace with 1200x900 RCBC to achieve formation immunity Limited space upstream to undertake ESC works due to cutting" Risk: Mod-High Reason: Risk of track washout in this location is quite high due to the limitd cover over this asset. Increasing to RCBC will provide flood immunity as access for this work is reasonable.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061351&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000061351 | Structures Renewal. | CU100699 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1523273 | Blackwater |  |  | 0 | KM | BW03ML128 | 0.8399 | BW03ML128 | 0.8399 | KM |  |  |  |  | 128.84 |  | 2024-06-30 |  |  |  |  | 4.5 | 3.4 |  |  |  | 15.3 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | LOW | Notification in process | RRIG INIF | FY23 IN | 20230625 | * 16.07.2020 16:47:18 AUSQLD Edward Brooks (R884255) * 16.07.2020 16:46:32 AUSQLD Edward Brooks (R884255) * DefectsCell 1, units 3 & 6 are sinking. * Cell 2 unit 6 is sinking. * Cell 5, unit 7 cracked haunch and pumping. * Cell 7, unit 7 cracked haunch’s and pumping. * Cell 8, units 3 & 6 are pumping and spalling in roof. * Cell 9, Units 7 & 8 have cracks in near haunch’s. * Cell 10, unit 7 cracked haunch’s and pumping. * Cell 12, unit 7 failing * Cell 13, Unit 6 has a broken leg, plaster wont repair this break. * Cell 15, unit 7 near and far haunch’s have severe cracks and roof is broken. * Cells 6 and 14 have ben grout filled as were failing. Also Cell 12 will also be grouted in FY21 * Renewal planned in FY23 and planned to be a complete remove and replace with new RCBC. * 30.12.2020 15:31:22 AUSQLD Edward Brooks (R884255) * Risk: High * Reason: All base slabs have failed under loaded track, increasing risk of track misalignment and derailment. Worst cells already grouted to try and prevent this, however this has left 6 or the 16 cells block and compromising hydro for system and increasing risk of track washout in severe weather event. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070081&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070081 | Structures Renewal. | CU100586 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 400774 | Blackwater |  |  | 0 | KM | BW03ML155 | 0.6199 | BW03ML155 | 0.6199 | KM |  |  |  |  | 155.62 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 15:34:08 AUSQLD Edward Brooks (R884255) * Defect: "Severe cracks throughout base slab and sever crack and exposed reinf in ceiling of insitu section. * Hydro completed in FY19 by AECOM" * Proposed: Remove and replace * Risk: High * Reason: Severe crcaking through ceiling, walls and base slab. High risk of collapse if left beyond FY23. differential movement could also lead to rail misalignment and derailment. * 12.04.2021 16:21:08 AUSQLD Jeremy Stevenson (R867415) * * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070082&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070082 | Structures Renewal | CU100370 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 378946 | Blackwater |  |  | 0 | KM | BW03ML155 | 0.68 | BW03ML155 | 0.68 | KM |  |  |  |  | 155.68 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.12.2020 15:40:29 AUSQLD Edward Brooks (R884255) * Defect: Severe Cracks throughout insitu section in walls base slab and ceiling. Localised spalling and exposed reinf in RCBC. * Proposed: Remove <(>&<)> Replace 1 / 1200x900 consider all culverts in catchment between 157km and 155km which is approx 8 culverts and determine if we can grout fill some culvert and up grade others. Currently in scope for replacement is 155.430km , 156.430km 156.730km , 156.800km. * Risk: High * Reason: Severe crcaking through ceiling, walls and base slab. High risk of collapse if left beyond FY23. differential movement could also lead to rail misalignment and derailment. to rail misalignment and derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044220&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044220 | Structures Renewal. | CU100376 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1329289 | Blackwater |  |  | 0 | KM | BW03ML156 | 0 | BW03ML156 | 0 | KM |  |  |  |  | 155.95 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 10.03.2020 08:29:50 AUSQLD Peter Rayner (R003851) * Defect - Notification 2000024982 culvert silted and moderate horizontal cracking in pipes. - Proposed Renewal - Marked on culvert as 156.000. Remove and replace likely, may look at inverts . If hydro ok. This tunnelline may be an option * 12.04.2021 16:21:52 AUSQLD Jeremy Stevenson (R867415) * Design FY21, remove and replace, extend by 2 cells under access road. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070083&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070083 | Structures Renewal. | CU100213 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1385290 | Blackwater |  |  | 0 | KM | BW03ML188 | 0.8 | BW03ML188 | 0.8 | KM |  |  |  |  | 188.8 |  | 2023-06-30 |  |  |  |  | 4 | 3.2 |  |  |  | 12.6 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 15:44:31 AUSQLD Edward Brooks (R884255) * Defect: Severe spalling <(>&<)> cracks in ceiling throughout, particularly at joints. Cracks also in base slab. Note pipe present in culvert consider in construction. * Proposed: Remove and replace. Existing service pipe in culvert * Risk: High * Reason: Severe cracking and corroded exposed reinforcement throughout cell. High risk of collapse due to loss of reinf section and bonding. High risk of trail alignment issued if ballast start to fall through large gaps which may lead to derailments. Budget increased by 300k to $750,000 based on advice from construction delivery team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070086&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070086 | Structures Renewal. | CU101447 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 589385 | Blackwater |  |  | 0 | KM | BW01ML563 | 0.0599 | BW01ML563 | 0.0599 | KM |  |  |  |  | 563.06 |  | 2023-06-30 |  |  |  |  | 4 | 4.5 |  |  |  | 18 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 15:59:47 AUSQLD Edward Brooks (R884255) * Defect: severe cracks in units 1-3,7, 2-5,6,7 <(>&<)> 3-7. Base slab also severely cracked in spans 1,2 <(>&<)> 3 * Proposed: Remove and replace, fix outlet, so self drains, cables on outlet. * Risk: High * Reason: Has been propped to reduce pumping and spread load. M160 culvert so only design for 15 TAL and taking 26.5TAL. Cracks in haunches are high risk of collapse worsened by the pumping. Critical section of NCL which takes passenger trains as well increasing the consequences of failure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070087&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070087 | Structures Renewal. | CU101457 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 944307 | Blackwater |  |  | 0 | KM | BW01ML564 | 0.13 | BW01ML564 | 0.13 | KM |  |  |  |  | 564.13 |  | 2023-06-30 |  |  |  |  | 3.5 | 4.5 |  |  |  | 15.8 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 16:03:07 AUSQLD Edward Brooks (R884255) * Defect: Smashed end units, units 1-11 <(>&<)>2-11 severe spalling in leg and severe haunch crack. Moderate spalling from unit 6-11 at joints in ceiling. * Proposed: Remove and replace 4/ 1200x1200 RCBC * Risk: Moderate * Reason: Left in scope as M160 culverts on main line taking regular 26.5TAL. Unit 11 is at risk of collapsing but may last beyond FY23, howvere the hydro came back requiring 4 cells vs exsting of 2, therefore high risk of track washout of main line. And therefore important to get rectified.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044223&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044223 | Structures Renewal. | CU100589 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 403094 | Blackwater | BW-CL |  | 0 | KM | BW03ML180 | 0.7399 | BW03ML180 | 0.7399 | KM |  |  |  |  | 180.74 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 10.03.2020 08:30:13 AUSQLD Peter Rayner (R003851) * Defect - Culverts moving apart, patched once to prevent falling ballast - Proposed Renewal - Remove and replace with RCBC * 31.12.2020 09:17:12 AUSQLD Edward Brooks (R884255) * Scopes deferred from FY22 for cost reasons. * 12.04.2021 16:21:53 AUSQLD Jeremy Stevenson (R867415) * Design FY21, hydro complete, design still coming. Like for like replacement 16m length * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083447&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083447 | Structures Renewal | CU100021 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 322345 | Blackwater | BW-LM |  | 0 | KM | BW13ML0 | 0.08 | BW13ML0 | 0.08 | KM |  |  |  |  | 0.08 |  | 2023-06-30 |  |  |  | 1/1800 X 600 RCBC |  |  |  | 0.1 |  | 100 | 131 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: To improve flood immunity at CL-188.800km, engineering advised that LM-0.080 culvert will need to be renewed. Improves formation immunity from 20% AEP to 2% but additional culvert to be upgraded Proposed: Remove and Replace 2/900 x 600 RCBC with CL-188.800 Final: 1/1800 x 600 RCBC Remove <(>&<)> Replace Risk: Moderate Reason: This work will improve flood immunity of network at the CL-188.800km and without this there is a risk of impact to neighbouring property when 188.800 is renewed. Improves formation immunity from 20% AEP to 2% but additional culvert to be upgraded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105045&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000105045 | Structures Renewal | CU200453 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 150000 | Goonyella | GA-OC |  | 0 | KM | GA03ML27 | 0.7199 | GA03ML27 | 0.7199 | KM |  |  |  |  | 27.72 |  | 2028-06-30 |  |  | R&R RCP | RCP | 4 | 1.7 | 3 | 4.2 | 1 | 13.3 | 5481 |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Notification completed | NWSC |  | 20230630 | Defect: Severe Cracking and sinking in unit 4. Look to be subgrade issues and pumping to be confirmed at site walkout. Proposed: Remove and Replace with RCBC or RCP Risk: Mod-High Reason: May be pumping causing increased deterioration of ballast and top alignment issues. The sinking under track may also cause the joint to open up and allow formation and ballast to fall through. Change: This asset has reached it's end of life with a construction year of 1972, therefore reasonable based on condition and age to bring this forward into FY23 to improve value and infrastructure efficiency across the network. Aligning this with neighbouring upgrade at Olive Downs means both assets will end up with a new design life. There is also the potential risk that due to the subgrade issues under this RCP causing the sinking of the unit, they increased moisture content in the subgrade for longer periods of time like we have seen in the last 12 months could lead to a further sinking of the asset allow ballast to fall through the joints and compromise track stability and required emergency works similar to seen at the 16km culvert not far from this culvert which resulted in a number of cancellations and delays to above rail traffic. Costs are intended to be shared with Olive Downs project so although this work was estimated at 400-500k, this will be reduced to 150k with shared costs. This is what has been allowed for in the characteristic fields.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083830&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000083830 | Structures Renewal | CU400505 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 498087 | Moura | MA |  | 0 | KM | MA03ML4 | 0.4899 | MA03ML4 | 0.4899 | KM |  |  |  |  | 4.49 |  | 2024-06-30 |  |  |  | 6/1500X600 RCBC | 4 | 1 |  |  |  | 12 | 141 |  | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | Defect: moderate to severe spalling in ceiling in every unit and span. Proposed: Remove and replace, can CIPP lining be considered for this size box? Final: 6/1500x600 RCBC Remove <(>&<)> Replace Risk: Mod-High Reason: moderate to severe spalling in majority of the unit in the ceiling with exposed reinf in most. Risk is that deterioration may speed up similar to cell 2 and a possible collapse fo the unit which may cause a derailment. Brought forward into FY23 as design completed and equally critical as BH-1.49km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070113&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070113 | Culvert Renewal NL 63.650. | CU300316 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 528856 | Newlands | NL-AB |  | 0 | KM | NL01ML63 | 0.65 | NL01ML63 | 0.65 | KM |  |  |  |  | 63.65 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 31.12.2020 07:50:54 AUSQLD Edward Brooks (R884255) * Defect: 2 Major circumference cracks, horzontal cracking * Proposed: Remove and Replace 1 / 1200x1200 RCBC * Drawing: AUR-Q-0831-4030 * Risk: Mod-High * Reason: These defects are relatively slow acting, however they are very severe cracks leting material through on occasion and horizontal cracking now also forming which is greater risk of failure. Existing construction details limited and therefore dfects enough of a concern now to warrant replacement after holding for a number of years. collapse of this size culvert will have significant impact to track closure time to recover without material onsite for planned closure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043688&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043688 | 4489 Structures Renewal. | CU100528 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 464553 | Blackwater | PARNABAL | WALTON | 0 | KM | BW03ML161 | 0.2 | BW03ML161 | 0.2 | KM |  |  |  |  | 161.2 |  | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 10.03.2020 08:29:56 AUSQLD Peter Rayner (R003851) * Defect - Dn Rd Side of culvert is moderately to serevely spalled. Unit 1 also showed minor crack in haunch. Insitu ceiling also looks deflected 2-5mm, unable to measure though. - Proposed Renewal - Renew Dn Rd side of the culvert, old insitu to be replaced with 300LA RCBC * 12.04.2021 16:21:53 AUSQLD Jeremy Stevenson (R867415) * Design Complete 14m replacement 1200 x 1200 Single Cell * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043797&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043797 | Structures Renewal | CU200380 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 532132 | Goonyella | WINCHESTER |  | 0 | KM | GA03ML32 | 0.07 | GA03ML32 | 0.07 | KM |  |  |  |  | 32.07 |  | 2023-06-30 |  |  |  |  | 3 | 2.5 |  |  |  | 7.5 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 14:19:47 AUSQLD Edward Brooks (R884255) * Defect: Special Defect Half culvert good condition. Old section has severe spalling and corrosion of reinforcement * Proposed: Remove and replace 5 units from RHS, all cells * Reason: Last 5 units are high risk of collapse with severe cracking and spalling present under track. Collapse of unit may lead to derailment. * 12.04.2021 16:21:05 AUSQLD Jeremy Stevenson (R867415) * Design FY21 * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075304&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075304 | Structures Renewal | CU201128 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 651587 | Goonyella | YUKAN |  | 0 | KM | GA01ML28 | 0.23 | GA01ML28 | 0.23 | KM |  |  |  |  | 28.23 |  | 2023-06-30 |  |  |  |  | 3.5 | 5 |  |  |  | 17.5 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 08:47:00 AUSQLD Edward Brooks (R884255) * Defect - NCL Affected. Special Defect. severe spalling in walls of units 1-9, 1-6 <(>&<)> 2-10. confirm with where insitu culvert ends , if under NCL then not Aurizon responsibility. Speed restriction has been put on culvert due to ballast falling between units and loosing top of line.This is casued by the sink and excessive pumping of these under capacity box units and base slab. * Proposed - Remove and replace as this main line to port and pumping will increase deterioration rate. Need to plan with QR as NCL over the top of section of culvert. * Final Design Solution: GHD 4/1200x900 RCBC * Risk if deferred: Units are moving apart caused by the excessive pumping under loaded trains. Ballast is falling into culvert causing dips in track and now a speed restriction has been put in place. This will cause significant delays to trains and have customer impacts therefore high risk. Although risk of derailment redced due to speed restriction, this is also a risk due to poor top of line.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041433&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000041433 | Structures Renewal | CU200853 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 474874 | Goonyella | YUKAN |  | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 28.35 |  | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2019-03-22 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230606 | * 07.08.2019 14:36:00 AUSQLD Jeremy Stevenson (R867415) * Reinforced Concrete Box Culvert * 2 / 1500 x 600 RCBC Remove and Replace RCBC 3/1200x600 (TBA) * 30.03.2020 13:41:29 AUSQLD Edward Brooks (R884255) * * Notification: 2000054430, for holding works until re-planning can be made. * 16.04.2020 20:05:43 AUSQLD Edward Brooks (R884255) * Delayed from FY20 delivery because of COVID-19 and state government requirement to maintain NCL open at all times. Delayed to FY23 due to QR restrictions on closures on NCL. Tentatively agreed October 2022 FY23 60hr closure. Renewal - Drawing AUR-Q-0772-4012. Remove and Replace RCBC 3/1200x600 RCBC 20.45m Long
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043809&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043809 | Structures Renewal. | CU101087 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 259630 | Blackwater |  |  | 0 | KM | BW08ML18 | 0.403 | BW08ML18 | 0.403 | KM |  |  |  |  | 18.4 |  | 2023-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 4.2 | 5393 | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | HIGH |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230710 | * 10.03.2020 08:29:13 AUSQLD Peter Rayner (R003851) * Defect - Moderate to Seevere spalling and cracking typ on edge of box units. - Proposed Renewal - Tunnel lined strengthening * 12.04.2021 16:21:52 AUSQLD Jeremy Stevenson (R867415) * Design FY21 Tunnel line, 500mm cover. Pumping issu es. Closure would be required, will be assumed. * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043687&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043687 | 4488 Structures Renewal | CU100222 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 85577 | Blackwater | PARNABAL |  | 0 | KM | BW03ML156 | 0.8 | BW03ML156 | 0.8 | KM |  |  |  |  | 156.8 |  | 2023-06-30 |  |  |  | ELIIMNATE & DIVERT | 3.5 | 3.4 |  |  |  | 11.9 | 5336 | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.03.2020 08:29:53 AUSQLD Peter Rayner (R003851) * Defect - TBC after remote inspection, 4 steps in base slab. - Proposed Renewal - Remove and replace with 1200x900 rcbc * 12.04.2021 16:21:53 AUSQLD Jeremy Stevenson (R867415) * Design completed 1200/900 RCBC * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082933&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082933 | Structures Design | CU100609 | CIVIL | STRUCTURES | RCBC-GROUT & DIVERT | DESIGN | 1 | SITE | 37000 | Blackwater | BW-CL |  | 0 | KM | BW03ML115 | 0.51 | BW03ML115 | 0.51 | KM |  |  |  |  | 115.51 |  | 2025-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Possible collapse as RHS completey blocked. Some misalignment visible from LHS Proposed: Possible eliminate and divert, hydro to confirm Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082918&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082918 | Structures Design | CU100112 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 37000 | Blackwater | BW-CL |  | 0.01 | KM | BW03ML77 | 0.1 | BW03ML77 | 0.0899 | KM |  |  |  |  | 77.09 |  | 2025-06-30 |  |  |  |  | 4 | 3.75 |  |  |  | 15 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: LHS widening severe corrosion and need replacing. Proposed: remove and replace widening. As large cover consider CIPP lining entire culvert or widening only. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082932&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082932 | Structures Design | CU100221 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 37000 | Blackwater | BW-CL |  | 0.025 | KM | BW03ML78 | 0 | BW03ML77 | 0.9799 | KM |  |  |  |  | 77.98 |  | 2025-06-30 |  |  |  |  | 3.5 | 3.75 |  |  |  | 13 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: widening severe corrosion 6 m long Proposed: Remove and replace widening. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082938&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082938 | Structures Design | CU300621 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 37000 | Newlands | NL-MN |  | 0 | KM | NL04ML85 | 0.3499 | NL04ML85 | 0.3499 | KM |  |  |  |  | 85.35 |  | 2025-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: HDPE extension looks very poorly constructed. Need to be replaced with RCP. Confirm can it be replaced without impacting track? Hydro likely compromised. Also service pipes in cells 1 <(>&<)> 5. Proposed: Remove and replace extension. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070068&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070068 | Structures Renewal. | CU100634 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 217400 | Blackwater |  |  | 0.0299 | KM | BW03ML79 | 0.2 | BW03ML79 | 0.17 | KM |  |  |  |  | 79.17 |  | 2023-06-30 |  |  |  |  | 3 | 3.8 |  |  |  | 11.3 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 15:14:05 AUSQLD Edward Brooks (R884255) * Defect: Invert severe corrosion in widening 6m. * Proposed: CIPP Line all culvert. Or replace widening with RCP * Risk: Moderate * Reason: widening severely corroded and risk of collapse which will impact access rd above and wil stop drainage though this culvert and increase risk to track washout. Included as multiple sites in this area need attention and hope is to gain some efficiency in cost and work when delivered. * 12.04.2021 16:21:07 AUSQLD Jeremy Stevenson (R867415) * uired * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082924&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082924 | Structures Design | CU100619 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 37000 | Blackwater | BW-CL |  | 0 | KM | BW03ML95 | 0.9649 | BW03ML95 | 0.9649 | KM |  |  |  |  | 95.965 |  | 2025-06-30 |  |  |  |  | 3.5 | 3.35 |  |  |  | 12 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: one CMP cell is 100% blocked with material. Possible collapse. Other reasonable condition Proposed: CIPP Line if Hydro suitable, otherwise Remove and replace Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082935&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082935 | Structures Design | CU101309 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 37000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML597 | 0.2899 | BW01ML597 | 0.2899 | KM |  |  |  |  | 597.29 |  | 2024-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.1 | 119 |  | 2021-10-05 | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | Defect: Severe Cracks in all RCPs Proposed: CIPP line if hydro suitable. Otherwise remove <(>&<)> replace Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070066&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070066 | Structures Renewal | CU100391 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 398520 | Blackwater |  |  | 0.02 | KM | BW03ML76 | 0.6999 | BW03ML76 | 0.7199 | KM |  |  |  |  | 76.72 |  | 2023-06-30 |  |  |  |  | 3 | 3.8 |  |  |  | 11.3 | 5708 | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG | FY23 IN | 20231030 | * 30.12.2020 15:02:01 AUSQLD Edward Brooks (R884255) * Defect: South extension severely corroded condition 4 * Proposed: Remove and replace South extension with RCP. Brief design scope for RCP install. CIPP also an option to avoid removal of widening which is under fill. * Risk: Mod-High * Reason: Widening severely corroded and risk of collapse which will impact access rd above and will stop drainage though this culvert and increase risk to track washout. * 12.04.2021 16:21:06 AUSQLD Jeremy Stevenson (R867415) * $250k) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070067&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070067 | Structures Renewal. | CU100594 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 716607 | Blackwater |  |  | 0.0299 | KM | BW03ML78 | 0.2 | BW03ML78 | 0.23 | KM |  |  |  |  | 78.23 |  | 2023-06-30 |  |  |  |  | 3 | 3.4 |  |  |  | 10.1 |  | 2021-03-31 | 2021-10-05 | Culvert Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 30.12.2020 15:05:50 AUSQLD Edward Brooks (R884255) * Defect: 6m widening left CMP severely corroded. * Proposed: CIPP Line all culvert. Or replace widening with RCP * Risk: Mod-High * Reason: Widening severely corroded and risk of collapse which will impact access rd above and wil stop drainage though this culvert and increase risk to track washout. * 12.04.2021 16:21:07 AUSQLD Jeremy Stevenson (R867415) * FY22 Design (Aug) awaiting design to confirm scope is CIPP. 8m fill above, allowed cost for remove a * 10m CIPP lining *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074409&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074409 | NL C21 SINGLE ABERDEEN 39.795-42.931. | NL-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 3.136 | KM | 3225200 | Newlands | ABERDEEN | BINBEE | 3.1339 | KM | NL01ML39 | 0.795 | NL01ML42 | 0.931 | KM | 58 | 4578 | 6264 | 3.136 | 39.795 | 42.931 | 2023-06-30 | SINGLE | BOTH |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 11:56:16 AUSQLD Sanjna Rajagopalan (R884639) * Awaiting tech scope still * 12.04.2021 16:20:49 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * * Start: 39.795km End: 42.931km 3.136 track km 4578 sleepers 58 rails Sleepers: Start: 39.800km End: 42.905km 4533 sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044304&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044304 | BW C21 DOWN ALDOGA 550.891-552.405. | BW-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.514 | KM | 1704780 | Blackwater | ALDOGA | ALDOGA | 1.5129 | KM | BW02ML550 | 0.891 | BW02ML552 | 0.405 | KM | 27 | 1709 | 2.916 | 1.514 | 550.891 | 552.405 | 2023-03-31 | DOWN | BOTH |  |  | 3.5 | 4.8 |  |  |  | 16.8 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 25.03.2021 11:49:16 AUSQLD Sanjna Rajagopalan (R884639) * TRACK UPGRADE: * * RE RAIL: * * LEFT RAIL: 550.967 - 552.330 - 12.5 rails * RIGHT RAIL: 551.425 - 552.330 - 8.5 rails * * SLEEPER: * * 551.235 - 552.405 - 1708 sleepers * currently - fist * * restress enture curve of 552.351 POST WALKOUT THE CHANGES ARE AS BELOW: RAIL: RIGHT: 550.880km - 552.330km LEFT: 550.880km - 552.330km 27 RAILS reuse existing 60kg from 551.028 - 551.425km elsewhere SLEEPERS: 551.235 - 552.405 - 1708 sleepers currently - fist Change captured in Sharepoint Change Request - 101 SITE WALKOUT AMENDMENTS: RAILS CUT IN: 550.891km CUT OUT: 552.330 27 rails Sleepers: CUT IN:551.235km CUT OUT: 552.405km 1709 Sleepers Central Station communication by Geoff McMahon on 30/06/2022 ".....Patrick Please find enclosed the approved BMF data for your survey support of TU BW Yarwun - Aldoga 550.880km -552.330km Dn planned for execution on the 27th August 2022 Duane, Terry: As per Rinaldo's earlier communication to you on the 12/04/2022 ".......On top of the scope identified (in yellow) previously. I've highlighted masts in orange (in the MIN SCOPE column). Due to some uncertainty with the staggers values surveyed for the three masts mentioned above. We have used the MMY existing stagger as a reference. Would you be able to check the existing stagger BEFORE construction to ensure what MMY measure is correct. Terry, please ensure this is additional work allocated in the operation steps........" Regards Geoff...."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051873&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000051873 | GA C21 DOWN BOLINGBROKE 67.072-74.798. | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 7.726 | KM | 6672479 | Goonyella | BOLINGBROKE | BALOOK | 7.735 | KM | GA01ML67 | 0.0719 | GA01ML74 | 0.798 | KM | 142 | 10319 | 15.452 | 7.726 | 67.072 | 74.798 | 2023-06-30 | DOWN | BOTH |  |  | 3.5 | 4.6 |  |  |  | 16.1 | 5662 | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240505 | * 18.02.2020 11:15:27 AUSQLD Milton Saha (R884640) * Track Upgrade Goonyella * Bolingbroke - Balook - 67.072 -74.798 (Length = 7.726km) (Down Both) * Average condition = 3.5 * Reason:1983 SC 60kg rail. Large radius/tangent fatigue rail renewal replacement strategy. * 08.09.2020 13:50:16 AUSQLD Milton Saha (R884640) * * This job is being moved to FY23 due to closure restraints i.e. We brought forward the big mindi track upgrade job and therefore this job is being pushed back to FY23. May require review from district engineer * 23.03.2021 11:48:36 AUSQLD Sanjna Rajagopalan (R884639) * Putting in FY23 Q4 - THIS SCOPE CAN BE PUSHED TO FY24 IF WE NEED TO. * 30.03.2021 17:15:04 AUSQLD Sanjna Rajagopalan (R884639) * FULL BALLAST REPLACEMENT IS REQUIRED
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044289&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044289 | BW C21 ENTRY BOORGOON 0.037-0.158. | BW-23ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.121 | KM | 624346 | Blackwater | BOORGOON | BOORGOON | 0.1209 | KM | BW23ML0 | 0.0369 | BW23ML0 | 0.158 | KM | 3 | 177 | 0.24 | 0.121 | 0.037 | 0.158 | 2023-12-31 | ENTRY | BOTH |  |  | 4 | 0.9 |  |  |  | 3.6 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 23:12:19 AUSQLD Sanjna Rajagopalan (R884639) * 1. 0.192 - 2.154 (entry road - after 10AB points till loadout from IM works) - need to ammend tech-scope 10AB to back of TLO - sleeper upgrade * 2. 0.037 - 0.156 (entry road - after 12AB points till 10AB points) - need to ammend SPM to show this, have tech-scope - track updgrade * 3. 4.085 - 4.165 (exit road - to tie in with previous track upgrade) - need to ammend SPM to show this, have tech-scope - track updgrade * 24.03.2021 16:40:02 AUSQLD Sanjna Rajagopalan (R884639) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074690&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074690 | GA C21 DOWN BROADLEA 155.988-158.231. | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.237 | KM | 2553823 | Goonyella | BROADLEA | CARBOROUGH DOWNS JCT | 2.2429 | KM | GA01ML155 | 0.9879 | GA01ML158 | 0.231 | KM | 42 | 3275 | 4.536 | 2.243 | 155.988 | 158.231 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 22.03.2021 12:03:36 AUSQLD Sanjna Rajagopalan (R884639) * Awaiting tech scope * 12.04.2021 16:20:49 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * * Start:155.988km End: 158.231km 42 rails Sleepers: Start:156.611km 3275 sleepers End: 158.225km --------------------------------------- Central Station communication by Geoff McMahon dated 14th April 2022 Patrick Please find enclosed the approved BMF data for your survey support of SRC Coppabella - Broadlea Dn 156.61km - 157.126km TLM planned for execution on the 11th May 2022 David, Jason, Hayley: Please action as per Rinaldo's attached latest OHW adjustment report on 14/04/2022 Regards Geoff --------------------------------
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063285&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063285 | GA C21 DN BROADLEA 163.119-163.833 | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.714 | KM | 985000 | Goonyella | BROADLEA | MALLAWA | 0.7139 | KM | GA01ML163 | 0.1189 | GA01ML163 | 0.8329 | KM | 14 | 1043 | 1.512 | 0.714 | 163.119 | 163.833 | 2023-06-30 | DN | BOTH |  |  | 3 | 2.4 |  |  |  | 7.2 | 38 | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20241230 | * 13.08.2020 14:54:32 AUSQLD Milton Saha (R884640) * 1. FY22 Rail Renewal Brought forward * 2. 163.119 -163.833 km Q4 * 3. DN Road Broadlea to Burton Downs * 4. 14 Rails * 5. Scope to be checked by AC * 22.01.2021 17:32:57 AUSQLD William Robertson (R863808) * Updated Tech Scope dated 16/10/2020 * Changed Start km: 160.200km * Changed End km: 167.843km * Increased No. Rails from 14 to 142 * Moved job to FY23 Moved job to FY23 Scope reduced to 163.119 -163.833 14 rails 1043 sleepers - please see attachment for section breakdown - done to be compeleted manually with formation job 002000052730 Central Station (COM-1105)dated 6th Dec 2021 by Geoff McMahon Patrick, Please find enclosed the approved BMF data for your survey support for TU GA Broadlea - Carborough Downs 163.090km to 163.873km DOWN which has been rescheduled for execution in FY23 I note that this survey was carried in March 2021 and so please carry out checks prior to planned works to ensure rail location has not been been altered Hayley/David As per Rinaldo's communication on the 10th May 2021 "......The minimum work to be done are 4 stagger adjustments back to design. Wayne advised adjustments are available therefore no need for new cantilevers......." Regards Geoff
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074706&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074706 | BW C21 DOWN DUARINGA 105.035-105.467. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.432 | KM | 771915 | Blackwater | DUARINGA | WALLAROO | 0.4319 | KM | BW03ML105 | 0.035 | BW03ML105 | 0.467 | KM | 8 | 592 | 0.864 | 0.432 | 105.035 | 105.467 | 2024-12-31 | DOWN | BOTH |  |  | 3 | 3.4 |  |  |  | 10.2 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20210918 | * 25.03.2021 11:19:42 AUSQLD Sanjna Rajagopalan (R884639) * track upgrade: * * Re rail: * 105.035 - 105.467 - both legs 8 rails total * * Sleepers: * 105.035 - 105.440 - 592 sleepers current are fist clips * 12.04.2021 16:20:58 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074703&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074703 | BW C21 DOWN EDUNGALBA 86.135-86.351. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.216 | KM | 550391 | Blackwater | EDUNGALBA | AROONA | 0.2159 | KM | BW03ML86 | 0.135 | BW03ML86 | 0.3509 | KM | 4 | 66 | 0.432 | 0.216 | 86.135 | 86.351 | 2023-06-30 | DOWN | BOTH |  |  | 3 | 3.4 |  |  |  | 10.2 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20210918 | * 25.03.2021 11:13:14 AUSQLD Sanjna Rajagopalan (R884639) * Track upgrade * * Re Rail: * 86.135 - 86.351 - both legs 4 rails total * * Sleepers: * Exisitng is fist * 86.135 - 86.175 - 66 sleepers * * another re rail scope starts at 86.820 notification 2000070847 * section between 2 scopes is good condition hence 2 x scopes. section between 2 scopes is good condition hence 2 x scopes. Changed latest renewal date from 31/03/2024 to 30/06/2023 --------------------- Central Station communication by Geoff McMahon on 27/05/2022 Patrick Please find enclosed the approved BMF data for your survey support of TU BW Edungalba - Aroona 86.135km - 86.351km Down works planned for execution on the 6th August 2022 Terry <(>&<)> Craig As per Rinaldo's communication on the 17th Jan "......There's no minimum OHW adjustment required for this only height and stagger support. Notification number is 2000074703......" Regards Geoff -------------------
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000062858&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000062858 | BW C21 DOWN EDUNGALBA 82.824-82.957. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.133 | KM | 144757 | Blackwater | EDUNGALBA | EDUNGALBA | 0.133 | KM | BW03ML82 | 0.8239 | BW03ML82 | 0.9569 | KM | 2 | 24 | 0.016 | 0.016 | 82.824 | 82.957 | 2023-06-30 | DOWN | BOTH | [8 empty] | 5121 |  | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 11.08.2020 13:00:49 AUSQLD Milton Saha (R884640) * FY22 TU Brought In 11/08/2020 * * 1. Rail is 1982 SC 60kg - Fatigue Scope * 2. No of Rails = 2 * 3. Edungalba * 4. 82.817 - 82.890km * 23.10.2020 11:41:10 AUSQLD Milton Saha (R884640) * * Updates * * 1. 82.824 -82.954 Left Rail * 2. 82.883 -82.957 Right Rail * 3. 2 Rails Regards Geoff ---------------------------------------------------- 11.08.2020 13:00:49 AUSQLD Milton Saha (R884640) FY22 TU Brought In 11/08/2020 1. Rail is 1982 SC 60kg - Fatigue Scope 2. No of Rails = 2 3. Edungalba 4. 82.817 - 82.890km 23.10.2020 11:41:10 AUSQLD Milton Saha (R884640) Updates 1. 82.824 -82.954 Left Rail 2. 82.883 -82.957 Right Rail 3. 2 Rails 0.133km Moved to FY23 after change board decision
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063013&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063013 | BW C21 DOWN EDUNGALBA 82.987-84.104. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.117 | KM | 1158054 | Blackwater | EDUNGALBA | EDUNGALBA | 1.088 | KM | BW03ML82 | 0.9869 | BW03ML84 | 0.1039 | KM | 21 | 1276 | 2.268 | 1.117 | 82.987 | 84.104 | 2023-06-30 | DOWN | [9 empty] | 80 |  | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 11.08.2020 13:17:19 AUSQLD Milton Saha (R884640) * 1. Fatigue Scope for Track Upgrade * 2. Sleeperare are derailment damaged and concrete fist sleepers * 3. Edungalba DN Road BW-03ML * 4. 83.090- 83.980 km * 5. 16 Rails * 6. 1276 Sleepers * 23.10.2020 11:57:01 AUSQLD Milton Saha (R884640) * * Updates * 1. Left = 82.987 -84.104 * 2. Right = 82.990 -84.098km * * 21 Rails total - from 16 rails - extra 5 rails to be delivered * * Sleeper Extents = 83.090 -83.964km = 874m = 1276 sleepers 1.117km track kms Moved to FY23 after change board decision
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052208&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052208 | MA C21 LOOP GLADSTONE YARD 527.694-529. | NC-08YR | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.563 | KM | 1685516 | Moura | GLADSTONE YARD | LOOP ROADS | 0.506 | KM | NC08YR527 | 0.6939 | NC08YR528 | 0.266 | KM | 29 | 2282 | 3.024 | 1.486 | 527.694 | 529.18 | 2023-06-30 | LOOP | BOTH |  |  | 3.5 | 0.9 |  |  |  | 3.2 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | HIGH |  | LOW | HIGH | Notification completed | RRIG | FY23 IN | 20230630 | * 24.02.2020 08:22:25 AUSQLD Milton Saha (R884640) * o Gladstone Yard Thru and Loop Roads (NC-08YR and NC-01PL): * § Low profile (20T) concrete sleepers to be installed to replace condition 3.5 timber sleepers * § Upgrade from 527.694km to 529.257km * 12.04.2021 16:20:55 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * * Loop Road portion length shown in notification 2000084656 Central station communication on the 20 Jan 2023 from Geoff McMahon Please find enclosed the approved BMF data for your survey support of TU BW Gladstone Yard 527.694 - 529.257km Loop Roads planned for execution on the 28th Jan 2023 Duane, Terry/Cassandra: As per Rinaldo's communication to you on the 26/09/2022 "........Refer to the attachments. There a few OHW modification required as part of this BMF. Note some are the height changes are on half wrap mast bracket. You may have to inspect and provide feedback. There is also turnout nest renewal in the middle of the BMF (highlighted in red cloud on layout N528-528 sheet 1). I've attached the IFC design (external design). Not sure when this will happen and who the PM for this is and the integration between this and the BMF. Please call me to discuss if you have any concern................." 10/01/2024 - Reopened Notification to allow WO to be PCOMd
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084546&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084546 | MA C21 GLADSTONE YARD THRU ROAD 527.69 | NC-01PL | CIVIL | TRACK UPGRADE |  | RENEWAL |  | KM |  | Moura | GLADSTONE YARD THRU ROAD | GLADSTONE YARD LOOP ROAD | 0.914 | KM | NC01PL528 | 0.266 | NC01PL529 | 0.1799 | KM |  |  |  |  | 527.694 | 529.108 | [13 empty] | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | HIGH |  | LOW | HIGH | Notification completed | RRIG | FY23 IN | 20230630 | Connects with 2000052208 - 2 notifications as scope splits across two lines. Cost and qtys only reflected in notification 2000052208 10/01/2024 - Reopened Notification to allow WO to be PCOMd
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074708&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074708 | BW C21 DOWN MIDGEE 627.545-628.733. | BW-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.188 | KM | 1381950 | Blackwater | MIDGEE | ROCKLANDS | 1.191 | KM | BW02ML627 | 0.545 | BW02ML628 | 0.7329 | KM | 22 | 1579 | 2.376 | 1.188 | 627.545 | 628.733 | 2024-06-30 | DOWN | BOTH |  |  | 3 | 4.5 |  |  |  | 13.5 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 25.03.2021 12:01:47 AUSQLD Sanjna Rajagopalan (R884639) * TRACK UPGRADE: * * RE RAIL: * 627.545 - 628.733 - BOTH LEGS - total 22 rails * Cut in at end of FY18 RR at northern end, roll 11 pair South * * Sleepers: * 627.620 - 628.701 * currently fist * 1579 sleepers Latest Renewal Date pushed to FY24 due after field measurements --------------------------------------------------------------- Central Station communication on 31/01/2023 from Geoff McMahon Patrick Please find enclosed the approved BMF data for your survey support of TU BW Midgee - Rocklands 627.545 - 628.733km Down TLM planned for execution on the 27th February 2023 Please advise Mark when works have been completed. Craig, Grant, Terry As per Rinaldo's earlier communication to you on the 3/06/2022 "...................... There is only one stagger mod. The notification is 2000074708...." Please liaise with Nigel and the PM for coordinating the works Regards Geoff ---------------------------------------------------
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074327&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074327 | GA C21 UP WAITARA 100.815-102.558. | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.743 | KM | 1868443 | Goonyella | WAITARA | BRAESIDE | 1.7419 | KM | GA02ML100 | 0.8149 | GA02ML102 | 0.558 | KM | 32 | 2295 | 3.486 | 1.743 | 100.815 | 102.558 | 2023-06-30 | UP | BOTH |  |  | 3 | 4.6 |  |  |  | 13.8 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 19.03.2021 23:53:41 AUSQLD Sanjna Rajagopalan (R884639) * Track Upgrade * 100.815 - 102.558 * GA - 02ML UP * Waitara - Braeside * 32 rails * 2295 sleepers * Q4 FY23 * DO NOT PUSH - MULTIPLE PLUGS AND STRONG RTI DEFECT HISTORY * 20.03.2021 00:04:02 AUSQLD Sanjna Rajagopalan (R884639) * CLASSIFICATIONS NOT COMING UP IN ZPM_NAMS CLASSIFICATIONS NOT COMING UP IN ZPM_NAMS CLASSIFICATIONS NOT COMING UP IN ZPM_NAMS Central Station communication on 23 May 2022 from Geoff McMahon "...Kevin Please find enclosed the approved BMF data for your survey support of TU Waitara - Braeside UP 100.815km - 102.558km works planned for execution on 13th July 2022 David, Hayley, Jason. As per Rinaldo's communication on the 27/02/2022 ".......The BMF above has only one mod. The adjustment can be done by simply removing the rake to zero. The rest will be just post height and stagger. The track notification is 2000074327. Construction is planned for 13th July 2022. Please liase with Aaron Low and track planner asap to ensure the OHW is part of the Operation Steps in the their WO and resourcing allocation. Attached is the OHW adjustment report...." Regards Geoff....."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044281&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044281 | GA C21 DOWN WANDOO 86.17-86.64 | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.47 | KM | 1013249 | Goonyella | WANDOO | WAITARA | 0.4699 | KM | GA01ML86 | 0.169 | GA01ML86 | 0.639 | KM | 9 | 687 | 0.94 | 0.47 | 86.17 | 86.64 | 2023-06-30 | DOWN | BOTH |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 23.03.2021 14:46:52 AUSQLD Sanjna Rajagopalan (R884639) * TRACK UPGRADE * 86.169 - 86.639 * DOWN * Currently 22T Fist * 687 sleepers * ties in with TU from 86.639 - 87.179 * Reason for gap between two is T/O * 12.04.2021 16:20:55 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * * * 19.05.2021 10:56:50 AUSQLD Sanjna Rajagopalan (R884639) * Extents amended after inspection * Rail - 86.121 - 86.610 - ie into FY20 TU starting, Left leg - 86.607km and right leg - 86.610km * * Sleepers - 86.169 - 86.639 - tie in with track upgrade FY20 from 86.639 to 87.179km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044280&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044280 | GA C21 DOWN WANDOO 86.006-86.115. | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.109 | KM | 513355 | Goonyella | WANDOO | WANDOO | 0.1089 | KM | GA01ML86 | 0.006 | GA01ML86 | 0.115 | KM | 2 | 113 | 0.216 | 0.109 | 86.006 | 86.115 | 2023-06-30 | DOWN |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 23.03.2021 14:21:30 AUSQLD Sanjna Rajagopalan (R884639) * Track Upgrade: * 86.02 - 86.100 * DOWN * 2 Rails * 113 Sleepers * FY24 Q4 * Cut out between 8A/B points and 12C/D points - hence Noti. 2000044281 starting at 86.17km * * * 19.05.2021 10:38:45 AUSQLD Sanjna Rajagopalan (R884639) * Extents were amended after inspection - 86.006 - 86.610 tie rail into FY20 TU starting, Left leg - 86.607km and right leg - 86.610km * Tie sleepers in with track upgrade FY20 from 86.639 to 87.179km * 19.05.2021 10:40:00 AUSQLD Sanjna Rajagopalan (R884639) * Ignore previous input * * Extents were amended after inspection 86.006 - 86.115 for Rail - Cut in at 86.115km end, determined by TO welds * * For sleepers - Cut in at 12C/D points. Between 8A/B and 12 C/D For sleepers - Cut in at 12C/D points. Between 8A/B and 12 C/D Dist start and end updates, and estimate updated
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074672&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074672 | BW C21 DOWN WYCARBAH 38.22-39.29. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.07 | KM | 1052346 | Blackwater | WYCARBAH | WESTWOOD | 1.0689 | KM | BW03ML38 | 0.22 | BW03ML39 | 0.2899 | KM | 14 | 1014 | 1.512 | 1.07 | 38.22 | 39.29 | 2022-12-31 | DOWN | BOTH |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20221231 | * 31.03.2021 19:31:34 AUSQLD Tracy Holmes (R870040) * Tech scope attached Tech scope attached Latest Expiry changed from 30.09.2023 to 31.12.2022 Latest exipry bought forward to Q1 30.09.2022 - based off field measurements Scope extended: Rail: 38.220km - 39.124km 17 rails Rail between 38.648km - 38.80km can be recovered to be used as part worn - change captured on #105 Sleepers: 38.598km - 39.120km 763 sleepers POST SITE WALKOUT: RE RAIL 38.220 - 38.648 - 8 rails 38.800 - 39.124 - 6 rails Gap in re rail is due to trail Heavy Duty GIJs located at 38.700 - should be kept in. Sleepers 38.596 - 39.290 - 1014 sleepers Change captured in #135 - please see email attachment for full history Central Station Ccommunication dated 18th Aug 2022 from Geoff McMahon ".....Kevin Please find enclosed the approved BMF data for your survey support of TU BW Wycarbah-Westwood 38.220km – 39.290km Dn TLM works planned for execution on the 17th October 2022. Craig, Grant, Terry: As per Rinaldo's communication on the 22/05/2022 "............The BMF has two OHW adjustments required. Refer to the attachment. ... .............. (Notification 2000074672), Please liaise with Anthony Maskell to coordinate with the Track work........" Regards Geoff .............."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078435&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078435 | BW C21 SINGLE STANWELL BALLOON 2.091-5. | BW-04BL | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.475 | TRACK KM | 1839202 | Blackwater | STANWELL BALLOON | STANWELL BALLOON | 2.475 | KM | BW04BL2 | 0.0909 | BW04BL4 | 0.5649 | KM | 35.5 | 3614 | 3.818 | 2.475 | 2.091 | 4.565 | 2023-06-30 | SINGLE |  |  |  | 3.8 | 1.65 | 1 | 2.1 | 1 | 7.98 | 5629 |  | 2021-10-05 | Track Upgrade | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20240630 | * 08.06.2021 16:37:28 AUSQLD Sanjna Rajagopalan (R884639) * Sleepers Only * 2.091km - 5.078km * Fist Clip * * Start at 2.091km where Fist clip sleepers begin (E Clip sleepers on lower chainage side of 2.091km) * * Turnout ER3.2A at 3.152km (E Clip sleepers between 3.152 and 3.195km) * * Turnout ER3.2B at 3.354km (E Clip sleepers between 3.354 and 3.383km) * * Bridge between 4.655 to 4.800km * * Stop to tie in with Last Long Bearer of Turnout 45A at 5.078km Changed to Track up grade: Rail: 2.091km - 4km - 35.5 rails - part worn rail can be used here updated FYestimate - to TU Reduced scope to stop sleepers before bridge. CRA score update to correctly reflect CRA Stanwell Powerhouse
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074392&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074392 | BW C63 - GIJ Reactive Works | BW | CIVIL | TRACK UPGRADE | GIJ | RENEWAL | 1 | LUMPSUM | 320000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 21.03.2021 08:21:16 AUSQLD William Schuh (R878634) * GIJ FIX ON FAIL BLACKWATER BUDGET * 31.03.2021 19:30:05 AUSQLD Tracy Holmes (R870040) identify locations. * 12.04.2021 16:22:43 AUSQLD Jeremy Stevenson (R867415) * FY22 no FoF Rail Budget - will have budget for FY2 3 as well as GIJ. Review Slab track as scopeitem f * or FY23 - very different unit rate to identify loc ations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074391&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074391 | GA C63 - GIJ Reactive Works | GA | CIVIL | TRACK UPGRADE | GIJ | RENEWAL | 1 | LUMPSUM | 340000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 21.03.2021 08:16:13 AUSQLD William Schuh (R878634) * GIJ FIX ON FAIL BUDGET * 31.03.2021 19:30:14 AUSQLD Tracy Holmes (R870040) identify locations. * 12.04.2021 16:22:42 AUSQLD Jeremy Stevenson (R867415) * FY22 no FoF Rail Budget - will have budget for FY2 3 as well as GIJ. Review Slab track as scopeitem f * or FY23 - very different unit rate to identify loc ations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074394&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074394 | MA C63 - GIJ Reactive Works | MA | CIVIL | TRACK UPGRADE | GIJ | RENEWAL | 1 | LUMPSUM | 40000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 1.3 |  |  |  | 6.5 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 21.03.2021 08:26:46 AUSQLD William Schuh (R878634) * GIJ FIX ON FAIL BUDGET MOURA * 31.03.2021 19:30:19 AUSQLD Tracy Holmes (R870040) identify locations. * 12.04.2021 16:22:43 AUSQLD Jeremy Stevenson (R867415) * FY22 no FoF Rail Budget - will have budget for FY2 3 as well as GIJ. Review Slab track as scopeitem f * or FY23 - very different unit rate to identify loc ations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074395&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074395 | NL C63 - GIJ Reactive Works | NL | CIVIL | TRACK UPGRADE | GIJ | RENEWAL | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 3.2 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 21.03.2021 08:29:41 AUSQLD William Schuh (R878634) * GIJ FIX ON FAIL NEWLANDS BUDGET * 31.03.2021 19:30:21 AUSQLD Tracy Holmes (R870040) identify locations. * 12.04.2021 16:22:44 AUSQLD Jeremy Stevenson (R867415) * FY22 no FoF Rail Budget - will have budget for FY2 3 as well as GIJ. Review Slab track as scopeitem f * or FY23 - very different unit rate to identify loc ations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075262&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075262 | BW Slab Track Reactive Works | BW | CIVIL | TRACK UPGRADE | SLAB TRACK | RENEWAL | 1 | LUMPSUM | 300000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:30:02 AUSQLD Sanjna Rajagopalan (R884639) * lumpsum for Slab Track renewals FY23 Blackwater System Reduced to $300,000
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075263&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075263 | GA Slab Track Reactive Works | GA | CIVIL | TRACK UPGRADE | SLAB TRACK | RENEWAL | 1 | LUMPSUM | 300000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Permanent Way -Other | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 15:33:32 AUSQLD Sanjna Rajagopalan (R884639) * Lumpsum for Slab Track for Goonyella System Reduced to $300,000
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044386&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044386 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 2500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043998&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043998 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GYA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 2750000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044387&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044387 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 500000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044388&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044388 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043305&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043305 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ BL10A. | TO000836 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 900000 | Blackwater | BAJOOL | BL10A | 0.0539 | KM | BW01ML604 | 0.677 | BW01ML604 | 0.677 | KM |  |  |  |  | 604.68 |  | 2021-06-30 |  |  |  |  | 3 | 4 |  |  |  | 12 | 4870 | 2019-07-15 | 2021-10-05 | Turnout Renewals | BESPOKE DESIGN | HIGH |  | HIGH | LOW | Notification completed | RRIG | FY23 IN | 20230808 | * 04.08.2020 16:41:42 AUSQLD Lachlan Prescott (R881571) * MOVED TO FY22 UNDER PCR2515 * 10.05.2021 12:37:12 AUSQLD Lachlan Prescott (R881571) * Moved to FY23 pending PCR4870 17.08.2021 11:08:05 AUSQLD K Alex Rohweder (R872340) PCR 4870 Approved. Move construction to FY23 05.10.2021 11:45:05 AUSQLD K Alex Rohweder (R872340) Capture more accurate cost per FY. Allocate $900,000.00 for FY23 (including materials. Allocate $482,000.00 in FY22 and $575,000.00 in FY21.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043307&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043307 | TURNOUTS ¦ CONSTRUCT - STG ¦ CH251A. | TO001147 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 2748000 | Blackwater | CALLEMONDAH | CH251A | 0.0539 | KM | BW13YR535 | 0.914 | BW13YR535 | 0.914 | KM |  |  |  |  | 535.91 |  | 2023-06-30 |  |  |  |  | 4 | 3.5 |  |  |  | 14 | 4745 | 2021-03-31 | 2021-10-05 | Turnout Renewals | BESPOKE DESIGN | HIGH |  | MEDIUM | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 27.02.2020 17:02:15 AUSQLD Lachlan Prescott (R881571) * Costs indicative only. This scope is remainder of 250/251 works not completed in FY21. Estimated total cost was $5,213,532, with app = roximately $1,500,000 expected to be spent in FY21 as preparation works for FY22. The remainder (approximately $3.8m) has been allocated to FY22. * 14.10.2020 16:02:11 AUSQLD Lachlan Prescott (R881571) * * some work deferred due to design staging and closure requirements. Remaining works will be completed as Stage Two. Stage Three to be raised as new N4 for FY23 * 26.02.2021 13:01:29 AUSQLD Lachlan Prescott (R881571) * * FY22 work moved to FY23, estimated cost pushed to FY23, therefore FY23 cost increased to $3.8m * 23.03.2021 11:58:23 AUSQLD Lachlan Prescott (R881571) * * FY23 unlikely to spend allocated $3.8m. Reduced to $2.5m, $1.3m deferred to FY24. FY24 increase accordingly. 23.08.2021 09:12:00 AUSQLD Alex Rohweder (R872340) Required End Date adjusted to 30.06.2023. * Approver should be Alex Rohweder
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073335&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000073335 | TURNOUTS ¦ CONSTRUCT ¦ UPGRADE ¦ KI7A | TO001089 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1025000 | Newlands | KAILI | KI7A | 0.034 | KM | NC03ML1165 | 0.8479 | NC03ML1165 | 0.8139 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 3.2 |  |  |  | 11.2 |  | 2021-03-31 | 2021-10-05 | Turnout Renewals | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN NON MRSB | 20260329 | * 01.03.2021 10:11:47 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 19.03.2021 11:59:00 AUSQLD Lachlan Prescott (R881571) * Cost of $795,500 includes FY22 estimated design cost of 63,640, to be stripped out later under a PCR * 19.03.2021 12:21:41 AUSQLD Lachlan Prescott (R881571) * Cost updated to 635,000 based on PM feedback 03/11/2021 Alex Rohweder (R872340) Defer the Construction Scope to FY23 with intention to improve project execution confidence. Non-Coal asset under scrutny of funding through RIG. Decision pending as per 3 November 2021.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063619&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063619 | TURNOUTS ¦ DESIGN ¦ IFC ¦ GE 293BC | TO000865 | CIVIL | TURNOUTS | DESIGN | DESIGN | 1 | TURNOUT | 107880 | Blackwater | CALLEMONDAH | 293BC | 0 | KM | BW01ML536 | 0.328 | BW01ML536 | 0.328 | KM | [6 empty] | 2023-08-11 |  |  | POINTS & X 60KG/M 16 CS SNX TG | OPTION 4 | 4 | 3.5 | 4 |  |  | 15.4 |  |  | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20240630 | * 29.10.2020 09:07:11 AUSQLD Lachlan Prescott (R881571) * UPDATED TO FY22. UNSURE WHY SHOWING AS FY21. * 10.05.2021 11:00:23 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5667 notification/s due date revised to 11th August 2023 Why: design resourcing. Design teams have committed to the below revised dates. OHLE Design IFC: 23rd June 2023 Signalling Design IFC: 28th July 2023
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063618&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063618 | TURNOUTS ¦ DESIGN ¦ IFC ¦ GE 293A | TO001150 | CIVIL | TURNOUTS | DESIGN | DESIGN | 1 | TURNOUT | 118680 | Blackwater | CALLEMONDAH | GE293A | 0 | KM | BW13YR536 | 0.234 | BW13YR536 | 0.234 | KM | [6 empty] | 2023-08-11 |  |  | POINTS & X 60KG/M 12 CS SNX TG | OPTION 4 | 4 | 3.5 | 4 |  |  | 15.4 |  |  | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20240630 | * 24.08.2020 09:44:43 AUSQLD Lachlan Prescott (R881571) * Design only * 10.05.2021 10:57:46 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5667 notification/s due date revised to 11th August 2023 Why: design resourcing. Design teams have committed to the below revised dates. OHLE Design IFC: 23rd June 2023 Signalling Design IFC: 28th July 2023
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065599&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065599 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 259A | TO001127 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 48820 | Blackwater | CALLEMONDAH | CH 259A | 0 | KM | BW07YR536 | 0.057 | BW07YR536 | 0.057 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 2 | 4.8 |  |  |  | 13.2 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.09.2020 07:09:06 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044001 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065598&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065598 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 260A | TO001136 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 49160 | Blackwater | CALLEMONDAH | CH 260A | 0 | KM | BW10YR536 | 0.101 | BW10YR536 | 0.101 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4.8 |  |  |  | 15.4 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 30.09.2020 07:08:45 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044000 be completed in FY24 30.09.2020 07:08:45 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044000 12/05/2022 Alex Rohweder (R872340) Asset condition and criticality reviewed. To best manage the asset reliability and interlocking renewal collaboration, defer DESIGN to FY28 and to have it constructed in FY30. Turnout asset can be sufficiently maintained via C16 and C10, confirmed with Terry Callaghan local track inspector. Monitor Through Road Rail condition in FY28, and if required, plan rail renewal in conjunction with turnout renewal in FY30 (with Rail asset management team).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052847&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052847 | TURNOUTS ¦ DESIGN ¦ IFP ¦ EC12A | TO000139 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 12100 | Newlands | EAGLEFIELD CK | EC12A | 0.069 | KM | NL01ML201 | 0.909 | NL01ML201 | 0.909 | KM | [6 empty] | 2023-06-30 |  |  | POINTS & X 60KG/M 12 CS SNX EO | OPTION 3 | 3.5 | 2 | 4 |  |  | 12.25 | 4882 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 13:41:53 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX * 10.05.2021 11:05:34 AUSQLD Lachlan Prescott (R881571) * To be moved to FY25 pending PCR4882 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052846&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052846 | TURNOUTS ¦ DESIGN ¦ IFP ¦ EC7A | TO000141 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 12100 | Newlands | EAGLEFIELD CK | EC7A | 0.069 | KM | NL01ML204 | 0.111 | NL01ML204 | 0.111 | KM | [6 empty] | 2022-06-30 |  |  | POINTS & X 60KG/M 12 CS SNX EO |  | 3.5 | 2 | 4 |  |  | 12.25 | 4882 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 13:41:40 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX * 10.05.2021 11:05:35 AUSQLD Lachlan Prescott (R881571) * To be moved to FY25 pending PCR4882 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052840&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052840 | TURNOUTS ¦ DESIGN ¦ IFP ¦ MMER1.3 | TO000879 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 17940 | Blackwater | MT MILLER | MM ER1.3A | 0.024 | KM | BW20ML0 | 0.451 | BW20ML0 | 0.4269 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 1 |  |  |  | 13 | 5289 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 13:40:03 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX * 10.05.2021 11:03:09 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 ALEX ROHWEDER (R872340) SWAP THE DESIGN SCOPE WITH MT. MILLER ER1.2A TO DESIGN IN FY23, AND TO CONSTRUCT IN FY25. REASON: ASSET CRITICALITY. PCR 5289 APPROVED. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052841&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000052841 | TURNOUTS ¦ DESIGN ¦ IFP ¦ MMER2.3B | TO000861 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 119000 | Blackwater | MT MILLER | MM ER2.3B | 0.035 | KM | BW01ML541 | 0.635 | BW01ML541 | 0.67 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.8 |  |  |  | 16.4 | 5289 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630 | * 28.02.2020 13:40:16 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution * 10.05.2021 11:03:10 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 28.02.2020 13:40:16 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution 10.05.2021 11:03:10 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 ALEX ROHWEDER (R872340) SWAP THE DESIGN SCOPE WITH MT. MILLER ER2.3B TO DESIGN IN FY23, AND TO CONSTRUCT IN FY25. REASON: ASSET CRITICALITY. PCR 5289 APPROVED.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065596&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065596 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WA 7AB | TO000317 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 31880 | Goonyella | WAITARA | WA 7AB | 0 | KM | GA02ML98 | 0.0369 | GA02ML98 | 0.0369 | KM | [6 empty] | 2023-12-01 |  |  |  |  | 3 | 4.4 | 5 |  |  | 14.4 | 5668 | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20231201 | * 30.09.2020 07:07:41 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043323 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy) 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5668 Recommended change from PM notification/s due dates revised to • IFP due 1st December 2023 (FY24) • IFC due 31st July 2024 (FY25 Q1) Reason: : priority is Design team produce all IFCs for TO construction in FY24 (these are WIP) Note: WA 7AB <(>&<)> WA9A construction remains unchanged being FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065597&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065597 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WA 9A | TO000368 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 83700 | Goonyella | WAITARA | WA 9A | 0 | KM | GA02PL98 | 0.168 | GA02PL98 | 0.168 | KM | [6 empty] | 2023-12-01 |  |  |  |  | 3 | 5 | 4 |  |  | 14.4 | 5668 | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20231201 | * 30.09.2020 07:08:20 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043324 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5668 Recommended change from PM notification/s due dates revised to • IFP due 1st December 2023 (FY24) • IFC due 31st July 2024 (FY25 Q1) Reason: : priority is Design team produce all IFCs for TO construction in FY24 (these are WIP) Note: WA 7AB <(>&<)> WA9A construction remains unchanged being FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044389&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044389 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 250000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 | 5650 | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043999&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043999 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ GYA | GA | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 250000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044390&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044390 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 50000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044391&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044391 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 50000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Turnout Components | LIKE FOR LIKE |  |  |  |  | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075288&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075288 | BLACK MOUNTAIN GMS RENEWAL | ST007230-01 | CONTROL SYSTEMS | ASSET PROTECTION | GMS | RENEWAL | 1 | SYSTEM | 105000 | Goonyella | BLACK MOUNTAIN |  | 0 | KM | GA01ML37 | 0.556 | GA01ML37 | 0.556 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 19:57:53 AUSQLD Scott Andrews (R003573) * BLACK MOUNTAIN GMS RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094332&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094332 | MA HBD DESIGN BELLDEEN MA160 | ST005270-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 30000 | Moura |  |  | 0 | KM | MA01ML160 | 0 | MA01ML160 | 0 | KM | [6 empty] | 2024-06-30 | [9 empty] | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | REJC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094635&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094635 | BW HBD DESIGN DUARINGA CL110 | ST005230-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 30000 | Blackwater | DUARINGA |  | 0 | KM | BW03ML110 | 0.069 | BW03ML110 | 0.069 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094637&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094637 | BW HBD DESIGN MARMOR NC598 | ST005250-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 30000 | Blackwater | MARMOR |  | 0 | KM | BW01ML597 | 0.752 | BW01ML597 | 0.752 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094636&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094636 | BW HBD DESIGN UMOLO-PARNABAL CL152 | ST002240-02 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 30000 | Blackwater | UMOLO | PARNABAL | 0 | KM | BW03ML152 | 0.171 | BW03ML152 | 0.171 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084242&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084242 | MA160 HBD BELLDEEN-MOURA MINE | ST005270-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 560000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML160 | 0 | MA01ML160 | 0 | KM |  |  |  |  | 160 | 160 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075324&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075324 | CL173 BLUFF RENEWAL HBD | ST005220-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 560000 | Blackwater | BLUFF |  | 0 | KM | BW03ML173 | 0.2849 | BW03ML173 | 0.2849 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240204 | * 31.03.2021 08:35:30 AUSQLD Scott Andrews (R003573) * RENEW DUAL TRACK HBD AT BLUFF CL173
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081497&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000081497 | HBD/HWD Mt Rainbow | ST003760-08 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 560000 | Moura | MOUNT RAINBOW | MOUNT RAINBOW | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2021-12-04 | [7 empty] | 25 |  | 25 |  |  | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093786&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093786 | BW HBD RENEWAL RED ROCK GG042 | ST005200-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 560000 | Blackwater | RED ROCK | RED ROCK | 0 | KM | BW08ML42 | 0.2429 | BW08ML42 | 0.2429 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 | 5457 |  |  | Safe Working Systems - Asset Protection |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230701
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075326&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075326 | BW IAMPS SYSTEM CONTRIBUTION | BW | CONTROL SYSTEMS | ASSET PROTECTION | IAMPS | RENEWAL | 1 | SYSTEM | 42000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240530 | * 31.03.2021 08:53:14 AUSQLD Scott Andrews (R003573) * BW SYSTEM CONTRIBUTION IAMPS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075291&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075291 | GA IAMPS SYSTEM CONTRIBUTION | GA | CONTROL SYSTEMS | ASSET PROTECTION | IAMPS | RENEWAL | 1 | SYSTEM | 42000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240530 | * 30.03.2021 20:10:58 AUSQLD Scott Andrews (R003573) * GA SYSTEM CONTRIBUTION IAMPS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075362&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075362 | NL IAMPS SYSTEM CONTRIBUTION | NL | CONTROL SYSTEMS | ASSET PROTECTION | IAMPS | RENEWAL | 1 | SYSTEM | 10500 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240530 | * 31.03.2021 12:36:02 AUSQLD Scott Andrews (R003573) * NL SYSTEM CONTRIBUTION IAMPS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075287&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075287 | MA SYSTEM IAMPS CONTRIBUTION | MA | CONTROL SYSTEMS | ASSET PROTECTION | IAMPS | RENEWAL | 1 | SYSTEM | 10500 | Moura | BYELLE | CALLIDE MINE | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240530 | * 30.03.2021 19:51:48 AUSQLD Scott Andrews (R003573) * MA SYSTEM IAMPS CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075320&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075320 | LCPS (LX PROT SYS) RENEWAL ADURAD RD BW | LX000661-01 | CONTROL SYSTEMS | ASSET PROTECTION | LX PROTECTION SYSTEM | RENEWAL | 1 | SITE | 231000 | Blackwater | ADURAD ROAD |  | 0 | KM | BW03ML189 | 0.6179 | BW03ML189 | 0.6179 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20231001 | * 31.03.2021 08:03:00 AUSQLD Scott Andrews (R003573) * RENEWAL OF LCPS (LEVEL CROSSING PROTECTION SYSTEM) AT ADURAD RD BLACKWATER
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075321&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075321 | DINGO RENEWAL LCPS LX PROT SYSTEM | LX000746-01 | CONTROL SYSTEMS | ASSET PROTECTION | LX PROTECTION SYSTEM | RENEWAL | 1 | SITE | 231000 | Blackwater | DINGO |  | 0 | KM | BW03ML141 | 0.26 | BW03ML141 | 0.26 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 31.03.2021 08:09:39 AUSQLD Scott Andrews (R003573) * RENEWAL OF LCPS (LEVEL CROSSING PROTECTION SYSTEM) AT FITZROY DEVELOPMENT ROAD AT DINGO. LEVEL CROSSING IS ALSO KNOWN AS NORMANBY ST = REET.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094632&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094632 | MA WEIGHBRIDGE DESIGN BOUNDARY HILL | ST007810-07 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 30000 | Moura | BOUNDARY HILL |  | 0 | KM | MA03ML2 | 0.7299 | MA03ML2 | 0.7299 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094634&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094634 | MA WEIGHBRIDGE DESIGN CALLIDE | ST003490-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 30000 | Moura | CALLIDE |  | 0 | KM | MA07ML14 | 0.0529 | MA07ML14 | 0.0529 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094599&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094599 | NL WEIGHBRIDGE DESIGN MCNAUGHTON | ST002865-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 30000 | Newlands | MCNAUGHTON |  | 0 | KM | NL04ML84 | 0.28 | NL04ML84 | 0.28 | KM | [6 empty] | 2023-06-30 | [9 empty] | 4 | 5434 |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094633&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000094633 | GA WEIGHBRIDGE DESIGN ISAAC PLAINS | ST007180-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | UNIT | 30000 | Goonyella | ISAAC PLAINS |  | 0 | KM | GA11ML4 | 0.256 | GA11ML4 | 0.256 | KM | [6 empty] | 2023-06-30 | [9 empty] | 16 |  |  |  | Safe Working Systems - Minor |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075289&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075289 | WEIGHER RENEWAL CARBOROUGH DOWNS | ST007190-02 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 800000 | Goonyella | CARBOROUGH DOWNS |  | 0 | KM | GA09ML4 | 0.227 | GA09ML4 | 0.227 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | HIGH | Notification completed | RRIG INIF | FY23 IN | 20231230 | * 30.03.2021 20:02:57 AUSQLD Scott Andrews (R003573) * WEIGHER RENEWAL CARBOROUGH DOWNS 4/07/2022 Central Station communication Geoff McMahon "...Alex Further to my email to you on the 30th June the alignment for the enclosed survey data for Carborough Downs Weighbridge -3.95km to 4.55km has been approved for your commissioning on 17th to 19th August. Chris , David, <(>&<)> Hayley As per Rinaldo's communication to you on the 3rd July "..........the BMF requires 5 stagger adjustments. Three of the require mast rake adjustments only. The noti is 2000075289. The commissioning date for Carborough Downs Weighbridge CZ4 is currently planned for the 17th August 2022......." Regards Geoff...."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075307&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075307 | WEIGHER RENEWAL ENSHAM | ST003040-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 800000 | Blackwater | ENSHAM |  | 0 | KM | BW11ML13 | 0.0449 | BW11ML13 | 0.0449 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 09:38:16 AUSQLD Scott Andrews (R003573) * WEIGHER RENEWAL ENSHAM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075340&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075340 | WEIGHBRIDGE RENEWAL GORDONSTONE | ST003130-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 800000 | Blackwater | GORDONSTONE |  | 0 | KM | BW10ML13 | 0.812 | BW10ML13 | 0.812 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 10:34:09 AUSQLD Scott Andrews (R003573) * RENEW WEIGHBRIDGE AT GORDONSTONE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075290&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075290 | WEIGHER RENEWAL LAKE VERMONT | ST007610-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 800000 | Goonyella | LAKE VERMONT |  | 0 | KM | GA19ML16 | 0.233 | GA19ML16 | 0.233 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 20:07:01 AUSQLD Scott Andrews (R003573) * WEIGHER RENEWAL LAKE VERMONT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075341&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075341 | WEIGHBRIDGE RENEWAL ROLLESTON MINE | ST007070-04 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 800000 | Blackwater | ROLLESTON MINE |  | 0 | KM | BW06ML106 | 0.8199 | BW06ML106 | 0.8199 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230726 | * 31.03.2021 10:39:49 AUSQLD Scott Andrews (R003573) * RENEW WEIGHBRIDGE AT KINROLA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044598&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044598 | Weigh Bridge Renewal Millenium TLO | ST007060-02 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | UNIT | 800000 | Goonyella | MILLENIUM |  | 0 | KM | GA16ML4 | 0.3519 | GA16ML4 | 0.3519 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230531 | * 29.03.2021 18:23:38 AUSQLD Scott Andrews (R003573) * RENEW WEIGHBRIDGE MILLENIUM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075213&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075213 | BW CAPACITY SUPPORT FIX ON FAIL | BW | CONTROL SYSTEMS | CAPACITY SUPPORT | FIX ON FAIL | REACTIVE WORKS | 1 | SYSTEM | 400000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Other Control Sys Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 19:50:29 AUSQLD Scott Andrews (R003573) * BW CAPACITY SUPPORT FIX ON FAIL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075212&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075212 | GA CAPACITY SUPPORT FIX ON FAIL | GA | CONTROL SYSTEMS | CAPACITY SUPPORT | FIX ON FAIL | REACTIVE WORKS | 1 | SYSTEM | 310000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Other Control Sys Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 19:45:20 AUSQLD Scott Andrews (R003573) * GA CAPACITY SUPPORT FIX ON FAIL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075214&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075214 | NL CAPACITY SUPPORT FIX ON FAIL | NL | CONTROL SYSTEMS | CAPACITY SUPPORT | FIX ON FAIL | REACTIVE WORKS | 1 | SYSTEM | 200000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Other Control Sys Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 19:54:30 AUSQLD Scott Andrews (R003573) * NL CAPACITY SUPPORT FIX ON FAIL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075211&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075211 | MA CAPACITY SUPPORT FX ON FAIL | MA | CONTROL SYSTEMS | CAPACITY SUPPORT | FIX ON FAIL | REACTIVE WORKS | 1 | SYSTEM | 200000 | Moura | BYELLE | CALLIDE MINE | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  | 2021-03-31 | 2021-10-05 | Other Control Sys Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 19:37:39 AUSQLD Scott Andrews (R003573) * CAPACITY SUPPORT FIX ON FAIL MA SYSTEM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046829&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046829 | CSI CER Renewal | ST005760-18 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 357000 | Newlands | KAILI CER | KAILI | 0 | KM | NC03ML1165 | 0.881 | NC03ML1165 | 0.881 | KM | [6 empty] | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 28.03.2021 16:58:05 AUSQLD Scott Andrews (R003573) * Renew CER at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078706&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078706 | CSI Dehydrator Renewal | ST005600-29 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27000 | Moura | BANANA RANGE | BANANA RANGE | 0 | KM | MA13CR0 | 0 | MA13CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 | 5688 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240530 | * 10.06.2021 18:20:05 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078703&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078703 | CSI Dehydrator Renewal | ST006380-25 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27000 | Goonyella | BLAIR ATHOL |  | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 18:19:04 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078701&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078701 | CSI Dehydrator Renewal | ST006250-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27000 | Newlands | BOVEY'S LOOKOUT |  | 0 | KM | NL08CR0 | 0 | NL08CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230531 | * 10.06.2021 17:33:55 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078705&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078705 | CSI Dehydrator Renewal | ST006270-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27000 | Blackwater | TABLE MOUNTAIN |  | 0 | KM | BW63CR0 | 0 | BW63CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 | 5688 |  | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240530 | * 10.06.2021 18:19:44 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078704&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078704 | CSI Dehydrator Renewal | ST006010-24 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27000 | Goonyella | TIERAWOOMBA |  | 0 | KM | GA45CR0 | 0 | GA45CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230531 | * 10.06.2021 18:19:24 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075298&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075298 | CSI Generator Renewal | ST006380-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 110000 | Goonyella | BLAIR ATHOL MWR |  | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5686 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230712 | * 31.03.2021 06:42:22 AUSQLD Scott Andrews (R003573) * RENEWAL OF BLAIR ATHOL TELECOMMUNICATIONS GENERATOR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078693&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078693 | CSI Generator Renewal | ST005730-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 110000 | Newlands | COLLINSVILLE |  | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 | 5686 |  | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification in process | RRIG | FY23 IN | 20230717 | * 10.06.2021 17:24:16 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085403&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000085403 | CSI Generator Renewal | ST005540-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 120000 | Blackwater | GOGANGO | GOGANGO | 0 | KM | BW03ML77 | 0 | BW03ML77 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Notification completed | SCPR |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078592&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078592 | CSI OF Renewal | ST005830-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 9140 | METERS | 800000 | Goonyella | BALOOK AT TO WANDOO SER |  | 9.1359 | KM | GA01ML76 | 0.78 | GA01ML85 | 0.92 | KM |  |  |  |  | 76.78 | 85.92 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:17:59 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078591&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078591 | CSI OF Renewal | ST003880-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5530 | METERS | 480000 | Goonyella | BALOOK SER TO BALOOK AT |  | 2.1169 | KM | GA01ML74 | 0.65 | GA01ML76 | 0.78 | KM |  |  |  |  | 71.248 | 76.78 | 2024-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:17:30 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078590&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078590 | CSI OF Renewal | ST001330-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5320 | METERS | 480000 | Goonyella | BOLINGBROKE ATW TO BALOOK TSC |  | 5.3289 | KM | GA01ML65 | 0.93 | GA01ML71 | 0.2479 | KM |  |  |  |  | 65.93 | 71.248 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:17:01 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078577&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078577 | CSI OF Renewal | ST000690-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5720 | METERS | 480000 | Goonyella | BOLINGBROKE FSS TO B'BROKE SER |  | 5.7789 | KM | GA01ML54 | 0.8699 | GA01ML60 | 0.6199 | KM |  |  |  |  | 54.9 | 60.62 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:08:46 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078489&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078489 | CSI OF Renewal | ST003940-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5310 | METERS | 480000 | Goonyella | BOLINGBROKE SER TO B'BROKE ATW |  | 5.3079 | KM | GA01ML60 | 0.6199 | GA01ML65 | 0.93 | KM |  |  |  |  | 60.62 | 65.93 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:11:15 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078601&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078601 | CSI OF Renewal | ST008920-08 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3400 | METERS | 280000 | Goonyella | BRAESIDE MIE TO BRAESIDE SER |  | 0 | KM | GA01ML104 | 0.2999 | GA01ML104 | 0.2999 | KM |  |  |  |  | 104.3 | 107.7 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 14:22:06 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078600&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078600 | CSI OF Renewal | ST001230-38 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1100 | METERS | 120000 | Goonyella | BRAESIDE TSC TO BRAESIDE MIE |  | 1.1 | KM | GA01ML103 | 0.2 | GA01ML104 | 0.2999 | KM |  |  |  |  | 103.2 | 104.3 | 2024-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 14:21:26 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046871&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046871 | CSI OF Renewal | ST004540-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3310 | METERS | 320000 | Goonyella | BRA-SER TO MII-ATE OF CABLE |  | 3.31 | KM | GA01ML107 | 0.6999 | GA01ML111 | -0.017 | KM |  |  |  |  | 107.7 | 111.01 | 2023-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 | 5617 | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230730
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078606&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078606 | CSI OF Renewal | ST000040-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 8041 | METERS | 640000 | Blackwater | DINGO TSC TO DINGO CER |  | 8.031 | KM | BW03ML133 | 0.3099 | BW03ML141 | 0.2999 | KM |  |  |  |  | 133.285 | 141.326 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20231122 | * 10.06.2021 14:24:35 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046831&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | NON-COAL | 002000046831 | CSI OF Renewal | ST005630-08 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2800 | METERS | 224000 | Moura | GLT-CER TO SGT-CER OF CABLE | GLT-CER TO SGT-CER OF CABLE | 2.6699 | KM | NC02ML529 | 0.13 | NC02ML526 | 0.46 | KM |  |  |  |  | 529.13 | 526.46 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG INIF | FY23 IN | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078580&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078580 | CSI OF Renewal | ST003980-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5150 | METERS | 480000 | Goonyella | HATFIELD SER - BOLINGBROKE FSS |  | 5.112 | KM | GA01ML49 | 0.752 | GA01ML54 | 0.9 | KM |  |  |  |  | 49.75 | 54.9 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20231218 | * 10.06.2021 14:00:16 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046841&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046841 | CSI OF Renewal | ST004780-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3015 | METERS | 440000 | Goonyella | MACARTHUR JUNCTION SER | COPPABELLA SER2 | 5.5469 | KM | GA01ML137 | 0.253 | GA01ML142 | 0.751 | KM |  |  |  |  | 137.203 | 140.218 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 08:39:07 AUSQLD Scott Andrews (R003573) * Renewal of Optical Fibre cable at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046789&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046789 | CSI OF Renewal | ST006740-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5100 | METERS | 400000 | Goonyella | MII-ATE TO MII-FSS OF CABLE |  | 5.0999 | KM | GA01ML111 | 0.0729 | GA01ML116 | 0.2 | KM |  |  |  |  | 111.1 | 116.2 | 2023-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046950&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046950 | CSI OF Renewal | ST001410-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4550 | METERS | 360000 | Goonyella | MII-ATW TO SWJ-SER OF CABLE |  | 4.5499 | KM | GA01ML123 | 0.0299 | GA01ML127 | 0.5799 | KM |  |  |  |  | 123.03 | 127.58 | 2023-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046788&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046788 | CSI OF Renewal | ST007310-53 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4250 | METERS | 360000 | Goonyella | MII-FSS TO MII-SER OF CABLE |  | 4.25 | KM | GA01ML116 | 0.2 | GA01ML120 | 0.462 | KM |  |  |  |  | 116.2 | 120.45 | 2023-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046787&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046787 | CSI OF Renewal | ST004820-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2580 | METERS | 240000 | Goonyella | MII-SER TO MII-ATW OF CABLE |  | 2.58 | KM | GA01ML120 | 0.462 | GA01ML123 | 0.0299 | KM |  |  |  |  | 120.45 | 123.03 | 2023-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046897&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046897 | CSI OF Renewal | ST000680-49 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5172 | METERS | 400000 | Goonyella | ONE-FSS TO JIL-SR3 OF CABLE | ONE-FSS TO JIL-SR3 OF CABLE | 0.444 | KM | GA01ML23 | 0.631 | GA01ML23 | 0.1869 | KM |  |  |  |  | 23.628 | 28.8 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046896&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046896 | CSI OF Renewal | ST005820-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 9003 | METERS | 720000 | Goonyella | PRAGUELANDS SER - OONOOIE FSS | OONOOIE FSS | 6.112 | KM | GA02YR20 | 20.6009 | GA02YR17 | 17.39 | KM |  |  |  |  | 28.8 | 23.628 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG INIF | FY23 IN | 20240630 | * 29.03.2021 08:33:58 AUSQLD Scott Andrews (R003573) * Renew Optical Fibre at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046895&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046895 | CSI OF Renewal | ST004030-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4875 | METERS | 400000 | Goonyella | PRAGUELANDS SER -GRASSTREE BEA |  | 5.024 | KM | GA01ML14 | 0.6149 | GA01ML9 | 0.5999 | KM |  |  |  |  | 14.625 | 9.75 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 28.03.2021 16:50:22 AUSQLD Scott Andrews (R003573) * Renew OF at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079375&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079375 | CSI OF Renewal | ST006670-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 840 | METERS | 80000 | Goonyella | SWJ-CER TO SWJ-TSC O/FBR CABLE |  | 0.8279 | KM | GA01ML127 | 0.4799 | GA01ML128 | 0.32 | KM |  |  |  |  | 127.48 | 128.32 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079376&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000079376 | CSI OF Renewal | ST006670-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5259 | METERS | 440000 | Goonyella | SWJ-CER TO TOT-SER O/FBR CABLE |  | 5.4189 | KM | GA01ML127 | 0.4799 | GA01ML132 | 0.89 | KM |  |  |  |  | 127.48 | 132.739 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046842&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046842 | CSI OF Renewal | ST008550-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1698 | METERS | 160000 | Goonyella | TOT-AT0 TO MCJ-SER OF CABLE | TOT-AT0 TO MCJ-SER OF CABLE | 1.7079 | KM | GA01ML135 | 0.515 | GA01ML137 | 0.27 | KM |  |  |  |  | 135.505 | 137.203 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046843&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046843 | CSI OF Renewal | ST006660-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2766 | METERS | 320000 | Goonyella | TOT-SER TO TOT-AT0 OF CABLE | TOT-SER TO TOT-AT0 OF CABLE | 3.494 | KM | GA01ML132 | 0.766 | GA01ML136 | 0.257 | KM |  |  |  |  | 132.739 | 135.505 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078603&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078603 | CSI OF Renewal | ST001950-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2705 | METERS | 200000 | Blackwater | TRYPHINIA ATE TO TRYPHINIA CER |  | 2.6859 | KM | BW03ML125 | 0.7139 | BW03ML128 | 0.4 | KM |  |  |  |  | 125.714 | 128.419 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 14:22:54 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078604&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078604 | CSI OF Renewal | ST006360-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4866 | METERS | 400000 | Blackwater | TRYPHINIA CER TO DINGO TSC |  | 4.868 | KM | BW03ML128 | 0.4189 | BW03ML133 | 0.3099 | KM |  |  |  |  | 128.419 | 133.285 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 14:23:44 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078597&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078597 | CSI OF Renewal | ST005800-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3200 | METERS | 280000 | Goonyella | WAITARA AT EAST TO WAITARA MI |  | 3.213 | KM | GA01ML94 | 0.9599 | GA01ML98 | 0.16 | KM |  |  |  |  | 94.96 | 98.16 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:19:55 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078599&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078599 | CSI OF Renewal | ST005790-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2750 | METERS | 240000 | Goonyella | WAITARA MWR TO BRAESIDE TSC |  | 2.7509 | KM | GA01ML100 | 0.45 | GA01ML103 | 0.2 | KM |  |  |  |  | 100.45 | 103.2 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 14:20:54 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078598&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078598 | CSI OF Renewal | ST001640-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2290 | METERS | 200000 | Goonyella | WAITRARA MI TO WAITARA MWR |  | 2.273 | KM | GA01ML98 | 0.16 | GA01ML100 | 0.45 | KM |  |  |  |  | 98.16 | 100.45 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:20:26 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074762&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074762 | CSI OF Renewal | ST008020-53 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5891 | METERS | 680000 | Blackwater | WALLAROO TSC | WALLAROO TRP-ATE | 8.4309 | KM | BW03ML118 | 0 | BW03ML126 | 0.4 | KM |  |  |  |  | 119.823 | 125.714 | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 23.03.2021 07:28:09 AUSQLD Scott Andrews (R003573) * Renew Optical Fibre pertaining to the Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078594&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078594 | CSI OF Renewal | ST000700-46 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4780 | METERS | 400000 | Goonyella | WANDOO FSS TO WANDOO WSS |  | 4.79 | KM | GA01ML87 | 0.219 | GA01ML92 | 0 | KM |  |  |  |  | 87.219 | 92 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:18:56 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078593&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078593 | CSI OF Renewal | ST004050-08 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1380 | METERS | 160000 | Goonyella | WANDOO SER TO WANDOO FSS |  | 1.383 | KM | GA01ML85 | 0.92 | GA01ML87 | 0.2999 | KM |  |  |  |  | 85.92 | 87.3 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:18:27 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078595&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078595 | CSI OF Renewal | ST009410-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2960 | METERS | 240000 | Goonyella | WANDOO WSS TO WAITARA AT EAST |  | 2.9519 | KM | GA01ML92 | 0 | GA01ML94 | 0.9599 | KM |  |  |  |  | 92 | 94.96 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230811 | * 10.06.2021 14:19:26 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078509&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078509 | CSI OF Renewal | ST005770-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1523 | METERS | 240000 | Goonyella | YUKAN AT TO BLACK MOUNTAIN TSC |  | 2.0139 | KM | GA01ML33 | 0.9899 | GA01ML36 | 0 | KM |  |  |  |  | 33.99 | 35.513 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20231218 | * 10.06.2021 13:54:24 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078508&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078508 | CSI OF Renewal | ST004060-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 400000 | Goonyella | YUKAN SER TO YUKAN AT |  | 5.1909 | KM | GA01ML28 | 0.8 | GA01ML33 | 0.9899 | KM |  |  |  |  | 28.8 | 33.99 | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 13:35:58 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075360&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075360 | CSI RADOME COVER RENEWAL NL SYSTEM | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME | RENEWAL | 3 | SITE | 109000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 12:23:52 AUSQLD Scott Andrews (R003573) * RENEWAL OF DEHYDRATORS AT SUMMER HILL AND BOVEY'S LOOKOUT AND RENEWAL OF RADOME AT ONE SITE. RADOME SITE TO BE DETERMINED IN MAY 2022 BASED ON CONDITION.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046827&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046827 | CSI Tower Renewal | ST006380-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | DESIGN INSPECTION | 1 | SITE | 10500 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.03.2021 17:21:50 AUSQLD Scott Andrews (R003573) * Check Tower at Functional Location for Design input and Design upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046825&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046825 | CSI Tower Renewal | ST005950-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | DESIGN INSPECTION | 1 | SITE | 10500 | Blackwater | CAPELLA | CAPELLA | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.03.2021 17:23:38 AUSQLD Scott Andrews (R003573) * Check Tower at Functional Location for Design input and Design upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046820&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046820 | CSI Tower Renewal | ST005280-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | DESIGN INSPECTION | 1 | SITE | 10500 | Blackwater | CROCKER PEAK | CROCKER PEAK | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.03.2021 17:17:43 AUSQLD Scott Andrews (R003573) * Check Tower at Functional Location for Design input and Design upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046822&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046822 | CSI Tower Renewal | ST005510-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | DESIGN INSPECTION | 1 | SITE | 10500 | Blackwater | GREGORY | GREGORY | 0 | KM | BW08ML62 | 0.2469 | BW08ML62 | 0.2469 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.03.2021 17:19:47 AUSQLD Scott Andrews (R003573) * Check Tower at Functional Location for Design input and Design upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046823&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046823 | CSI Tower Renewal | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | DESIGN INSPECTION | 1 | SITE | 10500 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.68 | BW03ML115 | 0.68 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 28.03.2021 17:15:16 AUSQLD Scott Andrews (R003573) * Check Tower at Functional Location for Design input and Design upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046826&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046826 | CSI Tower Renewal | ST006120-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 90000 | Blackwater | BLACKWATER | BLACKWATER | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM | [6 empty] | 2023-06-30 | ALL |  |  |  | 4 | 3.15 |  |  |  | 12.6 |  |  | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230920
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044607&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044607 | Tower Renewal Bluff | ST005520-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER MAJOR | RENEWAL | 1 | SITE | 136500 | Blackwater | BLUFF | BLUFF | 0 | KM | BW54CR0 | 0 | BW54CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230920 | * 28.03.2021 17:06:53 AUSQLD Scott Andrews (R003573) * Refurbish Tower and Footings ta Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075003&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075003 | Data Comms Design and Renewal | BW | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | SYSTEM | 700000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 25.03.2021 07:53:08 AUSQLD Scott Andrews (R003573) * Design and Renewal of central and field data comms routers, switches and firewalls.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075002&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075002 | Data Comms Design and Renewal | GA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | SYSTEM | 700000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 25.03.2021 07:43:15 AUSQLD Scott Andrews (R003573) * Design and Renewal of central and field data comms routers, switches and firewalls.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084390&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084390 | Data Comms Design and Renewal Newlands | NL | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 44 | UNIT | 656000 | Newlands | ABBOT POINT | LEICHHARDT RANGE | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044653&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000044653 | 44653_Interlocking_BW_Archer_Des | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING |  | DESIGN | 1 | UNIT | 277000 | Blackwater | ARCHER |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2021-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2019-07-15 | 2019-11-29 | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification in process | SCPR |  | 20240630 | Year of work altered to FY23 on 24 Feb 2023 as the works was not completed in FY22 and was re-scheduled to be completed in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065497&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065497 | SIG_Interlocking Renewal - CH Stg1D_Des | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN & ORDER | 1 | UNIT | 787730 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | MEDIUM | Notification in process | RRIG | FY23 IN | 20240430 | * 28.09.2020 10:36:23 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 1D)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074213&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074213 | SIG_Interlocking Renewal - CH Stg1E_Pln | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | PLANNING | 1 | UNIT | 112160 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 16.03.2021 17:05:53 AUSQLD Robert Love (R111379) * Complete planning phase for Callemondah Stage 1E - final cabling arrangement for GE OC West.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065499&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065499 | SIG_Interlocking Renewal - CH Stg2A_Pln | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | PLANNING | 1 | UNIT | 618400 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH |  | MEDIUM | HIGH | Notification in process | RRIG | FY23 IN | 20240630 | * 28.09.2020 10:37:46 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 2) * 16.03.2021 18:02:42 AUSQLD Robert Love (R111379) * Completion of first (1 of 3) phase of design and principal testing of the Callemondah Interlocking data, as per Callemondah Strategy Stage 2A.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065495&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065495 | SIG_Interlocking Renewal - CH Stg1C_Com | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 2899771 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 28.09.2020 10:35:02 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 1C) * 12.04.2021 16:21:03 AUSQLD Jeremy Stevenson (R867415) * Unique site, may drive critical path of closure * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073518&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073518 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 33000 | Goonyella | HAY POINT | BLAIR ATHOL | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 03.03.2021 12:10:24 AUSQLD Robert Love (R111379) * Replace 4 diagnostic PCs within the GA System. 1. JB North SER1 Interlocking. 2. JB South SER3 Interlocking. 3. JBM Master Interlocking 4. JN SER6 Interlocking
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073815&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073815 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 6 | UNIT | 70000 | Blackwater | MOUNT LARCOM | GREGORY | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 09.03.2021 15:35:21 AUSQLD Robert Love (R111379) * Replace existing Maintenance PC with Aurizon IT PC. PC to be installed on site with correct software and connected to interlocking and network to enable monitoring and security updates. 1. Kabra SER1 2 Rocklands 22/25 Loc (OC1) 3 Gracemere SER1 4 Ensham 5 Gregory Mine 6 Kabra SER2 (OC2)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065477&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065477 | SIG_Interlocking Renewal_GA_Balook_Pln | ST003880-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI | PLANNING | 1 | STATION | 153960 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 28.09.2020 10:21:52 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065397&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000065397 | SIG_Interlocking Renewal - CE_Com | ST002775-10 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI | RENEWAL | 1 | STATION | 2787822 | Newlands | COLLINSVILLE |  | 0 | KM | NL01ML76 | 0.9 | NL01ML76 | 0.9 | KM | [6 empty] | 2022-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  | 2021-10-05 | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 28.09.2020 09:16:22 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER. * 15.04.2021 16:22:59 AUSQLD Robert Love (R111379) * TCs to be retained, not replaced. No VDRs required - only minimal breakout points. There are no crossovers.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082014&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000082014 | 82014_interlocking_GA_Wotonga_rugcom_ren | ST005120-08 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | REMOVE SERIAL LINK | RENEWAL | 1 | UNIT | 50000 | Goonyella | WOTONGA | WOTONGA | 0 | KM | GA01ML174 | 0.0429 | GA01ML174 | 0.0429 | KM | [11 empty] | 4 | 4 |  |  |  | 16 |  |  | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | Add in coms card to microlok rack to remove ruggedcom serial links.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104551&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000104551 | SIG_Interlocking Renewal - MA_AE_Pln | ST003290-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE |  | Moura | ANNANDALE | ANNANDALE | 0 | KM | MA01ML0 | 0.1 | MA01ML0 | 0.1 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 | 5731 |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | NWSC |  | 20240630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104787&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000104787 | SIG_Interlocking Renewal_MA_Dumgree_Pln | ST003600 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 100000 | Moura | DUMGREE | DUMGREE | 0 | KM | MA01ML108 | 0.545 | MA01ML108 | 0.545 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Planning phase for the replacement of the VPI at Dumgree. PBI expected to be a Westrace MkII. Working components from the removed VPI are to be placed into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053200&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000053200 | SIG_Interlocking Renewal - MA_ED_Con | ST003640-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1431770 | Moura | EARLSFIELD |  | 0 | KM | MA01ML127 | 0.8589 | MA01ML127 | 0.8589 | KM | [6 empty] | 2022-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105107&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000105107 | SIG_Level Xing_Hut Replace_GA_KenLog_Pln | LX000663 | CONTROL SYSTEMS | LEVEL CROSSINGS | HOUSING REPLACEMENT | PLANNING | 1 | SITE | 0 | Goonyella | BLACKRIDGE | BLACKRIDGE | 0 | KM | GA05ML80 | 0.68 | GA05ML80 | 0.68 | KM | [11 empty] | 4.5 | 3 | 2 | 3 | 1 | 13.5 |  |  |  | Other Control Sys Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Notification completed | NWSC |  | 20230630 | Plan the replacement of the 4 location cases, defunct power supplies and defunct track circuits at Ken Logan Rd Level Crossing with a standard LX hut. Change track circuits to axlecounters. Use a standard power setup.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105103&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000105103 | SIG_Level Xing CT Replace_BW_Con | BW | CONTROL SYSTEMS | LEVEL CROSSINGS | RMS CT REPLACEMENT | RENEWAL | 1 | SITE | 20000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [17 empty] | 100 |  |  |  | Level Crossing Other | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | NWSC |  | 20240630 | New type-approved CT that has current carrying wire threaded through it rather than being wired into the circuit. This should prevent failure through most surges. Locations in Blackwater to be based on priorities with important LXs and the NCL given priority. The programme to replace CTs will continue in future years. This work came out of failure of RMS at Wuthung Rd where a train had authority to pass over a failed LX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075210&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075210 | SIG_Points_Impr_M23A Contact Rem_GA_Des | GA | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR REMOVAL | DESIGN | 9 | UNIT | 210000 | Goonyella | COPPABELLA | GOONYELLA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 | 5732 | 2021-03-31 | 2021-10-05 | Other Control Sys Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240626 | * 29.03.2021 14:32:40 AUSQLD Robert Love (R111379) * Design for the removal of the contactor from the following (14) M23A machines: Goonyella GA7A Pts, GA7B Pts, GA8A Pts, GA8B Pts, Moranbah MO9C Pts, MO10A Pts, Mt McLaren MM12B Pts, MM7A Pts, Blackridge BG7A Pts, BG12A Pts, BG12B Pts, Blair Athol BA7A Pts, BA7B Pts, BA8 PTs. This is to create spares of unsupported Contactor Relays and renew old machines in the field.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000048888&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000048888 | PwrRes AltCont Panel Review_Pln | ST002360-01 | CONTROL SYSTEMS | POWER RESILIENCE | ALT & CONT PANEL & UPS | PLANNING | 1 | UNIT | 20000 | Blackwater | BLACKWATER |  | 0 | KM |  | 0 |  | 0 | [7 empty] | 2022-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 | 2021-10-05 | Power Resilience | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | Review the replacement options for replacing the relay based Alternator Control Panels within the Blackwater System
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073818&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073818 | SIG_Power Renewal_Diesel Glow Plugs_Com | GA | CONTROL SYSTEMS | POWER RESILIENCE | GENSET IMPROVEMENTS | RENEWAL | 4 | UNIT | 46000 | Goonyella | HAY POINT | BLAIR ATHOL | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Power Resilience | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230511 | * 09.03.2021 17:38:26 AUSQLD Robert Love (R111379) * Complete 4 Genset upgrades to the glow plug, to have a delay between starting the glow plug and cranking the engine to improve reliable starting. The 4 sites are Lake Vermont SER1, Harrow, Stephens and Ingsdon.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074098&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074098 | SIG_Power Resillience UPS_GA_Com | GA | CONTROL SYSTEMS | POWER RESILIENCE | UPS | RENEWAL | 6 | STATION | 483260 | Goonyella | MALLAWA | STEPHENS | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Power Resilience | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 15.03.2021 15:18:47 AUSQLD Robert Love (R111379) * Commission replacement for Siel UPS at Lake Vermont, Harrow, Stephens, Isaac Plains and Mallawa. Also, replace Ingsdon Siel UPS.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070497&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070497 | Replace all station TC with axle counter | ST001150-03 | CONTROL SYSTEMS | TRAIN DETECTION | AXLE COUNTER | RENEWAL | 1 | STATION | 3378477 | Goonyella | WOTONGA | WOTONGA | 0.383 | KM | GA01ML171 | 0.8269 | GA01ML172 | 0.2099 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073877&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073877 | SIG_Train Detection_TC Replace - TA_Com | ST004380-03 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLE COUNTER | RENEWAL | 1 | STATION | 3203133 | Blackwater | TRYPHINIA | TRYPHINIA | 0 | KM | BW03ML128 | 0.3559 | BW03ML128 | 0.3559 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073926&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073926 | SIG_Train Detection_ML Int RX_GA_Com | GA | CONTROL SYSTEMS | TRAIN DETECTION | ML INT RX | RENEWAL | 3 | UNIT | 673468 | Goonyella | OAKY CREEK | SARAJI | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 11.03.2021 10:58:06 AUSQLD Robert Love (R111379) * Replacement of 3 ML Intermediate RX tracks (Oaky Creek OC22CAT and OC22CB1T, and Saraji SI14CBT).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043732&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043732 | SIG_Train Detection_GA_IsaacPlainsML_Des | ST004790 | CONTROL SYSTEMS | TRAIN DETECTION | ML TC TO AXLECOUNTER | DESIGN | 8 | UNIT | 1037253 | Goonyella | ISAAC PLAINS | ISAAC PLAINS | 0 | KM | GA01ML171 | 0.8289 | GA01ML171 | 0.8289 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5737 | 2021-03-31 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM |  | MEDIUM | HIGH | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103970&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000103970 | SIG_Train Detection_GA_Mallawa_ML_Pln | ST001210 | CONTROL SYSTEMS | TRAIN DETECTION | ML TC TO AXLECOUNTER | PLANNING | 1 | SITE | 150000 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML167 | 0.92 | GA01ML167 | 0.92 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Notification completed | NWSC |  | 20230630 | Replace all track circuits (primarily 26 defunct ML tracks) with 25 axlecounter tracks. Axlecounter is to be Frauschser.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103972&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000103972 | SIG_Train Detection_GA_PeakDowns_ML_Pln | ST000940 | CONTROL SYSTEMS | TRAIN DETECTION | ML TC TO AXLECOUNTER | PLANNING | 1 | SITE | 12000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.9529 | GA03ML43 | 0.9529 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 | 5728 |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | NWSC |  | 20240630 | Replace 7 ML track circuits in the balloon loop (freq E,F,G,H) with 2 Frauscher or Thales tracks. Preference is for Frauscher but there is a Thales axlecounter used for a semi-attached level crossing. This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100027&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000100027 | CS Transmission ACOM Blackwater Planning | BW | CONTROL SYSTEMS | TRANSMISSION | ACOM | PLANNING | 1 | LUMPSUM | 15000 | Blackwater | BLACKWATER SYSTEM CONTRIB |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 | 15 | 5684 |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100028&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000100028 | CS Transmission ACOM Goonyella Planning | GA | CONTROL SYSTEMS | TRANSMISSION | ACOM | PLANNING | 1 | LUMPSUM | 15000 | Goonyella | GOONYELLA PLANNING CONTRIB |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 | 15 | 5684 |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100026&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000100026 | CS Transmission ACOM Moura Planning | MA | CONTROL SYSTEMS | TRANSMISSION | ACOM | PLANNING | 1 | LUMPSUM | 10000 | Moura | MOURA SYSTEM CONTRIB |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 | 15 | 5684 |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100029&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000100029 | CS Transmission ACOM Newlands Planning | NL | CONTROL SYSTEMS | TRANSMISSION | ACOM | PLANNING | 1 | LUMPSUM | 10000 | Newlands | NEWLANDS PLANNING CONTRIB |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 | 15 | 5684 |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046775&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046775 | CS Trans DMR LINK Renewal | ST005590-05 | CONTROL SYSTEMS | TRANSMISSION | DMR | RENEWAL | 2 | SITE | 150000 | Moura | CALLIOPE RANGE | SPECIMEN HILL | 0 | KM | MA14CR0 | 0 | MA14CR0 | 0 | KM |  |  |  |  | 0 | 0 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 28.03.2021 20:21:34 AUSQLD Scott Andrews (R003573) * Replace Nera Link betwwen Calliope Range and Specimen Hill
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075248&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075248 | NMS RENEWAL | BW | CONTROL SYSTEMS | TRANSMISSION | NMS | RENEWAL | 1 | SYSTEM | 168000 | Blackwater | BLACKWATER SYSTEM |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5692 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 17:13:26 AUSQLD Scott Andrews (R003573) * BW ACOM, TETRA SYS SPLIT + CYBER, TETRA BASE, TETRA SINGLE CARRIER AND NMS RENEWAL BW SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075242&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075242 | NMS RENEWAL GA | GA | CONTROL SYSTEMS | TRANSMISSION | NMS | RENEWAL | 1 | SYSTEM | 168000 | Goonyella | GOONYELLA | GOONYELLA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5692 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 10:23:04 AUSQLD Scott Andrews (R003573) * NETWORK MANAGEMENT SYSTEM RENEWAL GA SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075285&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075285 | MA NMS | MA | CONTROL SYSTEMS | TRANSMISSION | NMS | RENEWAL | 1 | SYSTEM | 75600 | Moura | MOURA SYSTEM |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5692 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 19:38:16 AUSQLD Scott Andrews (R003573) * MA NMS SYSTEM CONTRIBUTION AND RADOME AT ONE SITE RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075230&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075230 | NMS RENEWAL NL | NL | CONTROL SYSTEMS | TRANSMISSION | NMS | RENEWAL | 1 | SYSTEM | 63000 | Newlands | NEWLANDS | NEWLANDS | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5692 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 29.03.2021 21:40:11 AUSQLD Scott Andrews (R003573) * NETWORK MANAGEMENT SYSTEM RENEWAL NL SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043364&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043364 | CS Transmission Power Supply | ST007170-15 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 33000 | Goonyella | MACARTHUR MINE LOADOUT | MACARTHUR MINE LOADOUT | 0 | KM | GA08ML4 | 0.339 | GA08ML4 | 0.339 | KM |  |  |  |  | 4.339 | 4.339 | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification completed | SCPR |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078665&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078665 | CS Transmission Renewal | ST004920-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 31000 | Goonyella | NORTH GOONYELLA SER1 |  | 0 | KM | GA01ML213 | 0.6999 | GA01ML213 | 0.6999 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 16:16:15 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078663&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078663 | CS Transmission Renewal | ST006670-02 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 31000 | Goonyella | SOUTH WALKER JUNCTION CER |  | 0 | KM | GA01ML127 | 0.4799 | GA01ML127 | 0.4799 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 16:14:03 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078662&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078662 | CS Transmission Renewal | ST001950-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 31000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML125 | 0.7139 | BW03ML125 | 0.7139 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 16:12:57 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075293&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075293 | VILLA FRANCA DC POWER SUPPLY RENEWAL | ST006780-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 31000 | Goonyella | VILLA FRANCA ATS |  | 0 | KM | GA05ML37 | 0.8499 | GA05ML37 | 0.8499 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 20:30:19 AUSQLD Scott Andrews (R003573) * VILLAFRANCA DC POWER SUPPLY RENEWAL TELECOMMS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078639&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078639 | CS Transmission Renewal | ST000790-16 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 31000 | Goonyella | VILLAFRANCA TSC |  | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 15:47:45 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046797&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046797 | Trans Pwr Supply Renewal | ST001330-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | BOLINGBROKE ATS 65.9KM | BOLINGBROKE ATS 65.9KM | 0 | KM | GA01ML65 | 0.93 | GA01ML65 | 0.93 | KM |  |  |  |  | 65.93 | 65.93 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046796&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046796 | Trans Pwr Supply Renewal | ST000690-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | BOLINGBROKE FS | BOLINGBROKE FS | 0 | KM |  | 0 |  | 0 | [5 empty] | 54.87 | 54.87 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043371&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043371 | 3380 Transmission Power Supply Renewal | ST006130-02 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Blackwater | BOONAL PSC 178.5KM | BOONAL PSC 178.5KM | 0 | KM | BW03ML178 | 0.5 | BW03ML178 | 0.5 | KM |  |  |  |  | 178.5 | 178.5 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046737&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046737 | Trans Pwr Supply Renewal | ST006720-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | COPPABELLA ATS 154.2KM | COPPABELLA ATS 154.2KM | 0 | KM | GA01ML154 | 0.17 | GA01ML154 | 0.17 | KM |  |  |  |  | 154.17 | 154.17 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046770&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046770 | Trans Pwr Supply Renewal | ST008600-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | ISAAC PLAINS MINE CER | ISAAC PLAINS MINE CER | 0 | KM | GA11ML4 | 0.256 | GA11ML4 | 0.256 | KM |  |  |  |  | 4.256 | 4.256 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046772&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046772 | Trans Pwr Supply Renewal | ST007540-11 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | LAKE VERMONT BALLOON SER | LAKE VERMONT BALLOON SER | 0 | KM | GA19ML14 | 0.08 | GA19ML14 | 0.08 | KM |  |  |  |  | 14.08 | 14.08 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046771&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046771 | Trans Pwr Supply Renewal | ST007870-21 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | LAKE VERMONT TCU | LAKE VERMONT TCU | 0 | KM | GA19ML1 | 0.273 | GA19ML1 | 0.273 | KM |  |  |  |  | 1.273 | 1.273 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046773&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046773 | Trans Pwr Supply Renewal | ST008560-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | MILLENNIUM MINE CER | MILLENNIUM MINE CER | 0 | KM | GA16ML4 | 0.3519 | GA16ML4 | 0.3519 | KM |  |  |  |  | 4.352 | 4.352 | 2023-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046754&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046754 | Trans Pwr Supply Renewal | ST007310-47 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | MINDI FS | MINDI FS | 0 | KM | GA01ML116 | 0.2 | GA01ML116 | 0.2 | KM |  |  |  |  | 116.2 | 116.2 | 2023-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043378&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043378 | 3387 Transmission Power Supply Renewal | ST007830-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | MOORVALE LOADOUT CER | MOORVALE LOADOUT CER | 0 | KM | GA03ML5 | 0.54 | GA03ML5 | 0.54 | KM |  |  |  |  | 5.54 | 5.54 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046760&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046760 | Trans Pwr Supply Renewal | ST000750-29 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | NORWICH PARK FS | NORWICH PARK FS | 0 | KM | GA03ML105 | 0.2 | GA03ML105 | 0.2 | KM |  |  |  |  | 105.2 | 105.2 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046761&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046761 | Trans Pwr Supply Renewal | ST005040-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | RED MOUNTAIN SER | RED MOUNTAIN SER | 0 | KM | GA03ML23 | 0.6199 | GA03ML23 | 0.6199 | KM |  |  |  |  | 23.62 | 23.62 | 2023-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046762&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046762 | Trans Pwr Supply Renewal | ST000720-16 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | RED MOUNTAIN TSC | RED MOUNTAIN TSC | 0 | KM | GA03ML19 | 0.46 | GA03ML19 | 0.46 | KM |  |  |  |  | 19.46 | 19.46 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046755&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046755 | Trans Pwr Supply Renewal | ST007510-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Goonyella | STEPHENS SER | STEPHENS SER | 0 | KM | GA03ML98 | 0.9819 | GA03ML98 | 0.9819 | KM |  |  |  |  | 98.982 | 98.982 | 2023-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046774&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000046774 | Trans Pwr Supply Renewal | ST009460-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 31000 | Blackwater | YARWUN ATS 545.2KM | YARWUN ATS 545.2KM | 0 | KM | BW01ML545 | 0.2099 | BW01ML545 | 0.2099 | KM |  |  |  |  | 545.21 | 545.21 | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078685&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000078685 | CS Transmission REVELOC Planning Phase | ST005490-JP | CONTROL SYSTEMS | TRANSMISSION | REVLOC | PLANNING | 1 | SITE | 150000 | Blackwater | ROCKHAMPTON |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 10.06.2021 16:38:06 AUSQLD Peter Rayner (R003851) * Renew REVELOC Application (Design)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075302&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075302 | GA TECH TRANS SDH TO IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SYSTEM | 105000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification in process | RRIG | FY23 IN | 20230630 | * 31.03.2021 07:02:29 AUSQLD Scott Andrews (R003573) * GA SYSTEM TECHNOLOGY TRANSFORMATION SDH TO IP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075361&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075361 | NL TECH TRANS SDH TO IP | NL | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SYSTEM | 78750 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5693 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240530 | * 31.03.2021 12:31:12 AUSQLD Scott Andrews (R003573) * NL SYSTEM TECHNOLOGY TRANSFORMATION SDH TO IP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075280&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075280 | BW TECH TRANS SDH TO IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SYSTEM | 105000 | Blackwater | BLACKWATER SYSTEM STATIONS |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | HIGH | MEDIUM | Notification in process | RRIG | FY23 IN | 20230630 | * 30.03.2021 17:28:49 AUSQLD Scott Andrews (R003573) * BW SYSTEM TECHNOLOGY TRANSFORMATION SDH TO IP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075215&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075215 | CS TELECOMMS BATTERIES | ST008820-05 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11500 | Newlands |  |  | 0 | KM | NL01ML54 | 0.5 | NL01ML54 | 0.5 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 20:29:32 AUSQLD Scott Andrews (R003573) * NL RENEW TELECOMMS bATTERIES IN AT 2 SITES. sITES TO BE DETERMINED IN MAY 2022
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075220&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075220 | CS Tele Batteries | ST005600-38 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Moura | BANANA RANGE MWR |  | 0 | KM | MA13CR0 | 0 | MA13CR0 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5689 | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240530 | * 29.03.2021 17:46:43 AUSQLD Scott Andrews (R003573) * RENEW TELECOMMUNICATIONS BATTERIES AT 2 SITES. SITES TO BE DETERMINED IN MAY 2022
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087332&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087332 | CS Tele Battery Renewal | ST006120-38 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | BLACKWATER MWR |  | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087308&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087308 | CS Tele Battery Renewal | ST005520-11 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | BLUFF MWR |  | 0 | KM | BW54CR0 | 0 | BW54CR0 | 0 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095816&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000095816 | CS TELE BATTERY RENEWAL BR | ST008920-06 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | BRAESIDE NEBO PSC | BRAESIDE NEBO PSC | 0 | KM | GA01ML104 | 0.2999 | GA01ML104 | 0.2999 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230521
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087331&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087331 | CS Tele Battery Renewal | ST005950-05 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | CAPELLA MWR |  | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075231&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075231 | Procure TELE BATTERIES CD | ST009210-48 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10500 | Goonyella | CARBOROUGH DOWNS TSC | CARBOROUGH DOWNS TSC | 0 | KM | GA01ML162 | 0.192 | GA01ML162 | 0.192 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 06:31:34 AUSQLD Scott Andrews (R003573) * RNEW TELECOMMUNICATIONS BATTERIES AT 8 SITES. SITES TO BE DETERMINED IN MAY 2022 BASED ON CONDITION. Procurement IV.00821.e.h.ga.04.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087330&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087330 | CS Tele Battery Renewal | ST002940-07 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | CLERMONT MWR |  | 0 | KM | BW03ML100 | 0.26 | BW03ML100 | 0.26 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095813&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000095813 | CS TELE BATTERY RENEWAL CA | ST001680-04 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | COPPABELLA MI | COPPABELLA MI | 0 | KM | GA01ML142 | 0.7479 | GA01ML142 | 0.7479 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230521
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087305&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087305 | CS Tele Battery Renewal | ST005660-02 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Moura | EARLSFIELD |  | 0 | KM | MA01ML127 | 0.8589 | MA01ML127 | 0.8589 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087309&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087309 | CS Tele Battery Renewal | ST003020-35 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | EMERALD MWR |  | 0 | KM | BW57CR0 | 0 | BW57CR0 | 0 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087307&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087307 | CS Tele Battery Renewal | ST005540-05 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | GOGANGO MWR |  | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113039&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000113039 | CS TELECOMM BATTERIES | ST008330-09 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11500 | Newlands | LEICHARDT RANGE HBD | LEICHARDT RANGE HBD | 0 | KM | NL01ML158 | 0.5999 | NL01ML158 | 0.5999 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087306&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087306 | procure CS Tele Battery Renewal Nanya | ST005960-14 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Goonyella | NANYA MWR |  | 0 | KM | GA42CR0 | 0 | GA42CR0 | 0 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630 | Procurement IV.00821.e.h.ga.04.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095834&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000095834 | CS TELE BATTERY RENEWAL NG | ST001780-17 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | NORTH GOONYELLA AT | NORTH GOONYELLA AT | 0 | KM | GA01ML207 | 0 | GA01ML207 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230521
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075249&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075249 | CS Tele Battery Renewal | ST006260-02 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | RAGLAN SOUTH MWR |  | 0 | KM | BW01ML582 | 0.439 | BW01ML582 | 0.439 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 17:21:46 AUSQLD Scott Andrews (R003573) * BW CSI BATTERIES AND RADOME. SITES TO BE DETERMINED MAY 2022 BASED ON CONDITION.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097739&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000097739 | Procure CS TELE BATTERY Tootoolah | ST008550-12 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10500 | Goonyella | TOOTOOLAH AT | TOOTOOLAH AT | 0 | KM | GA01ML135 | 0.512 | GA01ML135 | 0.512 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230630 | Procurement IV.00821.e.h.ga.04.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095814&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000095814 | CS TELE BATTERY RENEWAL TH | ST006660-15 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | TOOTOOLAH SER | TOOTOOLAH SER | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230521
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095815&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000095815 | CS TELE BATTERY RENEWAL WA | ST005800-10 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | WAITARA | WAITARA | 0 | KM | GA01ML94 | 0.9599 | GA01ML94 | 0.9599 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230521
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097762&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000097762 | Procure CS TELE BATTERY WAITARA MW | ST005790-37 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | WAITARA MW | WAITARA MW | 0 | KM | GA01ML100 | 0.45 | GA01ML100 | 0.45 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals |  | LOW | LOW | LOW | MEDIUM | Notification completed | NWSC |  | 20230630 | Procurement IV.00821.e.h.ga.04.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087333&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000087333 | CS Tele Battery Renewal | ST005530-37 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 10000 | Blackwater | WALLAROO MWR |  | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2023-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107398&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000107398 | CS TETRA Coverage Improvement | ST008830-09 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 180000 | Newlands | ABERDEEN HBD | ABERDEEN HBD | 0 | KM | NL01ML38 | 0.2 | NL01ML38 | 0.2 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | [5 empty] | 5482 |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075218&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075218 | CS TETRA RADIO NL | ST002650-07 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 340000 | Newlands | ARMUNA SER | ARMUNA SER | 0 | KM | NL01ML24 | 0.1069 | NL01ML24 | 0.1069 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 29.03.2021 21:04:05 AUSQLD Scott Andrews (R003573) * ADDITIONAL TETRA BASE FOR RADIO COVERAGE IMPROVEMENT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046778&DY_MAB=X&~OKCODE=ONLI | FY23 | Coal Traffic |  | COAL | 002000046778 | CS TETRA RADIO BW | ST009450 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 340000 | Blackwater | MEMOOLOO | MEMOOLOO | 0 | KM | BW06ML53 | 0.266 | BW06ML53 | 0.266 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | LOW | Notification in process | RRIG | FY23 IN | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075236&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075236 | CS TETRA RADIO GA | ST008040-16 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 340000 | Goonyella | MIDDLEMOUNT JUNCTION SER | MIDDLEMOUNT JUNCTION SER | 0 | KM | GA03ML125 | 0.511 | GA03ML125 | 0.511 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 08:13:34 AUSQLD Scott Andrews (R003573) * ADDITIONAL TETRA BASE FOR RADIO COVERAGE IMPROVEMENT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075235&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075235 | GA TETRA SYSTEM FIRMWARE UPDATE V8.0 | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SYSTEM | 194250 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | HIGH |  | MEDIUM | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 07:36:09 AUSQLD Scott Andrews (R003573) * GA CONTRIBUTION TO TETRA SYSTEM SPLIT + CYBER SECURITY UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075284&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075284 | MA TETRA SYSTEM FIRMWARE UPDATE V8.0 | MA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SYSTEM | 131250 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | HIGH |  | MEDIUM | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 19:30:27 AUSQLD Scott Andrews (R003573) * TETRA SYSTEM SLIP CYBER TETRA SINGLE CARRIER BASE RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075217&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075217 | NL TETRA SYSTEM FIRMWARE UPDATE V8.0 | NL | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SYSTEM | 89250 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | HIGH |  | MEDIUM | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 29.03.2021 20:52:48 AUSQLD Scott Andrews (R003573) * NL CONTRIBUTION TO TETRA SYSTEM SPLIT * 29.03.2021 21:24:48 AUSQLD Scott Andrews (R003573) * CYBER SECURITY TREATMENT FOR BASES
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084181&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000084181 | BW TETRA SYSTEM FIRMWARE UPDATE V8.0 | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SYSTEM | 195700 | Blackwater | BLACKWATER SYSTEM STATIONS |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2021-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112941&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000112941 | CS TETRA RADIO | ST005050-06 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | UNIT | 15000 | Goonyella | RIVERSIDE SER | RIVERSIDE SER | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20230630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075005&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075005 | DIGITAL TELEMETRY BOORGOON | ST002450-03 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 66150 | Blackwater | BOORGOON |  | 0 | KM | BW05ML9 | 0.5779 | BW05ML9 | 0.5779 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 | 5738 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 25.03.2021 08:24:39 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT BOORGOON WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075032&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075032 | DIGITAL TELEMETRY CURRAGH | ST002510-03 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 61500 | Blackwater | CURRAGH |  | 0 | KM | BW12ML9 | 0.082 | BW12ML9 | 0.082 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 | 5739 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 25.03.2021 09:11:04 AUSQLD Scott Andrews (R003573) * Renew VF Telemetry with Digital Telemetry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075296&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075296 | DIGITAL TELEMETRY GOONYELLA | ST004740-04 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 66150 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA13ML195 | 0.4199 | GA13ML195 | 0.4199 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5740 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 31.03.2021 06:32:23 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT GOONYELLA WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075346&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075346 | DIGITAL TELEMETRY GORDONSTONE | ST003120-05 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 66150 | Blackwater | GORDONSTONE | GORDONSTONE | 0 | KM | BW10ML7 | 0.79 | BW10ML7 | 0.79 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5741 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 31.03.2021 11:53:20 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT GORDONSTONE WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075295&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075295 | DIGITAL TELEMETRY RIVERSIDE | ST005050-04 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 61500 | Goonyella | RIVERSIDE | RIVERSIDE | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5742 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 31.03.2021 06:19:55 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT RIVERSIDE WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075004&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075004 | DIGITAL TELEMETRY TIKARDI | ST002620-04 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 1 | SITE | 66150 | Blackwater | TIKARDI |  | 0 | KM | BW05ML5 | 0.525 | BW05ML5 | 0.525 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 | 5743 | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 25.03.2021 08:06:13 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT TIKARDI WITH DIGITSL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075345&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075345 | DIGITAL TELEMETRY GREGORY MINE | ST003150-19 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 1 | SITE | 73500 | Blackwater | GREGORY MINE | GREGORY MINE | 0 | KM | BW09ML62 | 0.2469 | BW09ML62 | 0.2469 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 11:44:43 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT GREGORY MINE WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075283&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075283 | DIGITAL TELEMETRY KINROLA | ST002560-05 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 1 | SITE | 73500 | Blackwater | KINROLA |  | 0 | KM | BW05ML15 | 0.671 | BW05ML15 | 0.671 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 30.03.2021 17:55:14 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT KINROLA WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075297&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075297 | DIGITAL TELEMETRY MORANBAH NORTH | ST004850-04 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 1 | SITE | 73500 | Goonyella | MORANBAH NORTH | MORANBAH NORTH | 0 | KM | GA01ML192 | 0.1809 | GA01ML192 | 0.1809 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 06:36:52 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT MORANBAH NORTH AND REPLACE WITH DIGITAL TELEMETRY
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075342&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075342 | DIGITAL TELEMETRY YAN YAN | ST003260-07 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 1 | SITE | 73500 | Blackwater | YAN YAN | YAN YAN | 0 | KM | BW08ML50 | 0.875 | BW08ML50 | 0.875 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 11:17:32 AUSQLD Scott Andrews (R003573) * RENEW VF TELEMETRY AT YAN YAN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075233&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075233 | UTC DTC GA SYSTEM CONTRIBUTION | GA | CONTROL SYSTEMS | UTC DTC | UTC CODE AND SAFEWORKING | RENEWAL | 1 | SYSTEM | 840000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5734 | 2021-03-31 | 2021-10-05 | UTC DTC | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 06:38:25 AUSQLD Scott Andrews (R003573) * GA UTCU DTS SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075221&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075221 | UTC DTC MA SYSTEM CONTRIBUTION | MA | CONTROL SYSTEMS | UTC DTC | UTC CODE AND SAFEWORKING | RENEWAL | 1 | SYSTEM | 110250 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5735 | 2021-03-31 | 2021-10-05 | UTC DTC | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 29.03.2021 17:53:08 AUSQLD Scott Andrews (R003573) * UTC DTC RENEWAL MA SYSTEM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075363&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075363 | UTC DTC NL SYSTEM | NL | CONTROL SYSTEMS | UTC DTC | UTC CODE AND SAFEWORKING | RENEWAL | 1 | SYSTEM | 315000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5736 | 2021-03-31 | 2021-10-05 | UTC DTC | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 31.03.2021 12:40:25 AUSQLD Scott Andrews (R003573) * NL UTC DTC SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043411&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043411 | UTC DTC BW SYSTEM CONTRIBUTION | BW | CONTROL SYSTEMS | UTC DTC | UTC CODE AND SAFEWORKING | RENEWAL | 1 | SYSTEM | 840000 | Blackwater | BLACKWATER SYSTEM STATIONS |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5733 | 2021-03-31 | 2021-10-05 | UTC DTC | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 30.03.2021 07:12:48 AUSQLD Scott Andrews (R003573) * UTC DTC BW SYSTEM CONTRIBUTION CODE AND SAFEWORKING RENEWAL AND UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072504&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072504 | OHL Renewals to Improved Connection Stds | BW | ELECTRICAL | OVERHEAD | CONNECTION RENEWALS | RENEWAL | 1 | UNIT | 250000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | OH Reactive Works - Fix on Fail | STRATEGIC | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 09.02.2021 15:15:15 AUSQLD Rebecca Green (R882642) * Following on from the Electro Technical Consultants Development of Strategy for Overhead Catenary report of 11/9/20, Aurizon's OHL connection standards were flagged for review in FY21. This N4 is for renewal works associated with implementing the improved connection standards. * 09.03.2021 15:54:58 AUSQLD Rebecca Green (R882642) * (e.g. Catenary suspension clamps, earth wire clamps, PG clamps) * 12.04.2021 16:21:50 AUSQLD Jeremy Stevenson (R867415) * Scope will be defined in FY22. - Assumption for du ration is it is in This will be works only within constraints with ac * cess & resources (like the small components) * 1.11.2022: The scope is to replace old-style earth wire clamps with the current standard. The EA RAP team is currently compiling a list of locations for clamp replacements. This scope can most likely be executed without going on track and would be suitable scope for an external contractor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072498&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072498 | OHL Renewals to Improved Connection Stds | GA | ELECTRICAL | OVERHEAD | CONNECTION RENEWALS | RENEWAL | 1 | UNIT | 250000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | OH Reactive Works - Fix on Fail | STRATEGIC | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 09.02.2021 15:05:27 AUSQLD Rebecca Green (R882642) * Following on from the Electro Technical Consultants Development of Strategy for Overhead Catenary report of 11/9/20, Aurizon's OHL connection standards were flagged for review in FY21. This N4 is for renewal works associated with implementing the improved connection standards. * 09.03.2021 15:56:55 AUSQLD Rebecca Green (R882642) * (e.g. Catenary suspension clamps, earth wire clamps, PG clamps) * 12.04.2021 16:21:50 AUSQLD Jeremy Stevenson (R867415) * Scope will be defined in FY22. - Assumption for du ration is it is in This will be works only within constraints with ac * cess & resources. * 1.11.2022: The scope is to replace old-style earth wire clamps with the current standard. The EA RAP team is currently compiling a list of locations for clamp replacements. This scope can most likely be executed without going on track and would be suitable scope for an external contractor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072610&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072610 | Goonyella Ports OHLE Renewal | GA | ELECTRICAL | OVERHEAD | DBCT HAY POINT | RENEWAL | 1 | SITE | 1730000 | Goonyella | DBCT HAY POINT | GRASSTREE | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 0 | 8 | 2023-06-30 | [7 empty] | 0.1 |  | 100 | 52 | 2021-03-31 | 2021-10-05 | Goonyella Ports Overhead Line Renewal | BESPOKE DESIGN | MEDIUM |  | MEDIUM | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:17:21 AUSQLD Tracy Holmes (R870040) * No defined design at this stage. Scope is to migiate high number of dewirements in this area. Need to work through this on a yealry basis to sort through these issues. Goes through to FY28. FY23 focus - Mechanical seperation <(>&<)> cross overs Update 1/10/21: Estimate increased from $2M to $3.5M. Update 1/9/22: Estimate updated following development of Class 4 estimate. Reduced from $3M to $1.73M. PCR number 5430.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070371&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070371 | FEEDER WIRE CLEARANCE IMPROVEMENTS | GA-0281-0281AA | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | DESIGN | 1 | SITE | 205000 | Goonyella | MINDI | MINDI | 0.226 | KM | GA/120/055/S1 | 0 | GA/120/281/S1 | 0 | KM |  |  |  |  | 119.878 | 120.513 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 11.03.2021 09:45:13 AUSQLD Simon McPherson (R865828) * Design - clear siding wire, possible light portals to remove deenergised wire from proximity to live feeder wire. * 11.03.2021 10:49:23 AUSQLD Simon McPherson (R865828) * FY Estimate includes Design + Materials * 01.06.2021 15:51:24 AUSQLD Anand Vemuri (R875826) * Changed FLOCs / Codes to suit new subsection FLOCs. Changed FLOCs / Codes to suit new subsection FLOCs.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070365&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070365 | FEEDER WIRE CLEARANCE IMPROVEMENTS | BW-0553 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | DESIGN | 1 | SITE | 660000 | Blackwater | ROCKLANDS | ROCKLANDS | 11.0289 | KM | N/624/658/F1 | 0 | N/635/687/F1 | 0 | KM |  |  |  |  | 0.042 | 2.325 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20240630 | * 11.03.2021 10:44:08 AUSQLD Simon McPherson (R865828) * Relocation of feeder routes from Rocklands TSC off trackside masts support other electrical sections, and increase in feeder clearance to existing structures. * FY estimate Design + Materials
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070363&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070363 | FEEDER WIRE CLEARANCE IMPROVEMENTS. | BW-0531 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 175000 | Blackwater | AMBROSE | AMBROSE | 14.9469 | KM | N/567/559/U | 0 | N/582/506/U | 0 | KM |  |  |  |  | 570.93 | 571.235 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:14:18 AUSQLD Tracy Holmes (R870040) * Design in FY22
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070134&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070134 | FEEDER WIRE CLEARANCE IMPROVEMENTS | BW-0832 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 250000 | Blackwater | EDUNGALBA | EDUNGALBA | 18.7349 | KM | CW/82/843/D | 0 | CW/101/578/D | 0 | KM |  |  |  |  | 84.797 | 85.15 | 2023-06-30 | [7 empty] | 0.1 |  | 100 | 5644 | 2021-03-31 | 2021-10-05 | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20230724 | * 31.03.2021 19:14:10 AUSQLD Tracy Holmes (R870040) * Unit rate needs reviewing so potential change in cost. Design in FY22
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070368&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070368 | FEEDER WIRE CLEARANCE IMPROVEMENTS | GA-0221 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 1320000 | Goonyella | WAITARA | WAITARA | 15.819 | KM | GA/87/219/U | 0 | GA/103/038/U | 0 | KM |  |  |  |  | 98.189 | 100.5 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Outstanding notification | RRIG INIF | FY23 IN | 20250630 | * 31.03.2021 19:14:23 AUSQLD Tracy Holmes (R870040) * Design phase still to happen (so some change might happen) - Design in FY22 (no concept designs yet)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070377&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070377 | Overhead Headspan Renewal | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPAN | RENEWAL | 6 | STRUCTURES | 405000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  | 2021-03-31 | 2021-10-05 | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230714 | * 31.03.2021 19:14:35 AUSQLD Tracy Holmes (R870040) * Need confirmed delivery of this in previous years (based on unit rate based on the design) - could potentially need more time and cost IV.00826.E.B.GA.02.PR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070364&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070364 | SECTION INSULATOR - JILALAN | SQ020386 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/20/264/PR1 | 0 | GA/20/264/PR1 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:42:53 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:00 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:09 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070370&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070370 | SECTION INSULATOR - JILALAN | SQ020390 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/19/941/PR1 | 0 | GA/19/941/PR1 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:46:17 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:21 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:11 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068460&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000068460 | Section Insulator Renewal | SQ020385 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/20/265/JB2 | 0 | GA/20/265/JB2 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 26.11.2020 09:18:31 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 906A/906B 906/2 SW Section Insulator * 12.04.2021 16:21:01 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement (cash flow as well) *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070367&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070367 | Section Insulator Renewal | SQ020388 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/20/015/JB2 | 0 | GA/20/015/JB2 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:44:40 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:08 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:10 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070369&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070369 | Section Insulator Renewal | SQ020389 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/19/913/PR2 | 0 | GA/19/913/PR2 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:45:14 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:11 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:11 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070372&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070372 | Section Insulator Renewal | SQ020391 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/19/991/PR1 | 0 | GA/19/991/PR1 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:46:46 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:24 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:12 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070373&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000070373 | Section Insulator Renewal | SQ020392 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/20/239/PR1 | 0 | GA/20/239/PR1 | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 | 5640 | 2021-03-31 | 2021-10-05 | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240701 | * 14.01.2021 14:47:44 AUSQLD Nigel McDowell (R885053) * Renewal of obsolete Brown Baveri SI. * 31.03.2021 19:15:33 AUSQLD Tracy Holmes (R870040) long lead item procurement. * 12.04.2021 16:22:12 AUSQLD Jeremy Stevenson (R867415) * Dependent on design will determine scope, cost & d uration - No design at present. (need to design to * happen Q1 and deliver H2) Need long lead item pro curement. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063889&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063889 | Overhead Reactive Works | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM | 800000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | OH Reactive Works - Fix on Fail | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:17:09 AUSQLD Tracy Holmes (R870040) * Small components reactive works. Need to move this towards specific scope for FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063910&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000063910 | Overhead Reactive Works | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM | 800000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | OH Reactive Works - Fix on Fail | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:17:14 AUSQLD Tracy Holmes (R870040) * Small components reactive works. Need to move this towards specific scope for FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000098510&DY_MAB=X&~OKCODE=ONLI | FY23 |  | STRATEGIC | COAL | 002000098510 | AT¦BOLINGBROKE ATS AT2¦RENEWAL | ST001330-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 460000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML65 | 0.933 | GA01ML65 | 0.933 | KM |  |  |  |  | 65.933 | 65.933 | 2024-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20240630 | Placeholder. AT to be confirmed post condition testing in December 2022. EK (06/02/24): This update is an action required based on PCR 5847. See excerpt below: Balook Wandoo was FY23 scope which we have not been able to gain access to due to land owner imposed restrictions. This PCR is to scope substitute Balook Wandoo AT2 (2000050168) with Bollingbroke AT2 (2000098510). This will allow Bollingbroke AT1 and Bollingbroke AT2 to be completed at the same time in March FY24 and allow time to resolve access issued at Balook Wandoo before FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050165&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000050165 | Power Systems AT Renewal | ST000710-34 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 460000 | Goonyella | COPPABELLA FS - AT2 | COPPABELLA FS | 0 | KM | GA03ML2 | 0.314 | GA03ML2 | 0.314 | KM |  |  |  |  | 2.314 | 2.314 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Autotransformer Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 01.06.2020 20:43:48 AUSQLD Emma-Kate Clyburn (R870828) * Site to be confirmed in Jan 2021 * 18.03.2021 09:35:20 AUSQLD Dhavalkumar Patel (R866429) * * Site Confirmed - ST000710-34 COPPABELLA FS - AT2 * 12.04.2021 16:12:16 AUSQLD Jeremy Stevenson (R867415) * Current procurement contract will expire in FY23 - * need to discuss this in FY23. (design implementat * ion for FY23 for reduction in cost with optimised * design) - scope is low but as the design is being * optimised in FY23 there may be change to scope on * AT), duration is medium due to AT failures elsewhe * re in the system. * * 12.04.2021 16:14:06 AUSQLD Jeremy Stevenson (R867415) * Current procurement contract will expire in FY23 - need to discuss this in FY23. (design implementat * ion for FY23 for reduction in cost with optimised design) - scope is low but as the design is being optimised in FY23 there may be change to scope on AT), duration is medium due to AT failures elsewhe * re in the system.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000048009&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000048009 | Power Systems AT Renewal | ST001490-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 460000 | Blackwater | OAKY CREEK ATS - AT1 | OAKY CREEK ATS | 0 | KM | BW07FK77 | 0.223 | BW07FK77 | 0.223 | KM |  |  |  |  | 77.723 | 77.723 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Autotransformer Renewal | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 18.03.2021 08:54:40 AUSQLD Dhavalkumar Patel (R866429) * Oaky Creek ATS - AT1 replacement is postponed to FY23 due to unexpected failure of Rangal FS AT4 (ST000340-36). * * Rangal FS AT4 is added to FY22 AT Renewals scope. * 12.04.2021 16:22:27 AUSQLD Jeremy Stevenson (R867415) * Current procurement contract will expire in FY23 - need to discuss this in FY23. (design implementat * ion for FY23 for reduction in cost with optimised design) - scope is low but as the design is being optimised in FY23 there may be change to scope on AT), duration is medium due to AT failures elsewhe * re in the system.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000048017&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000048017 | Power Systems AT Renewal. | ST000340-33 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 460000 | Blackwater | RANGAL FS - AT1 | RANGAL FS | 0 | KM |  | 0 |  | 0 | [5 empty] | 194.97 | 194.97 | 2022-06-30 |  |  |  |  | 3 | 4.8 |  |  |  | 14.4 | 10 | 2020-03-06 | 2020-11-13 | Autotransformer Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | SCPR |  | 20220930 | PS-AR-ATs-RL AT1 (FY22) IV.00505.E.K.CO.01 Rangal Phil Brown's project 2-4 April Closure. Callemondah FS AT4 failed in service. So, Callemondah FS AT4 is prioritised over Rangal FS AT1. Rangal FS AT1 now to be renewed in early FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000045958&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000045958 | Burton (Mallawa) CD Install on 622/20 | SQ110064 | ELECTRICAL | POWER SYSTEMS | CURRENT DETECTOR | RENEWAL | 1 | UNIT | 15000 | Goonyella | BURTON (MALLAWA) | BURTON (MALLAWA) | 0 | KM |  | 0 |  | 0 | [5 empty] | 0.12 | 0.12 | 2021-06-30 | BURTON BALLOON LOOP | BN | [5 empty] | 0.1 |  | 100 |  |  | 2021-10-05 | Current Detectors | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | PS-AR-CD-Constr-Mallawa 622/20 IV.00823.E.A.GA.02.CO MALLAWA Modified from FY21 to FY22 Modified by Adrian Barnes 22 Sep 2021: Moved from FY22 to FY23, see SCR ID 130. 10/10/2022: K Robinson: Burton 622/20 CD competed on 4/10/2022. Completed QA added 10/10.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000045936&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000045936 | Coppabella Yard CD Installation on 232/3 | GA | ELECTRICAL | POWER SYSTEMS | CURRENT DETECTOR | RENEWAL | 1 | UNIT | 15000 | Goonyella | COPPABELLA YARD | COPPABELLA YARD | 0 | KM |  | 0 |  | 0 | [5 empty] | 145.28 | 145.28 | 2023-06-30 | THIRD ROAD | GA | [5 empty] | 0.1 |  | 100 |  |  | 2021-10-05 | Current Detectors | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | Modified from FY21 to FY22 Modified by Adrian Barnes 22 Sep 2021: Moved from FY22 to FY23, see SCR ID 130. 10/10/2022 K Robinson: Coppabella 232_3 CD completed on the 4/10/2022. Completed QA 10/10.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000045955&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000045955 | Saraji CD Installation on 311/6 | SQ110058 | ELECTRICAL | POWER SYSTEMS | CURRENT DETECTOR | RENEWAL | 1 | UNIT | 15000 | Goonyella | SARAJI | SARAJI | 0 | KM |  | 0 |  | 0 | [5 empty] | 64.87 | 64.87 | 2023-06-30 | SARAJI BALLOON LOOP | OC | [5 empty] | 0.1 |  | 100 |  |  | 2021-10-05 | Current Detectors | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | PS-AR-CD-Constr-Saraji 311/6 IV.00823.E.A.GA.07.CO Saraji Modified from FY21 to FY22 Modified by Adrian Barnes 22 Sep 2021: Moved from FY22 to FY23, see SCR ID 130.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072420&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072420 | PS-AR-BW-CD-Const-SL 811/5 | BW-0811 | ELECTRICAL | POWER SYSTEMS | CURRENT DETECTOR | RENEWAL | 1 | UNIT | 15000 | Blackwater | STANWELL | STANWELL | 0 | KM | CW/25/376/U | 0 | CW/25/376/U | 0 | KM | [6 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Current Detectors | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:17:51 AUSQLD Tracy Holmes (R870040) * Std design (SCADA works) - uncertain on scope <(>&<)> cost based on available wires (are there enough??) - will be confirmed by Aug 21 3/4/23 K.Robinson: IO list, BOM, Drawings and SOW provided for construction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072421&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072421 | Stanwell CD Installation on 811/6 | BW-0811 | ELECTRICAL | POWER SYSTEMS | CURRENT DETECTOR | RENEWAL | 1 | UNIT | 15000 | Blackwater | STANWELL | STANWELL | 0 | KM | CW/25/472/U | 0 | CW/25/472/U | 0 | KM | [6 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Current Detectors | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 31.03.2021 19:17:59 AUSQLD Tracy Holmes (R870040) * Std design (SCADA works) - uncertain on scope <(>&<)> cost based on available wires (are there enough??) - will be confirmed by Aug 21 3/4/23 K.Robinson: BOM, SOW, Diagrams and IO list added for construction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071212&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071212 | Earthing and bonding renewals | BW | ELECTRICAL | POWER SYSTEMS | EARTHING AND BONDING | RENEWAL | 1 | LUMPSUM | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 15.01.2021 10:10:33 AUSQLD Adrian Barnes (R886902) * A high-level N4 to cover all E<(>&<)>B renewal in the Blackwater traction power system. * 17.03.2021 10:14:44 AUSQLD Adrian Barnes (R886902) * This N4 excludes the LV system earthing renewals, but includes all other earthing and bonding for the traction power system. * 12.04.2021 16:22:23 AUSQLD Jeremy Stevenson (R867415) * Placeholders and scope will be defined based on wo rks in FY22 - detailed scope in FY22 - not closure * related *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071228&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071228 | Earthing and bonding renewals | GA | ELECTRICAL | POWER SYSTEMS | EARTHING AND BONDING | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 15.01.2021 10:30:37 AUSQLD Michael Simmers (R886887) * High level N4 for Goonyella earthing and bonding renewals * 17.03.2021 10:18:59 AUSQLD Adrian Barnes (R886902) * This N4 excludes the LV system earthing renewals, but includes all other earthing and bonding for the traction power system. * * 12.04.2021 16:22:24 AUSQLD Jeremy Stevenson (R867415) * Placeholders and scope will be defined based on wo rks in FY22 - detailed scope in FY22 - not closure * related *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073570&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073570 | Rolleston Line Fault Location | BW | ELECTRICAL | POWER SYSTEMS | FAULT LOCATORS | RENEWAL | 11 | UNIT | 200000 | Blackwater | KINROLA | ROLLESTON | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Fault Locator Install | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20240630 | * 03.03.2021 14:39:15 AUSQLD Nigel McDowell (R885053) * Initial high-level N4 created. * Install and commission fault location system on Rolleston Line. * 10.03.2021 13:22:45 AUSQLD Adrian Barnes (R886902) * Approximate quantity is six. This is to rectify the situation, since the existing protection relays (ICE) do not accurately report the fault location. * 12.04.2021 16:21:43 AUSQLD Jeremy Stevenson (R867415) * Std design with bespoke - FY22 design to confirm t his (PSE hasn't been completed) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074062&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074062 | BLACKRIDGE PSC LV EARTH SYSTEM | ST001360-02 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | BLACKRIDGE | BLACKRIDGE | 0 | KM | GA05ML85 | 0.4939 | GA05ML85 | 0.4939 | KM |  |  |  |  | 85.562 | 85.562 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230602 | * 12.03.2021 14:57:45 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:53 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:08 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074063&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074063 | BLACKRIDGE - BLAIR ATHOL PSC LV EARTH SY | ST001790-02 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | BLACKRIDGE - BLAIR ATHOL | BLACKRIDGE - BLAIR ATHOL | 0 | KM | GA05ML94 | 0.4879 | GA05ML94 | 0.4879 | KM |  |  |  |  | 94.548 | 94.548 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230604 | * 12.03.2021 14:57:56 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:57 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:08 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074044&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074044 | BOONAL PSC LV EARTH SYSTEM | ST001850-02 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | BOONAL | BOONAL | 0 | KM | BW03ML181 | 0.338 | BW03ML181 | 0.338 | KM |  |  |  |  | 181.291 | 181.291 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:27:43 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:27 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:02 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074046&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074046 | PS-AR-GA-E&B-Const-BL | ST001440-04 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML154 | 0.1739 | GA01ML154 | 0.1739 | KM |  |  |  |  | 153.997 | 153.997 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:28:15 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:23 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:02 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074055&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074055 | DUARINGA WALLAROO PSC LV EARTH SYSTEM | ST001940-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | DUARINGA WALLAROO | DUARINGA WALLAROO | 0 | KM | BW03ML111 | 0.0739 | BW03ML111 | 0.0739 | KM |  |  |  |  | 111.231 | 111.231 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230601 | * 12.03.2021 14:48:41 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:59 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:06 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074004&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074004 | EPALA PSC LV EARTH SYSTEM | ST001870-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | EPALA | EPALA | 0 | KM | BW01ML574 | 0.01 | BW01ML574 | 0.01 | KM |  |  |  |  | 571.663 | 571.663 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230603 | * 12.03.2021 14:01:04 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:35 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:01 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074040&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074040 | MIDGEE PSC LV EARTH SYSTEM | ST001900-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | MIDGEE | MIDGEE | 0 | KM | BW01ML624 | 0.379 | BW01ML624 | 0.379 | KM |  |  |  |  | 621.923 | 621.923 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 13:40:39 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:41 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:21:59 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074060&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074060 | MORANBAH - VILLAFRANCA PSC LV EARTH SYST | ST001290-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | MORANBAH - VILLAFRANCA | MORANBAH - VILLAFRANCA | 0 | KM | GA05ML37 | 0.4319 | GA05ML37 | 0.4319 | KM |  |  |  |  | 37.47 | 37.47 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230601 | * 12.03.2021 14:57:22 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:43 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:06 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074050&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074050 | MORANBAH VILLAFRANCA PSC LV EARTH SYSTEM | ST001280-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | MORANBAH VILLAFRANCA | MORANBAH VILLAFRANCA | 0 | KM | GA05ML28 | 0.7019 | GA05ML28 | 0.7019 | KM |  |  |  |  | 28.743 | 28.743 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:29:00 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:23 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:04 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074061&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074061 | MOUNT MCLAREN-BLACKRIDGE PSC LV EARTH SY | ST001340-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML65 | 0.9649 | GA05ML65 | 0.9649 | KM |  |  |  |  | 65.991 | 65.991 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230603 | * 12.03.2021 14:57:34 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:43 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:07 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074049&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074049 | NORWICH PARK PSC LV EARTH SYSTEM | ST001400-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | NORWICH PARK | NORWICH PARK | 0 | KM | GA03ML115 | 0.4 | GA03ML115 | 0.4 | KM |  |  |  |  | 115.34 | 115.34 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:28:46 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:07 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:04 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074045&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074045 | TRYPHINIA PSC LV EARTH SYSTEM | ST001950-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | TRYPHINIA | TRYPHINIA | 0 | KM | BW03ML125 | 0.7139 | BW03ML125 | 0.7139 | KM |  |  |  |  | 125.784 | 125.784 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:27:43 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:15 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:01 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074048&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074048 | WINCHESTER PSC LV EARTH SYSTEM | ST001800-02 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | WINCHESTER | WINCHESTER | 0 | KM | GA03ML30 | 0.017 | GA03ML30 | 0.017 | KM |  |  |  |  | 29.977 | 29.977 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:28:36 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:29 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:04 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074032&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074032 | WINDAH PSC LV EARTH SYSTEM | ST002140-01 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW03ML55 | 0.0929 | BW03ML55 | 0.0929 | KM |  |  |  |  | 54.1 | 54.1 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:17:19 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:18:38 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:01 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074047&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074047 | WOTONGA PSC LV EARTH SYSTEM | ST005310-01 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 30000 | Goonyella | WOTONGA | WOTONGA | 0 | KM | GA01ML184 | 0.8359 | GA01ML184 | 0.8359 | KM |  |  |  |  | 184.636 | 184.636 | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 12.03.2021 14:28:23 AUSQLD Tracy Holmes (R870040) * INSTALLATION OF ISOLATION TRANSFORMER TO REPLACE 'DIRECT EARTH' SYSTEM * 31.03.2021 19:19:30 AUSQLD Tracy Holmes (R870040) these. * 12.04.2021 16:22:02 AUSQLD Jeremy Stevenson (R867415) * No design complete - will be done in FY22 - No con tract set up for purchase these yet. New product t * ype of MRSB. No outages needed for these. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074287&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074287 | MI Design Only 901A/902L Grasstree | ST007640-08 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 42535 | Goonyella | GRASS TREE | GRASS TREE | 0 | KM | GA/9/605/U | 0 | GA/9/605/U | 0 | KM |  |  |  |  | 9.605 |  | 2023-06-30 |  |  |  |  | 3.2 | 4.6 |  |  |  | 14.7 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:20:10 AUSQLD Tracy Holmes (R870040) * 3 bespoke design to done FY22 1/4/2022 R.Licis: Scope and Renewal Inspection form attached.This is a bespoke design. 9/9/2022 R.Licis: This notification is now a Design only N4 notification. Actual renewal itself will be done in FY25 (new noti). PM to update unit cost in SPM. PM to update SAP budget accordingly. PCR 5459 lodged for PM approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074360&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074360 | MI Design Only 911H/912A Grasstree | ST007640-07 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 42535 | Goonyella | GRASSTREE | GRASSTREE | 0 | KM | GA/9/595/D | 0 | GA/9/595/D | 0 | KM |  |  |  |  | 9.605 |  | 2023-06-30 |  |  |  |  | 3.2 | 2.3 |  |  |  | 7.4 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:20:20 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 1/4/2022 R.Licis: Scope and Inspection form attached. This is a bespoke design. 9/9/2022 R.Licis: This notification is now a Design only N4 notification. Actual renewal itself will be done in FY25 (new noti). PM to update unit cost in SPM. PM to update SAP budget accordingly. PCR 5461 lodged for PM approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044403&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044403 | MI Renewal 155/20 Boorgoon | SQ030057 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | BOORGOON | BOORGOON | 0 | KM | BG/0/044/BL | 0 | BG/0/044/BL | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.7 | 1.5 |  |  |  | 5.6 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:37:04 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:55 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * Scope: C Type (BOM Attached) WBS: IV.00824.E.D.BW.01.CO 26/6/2023 R.Licis: ZPM_N4_MI added.QA attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044464&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044464 | MI Renewal 231/5 Coppabella | SQ030279 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA/142/671/U | 0 | GA/142/671/U | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:46:10 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:58 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 1/4/2022 R.Licis: Scope and inspection form attached. Scope type is type D2 generic template for LS150 mast. 11/4/2022 R.Licis Scope: D2 LS150 WBS: IV.00824.E.D.GA.01 30/01/2023 R.Christensen D2 IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044463&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044463 | MI Renewal 231/6 Coppabella | SQ030278 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA/145/391/D | 0 | GA/145/391/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:45:13 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:56 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * Scope: D1 LS150 WBS:IV.00824.E.D.GA.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044462&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044462 | MI Renewal 232/7 Coppabella | SQ030267 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA/142/874/D | 0 | GA/142/874/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:44:13 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:56 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 1/4/2022 R.Licis: Scope and inspection form attached. Scope is type F1 double 11/4/2022 R.Licis: Scope: F1 Double WBS: IV.00824.E.D.GA.01 10/10/2022 K.Robinson: 232_7 MI Renewal completed on 4/10/2022. Completed QA attached 10/10/22. Isolator wasn't D1 and had to be mod ified on site. Feeds remained the same but everything else was replaced.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044461&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044461 | MI Renewal 232/8 Coppabella | SQ030266 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA/142/571/D | 0 | GA/142/571/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:42:06 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:56 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 1/4/2022 R.Licis: Scope and inspection form attached. Scope type is D1 for LS150 mast 11/4/2022 R.Licis: Scope: D1 LS150 WBS: IV.00824.E.D.GA.01 30/01/2023 R.Christensen D1 IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093654&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093654 | NI Renewal 231A/232H South Walker TSC | ST006540-05 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML127 | 0.113 | GA01ML127 | 0.113 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC | FY23 IN | 20230630 | 18/3/2022 R.Licis: Scope Inspection forms attached for FY23 1/4/2022 R.Licis: This is a type F4 scope. 11/4/2022 R.Licis: Scope: F4 DOUBLE NON-POLLUTED WBS: IV.00824.E.D.GA.06
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093655&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093655 | NI Renewal 232H/233A South Walker TSC | ST006540-04 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML127 | 0.1089 | GA01ML127 | 0.1089 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC | FY23 IN | 20230630 | 18/3/2022 R.Licis: Scope Inspection forms attached for FY23. 1/4/2022 R.Licis: Scope is type F4 11/4/2022 R.Licis Scope:F4 DOUBLE NON-POLLUTED WBS: IV.00824.E.D.GA.06
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093653&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093653 | NI Renewal 281B/282A South Walker TSC | ST006540-03 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML127 | 0.098 | GA01ML127 | 0.098 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC | FY23 IN | 20230630 | 18/3/2022 R.Licis: Scope Inspection forms attached for FY23 1/4/2022 R.Licis: Scope is type F4 11/4/2022 R.Licis: Scope: F4 Double Non-Polluted WBS: IV.00824.E.D.GA.06
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075921&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075921 | MI Renewal 912/9 Dalrymple | SQ030501 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0 | KM | DL/3/933/DR3 | 0 | DL/3/933/DR3 | 0 | KM |  |  |  |  | 3.933 | 3.933 | 2024-06-30 |  |  |  |  | 3.44 | 2.6 | 2 |  | 1 | 11.35 | 5681 |  |  | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230712 | 11/3/2022 R.Licis: Scope and inspection forms attached. 17/3/2022 R.Licis: Inspected scope attached to noti. This noti is moved to FY23 to replace 912/7 DalyBay (originally in FY23). 1/4/2022 R.Licis: Scope is type C 11/4/2022 R.Licis: Scope: Type C WBS:IV.00824.E.D.GA.02 30/01/2023 R.Christensen: C IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093614&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093614 | MI Renewal 906/3 Jilalan | SQ030565 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54828 | Goonyella | JILALAN |  | 0 | KM | GA/20/190/PR2 | 0 | GA/20/190/PR2 | 0 | KM |  |  |  |  | 20.265 |  | 2022-06-30 |  |  |  |  | 2.9 | 1.9 |  |  |  | 5.51 |  | 2020-03-06 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230630 | 18/1/2022 R.Licis: N4 created. Inspection done. Scope attached.Renewal in FY23 1/4/2022 R.Licis: Scope is type C 11/4/2022 R.Licis Scope: C Type WBS: IV.00824.E.D.GA.04 30/01/2023 R.Christensen: C IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093615&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000093615 | MI Renewal 907/2 Jilalan | SQ030568 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54828 | Goonyella | JILALAN |  | 0 | KM | GA/20/239/PR1 | 0 | GA/20/239/PR1 | 0 | KM |  |  |  |  | 20.265 |  | 2022-06-30 |  |  |  |  | 2.9 | 1.9 |  |  |  | 5.51 |  | 2020-03-06 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230630 | 18/1/2022 R.Licis: N4 created. Inspection done. Scope attached.Renewal in FY23 1/4/2022 R.Licis: Scope is type C 11/4/2022 R.Licis: Scope: C Type WBS: IV.00824.E.D.GA.04 30/01/2023 R.Christensen: C IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074289&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074289 | MI Renewal 901/4 Jilalan | SQ030561 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 56086 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/634/U | 0 | GA/17/634/U | 0 | KM |  |  |  |  | 17.634 |  | 2024-06-30 |  |  |  |  | 4 | 4.8 | 2 | 4.2 | 1 | 16.8 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Notification completed | SCPR |  | 20230630 | ZH: Corrective 2000092900 is open on this MI. 29/6/2022 R.Licis: Zane Hooton has requested that this MI at Jilalan 901/4 is swapped into FY23 MI Renewal and swap out Jilalan 902K/904H at to FY24. PCR number to be advised. Therefore Jilalan 901/4 to be done in FY23 now. Scope type for Jilalan 901/4 is F4. Bill of material attached. 5/8/2022 R.Licis: PCR number is 5432
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075927&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000075927 | MI Renewal 902/5 Jilalan | SQ030543 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54380 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/522/DM | 0 | GA/22/522/DM | 0 | KM |  |  |  |  | 22.522 | 22.522 | 2023-06-30 |  |  |  |  | 3.44 | 4.8 | 2 | 4.2 | 1 | 14.45 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | SCPR |  | 20230630 | 11/3/2022 R.Licis: Scope and inspection form attached. 17/10/2022 R.Licis: This is brought earlier to FY22 as it was instrumental to renewing an existing FY23 MI at Jilalan. PCR 5476 subm itted and BOM attached. WBS: IV.00824.E.D.GA.04.CO Scope type F4 22/12/2022 K.Robinson. C-type. Stanger blade already present. QA attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044522&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044522 | MI Renewal 901/7 Jilalan | SQ030553 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/23/406/UM | 0 | GA/23/406/UM | 0 | KM |  |  |  |  | 23.406 |  | 2023-06-30 |  |  |  |  | 2.9 | 4.8 |  |  |  | 13.9 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:44:10 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 901/7 * 22.03.2021 16:10:11 AUSQLD Rinaldo Licis (R851602) * MI 901/7 swapped with MI 632/25. MI 901/7 to be renewed in FY23 * 12.04.2021 16:21:47 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * R.Licis 11/4/2022 Scope: C Type WBS: IV.00824.E.D.GA.04 30.01.2023 R.Christensen: C IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075943&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000075943 | MI Renewal 622/2 Burton/Mallawa | SQ030207 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA/173/739/D | 0 | GA/173/739/D | 0 | KM |  |  |  |  | 173.739 | 173.739 | [5 empty] | 3.02 | [5 empty] | 5073 |  |  | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20230224 | 23/11/2021 R.Licis: 622/2 Mallawa (FY25) swapped with 241B/242C (FY22)as per PCR 5073. Mod-ID on this notification changed from FY25 to FY22.WBS to be updated. 12/9/2022 R.Licis: PM has requested to move 622/2 MI renewal to FY25. PCR 5463 submitted. 30/01/2023 R.Christensen: B2 IFC Drawing attached 6/2/2023: R.Licis: 622/2 Mallawa moved from FY25 to FY23 due to corrective issue of isolator unable to be opened. Isolator has been DNOB'd. It will be swapped with Tootoolah 232/9 currently in FY23. Scope for both is identical B2 double, therefore no cost issue. PM has been made aware of Ryan Christensen. PCR 5598 has been lodged
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074281&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000074281 | MI Renewal 551/8 Midgee | SQ030174 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | MIDGEE | MIDGEE | 0 | KM | N/622/940/U | 0 | N/622/940/U | 0 | KM |  |  |  |  | 622.94 |  | 2023-06-30 |  |  |  |  | 3.4 | 4.1 |  |  |  | 13.9 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:20:44 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 11/4/2022 R.Licis: Scope: C Type WBS: IV.00824.E.D.BW.02.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044476&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044476 | MI Renewal 281/2 Mindi | SQ030282 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MINDI | MINDI | 0 | KM | GA/120/597/U | 0 | GA/120/597/U | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.8 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:48:54 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:59 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 1/4/2022 R.Licis: Scope and Inspection form attached. Scope type is D1 generic template for LS127 mast 11/4/2022 R.Licis: Scope: D1 LS127 WBS: IV.00824.E.D.GA.05 30/01/2023 R.Christensen D1 IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044474&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044474 | MI Renewal 282/3 Mindi | SQ030274 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MINDI | MINDI | 0 | KM | GA/120/472/D | 0 | GA/120/472/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.6 | 1.9 |  |  |  | 8.7 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20230630 | * 10.11.2020 14:47:08 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:58 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * Scope: D2 LS150 WBS: IV.00824.E.D.GA.05 Note that corrective 2000092298 is open on this FLOC. 30/01/2023 R.Christensen D2 IFC Drawing attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091896&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000091896 | MI Renewal 521/2 Mt Larcom | SQ030148 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | MT LARCOM | MT LARCOM | 0 | KM | N/566/770/U | 0 | N/566/770/U | 0 | KM |  |  |  |  | 566.77 | 566.77 | 2023-06-30 |  |  |  |  | 4.09 | 4.1 |  |  |  | 16.77 |  |  |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC | FY23 OUT | 20230630 | 15/2/2022 R.Licis: N4 created for FY24 2/3/2022 R.Licis: Inspection and Scope attached 6/3/2022 R.Licis: This is one to replace Rockland 551/5 (originally in FY23). Due to access issue Rockland 551/5 will be FY25. Ladder renewal design will be done in FY24. Therefore 521/5 Mt Larcom will be done in FY23 now. 11/4/2022 R.Licis: Scope: H2 DOUBLE POLLUTED ,FW IN FRONT WBS:IV.00824.E.D.BW.07.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044437&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044437 | MI Renewal 551/6 Rockland | SQ030168 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/532/U | 0 | N/631/532/U | 0 | KM |  |  |  |  | 631.532 |  | 2023-06-30 |  |  |  |  | 2.8 | 4.5 |  |  |  | 12.6 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:41:35 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 551/6 * 22.03.2021 15:34:01 AUSQLD Rinaldo Licis (R851602) * MI 551/6 at Rockland (FY22) swapped with Rockland 101A/102G (FY21). MI 551/6 to be renewed in FY23 now * 12.04.2021 16:21:46 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 11/4/2022 R.Licis: Scope: A2 Type (BOM Attached) WBS: IV.00824.E.D.BW.03.co 28/08/22 GK: Completed in August system closure documents attached to noti. New switch label has been ordered waiting for arrival. Clearance issue of 295mm from tip of switch blade in open position to above feed please see attached photo in noti.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044438&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044438 | MI Renewal 551E/552D Rockland | SQ030734 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/590/D | 0 | N/631/590/D | 0 | KM |  |  |  |  | 631.59 |  | 2023-06-30 |  |  |  |  | 2.7 | 4.5 |  |  |  | 12.2 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:42:07 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 551E/552D * 22.03.2021 15:39:18 AUSQLD Rinaldo Licis (R851602) * MI 551E/552D at Rockland swapped with 551A/552E. MI 551E/552D to be renewed in FY23. * 12.04.2021 16:21:46 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 11/4/2022 R.Licis Scope: B1 Type WBS:IV.00824.E.D.BW.03 11/7/2022 R.Licis: PCR 5406 submitted for Rockland 551E/552D MI Renewal Transferred to FY23 28/08/22 GK: Completed in August system closure See attached documents in Noti. New isolator label has been ordered waiting for arrival to complete.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044439&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044439 | MI Renewal 552/5 Rocklands | SQ030182 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | CW/631/641/U | 0 | CW/631/641/U | 0 | KM |  |  |  |  | 631.641 |  | 2023-06-30 |  |  |  |  | 4.1 | 1.5 |  |  |  | 6.2 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:43:33 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 552/5 * 22.03.2021 16:06:08 AUSQLD Rinaldo Licis (R851602) * MI 552/5 to be swapped with MI 122/5. MI 552/5 to be renewed in FY23 * 12.04.2021 16:21:47 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * Issue with ladder access. Ladder may need to be renewed. See photo attahced. Inspection to be done early March 2022. Potentially swap with Mt Larcom 522/8. Propose ladder design in FY24 and construction of ladder and renewing of MI in FY25 2/3/2022 R.Licis: Inspected. No ladder is required. 11/4/2022 R.Licis: Scope: A2 Type (bom attached) WBS: IV.00824.E.D.BW.03 11/7/2022 R.Licis: PCR-5407 submitted for 552/5 to be done in FY23 28/08/22 GK: Completed in the August system closure documents attached to Noti. New switch label has been ordered waiting for arrival.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044440&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044440 | MI Renewal 551E/553C Rockland | SQ030177 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/792/U | 0 | N/631/792/U | 0 | KM |  |  |  |  | 631.792 |  | 2023-06-30 |  |  |  |  | 4.5 | 1.5 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:42:43 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 551E/553C * 22.03.2021 15:44:21 AUSQLD Rinaldo Licis (R851602) * MI 551E/553C at Rockland to be swapped with MI 121/2 Grantleigh East. MI 551E/553C to be renewed in FY23. * 12.04.2021 16:21:47 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 11/4/2022 R.Licis: Scope: H1 Single Polluted WBS: IV.00824.E.D.BW.03 11/7/2022 R.Licis: PCR 5408 submitted for renewal of MI in FY23
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044442&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044442 | MI Renewal 551/4 Rockland | SQ030170 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/966/U | 0 | N/631/966/U | 0 | KM |  |  |  |  | 631.966 |  | 2023-06-30 |  |  |  |  | 4.1 | 1.5 |  |  |  | 6.2 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 06.03.2020 14:40:28 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 551/4 * 22.03.2021 15:14:52 AUSQLD Rinaldo Licis (R851602) * MI 551/4 at Rockland swapped with MI 161/8 at Ensham. 551/4 to be done in FY23. * 12.04.2021 16:21:44 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 11/4/2022 R.Licis: Scope: H1 SINGLE POL (BOM attached) WBS:IV.00824.E.D.BW.03 11/7/2022 R.Licis: PCR 5410 submitted for 551/4 to be done in FY23
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092791&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000092791 | MI Renewal 822/6 Wycarbah | SQ030023 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WARREN | WARREN | 0 | KM | CW/36/234/D | 0 | CW/36/234/D | 0 | KM |  |  |  |  | 25.152 |  | 2023-06-30 |  |  |  |  | 3.4 | 3.4 |  |  |  | 11.6 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | NWSC | FY23 IN | 20230630 | 4/3/2022 R.Licis: N4 Created for FY23. This was replacing 811/4 Warren (from FY23). Scope and pictures attached. 8/2/2022 R.Licis: Scope attached after inspection 11/4/2022 R.Licis: Scope: C Type WBS: IV.00824.E.D.BW.06.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044444&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044444 | MI Renewal 821/3 Westwood | SQ030012 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | CW/45/834/U | 0 | CW/45/834/U | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.9 | 3.4 |  |  |  | 13.3 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:21:42 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) WBSE: IV.00824.E.D.BW.05.CO R.Licis 11/4/2022: Scope Type: B2 Double (BOM attached) WBSE: IV.00824.E.D.BW.05 13/4/2022 R.Licis: Updated the B2 double bill of material. See updated attachment in noti. Updated the BOM in WO (Component tab): - Increased isolator lug 65010651 from qty 2 to 4 27/07/22 GK: Completed in July system closure Mtce sheet attached to Noti.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044446&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044446 | MI Renewal 821/4 Westwood | SQ030013 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | CW/47/422/U | 0 | CW/47/422/U | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.6 | 3.4 |  |  |  | 15.6 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240206 | * 31.03.2021 19:21:47 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 11/4/2022 R.Licis: Scope: H2 Double Non-Polluted WBS: IV.00824.E.D.BW.05.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044447&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044447 | MI Renewal 822/2 Westwood | SQ030019 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | CW/47/422/D | 0 | CW/47/422/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4.6 | 3.4 |  |  |  | 15.6 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20240206 | * 31.03.2021 19:21:56 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 11/4/2022 R.Licis: Scope: H2 Double Non-Polluted WBS: IV.00824.E.D.BW.05.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044445&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044445 | MI Renewal 822/4 Westwood | SQ030021 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | CW/45/834/D | 0 | CW/45/834/D | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.9 | 3.4 |  |  |  | 13.3 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:21:44 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 11/4/2022 R.Licis: Scope: B2 Double (BOM Attached) WBS:IV.00824.E.D.BW.05.CO 13/4/2022 R.Licis: Updated the B2 double bill of material. See updated attachment in noti. Also updated the BOM in WO (Component tab): - Changed single pole 55013298 to double pole 55013785 - Increased isolator lug 65010651 from qty 2 to 4 27/07/22 GK: Completed in July system closure mtce sheet uploaded to Noti.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044443&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044443 | MI Renewal 822/5 Westwood | SQ030022 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | CW/45/384/R | 0 | CW/45/384/R | 0 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.9 | 3.4 |  |  |  | 13.3 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification completed | RRIG | FY23 IN | 20230630 | * 31.03.2021 19:21:32 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 11/4/2022 R.Licis: Scope: B2 Single WBS: IV.00824.E.D.BW.05.CO Primary Scope 1. Convert MI Box to Manual to Isolator 2. Replace existing Haycolec isolator blade with Stanger type and keep support steelwork. 4. Install new isolator guide tube 5. Disconnect MI cables at MI and PSC 6. Update SCADA I/O 7. Use bird nest deterrent (Firefly) on isolator 8. Isolation Diagram, Asbuilt and NAMS Update Design Type: B2 VARIANT 3 27/07/22 GK - Completed in July system closure Mtce sheet uploaded to Noti.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044492&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  |  | 002000044492 | MI Renewal 201/4 at Yukan Yard GA29k275 | SQ030308 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 22000 | Goonyella | YUKAN |  | 0 | KM | GA/29/275/U | 0 | GA/29/275/U | 0 | KM | [6 empty] | 2021-06-30 |  |  |  |  | 4.1 | 1.9 |  |  |  | 7.79 |  | 2019-07-15 | 2019-11-29 | Other Power Systems Renewals | HEAVY MAINTENANCE |  |  |  |  | Notification in process | SCPR |  | 20230630 | 13/9/2021 R.Licis: STATUS 1. Work cancelled. Unable to secure NCL access from QE 2. Awaiting advise from PM to move this FY22 MI Renewal 3. Tentatively programmed for May 2022. All materials have been received. 4. Notification was put in process again. Dates and MOD ID to be updated once given the go ahead by PM. 25/10/2021 R.Licis MI Renewal design drawing attached to notification (3 dwgs) 09/02/22 MOD-ID pushed to 2025, to be updated when scheduled 8/6/22 Noti and WO were PCOM / closed by mistake, this work was not executed. Set Mod ID to FY22 to have this addressed. 21/7/2022 R.licis: Net Ops is planning to install this in FY23. A window in March 2023 is likely. Currently stock taking the material required for this work. Will create a PCR once this is confirmed. 9/9/2022 R.Licis: PM has requested that this renewal is to be done in FY23. PCR 54622 lodged. 10/10/2022 K.Robinson: Yukan 201_4 switch renewal completed on 3/10/22. Completed QA attached 10/10/2022. Potentially some clearance issues still need rectification. Photos provided.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073495&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073495 | BOLINGBROKE 60.573km PSC BATT CHARGER | ST001610-02 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML60 | 0.5729 | GA01ML60 | 0.5729 | KM |  |  |  |  | 60.573 |  | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 02.03.2021 14:54:25 AUSQLD Adrian Barnes (R886902) * RENEWAL OF PSC BATTERY CHARGER. NOTE THERE IS ALSO AN N4 FOR THE PSC BUILDING (2000073494). BOTH THIS AND THAT N4 MAY NOT PROCEED IF DC IS AVAILABLE FROM NEARBY SER. INVESTIGATE DURING DETAILED SCOPING. * 12.04.2021 16:21:41 AUSQLD Jeremy Stevenson (R867415) * Std design (IFC due Q4 21) - long lead item (need cash flow released) * * This PSC is adjacent to a SER which will be renewed. It is feasible to move the equipment (RTU, DC distribution board) into this new SER, and install a dc-dc converter, negating the need for a new DC system. A PCR will be raised to remove this N4 from FY24. -Adrian Barnes, Aug 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044542&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044542 | BOONAL PSC BATTERY CHARGER | ST001980-06 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Blackwater | BOONAL | BOONAL | 0 | KM | BW03ML179 | 0.448 | BW03ML179 | 0.448 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.4 |  |  |  | 13.6 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 10.03.2021 15:56:37 AUSQLD Adrian Barnes (R886902) * Renewal of PSC battery charger (NIFE) * 12.04.2021 16:21:55 AUSQLD Jeremy Stevenson (R867415) * Std design (IFC due Q4 21) - long lead item (need cash flow released) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073499&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073499 | BOORGOON 9.61KM PSC BATTERY CHARGER | ST002290-02 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Blackwater | BOORGOON | BOORGOON | 0 | KM | BW05ML9 | 0.6099 | BW05ML9 | 0.6099 | KM |  |  |  |  | 9.61 |  | 2023-06-30 |  |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 02.03.2021 15:56:38 AUSQLD Adrian Barnes (R886902) * RENEWAL OF PSC BATTERY CHARGER AT BOORGOON 9.610KM ON KA LINE. * 12.04.2021 16:21:43 AUSQLD Jeremy Stevenson (R867415) * Std design (IFC due Q4 21) - long lead item (need cash flow released) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073498&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073498 | BURNGROVE PSC BATTERY CHARGER | ST000070-12 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Blackwater | BURNGROVE | BURNGROVE | 0 | KM | BW03ML202 | 0.5 | BW03ML202 | 0.5 | KM |  |  |  |  | 202.5 |  | 2023-06-30 |  |  |  |  | 4 | 2.1 |  |  |  | 8.4 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 02.03.2021 15:51:12 AUSQLD Adrian Barnes (R886902) * RENEWAL OF PSC BATTERY CHARGER * 12.04.2021 16:21:41 AUSQLD Jeremy Stevenson (R867415) * Std design (IFC due Q4 21) - long lead item (need cash flow released) * * Note that after TCU circuit breakers are decommissioned, this DC supply will supply the MI and CD. Note: Attached LV circuit is to be used a guide only. The circuits at this site are sliightly different. Plaease as-built this drawing to reflect the actual wiring on site. Works completed by Justin Lynam - Closed out today 05.08.2022
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043298&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000043298 | MACKENZIE PSC BATTERY CHARGER | ST002060-04 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Blackwater | MACKENZIE | MACKENZIE | 0 | KM | BW08ML25 | 0.556 | BW08ML25 | 0.556 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 1.1 |  |  |  | 4.4 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:23:09 AUSQLD Tracy Holmes (R870040) * Std design (IFC due Q4 21) - long lead item (need cash flow released)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044559&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000044559 | MALLAWA PSC BATTERY CHARGER | ST001450-04 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML168 | 0.1779 | GA01ML168 | 0.1779 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 31.03.2021 19:23:22 AUSQLD Tracy Holmes (R870040) * Std design (IFC due Q4 21) - long lead item (need cash flow released) 31.03.2021 19:23:22 AUSQLD Tracy Holmes (R870040) Std design (IFC due Q4 21) - long lead item (need cash flow released)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073491&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073491 | MORANBAH NTH 0.512KM PSC BATTERY CHARGER | ST005320-01 | ELECTRICAL | POWER SYSTEMS | PSC BATTERY CHARGER | RENEWAL | 1 | SITE | 30000 | Goonyella | MORANBAH NORTH | MORANBAH NORTH | 0 | KM | GA12ML0 | 0.514 | GA12ML0 | 0.514 | KM |  |  |  |  | 0.512 |  | 2023-06-30 |  |  |  |  | 4 | 2.9 |  |  |  | 11.6 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 02.03.2021 14:21:34 AUSQLD Adrian Barnes (R886902) * Renewal of SAB NIFE battery charger at Moranbah North PSC 0.512 km on GA * 12.04.2021 16:21:40 AUSQLD Jeremy Stevenson (R867415) * Std design (IFC due Q4 21) - long lead item (need cash flow released) * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073494&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000073494 | BOLINGBROKE 60.573km PSC RENEWAL | ST001610-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML60 | 0.5729 | GA01ML60 | 0.5729 | KM |  |  |  |  | 60.573 |  | 2023-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2021-03-31 | 2021-10-05 | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification completed | RRIG INIF | FY23 IN | 20230630 | * 02.03.2021 14:42:29 AUSQLD Adrian Barnes (R886902) * RENEWAL OF PSC BUILDING AND CHARGER. DURING DETAILED SCOPING, DETERMINE IF NEARBY SER CAN BE USED AS DC SUPPLY, IF SO, THIS PSC MAY BE DECOMMISSIONED INSTEAD. * 10.03.2021 15:42:26 AUSQLD Adrian Barnes (R886902) * This N4 is for the building only. The N4 for the charger is 2000073495 * 12.04.2021 16:21:41 AUSQLD Jeremy Stevenson (R867415) * Scope still needs to be determined if it is PSE or PSC standard replacement (could have long lead ti * me and change in cost if this changes) * This PSC (Bolingbroke 60.573) is adjacent to a SER that will be renewed, the equipment (RTU, DC distribution board) will be moved into that SER, and the power and control cables (to motorised isolators) will be extended to that new building. This N4 will be repurposed from RENEWAL to DESIGN, to prepare for the renewal of Jilalan yard 21.971 km PSC (RENEWAL N4 2000081064). -Adrian Barnes August 2022
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072782&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072782 | MO/401 Protection Relay Design | ST000780-16 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.9 |  |  |  | 10.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072783&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072783 | MO/411 Protection Relay Design | ST000780-17 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.9 |  |  |  | 10.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072784&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072784 | MO/BS1-2 Protection Relay Design | ST000780-18 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.9 |  |  |  | 10.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072768&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072768 | SI/311 Protection Relay Design | ST000740-10 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.8 |  |  |  | 6.3 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072780&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072780 | SI/321 Protection Relay Design | ST000740-11 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.8 |  |  |  | 6.3 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072781&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072781 | SI/BS1-2 Protection Relay Design | ST000740-12 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | SITE | 12000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.8 |  |  |  | 6.3 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072763&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072763 | GC/191 Protection Relay Renewal | ST000760-12 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.4 | 1.4 |  |  |  | 4.8 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:23:36 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072761&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072761 | GC/331 Protection Relay Renewal | ST000760-11 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 12000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 4.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:23:37 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072764&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072764 | GC/BS1-2 Protection Relay Renewal | ST000760-13 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.4 |  |  |  | 4.9 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:23:49 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072443&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072443 | RR/161 Protection Relay Renewal | ST000090-14 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Blackwater | RED ROCK | RED ROCK | 0 | KM | BW08ML42 | 0.14 | BW08ML42 | 0.14 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.1 |  |  |  | 7.4 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:23:50 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072442&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072442 | RR/181 Protection Relay Renewal | ST000090-13 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Blackwater | RED ROCK | RED ROCK | 0 | KM | BW08ML42 | 0.14 | BW08ML42 | 0.14 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.1 |  |  |  | 7.4 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:23:52 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072441&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072441 | RR/BS1-2 Protection Relay Renewal | ST000090-12 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Blackwater | RED ROCK | RED ROCK | 0 | KM | BW08ML42 | 0.14 | BW08ML42 | 0.14 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 2.1 |  |  |  | 7.4 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:24:04 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072765&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072765 | VA/411 Protection Relay Renewal | ST000790-10 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Goonyella | VILLAFRANCA | VILLAFRANCA | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 4.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:24:05 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072766&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072766 | VA/421 Protection Relay Renewal | ST000790-11 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Goonyella | VILLAFRANCA | VILLAFRANCA | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 4.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:24:06 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072767&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072767 | VA/BS1-2 Protection Relay Renewal | ST000790-12 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Goonyella | VILLAFRANCA | VILLAFRANCA | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 4.2 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:24:18 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072440&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000072440 | YY/189 Protection Relay Renewal | ST000460-11 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | SITE | 47000 | Blackwater | YAN YAN | YAN YAN | 0 | KM | BW10ML0 | 0.1179 | BW10ML0 | 0.1179 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 3.5 | 1.1 |  |  |  | 3.9 |  | 2021-03-31 | 2021-10-05 | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20240630 | * 31.03.2021 19:24:18 AUSQLD Tracy Holmes (R870040) * Design in FY22 (based on FY21 design) - still have changes to discuss to this design based on learnings from FY21 thus can change, scope, cost <(>&<)> duration
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071454&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071454 | Substation Renewals Program | BW | ELECTRICAL | POWER SYSTEMS | SUBSTATION RENEWALS | DESIGN | 1 | UNIT | 500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Traction Substation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20240329 | * 09.03.2021 16:00:25 AUSQLD Rebecca Green (R882642) * There are 22 AIS substations planned for renewal over the next decade. The FY23 scope will be refined following the concept study and discussions with the RIG being undertaken in FY21.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071453&DY_MAB=X&~OKCODE=ONLI | FY23 |  |  | COAL | 002000071453 | Substation Renewals Program | GA | ELECTRICAL | POWER SYSTEMS | SUBSTATION RENEWALS | DESIGN | 1 | UNIT | 500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Traction Substation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 IN | 20240329 | * 09.03.2021 16:01:01 AUSQLD Rebecca Green (R882642) * There are 22 AIS substations planned for renewal over the next decade. The FY23 scope will be refined following the concept study and discussions with the RIG being undertaken in FY21.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094589&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094589 | C60-ACP-BW-km | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094611&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094611 | C60-ACP-GA-km | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094613&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094613 | C60-ACP-MA-km | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 50000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094612&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094612 | C60-ACP-NL-km | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094342&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094342 | C60-ACP-BW-RAGLAN-586.058km | BW-01CR | CIVIL | ACCESS POINTS | EARTHWORKS | RENEWAL | 1 | UNIT | 23951 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01ML586 | 0.058 | BW01ML586 | 0.058 | KM |  |  |  |  | 586.058 | 586.058 | 2024-06-30 |  |  |  |  | 0 | 10 | 1 | 0 | 1 | 100 |  | 2022-03-31 |  | Access Points & Rds | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is a Civil N4 renewal created to alter an existing embankment to create space for isolator operator on OHW portal mast N/586/058 Raglan. Associated isolator number is 542/3 Attached is the scope and estimate provided by Evan Zhou (Civil Engineering). This work will likely to be done at the same at time with notification 2000094343. Construction to be managed by Nathan McCosker's team
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094343&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094343 | C60-ACP-BW-RAGLAN-586.091km | BW-01CR | CIVIL | ACCESS POINTS | EARTHWORKS | RENEWAL | 1 | UNIT | 13446 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01ML586 | 0.0909 | BW01ML586 | 0.0909 | KM |  |  |  |  | 586.091 | 586.091 | 2024-06-30 |  |  |  |  | 0 | 10 | 1 | 0 | 1 | 100 |  | 2022-03-31 |  | Access Points & Rds | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is a Civil N4 renewal created to alter an existing mini retaining wall to create space for isolator operator on OHW portal mast N/586/091 Raglan. Associated isolator number is 542/4 Attached is the scope and estimate provided by Evan Zhou (Civil Engineering). This work will likely to be done at the same at time with notification 2000094342. Construction to be managed by Nathan McCosker's team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094588&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000094588 | C60-ACP-MA-BELLDEEN-156.087km | AP400037 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML156 | 0.0869 | MA01ML156 | 0.0869 | KM |  |  |  |  | 156.087 | 156.087 | 2024-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 | 5757 | 2022-03-31 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | AP400037 MA 156.087km Dawson Hwy Belldeen Access Point Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121158&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000121158 | C60-ACP-GA-DALY BAY-9.523km | AP200121 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA02ML9 | 0.523 | GA02ML9 | 0.523 | KM |  |  |  |  | 9.523 | 9.523 | 2024-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 | 5757 |  |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | FY24 ACCESS POINT DESIGN- IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094585&DY_MAB=X&~OKCODE=ONLI | FY24 | Dual Traffic | FUTURE SCOPE | COAL | 002000094585 | C60-ACP-BW-RAGLAN-591.798km | AP100303 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW02ML591 | 0.798 | BW02ML591 | 0.798 | KM |  |  |  |  | 591.798 | 591.798 | 2024-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 | 5757 | 2022-03-31 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | AP100303 at 591.798km Capricorn Highway (Marble Creek)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094587&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000094587 | C60-ACP-NL-SONOMA-91.379km | AP300142 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands | SONOMA | BIRRALEE | 0 | KM | NL01ML91 | 0.379 | NL01ML91 | 0.379 | KM |  |  |  |  | 91.379 | 91.379 | 2024-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 | 5757 | 2022-03-31 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Design Bowen Development Road Birralee Desktop review limited due to no google street view in Newlands system beyond 29km. This Access Point is on TMR road corridor so will require road safety audit by an approved contractor (where further information will be gathered).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094261&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094261 | C60-ACP-BW-ROCKLANDS-631.792km | BW-01CR | CIVIL | ACCESS POINTS | IFP - STAIRS | DESIGN | 1 | UNIT | 25335 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW01ML631 | 0.8 | BW01ML631 | 0.8 | KM |  |  |  |  | 631.792 | 631.792 | 2024-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2022-03-31 |  | Access Points & Rds | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is a Civil Design N4 notification created to renew an existing stairs (NCL 631k800 Down)connecting the access road at the top of embankment down to 551/5 isolator mast at N/631/792/D. The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Engineering) attached as well.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094315&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094315 | C60-ACP-BW-ROCKLANDS-1.533km | BW-03CR | CIVIL | ACCESS POINTS | IFP - WALKWAY | DESIGN | 1 | UNIT | 7056 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.533 | BW03ML1 | 0.533 | KM |  |  |  |  | 1.533 | 1.533 | 2024-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2022-03-31 |  | Access Points & Rds | STRATEGIC | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is a Civil Design Only N4 notification created to design a walkway platform from the top of embankment of Rockland TSC to mast CW/1/553/U The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Eng ineering) attached as well. Another design walkway associated to this noti is 2000094316 (also at Rockland TSC). Design Estimate attached was therefore halved.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094316&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094316 | C60-ACP-BW-ROCKLANDS-1.588km | BW-03CR | CIVIL | ACCESS POINTS | IFP - WALKWAY | DESIGN | 1 | UNIT | 7056 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.558 | BW03ML1 | 0.558 | KM |  |  |  |  | 1.588 | 1.588 | 2024-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2022-03-31 |  | Access Points & Rds | STRATEGIC | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is a Civil Design Only N4 notification created to design a walkway platform from the top of embankment of Rockland TSC to mast CW/1/558/U The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Eng ineering) attached as well.Another design walkway associated to this noti is 2000094315(also at Rockland TSC). Design Estimate attached was therefore halved.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068902&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000068902 | Access Roads Reactive | BW | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 325000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068903&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000068903 | Access Roads Reactive | GA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 285000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068905&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000068905 | Access Roads Reactive | MA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 185000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068904&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000068904 | Access Roads Reactive | NL | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 175000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110777&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000110777 | C14-UC-MOURA-MONUMENTING | MA | CIVIL | BALLAST UNDERCUTTING |  |  | 1 | EA | 150000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [18 empty] | 5572 |  |  | Mainline Excavator Undercutting - C14 |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20240630 | Notification to cover surveying and monumenting where monuments are not existing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110778&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000110778 | C14-UC-NEWLANDS-MONUMENTING | NL | CIVIL | BALLAST UNDERCUTTING |  |  | 1 | EA | 150000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [18 empty] | 5572 |  |  | Mainline Excavator Undercutting - C14 |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20240630 | Notification to cover surveying and monumenting where monuments are not existing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134946&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000134946 | C14 GA WANDOO UP RD RESIDUAL 81.605. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.295 | KM | 177891 | Goonyella | BALOOK | WANDOO | 0.1439 | KM | GA02ML81 | 0.6049 | GA02ML81 | 0.7489 | KM |  |  |  |  | 81.605 | 81.9 | 2023-06-30 | UP |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | NWSC | FY23 IN | 20240805 | 22.03.2021 10:47:48 AUSQLD Tracy Holmes (R870040) Planned up to crossing 5774 80.55 in FY21, needs doing after this point more than planned scope 12.04.2021 16:23:14 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk Original notification 2000074543 - new notification created as original had work order link. - 07/02/2024. Intended to be completed in FY24 Original notification 2000074543 - new notification created as original had work order link. - 07/02/2024. Intended to be completed in FY24 ⚡⚡⚡Update⚡⚡⚡ Original notification 2000074543 was for 81.605-81.900 Scope completed on 07/08/22 was 81.749-81.829 New notifications raised to complete residual are: 2000134946: 81.605-81.749 2000137559: 81.829-81.900
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137559&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000137559 | C14 GA WANDOO UP RD RESIDUAL 81.605. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 | RENEWAL | 0.295 | KM | 177891 | Goonyella | BALOOK | WANDOO | 0.0709 | KM | GA02ML81 | 0.8289 | GA02ML81 | 0.9 | KM |  |  |  |  | 81.605 | 81.9 | 2023-06-30 | UP |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | NWSC | FY23 IN | 20240903 | 22.03.2021 10:47:48 AUSQLD Tracy Holmes (R870040) Planned up to crossing 5774 80.55 in FY21, needs doing after this point more than planned scope 12.04.2021 16:23:14 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk Original notification 2000074543 - new notification created as original had work order link. - 07/02/2024. Intended to be completed in FY24 Original notification 2000074543 - new notification created as original had work order link. - 07/02/2024. Intended to be completed in FY24 ⚡⚡⚡Update⚡⚡⚡ Original notification 2000074543 was for 81.605-81.900 Scope completed on 07/08/22 was 81.749-81.829 New notifications raised to complete residual are: 2000134946: 81.605-81.749 2000137559: 81.829-81.900
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094521&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094521 | C14 Adj C13 ML Lead Bajool 8CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.057 | KM | 18003 | Blackwater | ARCHER | BAJOOL | 0.057 | KM | BW01ML606 | 0.513 | BW01ML606 | 0.5699 | KM |  |  |  |  | 606.513 | 606.57 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094444&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094444 | C14 Adj C13 Divergent Bajool 8CD | BW-42XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.076 | KM | 24004 | Blackwater | BAJOOL | BAJOOL | 0.0759 | KM | BW42XR606 | 0.464 | BW42XR606 | 0.54 | KM |  |  |  |  | 606.464 | 606.54 | 2024-06-30 | CROSSOVER |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094477&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094477 | C14 Adj C13 ML Exit Bajool 8CD. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.014 | KM | 4422 | Blackwater | BAJOOL | MARMOR | 0.014 | KM | BW01ML606 | 0.45 | BW01ML606 | 0.464 | KM |  |  |  |  | 606.45 | 606.464 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie into FY23 Undercut of Bajool 7AB on the southern end at approx 606.450km Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094478&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094478 | C14 Adj C13 ML Exit Balook ER1.2A. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.059 | KM | 20780 | Goonyella | BALOOK | BOILINGBROKE | 0.0589 | KM | GA01ML74 | 0.7399 | GA01ML74 | 0.799 | KM |  |  |  |  | 74.74 | 74.799 | 2024-06-30 | DOWN |  |  |  | 4.3 | 5 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 229 created to update Start KM on notification to 74.740km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094479&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094479 | C14 Adj C13 ML Exit Blackridge 12AB. | GA-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.208 | KM | 36226 | Goonyella | BLACKRIDGE | BLAIR ATHOL MINE | 0.2079 | KM | GA05ML86 | 0.9799 | GA05ML87 | 0.1779 | KM |  |  |  |  | 86.98 | 87.178 | 2024-06-30 | MAIN |  |  |  | 4.3 | 1.2 | 2 | 2.5 | 1 | 10.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 233 created to update End KM on notification to 87.178km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094446&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094446 | C14 Adj C13 Divergent Blackwater ER5.2E | BW-26CT | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 24389 | Blackwater | BLACKWATER | BLACKWATER | 0.05 | KM | BW26CT189 | 0.1499 | BW26CT189 | 0.2 | KM |  |  |  |  | 189.2 | 189.15 | 2024-06-30 | LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | divergent leg BW-26CT Loop Siding cut out at 189.150km Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094445&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094445 | C14 Adj C13 Divergent Blackwater ER5.2D | BW-46YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.042 | KM | 20487 | Blackwater | BLACKWATER | BLACKWATER | 0.042 | KM | BW46YR189 | 0.223 | BW46YR189 | 0.265 | KM |  |  |  |  | 189.223 | 189.265 | 2024-06-30 | LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent Leg BW-46YR Cut out at 189.265km Melissa Durnsford (7/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094524&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094524 | C14 Adj C13 ML Lead Blackwater ER5.2D. | BW-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.017 | KM | 8292 | Blackwater | BLACKWATER | BOONAL | 0.017 | KM | BW05PL189 | 0.2479 | BW05PL189 | 0.265 | KM |  |  |  |  | 189.248 | 189.265 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Cut out at 189.265km on Western End Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094525&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094525 | C14 Adj C13 ML Lead Blackwater ER5.2E | BW-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.011 | KM | 5366 | Blackwater | BLACKWATER | SAGITTARIUS | 0.0109 | KM | BW05PL189 | 0.199 | BW05PL189 | 0.2099 | KM |  |  |  |  | 189.199 | 189.21 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Cut out at 189.210km western end - tie into C14 adjacent to ER5.2D Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094447&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094447 | C14 Adj C13 Divergent Bluff 10AB. | BW-04PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.079 | KM | 49284 | Blackwater | BLUFF | BLUFF | 0.079 | KM | BW04PL169 | 0.041 | BW04PL169 | 0.1199 | KM |  |  |  |  | 169.041 | 169.12 | 2024-06-30 | PASSING LOOP |  |  |  | 4.8 | 3.4 | 2 | 3.6 | 1 | 17.3 |  | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Divergent Leg BW-04PL Cut out at 169.120km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094482&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094482 | C14 Adj C13 ML Exit Bluff 10AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.042 | KM | 26202 | Blackwater | BLUFF | WALTON | 0.042 | KM | BW03ML169 | 0 | BW03ML169 | 0.042 | KM |  |  |  |  | 169 | 169.042 | 2024-06-30 | DOWN |  |  |  | 4.8 | 3.4 | 2 | 3.6 | 1 | 17.3 |  | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094481&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094481 | C14 Adj C13 ML Exit Blackwater ER5.2E. | BW-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.023 | KM | 11219 | Blackwater | BOONAL | BLACKWATER | 0.0229 | KM | BW05PL189 | 0.1499 | BW05PL189 | 0.1729 | KM |  |  |  |  | 189.15 | 189.173 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094526&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094526 | C14 Adj C13 ML Lead Bluff 10AB. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.102 | KM | 63633 | Blackwater | BOONAL | BLUFF | 0.1019 | KM | BW03ML169 | 0.0779 | BW03ML169 | 0.1799 | KM |  |  |  |  | 169.078 | 169.18 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 |  | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094557&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094557 | C14 Adj C13 ML Lead Waitara 10AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.043 | KM | 7046 | Goonyella | BRAESIDE | WAITARA | 0.0429 | KM | GA01ML100 | 0.46 | GA01ML100 | 0.4169 | KM |  |  |  |  | 100.46 | 100.417 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Cut until LX at 100.460
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094559&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094559 | C14 Adj C13 ML Lead Waitara 12BC. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.076 | KM | 12454 | Goonyella | BRAESIDE | WAITARA | 0.0759 | KM | GA01ML100 | 0.644 | GA01ML100 | 0.7199 | KM |  |  |  |  | 100.644 | 100.72 | 2024-06-30 | DOWN |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094533&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094533 | C14 Adj C13 ML Lead Coppabella 46AB. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.126 | KM | 25557 | Goonyella | BRODLEA | COPPABELLA | 0.126 | KM | GA02ML147 | 0.6239 | GA02ML147 | 0.75 | KM |  |  |  |  | 147.624 | 147.75 | 2024-06-30 | UP |  |  |  | 4.5 | 4.6 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie in with Coppabella 45AB adjacent C14 Melissa Durnsford 19/07/2022: Scope change request number 221 created to update End KM on notification to 147.750km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094486&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094486 | C14 Adj C13 ML Exit Coppabella 45AB. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 10142 | Goonyella | BRODLEA | COPPABELLA | 0.05 | KM | GA02ML147 | 0.8279 | GA02ML147 | 0.878 | KM |  |  |  |  | 147.828 | 147.878 | 2024-06-30 | UP |  |  |  | 4.8 | 4.6 | 2 | 4.1 | 1 | 19.7 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094495&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094495 | C14 Adj C13 ML Exit Mallawa 8CD. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.037 | KM | 11758 | Goonyella | BURTON JCT | MALLAWA | 0.0369 | KM | GA02ML168 | 0.2 | GA02ML168 | 0.2369 | KM |  |  |  |  | 168.2 | 168.237 | 2024-06-30 | UP |  |  |  | 4.1 | 2.4 | 2 | 3.2 | 1 | 13.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 231 created to update End KM on notification to 168.237km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094542&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094542 | C14 Adj C13 ML Lead/Exit Mallawa 9AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 15889 | Goonyella | BURTON JCT | MALLAWA | 0.05 | KM | GA01ML168 | 0.23 | GA01ML168 | 0.28 | KM |  |  |  |  | 168.23 | 168.28 | 2024-06-30 | DOWN |  |  |  | 4.8 | 2.5 | 2 | 3.3 | 1 | 15.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | C14 Adj C13 ML Lead/Exit Mallawa 9AB C14 Adj C13 ML Lead/Exit Mallawa 9AB
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094496&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094496 | C14 Adj C13 ML Exit Mallawa 9AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 15889 | Goonyella | BURTON JCT | MALLAWA | 0.05 | KM | GA01ML168 | 0.329 | GA01ML168 | 0.379 | KM |  |  |  |  | 168.329 | 168.379 | 2024-06-30 | DOWN |  |  |  | 4.8 | 2.5 | 2 | 3.3 | 1 | 15.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094448&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094448 | C14 Adj C13 Divergent Callemondah 213A. | BW-06XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 14881 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.025 | KM | BW06XR0 | 0.4149 | BW06XR0 | 0.44 | KM |  |  |  |  | 0.415 | 0.44 | 2024-06-30 | CROSSOVER |  |  |  | 4.6 | 2.6 | 2 | 3.3 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Tie into Callemondah 213B undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094484&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094484 | C14 Adj C13 ML Exit Callemondah 213B. | BW-17YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.019 | KM | 11309 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.0189 | KM | BW17YR0 | 0.4199 | BW17YR0 | 0.439 | KM |  |  |  |  | 0.42 | 0.439 | 2024-06-30 | APPROACH |  |  |  | 4.3 | 2.6 | 2 | 3.3 | 1 | 14.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Tie into adjoining C13 undercut on 205A
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094528&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094528 | C14 Adj C13 ML Lead Callemondah 213A. | BW-20YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 29762 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.05 | KM | BW20YR0 | 0.438 | BW20YR0 | 0.4879 | KM |  |  |  |  | 0.438 | 0.488 | 2024-06-30 | BALLOON |  |  |  | 4.6 | 2.6 | 2 | 3.3 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | No adjacent on lower kilometerage end as 212B is only 8m away
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094449&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094449 | C14 Adj C13 Divergent Callemondah 213B. | BW-06XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.025 | KM | 14881 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.025 | KM | BW06XR0 | 0.465 | BW06XR0 | 0.44 | KM |  |  |  |  | 0.465 | 0.44 | 2024-06-30 | CROSSOVER |  |  |  | 4.3 | 2.6 | 2 | 3.3 | 1 | 14.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Tie into 213A on the divergent leg
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094529&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094529 | C14 Adj C13 ML Lead Callemondah 213B. | BW-17YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 5357 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.0089 | KM | BW17YR0 | 0.466 | BW17YR0 | 0.4749 | KM |  |  |  |  | 0.466 | 0.475 | 2024-06-30 | APPROACH |  |  |  | 4.3 | 2.6 | 2 | 3.3 | 1 | 14.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094451&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094451 | C14 Adj C13 Divergent Collinsville 12AB. | NL-06PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.047 | KM | 24089 | Newlands | COLLINSVILLE | COLLINSVILLE | 0.047 | KM | NL06PL77 | 0.1419 | NL06PL77 | 0.095 | KM |  |  |  |  | 77.142 | 77.095 | 2024-06-30 | MAIN |  |  |  | 4.2 | 2.5 | 2 | 3.3 | 1 | 13.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094453&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094453 | C14 Adj C13 Divergent Coppabella 46AB. | GA-01FK | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 10142 | Goonyella | COPPABELLA | COPPABELLA | 0.05 | KM | GA01FK1 | 0.2909 | GA01FK1 | 0.341 | KM |  |  |  |  | 1.341 | 1.291 | 2024-06-30 | FORK |  |  |  | 4.5 | 4.6 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094487&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094487 | C14 Adj C13 ML Exit Coppabella 46AB | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.07 | KM | 14198 | Goonyella | COPPABELLA | COPPABELLA | 0.07 | KM | GA02ML147 | 0.545 | GA02ML147 | 0.4749 | KM |  |  |  |  | 147.545 | 147.475 | 2024-06-30 | UP |  |  |  | 4.5 | 4.6 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122574&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000122574 | C14 Adj C13 Divergent Coppabella 45AB. | GA-59XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 10142 | Goonyella | COPPABELLA | COPPABELLA | 0.099 | KM | GA59XR147 | 0.779 | GA59XR147 | 0.878 | KM |  |  |  |  | 147.779 | 147.829 | 2024-06-30 | CROSSOVER |  |  |  | 4.8 | 4.6 | 2 | 4.1 | 1 | 19.7 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | NWSC |  | 20240122
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094532&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094532 | C14 Adj C13 ML Lead Coppabella 45AB | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.03 | KM | 6085 | Goonyella | COPPABELLA | COPPABELLA | 0.0299 | KM | GA02ML147 | 0.75 | GA02ML147 | 0.78 | KM |  |  |  |  | 147.78 | 147.75 | 2024-06-30 | UP |  |  |  | 4.8 | 4.6 | 2 | 4.1 | 1 | 19.7 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Tie in with Coppabella 46AB adjacent C14 Melissa Durnsford 19/07/2022: Scope change request number 222 created to update End KM on notification to 147.750km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094454&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094454 | C14 Adj C13 Divergent Dingo 12CD | BW-85XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 17913 | Blackwater | DINGO | DINGO | 0.049 | KM | BW03ML140 | 0.68 | BW03ML140 | 0.7289 | KM |  |  |  |  | 140.68 | 140.729 | 2024-06-30 | CROSSOVER |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Divergent Leg BW-82XR cut out at 140.680km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094488&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094488 | C14 Adj C13 ML Exit Dingo 12CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.014 | KM | 5118 | Blackwater | DINGO | GOOWARRA | 0.014 | KM | BW03ML140 | 0.7289 | BW03ML140 | 0.7429 | KM |  |  |  |  | 140.729 | 140.743 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Eastern End Cut out at 140.620km Melissa Durnsford 19/07/2022: Scope change request number 230 created to update End KM on notification to 140.743km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094548&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094548 | C14 Adj C13 ML Lead Mt Larcom 11CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.094 | KM | 22036 | Blackwater | EPALA | MOUNT LARCOM | 0.094 | KM | BW01ML564 | 0.756 | BW01ML564 | 0.8499 | KM |  |  |  |  | 564.756 | 564.85 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Northern End cut out prior to Level Crossing (Narrows Road) 564.850km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094456&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094456 | C14 Adj C13 Divergent German Creek 9AB. | GA-04FK | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 18157 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.0599 | KM | GA04FK0 | 0 | GA04FK0 | 0.0599 | KM |  |  |  |  | 0 | 0.06 | 2024-06-30 | FORK |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103493&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103493 | C14 Adj C13 ML Exit German Creek 7AB | GA-22ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.028 | KM | 8473 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.028 | KM | GA22ML131 | 0.8 | GA22ML131 | 0.8279 | KM |  |  |  |  | 131.8 | 131.828 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.25 | 185 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | New notification for German Creek 7AB
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094489&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094489 | C14 Adj C13 ML Exit German Creek 9AB | GA-22ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.077 | KM | 23302 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.0769 | KM | GA22ML131 | 0.8169 | GA22ML131 | 0.7399 | KM |  |  |  |  | 131.817 | 131.74 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 223 created to update End KM on notification to 131.740km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094535&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094535 | C14 Adj C13 ML Lead German Creek 7AB | GA-22ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.038 | KM | 11500 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.0379 | KM | GA22ML131 | 0.8619 | GA22ML131 | 0.9 | KM |  |  |  |  | 131.862 | 131.9 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094455&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094455 | C14 Adj C13 Divergent German Creek 7AB | GA-22ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 15131 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.05 | KM | GA22ML136 | 0.4 | GA22ML136 | 0.45 | KM |  |  |  |  | 136.4 | 131.829 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent scope is the other end of the balloon loop where it ties back to 7AB
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094457&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094457 | C14 Adj C13 Divergent Gracemere 12CD | BW-49XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.111 | KM | 17649 | Blackwater | GRACEMERE | GRACEMERE | 0.111 | KM | BW49XR4 | 0 | BW49XR4 | 0.111 | KM |  |  |  |  | 4 | 4.111 | 2024-06-30 | CROSSOVER |  |  |  | 4.2 | 3.4 | 2 | 3.6 | 1 | 15.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094554&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094554 | C14 Adj C13 ML Lead Rocklands 9AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.002 | KM | 786 | Blackwater | GRACEMERE | ROCKLANDS | 0.002 | KM | BW03ML0 | 0.925 | BW03ML0 | 0.927 | KM |  |  |  |  | 0.925 | 0.927 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094490&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094490 | C14 Adj C13 ML Exit Gracemere 12CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.092 | KM | 14628 | Blackwater | GRACEMERE | ROCKLANDS | 0.0919 | KM | BW03ML3 | 0.9499 | BW03ML4 | 0.0379 | KM |  |  |  |  | 3.95 | 4.038 | 2024-06-30 | DOWN |  |  |  | 4.2 | 3.4 | 2 | 3.6 | 1 | 15.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Eastern End 3.950km to 4.200km on western end (eventually could tie into C14 Adjacent to 11AB Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094551&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094551 | C14 Adj C13 ML Lead Rocklands 10AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 19647 | Blackwater | GRACEMERE | ROCKLANDS | 0.05 | KM | BW01ML631 | 0.78 | BW01ML631 | 0.8299 | KM |  |  |  |  | 631.78 | 631.83 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | 631.710km to 631.830km (will tie into C14 at Rocklands 12CD) Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document While 10AB was undercut in FY23 as a fix on fail, the C14 adjoining needs to remain in FY24 as it was not completed as part of the fix on fail.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094491&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094491 | C14 Adj C13 ML Exit Hay Point 11CD | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.008 | KM | 2695 | Goonyella | HAY POINT | HAY POINT | 0.008 | KM | GA02BA3 | 0.635 | GA02BA3 | 0.643 | KM |  |  |  |  | 3.635 | 3.643 | 2024-06-30 | BALLOON |  |  |  | 3.9 | 2.3 | 2 | 3.3 | 1 | 12.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094458&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094458 | C14 Adj C13 Divergent Hay Point 11CD | GA-02XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.08 | KM | 26951 | Goonyella | HAY POINT | HAY POINT | 0.08 | KM | GA02XR3 | 0.68 | GA02XR3 | 0.76 | KM |  |  |  |  | 3.68 | 3.76 | 2024-06-30 | CROSSOVER |  |  |  | 3.9 | 2.3 | 2 | 3.2 | 1 | 12.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094539&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094539 | C14 Adj C13 ML Lead Jilalan 82AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 20964 | Goonyella | JILALAN | JILALAN | 0.0599 | KM | GA01ML22 | 0.634 | GA01ML22 | 0.6939 | KM |  |  |  |  | 22.634 | 22.694 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094459&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094459 | C14 Adj C13 Divergent Jilalan 83AB. | GA-01YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 17470 | Goonyella | JILALAN | JILALAN | 0.05 | KM | GA01YR23 | 0.264 | GA01YR23 | 0.2139 | KM |  |  |  |  | 23.264 | 23.214 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094492&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094492 | C14 Adj C13 ML Exit Jilalan 48AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.016 | KM | 5591 | Goonyella | JILALAN | PRAGUELANDS | 0.016 | KM | GA01ML17 | 0.5699 | GA01ML17 | 0.5859 | KM |  |  |  |  | 17.57 | 17.586 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094493&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094493 | C14 Adj C13 ML Exit Jilalan 82AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.008 | KM | 2795 | Goonyella | JILALAN | PRAGUELANDS | 0.008 | KM | GA01ML22 | 0.5979 | GA01ML22 | 0.5899 | KM |  |  |  |  | 22.598 | 22.59 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094494&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094494 | C14 Adj C13 ML Exit Jilalan 83AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.058 | KM | 20266 | Goonyella | JILALAN | PRAGUELANDS | 0.058 | KM | GA01ML23 | 0.228 | GA01ML23 | 0.17 | KM |  |  |  |  | 23.228 | 23.17 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094540&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094540 | C14 Adj C13 ML Lead Jilalan 83AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 18519 | Goonyella | JILALAN | YUKAN | 0.0529 | KM | GA01ML23 | 0.261 | GA01ML23 | 0.314 | KM |  |  |  |  | 23.261 | 23.314 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094536&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094536 | C14 Adj C13 ML Lead Gracemere 12CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.089 | KM | 14151 | Blackwater | KABRA | GRACEMERE | 0.0889 | KM | BW03ML4 | 0.111 | BW03ML4 | 0.2 | KM |  |  |  |  | 4.111 | 4.2 | 2024-06-30 | DOWN |  |  |  | 4.2 | 3.4 | 2 | 3.6 | 1 | 15.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094541&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094541 | C14 Adj C13 ML Lead Mallawa 8CD | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 16842 | Goonyella | MALLAWA | CARBOROUGH DOWNS | 0.0529 | KM | GA02ML168 | 0.1539 | GA02ML168 | 0.101 | KM |  |  |  |  | 168.154 | 168.101 | 2024-06-30 | UP |  |  |  | 4.1 | 2.4 | 2 | 3.2 | 1 | 13.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 232 created to update End KM on notification to 168.101km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094460&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094460 | C14 Adj C13 Divergent Mallawa 8CD | GA-63XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 15889 | Goonyella | MALLAWA | MALLAWA | 0.05 | KM | GA02ML168 | 0.2 | GA02ML168 | 0.1499 | KM |  |  |  |  | 168.2 | 168.15 | 2024-06-30 | CROSSOVER |  |  |  | 4.1 | 2.4 | 2 | 3.2 | 1 | 13.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094497&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094497 | C14 Adj C13 ML Exit McNaughton 7A. | NL-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.139 | KM | 24464 | Newlands | MCNAUGHTON | MCNAUGHTON | 0.139 | KM | NL04ML81 | 0.5709 | NL04ML81 | 0.7099 | KM |  |  |  |  | 81.571 | 81.71 | 2024-06-30 | MAIN |  |  |  | 3.2 | 1.7 | 2 | 2.8 | 1 | 9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Melissa Durnsford (19/07/2022): Scope change request number 217 created to update End KM on notification to 81.710km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094461&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094461 | C14 Adj C13 Divergent McNaughton 7A | NL-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.075 | KM | 13200 | Newlands | MCNAUGHTON | MCNAUGHTON | 0.0749 | KM | NL04ML85 | 0.7099 | NL04ML85 | 0.785 | KM |  |  |  |  | 85.71 | 85.785 | 2024-06-30 | MAIN |  |  |  | 3.2 | 1.7 | 2 | 2.8 | 1 | 9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094485&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094485 | C14 Adj C13 ML Exit Collinsville 12AB. | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.039 | KM | 19989 | Newlands | MCNAUGHTON JCT | COLLINSVILLE | 0.0389 | KM | NL01ML77 | 0.1419 | NL01ML77 | 0.1029 | KM |  |  |  |  | 77.142 | 77.103 | 2024-06-30 | MAIN |  |  |  | 4.2 | 2.5 | 2 | 3.3 | 1 | 13.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: SCR Number 218 Created to amend end KM on notification to 77.103km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094531&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094531 | C14 Adj C13 ML Lead Collinsville 12AB | NL-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.005 | KM | 2563 | Newlands | MCNAUGHTON JCT | COLLINSVILLE | 0.005 | KM | NL01ML77 | 0.1749 | NL01ML77 | 0.1799 | KM |  |  |  |  | 77.175 | 77.18 | 2024-06-30 | MAIN |  |  |  | 4.2 | 2.5 | 2 | 3.3 | 1 | 13.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094543&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094543 | C14 Adj C13 ML Lead McNaughton 7A | NL-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.051 | KM | 8976 | Newlands | MCNAUGHTON JCT | MCNAUGHTON | 0.0509 | KM | NL04ML81 | 0.4839 | NL04ML81 | 0.535 | KM |  |  |  |  | 81.484 | 81.535 | 2024-06-30 | MAIN |  |  |  | 3.2 | 1.7 | 2 | 2.8 | 1 | 9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110596&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000110596 | C14 Adj C13 ML Lead Rocklands 12AB | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.1 | KM | 62385 | Blackwater | MIDGEE | ROCKLANDS | 0.1 | KM | BW02ML631 | 0.5799 | BW02ML631 | 0.68 | KM |  |  |  |  | 631.58 | 631.68 | 2024-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.6 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | NWSC |  | 20240630 | Lachlan Crow (09/01/2023): Additional FY24 Scope. No adjoining exit C14 as it was recently undercut in 2021. Therefore, 100m adjoining lead C14 to tie into Rocklands 50CD.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094553&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094553 | C14 Adj C13 ML Lead Rocklands 12CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.012 | KM | 4715 | Blackwater | MIDGEE | ROCKLANDS | 0.012 | KM | BW01ML631 | 0.6179 | BW01ML631 | 0.63 | KM |  |  |  |  | 631.618 | 631.63 | 2024-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.6 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094507&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094507 | C14 Adj C13 ML Exit Rocklands 12CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.031 | KM | 12181 | Blackwater | MIDGEE | ROCKLANDS | 0.0309 | KM | BW01ML631 | 0.679 | BW01ML631 | 0.7099 | KM |  |  |  |  | 631.679 | 631.71 | 2024-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.6 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094498&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094498 | C14 Adj C13 ML Exit Millennium Jct 7AB. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 17504 | Goonyella | MILLENNIUM JCT | RED MOUNTAIN | 0.0599 | KM | GA03ML16 | 0.5799 | GA03ML16 | 0.64 | KM |  |  |  |  | 16.58 | 16.64 | 2024-06-30 | MAIN |  |  |  | 4.5 | 2.8 | 2 | 3.4 | 1 | 15.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094544&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094544 | C14 Adj C13 ML Lead Millennium Jct 7AB | GA-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.1 | KM | 29173 | Goonyella | MOORVALE JCT | MILLENNIUM JCT | 0.1 | KM | GA03ML16 | 0.4329 | GA03ML16 | 0.533 | KM |  |  |  |  | 16.433 | 16.533 | 2024-06-30 | MAIN |  |  |  | 4.5 | 2.8 | 2 | 3.4 | 1 | 15.3 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 220 created to update Start KM on notification to 16.433km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094502&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094502 | C14 Adj C13 ML Exit Mt Larcom 11CD. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.109 | KM | 25553 | Blackwater | MOUNT LARCOM | EUROA | 0.1089 | KM | BW01ML564 | 0.5999 | BW01ML564 | 0.7089 | KM |  |  |  |  | 564.6 | 564.709 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094463&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000094463 | C14 Adj C13 Divergent Mt Larcom 11CD | BW-29XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.068 | KM | 15941 | Blackwater | MOUNT LARCOM | MOUNT LARCOM | 0.068 | KM | BW29XR564 | 0.7119 | BW29XR564 | 0.78 | KM |  |  |  |  | 564.712 | 564.78 | 2024-06-30 | CROSSOVER |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent Leg BW-29XR to 564.780km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094523&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094523 | C14 Adj C13 ML Lead Blackridge 12AB | GA-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 10450 | Goonyella | MOUNT MCLAREN | BLACKRIDGE | 0.0599 | KM | GA05ML86 | 0.931 | GA05ML86 | 0.8709 | KM |  |  |  |  | 86.931 | 86.871 | 2024-06-30 | MAIN |  |  |  | 4.3 | 1.2 | 2 | 2.5 | 1 | 10.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094549&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094549 | C14 Adj C13 ML Lead Peak Downs ER1.2A. | GA-17ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 24018 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0529 | KM | GA17ML44 | 0.9579 | GA17ML45 | 0.008 | KM |  |  |  |  | 45.008 | 44.958 | 2024-06-30 | BALLOON |  |  |  | 4.6 | 1.1 | 2 | 2.5 | 1 | 11.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094503&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094503 | C14 Adj C13 ML Exit Peak Downs ER1.2A | GA-17ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 22658 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.05 | KM | GA17ML45 | 0.0369 | GA17ML45 | 0.0869 | KM |  |  |  |  | 45.037 | 45.087 | 2024-06-30 | BALLOON |  |  |  | 4.6 | 1.1 | 2 | 2.5 | 1 | 11.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094537&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094537 | C14 Adj C13 ML Lead Hay Point 11CD. | GA-02BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 16845 | Goonyella | PRAGUELANDS | HAY POINT | 0.05 | KM | GA02BA3 | 0.68 | GA02BA3 | 0.7299 | KM |  |  |  |  | 3.68 | 3.73 | 2024-06-30 | BALLOON |  |  |  | 3.9 | 2.3 | 2 | 3.2 | 1 | 12.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094505&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094505 | C14 Adj C13 ML Exit Rocklands 10AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.02 | KM | 7859 | Blackwater | ROCKLANDS | MIDGEE | 0.02 | KM | BW01ML631 | 0.7099 | BW01ML631 | 0.7299 | KM |  |  |  |  | 631.71 | 631.73 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document While 10AB has been removed, the adjoining C14 needs to remain in scope as it was not completed as part of the fix on fail undercut.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094506&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094506 | C14 Adj C13 ML Exit Rocklands 11AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.037 | KM | 14538 | Blackwater | ROCKLANDS | MIDGEE | 0.0369 | KM | BW01ML631 | 0.81 | BW01ML631 | 0.8469 | KM |  |  |  |  | 631.81 | 631.847 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | 631.810km - 631.930km (ties into Rocklands 10AB divergent leg of C14 Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094508&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094508 | C14 Adj C13 ML Exit Rocklands 9AB. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.047 | KM | 18468 | Blackwater | ROCKLANDS | ROCKLANDS | 0.047 | KM | BW03ML0 | 0.877 | BW03ML0 | 0.8299 | KM |  |  |  |  | 0.877 | 0.83 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Cut from end of splays to 0.830km BW-03ML Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094465&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094465 | C14 Adj C13 Divergent Rocklands 10AB. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.08 | KM | 31435 | Blackwater | ROCKLANDS | ROCKLANDS | 0.08 | KM | BW01ML631 | 0.7299 | BW01ML631 | 0.81 | KM |  |  |  |  | 631.73 | 631.81 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Divergent Leg BW-01ML to 631.810km Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document While 10AB has been removed, the adjoining scope needs to remain in place as it was not completed as part of the fix on fail.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094552&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094552 | C14 Adj C13 ML Lead Rocklands 11AB. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.085 | KM | 33399 | Blackwater | ROCKLANDS | ROCKLANDS | 0.085 | KM | BW01ML631 | 0.885 | BW01ML631 | 0.9699 | KM |  |  |  |  | 631.885 | 631.97 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094480&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094480 | C14 Adj C13 ML Exit Blackwater ER5.2D | BW-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.013 | KM | 6341 | Blackwater | SAGITTARIUS | BLACKWATER | 0.0129 | KM | BW05PL189 | 0.2099 | BW05PL189 | 0.223 | KM |  |  |  |  | 189.21 | 189.223 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Cut out at 189.210km eastern end - tie into C14 adjacent to ER5.2E Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094555&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094555 | C14 Adj C13 ML Lead Sagittarius 12AB | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.07 | KM | 23692 | Blackwater | SAGITTARIUS | BLACKWATER | 0.07 | KM | BW04ML191 | 0.8149 | BW04ML191 | 0.7449 | KM |  |  |  |  | 191.815 | 191.745 | 2024-06-30 | UP |  |  |  | 3.9 | 3.2 | 2 | 3.6 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094509&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094509 | C14 Adj C13 ML Exit Sagittarius 12AB | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.017 | KM | 5754 | Blackwater | SAGITTARIUS | CURRAGH | 0.017 | KM | BW04ML191 | 0.888 | BW04ML191 | 0.905 | KM |  |  |  |  | 191.888 | 191.905 | 2024-06-30 | UP |  |  |  | 3.9 | 3.2 | 2 | 3.6 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Melissa Durnsford (19/07/2022): SCR Number 214 Created to update End KM On Notification to 191.905km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094466&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094466 | C14 Adj C13 Divergent Sagittarius12AB | BW-98XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 16923 | Blackwater | SAGITTARIUS | SAGITTARIUS | 0.05 | KM | BW03ML191 | 0.8149 | BW03ML191 | 0.8649 | KM |  |  |  |  | 191.815 | 191.865 | 2024-06-30 | CROSSOVER |  |  |  | 3.9 | 3.2 | 2 | 3.6 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094510&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094510 | C14 Adj C13 ML Exit South Walker 9AB. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 32673 | Goonyella | SOUTH WALKER JCT | MINDI | 0.049 | KM | GA01ML127 | 0.44 | GA01ML127 | 0.4889 | KM |  |  |  |  | 127.44 | 127.489 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.7 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094556&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094556 | C14 Adj C13 ML Lead South Walker 9AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.021 | KM | 14003 | Goonyella | TOOTOOLAH | SOUTH WALKER JCT | 0.021 | KM | GA01ML127 | 0.541 | GA01ML127 | 0.562 | KM |  |  |  |  | 127.541 | 127.562 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.7 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 228 created to update End KM on notification to 127.562km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094534&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094534 | C14 Adj C13 ML Lead Dingo 12CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.064 | KM | 23397 | Blackwater | UMOLO | DINGO | 0.064 | KM | BW03ML140 | 0.6199 | BW03ML140 | 0.684 | KM |  |  |  |  | 140.62 | 140.684 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Western End cut out at 140.745 (can eventually tie into C14 adjacent to 11AB when Undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094512&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094512 | C14 Adj C13 ML Exit Waitara 11AB. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 8194 | Goonyella | WAITARA | BRAESIDE | 0.05 | KM | GA02ML100 | 0.5939 | GA02ML100 | 0.644 | KM |  |  |  |  | 100.594 | 100.644 | 2024-06-30 | UP |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094467&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094467 | C14 Adj C13 Divergent Waitara 10AB | GA-45XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.059 | KM | 9668 | Goonyella | WAITARA | WAITARA | 0.0589 | KM | GA01ML100 | 0.381 | GA01ML100 | 0.44 | KM |  |  |  |  | 100.381 | 100.44 | 2024-06-30 | CROSSOVER |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094468&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094468 | C14 Adj C13 Divergent Waitara 11AB. | GA-02PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.044 | KM | 7210 | Goonyella | WAITARA | WAITARA | 0.0439 | KM | GA02PL100 | 0.5939 | GA02PL100 | 0.55 | KM |  |  |  |  | 100.594 | 100.55 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094469&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094469 | C14 Adj C13 Divergent Waitara 12BC | GA-46XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.093 | KM | 15240 | Goonyella | WAITARA | WAITARA | 0.0929 | KM | GA01ML100 | 0.643 | GA01ML100 | 0.55 | KM |  |  |  |  | 100.643 | 100.55 | 2024-06-30 | CROSSOVER |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094511&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094511 | C14 Adj C13 ML Exit Waitara 10AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.071 | KM | 11635 | Goonyella | WAITARA | WANDOO | 0.0709 | KM | GA01ML100 | 0.381 | GA01ML100 | 0.3099 | KM |  |  |  |  | 100.381 | 100.31 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Finish C14 before Waitara 101 B/C at 100.310m
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094513&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094513 | C14 Adj C13 ML Exit Waitara 12BC | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.119 | KM | 19501 | Goonyella | WAITARA | WANDOO | 0.1189 | KM | GA01ML100 | 0.5939 | GA01ML100 | 0.4749 | KM |  |  |  |  | 100.594 | 100.475 | 2024-06-30 | DOWN |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Continue C14 until LX at 100.475
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094522&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094522 | C14 Adj C13 ML Lead Balook ER1.2A | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.073 | KM | 25711 | Goonyella | WANDOO | BALOOK | 0.0729 | KM | GA01ML74 | 0.8319 | GA01ML74 | 0.905 | KM |  |  |  |  | 74.832 | 74.905 | 2024-06-30 | DOWN |  |  |  | 4.3 | 5 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094558&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094558 | C14 Adj C13 ML Lead Waitara 11AB | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.074 | KM | 12126 | Goonyella | WANDOO | WAITARA | 0.0739 | KM | GA02ML100 | 0.4749 | GA02ML100 | 0.549 | KM |  |  |  |  | 100.475 | 100.549 | 2024-06-30 | UP |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Continue C14 until LX at 100.475
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094560&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094560 | C14 Adj C13 ML Lead Warren 7AB | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 11831 | Blackwater | WARREN | STANWELL | 0.05 | KM | BW04ML27 | 0.3649 | BW04ML27 | 0.315 | KM |  |  |  |  | 27.365 | 27.315 | 2024-06-30 | UP |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094515&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094515 | C14 Adj C13 ML Exit Warren 7CD. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.022 | KM | 5206 | Blackwater | WARREN | STANWELL | 0.0219 | KM | BW03ML27 | 0.4729 | BW03ML27 | 0.4949 | KM |  |  |  |  | 27.473 | 27.495 | 2024-06-30 | UP |  |  |  | 4.5 | 3.4 | 2 | 3.6 | 1 | 16.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 226 created to update Start KM on notification to 27.473km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094470&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094470 | C14 Adj C13 Divergent Warren 7AB | BW-58XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.085 | KM | 20112 | Blackwater | WARREN | WARREN | 0.085 | KM | BW03ML27 | 0.45 | BW03ML27 | 0.3649 | KM |  |  |  |  | 27.45 | 27.365 | 2024-06-30 | CROSSOVER |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent Leg BW-58XR cut to 27.450km to tie in with Warren 7CD diverent leg undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094471&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094471 | C14 Adj C13 Divergent Warren 7CD | BW-58XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.091 | KM | 21532 | Blackwater | WARREN | WARREN | 0.0909 | KM | BW58XR27 | 0.45 | BW58XR27 | 0.541 | KM |  |  |  |  | 27.541 | 27.45 | 2024-06-30 | CROSSOVER |  |  |  | 4.5 | 3.4 | 2 | 3.6 | 1 | 16.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent Leg BW-58XR cut to 27.450km to tie in with Warren 7AB diverent leg undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094514&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094514 | C14 Adj C13 ML Exit Warren 7AB. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.054 | KM | 12777 | Blackwater | WARREN | WYCARBAH | 0.0539 | KM | BW04ML27 | 0.4129 | BW04ML27 | 0.467 | KM |  |  |  |  | 27.413 | 27.467 | 2024-06-30 | UP |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.8 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford 19/07/2022: Scope change request number 225 created to update End KM on notification to 27.467km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094472&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094472 | C14 Adj C13 Divergent Westwood 11AB | BW-61XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.056 | KM | 11287 | Blackwater | WESTWOOD | WESTWOOD | 0.056 | KM | BW03ML45 | 0.334 | BW03ML45 | 0.39 | KM |  |  |  |  | 45.334 | 45.39 | 2024-06-30 | CROSSOVER |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Divergent Leg BW-61XR to 45.390km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094516&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094516 | C14 Adj C13 ML Exit Westwood 11AB. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.073 | KM | 14714 | Blackwater | WESTWOOD | WYCARBAH | 0.0729 | KM | BW03ML45 | 0.26 | BW03ML45 | 0.333 | KM |  |  |  |  | 45.26 | 45.333 | 2024-06-30 | DOWN |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094517&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094517 | C14 Adj C13 ML Exit Westwood 7BC. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.085 | KM | 17133 | Blackwater | WESTWOOD | WYCARBAH | 0.085 | KM | BW03ML47 | 0.4199 | BW03ML47 | 0.505 | KM |  |  |  |  | 47.42 | 47.505 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094473&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094473 | C14 Adj C13 Divergent Westwood 7BC. | BW-03PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 10683 | Blackwater | WESTWOOD | WYCARBAH | 0.0529 | KM | BW03PL47 | 0.503 | BW03PL47 | 0.45 | KM |  |  |  |  | 47.503 | 47.45 | 2024-06-30 | PASSING LOOP |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Divergent Leg BW-03PL to 47.450km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094562&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094562 | C14 Adj C13 ML Lead Westwood 11AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.051 | KM | 10280 | Blackwater | WINDAH | WESTWOOD | 0.0509 | KM | BW03ML45 | 0.379 | BW03ML45 | 0.4299 | KM |  |  |  |  | 45.379 | 45.43 | 2024-06-30 | DOWN |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094563&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094563 | C14 Adj C13 ML Lead Westwood 7BC | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 12094 | Blackwater | WINDAH | WESTWOOD | 0.0599 | KM | BW03ML47 | 0.4799 | BW03ML47 | 0.54 | KM |  |  |  |  | 47.48 | 47.54 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094561&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094561 | C14 Adj C13 ML Lead Warren 7CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.02 | KM | 4732 | Blackwater | WYCARBAH | WARREN | 0.02 | KM | BW03ML27 | 0.541 | BW03ML27 | 0.561 | KM |  |  |  |  | 27.541 | 27.561 | 2024-06-30 | UP |  |  |  | 4.5 | 3.4 | 2 | 3.6 | 1 | 16.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Western End cut out prior to Warren Road Level Crossing at the 27.590km Melissa Durnsford 19/07/2022: Scope change request number 227 created to update End KM on notification to 27.561km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094519&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094519 | C14 Adj C13 ML Exit Yukan 7AB. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.075 | KM | 32619 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.0749 | KM | GA02ML28 | 0.755 | GA02ML28 | 0.8299 | KM |  |  |  |  | 28.755 | 28.83 | 2024-06-30 | UP |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 16.4 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094538&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094538 | C14 Adj C13 ML Lead Jilalan 48AB | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 17470 | Goonyella | YUKAN | JILALAN | 0.05 | KM | GA01ML17 | 0.6169 | GA01ML17 | 0.667 | KM |  |  |  |  | 17.617 | 17.667 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094566&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094566 | C14 Adj C13 ML Lead/Exit Yukan 9AB. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.063 | KM | 27400 | Goonyella | YUKAN | YUKAN | 0.063 | KM | GA02ML28 | 0.533 | GA02ML28 | 0.4699 | KM |  |  |  |  | 28.533 | 28.47 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094520&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094520 | C14 Adj C13 ML Exit Yukan 9AB | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 21311 | Goonyella | YUKAN | YUKAN | 0.049 | KM | GA02ML28 | 0.5639 | GA02ML28 | 0.6129 | KM |  |  |  |  | 28.564 | 28.613 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094564&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094564 | C14 Adj C13 ML Lead Yukan 10BC. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 21746 | Goonyella | YUKAN | YUKAN | 0.05 | KM | GA02ML28 | 0.663 | GA02ML28 | 0.6129 | KM |  |  |  |  | 28.663 | 28.613 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000106745&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000106745 | FY24 C01 Plant Depreciation - BW | BW | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 1 | LUMPSUM | -3255597 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [13 empty] | Mainline Undercutting - C01 | [5 empty] | Outstanding notification | RRIG |  | 20240630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000106746&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000106746 | FY24 C01 Plant Depreciation - GA | GA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 1 | LUMPSUM | -2958628 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [13 empty] | Mainline Undercutting - C01 | [5 empty] | Outstanding notification | RRIG |  | 20240630 | FY24 C01 Plant Depreciation - GA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094913&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094913 | C01-BU-BW-BAJOOL-603.700km-UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.916 | KM | 463646 | Blackwater | BAJOOL | BAJOOL | 0.916 | KM | BW01ML603 | 0.6999 | BW01ML604 | 0.63 | KM |  |  |  |  | 603.7 | 604.63 | 2024-06-30 | DOWN |  |  |  | 3.8 | 4.5 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to moderately fouled ballast with severe patches Near D7 top defect Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094868&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094868 | C01-BU-GA-BALOOK-76.060km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.304 | KM | 826094 | Goonyella | BALOOK | WANDOO | 2.3039 | KM | GA01ML76 | 0.0599 | GA01ML78 | 0.3499 | KM |  |  |  |  | 76.06 | 78.35 | 2024-06-30 | DOWN |  |  |  | 3.8 | 4.8 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Moderate to highly fouled ballast Rough track geometry at 76km end, improves toward 78km end Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 178 Created to update Cut in to 76.060km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094937&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094937 | C01-BU-BW-BLACKWATER-190.500km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.314 | KM | 845530 | Blackwater | BLACKWATER | SAGITTARIUS | 1.314 | KM | BW04ML190 | 0.5 | BW04ML191 | 0.78 | KM |  |  |  |  | 190.5 | 191.78 | 2024-06-30 | UP |  |  |  | 3.8 | 3.2 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast D7 top defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094926&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094926 | C01-BU-BW-BLUFF-169.206km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.554 | KM | 731918 | Blackwater | BLUFF | BLUFF | 1.554 | KM | BW03ML169 | 0.2059 | BW03ML170 | 0.761 | KM |  |  |  |  | 169.206 | 170.761 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled sections, highly fouled on average Several D7 or near D7 track geometry defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 197 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094934&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094934 | C01-BU-BW-BLUFF-169.206km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.553 | KM | 617977 | Blackwater | BLUFF | BLUFF | 1.5529 | KM | BW04ML169 | 0.2059 | BW04ML170 | 0.761 | KM |  |  |  |  | 169.206 | 170.761 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled sections of ballast otherwise moderately fouled Near D7 generally with some D7 and moderate geometry Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 179 Created to Update Cut in and Cut out to 169.206km - 170.761km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094935&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094935 | C01-BU-BW-BLUFF-178.690km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.44 | KM | 1169182 | Blackwater | BLUFF | BOONAL | 2.4399 | KM | BW04ML178 | 0.6899 | BW04ML181 | 0.1499 | KM |  |  |  |  | 178.69 | 181.15 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Serverely fouled ballast for the first section of scope, then only in patches D7 top and Twist defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 194 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094890&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094890 | C01-BU-GA-BOILINGB-64.9000km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.997 | KM | 579939 | Goonyella | BOILINGB | BALOOK | 0.9969 | KM | GA02ML64 | 0.9 | GA02ML65 | 0.9 | KM |  |  |  |  | 64.9 | 65.9 | 2024-06-30 | UP |  |  |  | 4 | 5 | 2 | 4 | 1 | 16.8 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly fouled ballast on average, some severe fouling and some moderate Rough track geometry, with seven near or at D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103691&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103691 | C01-BU-GA-BOILINGB-65.940km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.262 | KM | 734086 | Goonyella | BOILINGB | BALOOK | 1.262 | KM | GA02ML65 | 0.9399 | GA02ML67 | 0.2 | KM |  |  |  |  | 65.94 | 67.2 | 2024-06-30 | UP |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 14.7 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast on average, some severe fouling and some moderate Rough track geometry, with seven near or at D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094865&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094865 | C01-BU-GA-BOILINGB-67.310km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.3 | KM | 824660 | Goonyella | BOILINGB | BALOOK | 2.2999 | KM | GA01ML67 | 0.2999 | GA01ML69 | 0.5999 | KM |  |  |  |  | 67.3 | 69.6 | 2024-06-30 | DOWN |  |  |  | 3.8 | 5 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast with severe patches moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094867&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094867 | C01-BU-GA-BOILINGB-71.410km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.051 | KM | 1093929 | Goonyella | BOILINGB | BALOOK | 3.051 | KM | GA01ML71 | 0.4 | GA01ML74 | 0.45 | KM |  |  |  |  | 71.4 | 74.45 | 2025-06-30 | DOWN |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Moderate to highly fouled ballast moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094965&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094965 | C01-BU-GA-BOILINGB-69.610km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.808 | KM | 648254 | Goonyella | BOLINGBROKE | BALOOK | 1.808 | KM | GA01ML69 | 0.5999 | GA01ML71 | 0.4 | KM |  |  |  |  | 69.6 | 71.4 | 2024-06-30 | DOWN |  |  |  | 3.8 | 5 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | "Highly fouled ballast with severe patches moderately rough track geometry with a near D7 at crossings" Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094936&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094936 | C01-BU-BW-BOONAL-182.900km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.385 | KM | 1622000 | Blackwater | BOONAL | BLACKWATER | 3.3849 | KM | BW04ML182 | 0.89 | BW04ML186 | 0.2999 | KM |  |  |  |  | 182.89 | 186.3 | 2024-06-30 | UP |  |  |  | 3.8 | 3.2 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Rough - D7 tops, near D7 tops and moderately rough Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 192 Created (Need to split and create two more notifications) Melissa Durnsford 11/07/2022: Uploaded Site Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103507&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103507 | C01-BU-BW-BOONAL-186.430km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.54 | KM | 258753 | Blackwater | BOONAL | BLACKWATER | 0.54 | KM | BW04ML186 | 0.4299 | BW04ML186 | 0.9699 | KM |  |  |  |  | 186.43 | 186.97 | 2024-06-30 | UP |  |  |  | 3.75 | 3.15 | 2 | 3.6 | 1 | 13.5 | 185 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Rough - D7 tops, near D7 tops and moderately rough Removed from FY24 WO 80113067 due to flood rock and RM902 unable to complete this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094938&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094938 | C01-BU-BW-BORGOON JCT-9.639km-MAIN. | BW-05ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.785 | KM | 1467234 | Blackwater | BORGOON JCT | KINROLA JCT | 2.785 | KM | BW05ML9 | 0.639 | BW05ML12 | 0.5 | KM |  |  |  |  | 9.639 | 12.5 | 2024-06-30 | MAINLINE |  |  |  | 4 | 0.9 | 2 | 2 | 1 | 8 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast D7 top defects with generally rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 187 Created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094939&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094939 | C01-BU-BW-BORGOON JCT-12.500km-MN | BW-05ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.197 | KM | 1157456 | Blackwater | BORGOON JCT | KINROLA JCT | 2.197 | KM | BW05ML12 | 0.5 | BW05ML14 | 0.6999 | KM |  |  |  |  | 12.5 | 14.7 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 0.9 | 2 | 2 | 1 | 7.6 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast D7 top defects with generally rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094870&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094870 | C01-BU-GA-BRAESIDE-107.950km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.764 | KM | 847236 | Goonyella | BRAESIDE | BRAESIDE | 1.764 | KM | GA01ML107 | 0.9499 | GA01ML109 | 0.7149 | KM |  |  |  |  | 107.95 | 109.715 | 2025-06-30 | DOWN |  |  |  | 3.8 | 4.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Patches of severely and highly fouled ballast Moderately rough track geometry in most fouled locations Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094875&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094875 | C01-BU-GA-BURTON-JCT-166.400km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.353 | KM | 1208451 | Goonyella | BURTON JCT | MALLAWA | 1.3529 | KM | GA01ML166 | 0.4 | GA01ML167 | 0.75 | KM |  |  |  |  | 166.4 | 167.75 | 2024-06-30 | DOWN |  |  |  | 3.8 | 2.4 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | moderately fouled ballast with some severe patches D7 top defects and rough sections according to track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094945&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094945 | C01-BU-BW-CREW-12.100km-MN. | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.1 | KM | 1053819 | Blackwater | CREW | MACKENZIE JCT | 3.1 | KM | BW08ML12 | 0.1 | BW08ML15 | 0.2 | KM |  |  |  |  | 12.1 | 15.2 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 1.2 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast with severe patches Near D7 top in a number of locations, moderately rough track for the remainder Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094946&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094946 | C01-BU-BW-CREW-15.200km-MN | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.45 | KM | 492916 | Blackwater | CREW | MACKENZIE JCT | 1.4499 | KM | BW08ML15 | 0.2 | BW08ML16 | 0.65 | KM |  |  |  |  | 15.2 | 16.65 | 2025-06-30 | MAINLINE |  |  |  | 3.5 | 1.2 | 2 | 3 | 1 | 10.5 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly fouled ballast with severe patches Minimal track geometry defefects Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094921&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094921 | C01-BU-BW-DINGO-141.500km-DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.711 | KM | 1291171 | Blackwater | DINGO | UMOLO | 1.711 | KM | BW03ML141 | 0.5 | BW03ML143 | 0.2099 | KM |  |  |  |  | 141.5 | 143.21 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled toward high km, highly fouled on average Moderately rough track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 200 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094920&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094920 | C01-BU-BW-EDUNGALBA-83.130km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.54 | KM | 525688 | Blackwater | EDUNGALBA | AROONA | 0.54 | KM | BW03ML83 | 0.13 | BW03ML83 | 0.67 | KM |  |  |  |  | 83.13 | 83.67 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast Moderate track geometry, getting rough from about 84.0km Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 199 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104554&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104554 | C01-BU-BW-EDUNGALBA-83.735km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.736 | KM | 716494 | Blackwater | EDUNGALBA | AROONA | 0.7359 | KM | BW03ML83 | 0.7349 | BW03ML84 | 0.4899 | KM |  |  |  |  | 83.735 | 84.49 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Refer to notification 2000094920, had to split for neutral section. Neutral section km's will be completed by C14 Severely fouled ballast Moderate track geometry, getting rough from about 84.0km Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 199 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103510&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103510 | C01-BU-BW-EPALA-581.175km-UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.085 | KM | 44004 | Blackwater | EPALA | RAGLAN | 0.085 | KM | BW01ML581 | 0.1749 | BW01ML581 | 0.26 | KM |  |  |  |  | 581.175 | 581.26 | 2024-06-30 | UP |  |  |  | 4 | 4.1 | 2 | 3.9 | 1 | 15.6 | 185 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast D7 top defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103511&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103511 | C01-BU-BW-EPALA-581.260km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.64 | KM | 331327 | Blackwater | EPALA | RAGLAN | 0.64 | KM | BW01ML581 | 0.26 | BW01ML581 | 0.9 | KM |  |  |  |  | 581.26 | 581.9 | 2024-06-30 | UP |  |  |  | 4 | 4.1 | 2 | 3.9 | 1 | 15.6 | 185 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast D7 top defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094908&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094908 | C01-BU-BW-EPALA-582.700km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.2 | KM | 621237 | Blackwater | EPALA | RAGLAN | 1.1999 | KM | BW01ML582 | 0.6999 | BW01ML583 | 0.9 | KM |  |  |  |  | 582.7 | 583.9 | 2024-06-30 | UP |  |  |  | 3.8 | 4.1 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast Moderately rough track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094927&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094927 | C01-BU-BW-GRACEMERE-11.100km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.208 | KM | 1332157 | Blackwater | GRACEMERE | KABRA | 2.208 | KM | BW04ML11 | 0.1 | BW04ML13 | 0.3099 | KM |  |  |  |  | 11.1 | 13.31 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast Minimal track geometry defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Documents
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094899&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094899 | C01-BU-GA-HARROW-60.500km-MAIN. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.8 | KM | 1440320 | Goonyella | HARROW | SARAJI | 2.7999 | KM | GA03ML60 | 0.5 | GA03ML63 | 0.2999 | KM |  |  |  |  | 60.5 | 63.3 | 2025-06-30 | MAINLINE |  |  |  | 3.5 | 1.8 | 2 | 3 | 1 | 10.5 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to severely fouled ballast moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 184 Created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094900&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094900 | C01-BU-GA-HARROW-63.440km-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.26 | KM | 648144 | Goonyella | HARROW | SARAJI | 1.26 | KM | GA03ML63 | 0.44 | GA03ML64 | 0.6999 | KM |  |  |  |  | 63.44 | 64.7 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 1.8 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly fouled ballast with some moderate and some severe patches Rough track geometry with near D7 defects at a number of locations Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 185 Created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094889&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094889 | C01-BU-GA-HATFIELD-54.000km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.785 | KM | 837598 | Goonyella | HATFIELD | BOILINGB | 0.785 | KM | GA02ML54 | 0.0309 | GA02ML54 | 0.8159 | KM |  |  |  |  | 54.031 | 54.816 | 2024-06-30 | UP |  |  |  | 3.3 | 5 | 2 | 4 | 1 | 13.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Ballast fouling varies, some severely fouled sections, moderately fouled on average but all rough Rough track geometry with D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103599&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103599 | C01-BU-GA-HATFIELD-54.920km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.933 | KM | 995514 | Goonyella | HATFIELD | BOILINGB | 0.933 | KM | GA02ML54 | 0.92 | GA02ML55 | 0.8499 | KM |  |  |  |  | 54.92 | 55.85 | 2024-06-30 | UP |  |  |  | 3.3 | 5 | 2 | 4 | 1 | 13.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Ballast fouling varies, some severely fouled sections, moderately fouled on average but all rough Rough track geometry with D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094964&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094964 | C01-BU-GA-HATFIELD-57.920km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.467 | KM | 1307583 | Goonyella | HATFIELD | BOILINGBROKE | 2.467 | KM | GA01ML57 | 0.92 | GA01ML60 | 0.3699 | KM |  |  |  |  | 57.92 | 60.37 | 2025-06-30 | DOWN |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | "Generally highly fouled ballast moderately rough track geometry" Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094883&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094883 | C01-BU-GA-JILALAN-17.570km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.773 | KM | 576018 | Goonyella | JILALAN | JILALAN | 0.773 | KM | GA02ML17 | 0.5699 | GA02ML18 | 0.3499 | KM |  |  |  |  | 17.57 | 18.35 | 2024-06-30 | UP |  |  |  | 3.8 | 4.8 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | High to severely fouled ballast Moderately rough track according to track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094941&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094941 | C01-BU-BW-KINROLA JCT-5.500km-MN. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4 | KM | 2253700 | Blackwater | KINROLA JCT | KENMARE | 4 | KM | BW06ML5 | 0.5 | BW06ML9 | 0.5 | KM |  |  |  |  | 5.5 | 9.5 | 2024-06-30 | MAINLINE |  |  |  | 3.5 | 1.2 | 2 | 3 | 1 | 10.5 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast Moderate track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094942&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094942 | C01-BU-BW-KINROLA JCT-9.500km-MN | BW-06ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.27 | KM | 1842399 | Blackwater | KINROLA JCT | KENMARE | 3.27 | KM | BW06ML9 | 0.5 | BW06ML12 | 0.77 | KM |  |  |  |  | 9.5 | 12.77 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 1.2 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast Near D7 top to moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 190 Created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094871&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094871 | C01-BU-GA-MACARTH-JCT-137.300km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.406 | KM | 732539 | Goonyella | MACARTH JCT | COPPABELLA | 1.4059 | KM | GA01ML137 | 0.2999 | GA01ML138 | 0.6999 | KM |  |  |  |  | 137.3 | 138.7 | 2024-06-30 | DOWN |  |  |  | 4 | 4.6 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severe fouling for the first approx 700m of scope, then ties remaining fouled patch together D7 top and rough track geometry runs for several hundred metres Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094872&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094872 | C01-BU-GA-MACARTH-JCT-139.700km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.2 | KM | 625211 | Goonyella | MACARTH JCT | COPPABELLA | 1.1999 | KM | GA01ML139 | 0.6999 | GA01ML140 | 0.9 | KM |  |  |  |  | 139.7 | 140.9 | 2024-06-30 | DOWN |  |  |  | 4 | 4.6 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast in 200-300m sections Very near D7 top and twist according to track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094911&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094911 | C01-BU-BW-MARMOR-599.000km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.565 | KM | 1298310 | Blackwater | MARMOR | BAJOOL | 2.5649 | KM | BW01ML599 | 0 | BW01ML601 | 0.6999 | KM |  |  |  |  | 599 | 601.7 | 2025-06-30 | DOWN |  |  |  | 3.8 | 4.1 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | severely fouled sections of ballast otherwise moderately fouled Moderatley rough track geometry with near D7 sections Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094912&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094912 | C01-BU-BW-MARMOR-602.450km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.659 | KM | 333562 | Blackwater | MARMOR | BAJOOL | 0.659 | KM | BW01ML602 | 0.45 | BW01ML603 | 0.1 | KM |  |  |  |  | 602.45 | 603.1 | 2025-06-30 | UP |  |  |  | 3.5 | 4.1 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Moderate to highly fouled ballast Moderatley rough track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094968&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094968 | C01-BU-BW-MIDGEE-623.900km-DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.4 | KM | 1009930 | Blackwater | MIDGEE | MIDGEE | 1.3999 | KM | BW02ML623 | 0.9 | BW02ML625 | 0.2999 | KM |  |  |  |  | 623.9 | 625.3 | 2025-06-30 | DOWN |  |  |  | 3.5 | 4.5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | "Moderate to high ballast fouling Minimal track geometry defects with moderate roughness near LX" Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094917&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094917 | C01-BU-BW-MIDGEE-627.700km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.305 | KM | 941399 | Blackwater | MIDGEE | ROCKLANDS | 1.3049 | KM | BW02ML627 | 0.6999 | BW02ML629 | 0 | KM |  |  |  |  | 627.7 | 629 | 2024-06-30 | DOWN |  |  |  | 3.8 | 4.5 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Patchy, severely fouled patches of ballast otherwise moderately fouled D7 top a crossing, near D7 top after that, otherwise moderately rough or okay Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094918&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094918 | C01-BU-BW-MIDGEE-629.800km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.77 | KM | 555461 | Blackwater | MIDGEE | ROCKLANDS | 0.77 | KM | BW02ML629 | 0.8 | BW02ML630 | 0.5699 | KM |  |  |  |  | 629.8 | 630.57 | 2025-06-30 | DOWN |  |  |  | 3.5 | 4.5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Moderate to high ballast fouling Minimal track geometry defects with moderate roughness in isolated areas Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094919&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094919 | C01-BU-BW-MIDGEE-630.720km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.731 | KM | 527328 | Blackwater | MIDGEE | ROCKLANDS | 0.7309 | KM | BW02ML630 | 0.7199 | BW02ML631 | 0.45 | KM |  |  |  |  | 630.72 | 631.45 | 2025-06-30 | DOWN |  |  |  | 3.5 | 4.5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Moderate to high ballast fouling Minimal track geometry defects with moderate roughness in isolated areas Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094895&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094895 | C01-BU-GA-MILLENIUM-JCT-18.900km-MN. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.615 | KM | 1244948 | Goonyella | MILLENIUM JCT | RED MOUNTAIN | 1.6149 | KM | GA03ML18 | 0.9 | GA03ML20 | 0.52 | KM |  |  |  |  | 18.9 | 20.52 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 2.5 | 2 | 3 | 1 | 12.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly fouled ballast on average, some severe fouling and some moderate Few D7 defects according to the track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094931&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094931 | C01-BU-BW-PARNABAL-156.550km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.411 | KM | 561471 | Blackwater | PARNABAL | WALTON | 1.411 | KM | BW04ML156 | 0.55 | BW04ML158 | 0 | KM |  |  |  |  | 156.55 | 158 | 2024-06-30 | UP |  |  |  | 4 | 3.4 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast Near D7 top and Twist Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094932&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094932 | C01-BU-BW-PARNABAL-161.600km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.547 | KM | 615589 | Blackwater | PARNABAL | WALTON | 1.5469 | KM | BW04ML161 | 0.5999 | BW04ML163 | 0.25 | KM |  |  |  |  | 161.6 | 163.25 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast Moderate to near D7 top defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 180 created to update Cut out to 163.250km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094924&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094924 | C01-BU-BW-PARNABAL-162.291km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.851 | KM | 400812 | Blackwater | PARNABAL | WALTON | 0.8509 | KM | BW03ML162 | 0.2909 | BW03ML163 | 0.1519 | KM |  |  |  |  | 162.291 | 163.152 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled sections, highly fouled on average Moderately rough track geometry, near D7 in sections Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 195 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094898&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094898 | C01-BU-GA-PEAK-DNS-57.650km-MN. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.161 | KM | 1111618 | Goonyella | PEAK DNS | HARROW | 2.161 | KM | GA03ML57 | 0.65 | GA03ML59 | 0.81 | KM |  |  |  |  | 57.65 | 59.81 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 1.8 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to severely fouled ballast moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request #183 created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094882&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094882 | C01-BU-GA-PRAGUELANDS-14.600km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.244 | KM | 1672167 | Goonyella | PRAGUELANDS | PRAGUELANDS | 2.244 | KM | GA02ML14 | 0.5999 | GA02ML16 | 0.8499 | KM |  |  |  |  | 14.6 | 16.85 | 2024-06-30 | UP |  |  |  | 4 | 4.6 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | High to severely fouled ballast D7 top at 16.620, near D7 top at 15.450 and a near D7 top at 14.700 at crossing according to track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Document Uploaded Inspected 10/11/23 E.H No Change.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094909&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094909 | C01-BU-BW-RAGLAN-584.050km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.7 | KM | 362389 | Blackwater | RAGLAN | MARMOR | 0.6999 | KM | BW01ML584 | 0.05 | BW01ML584 | 0.75 | KM |  |  |  |  | 584.05 | 584.75 | 2024-06-30 | UP |  |  |  | 3.8 | 4.9 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled for half of the scope with the rest of the scope only moderatley fouled Moderately rough track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094902&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094902 | C01-BU-GA-SARAJI-70.800.-MN. | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.8 | KM | 1273583 | Goonyella | SARAJI | LAKE VERMONT JCT | 2.7999 | KM | GA03ML70 | 0.8 | GA03ML73 | 0.5999 | KM |  |  |  |  | 70.8 | 73.6 | 2025-06-30 | MAINLINE |  |  |  | 3.5 | 1.6 | 2 | 3 | 1 | 10.5 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Moderately fouled ballast generally with some high and severe patches Generally good track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094903&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094903 | C01-BU-GA-SARAJI-80.655km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.448 | KM | 658624 | Goonyella | SARAJI | LAKE VERMONT JCT | 1.4479 | KM | GA03ML80 | 0.65 | GA03ML82 | 0.1 | KM |  |  |  |  | 80.65 | 82.1 | 2025-06-30 | MAINLINE |  |  |  | 3.5 | 1.6 | 2 | 3 | 1 | 10.5 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly fouled ballast with severe and moderate sections Generally good track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094943&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094943 | C01-BU-BW-STARLEE-80.770km-MN. | BW-06ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.23 | KM | 1632238 | Blackwater | STARLEE | METEOR DNS SOUTH JCT | 2.2299 | KM | BW06ML80 | 0.77 | BW06ML83 | 0 | KM |  |  |  |  | 80.77 | 83 | 2024-06-30 | MAINLINE |  |  |  | 3.8 | 2.3 | 2 | 3 | 1 | 11.4 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to Severely fouled ballast Near D7 top defects Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094922&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094922 | C01-BU-BW-UMOLO-148.645km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.794 | KM | 2108434 | Blackwater | UMOLO | PARNABAL | 2.794 | KM | BW03ML148 | 0.645 | BW03ML151 | 0.454 | KM |  |  |  |  | 148.645 | 151.454 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled sections, highly fouled on average Moderately rough track geometry, near D7 for the first few hundred metres Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 201 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094930&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094930 | C01-BU-BW-UMOLO-151.800km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.173 | KM | 466765 | Blackwater | UMOLO | PARNABAL | 1.173 | KM | BW04ML151 | 0.8 | BW04ML153 | 0.04 | KM |  |  |  |  | 151.8 | 153.04 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly to Severely fouled ballast Near D7 top and twist Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103508&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103508 | C01-BU-BW-UMOLO-153.040km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.112 | KM | 44568 | Blackwater | UMOLO | PARNABAL | 0.112 | KM | BW04ML153 | 0.04 | BW04ML153 | 0.1519 | KM |  |  |  |  | 153.04 | 153.152 | 2024-06-30 | UP |  |  |  | 3.75 | 3.35 | 2 | 3.6 | 1 | 13.5 | 185 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly to Severely fouled ballast Near D7 top and twist
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103509&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103509 | C01-BU-BW-UMOLO-153.152km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.331 | KM | 529637 | Blackwater | UMOLO | PARNABAL | 1.3309 | KM | BW04ML153 | 0.1519 | BW04ML154 | 0.4 | KM |  |  |  |  | 153.152 | 154.4 | 2024-06-30 | UP |  |  |  | 3.75 | 3.35 | 2 | 3.6 | 1 | 13.5 | 185 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly to Severely fouled ballast Near D7 top and twist
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094923&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094923 | C01-BU-BW-UMOLO-153.900km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.415 | KM | 2129685 | Blackwater | UMOLO | PARNABAL | 2.415 | KM | BW03ML153 | 0.9 | BW03ML156 | 0.2 | KM |  |  |  |  | 153.9 | 156.2 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Low km end is highly to severely fouled, remainder is moderately fouled Moderately rough track geometry, near D7 in sections Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 202 created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094869&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094869 | C01-BU-GA-WAITARA-106.500km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.138 | KM | 546573 | Goonyella | WAITARA | BRAESIDE | 1.1379 | KM | GA01ML106 | 0.5 | GA01ML107 | 0.65 | KM |  |  |  |  | 106.5 | 107.65 | 2024-06-30 | DOWN |  |  |  | 4 | 4.4 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast in the middle section of scope Very rough track geometry, several near D7 top and twists Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094925&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094925 | C01-BU-BW-WALTON-163.740km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.03 | KM | 956109 | Blackwater | WALTON | BLUFF | 2.0299 | KM | BW03ML163 | 0.7399 | BW03ML165 | 0.6999 | KM |  |  |  |  | 163.74 | 165.7 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled either side of the crossing D7 top defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 196 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094892&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094892 | C01-BU-GA-WANDOO-96.400km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.955 | KM | 797664 | Goonyella | WANDOO | WAITARA | 0.9549 | KM | GA02ML96 | 0.4 | GA02ML97 | 0.3549 | KM |  |  |  |  | 96.4 | 97.355 | 2025-06-30 | UP |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | C01-BU-GA-WANDOO-96.400km-UP Highly fouled ballast Sections of rough track geometry with at and near D7 top defects Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094876&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094876 | C01-BU-GA-WOTONGA-178.400km-DN. | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.453 | KM | 1134205 | Goonyella | WOTONGA | MORANBAH NTH JCT | 2.4529 | KM | GA01ML178 | 0.4 | GA01ML180 | 0.8489 | KM |  |  |  |  | 178.4 | 180.849 | 2024-06-30 | DOWN |  |  |  | 4 | 1.5 | 2 | 3 | 1 | 12 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | High to severe fouled ballast Near D7 defects with generally rough track geometry. Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 198 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094877&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094877 | C01-BU-GA-WOTONGA-184.000km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.074 | KM | 958965 | Goonyella | WOTONGA | MORANBAH NTH JCT | 2.0739 | KM | GA01ML184 | 0 | GA01ML186 | 0.05 | KM |  |  |  |  | 184 | 186.05 | 2024-06-30 | DOWN |  |  |  | 4 | 1.5 | 2 | 3 | 1 | 12 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | High to severely fouled ballast D7 top and twist defects according to track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Site Inspection Documetn Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094885&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094885 | C01-BU-GA-YUKAN-33.940km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.513 | KM | 1848111 | Goonyella | YUKAN | BLACK MTN | 2.8629 | KM | GA02ML33 | 0.9399 | GA02ML36 | 0.8 | KM |  |  |  |  | 33.94 | 36.45 | 2024-06-30 | UP |  |  |  | 4 | 4.4 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast in patches Generally rough track geometry with several D7 top defects Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094886&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094886 | C01-BU-GA-YUKAN-36.815.4km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.005 | KM | 739097 | Goonyella | YUKAN | BLACK MTN | 1.0049 | KM | GA02ML36 | 0.8 | GA02ML37 | 0.8 | KM |  |  |  |  | 36.8 | 37.8 | 2024-06-30 | UP |  |  |  | 3.5 | 4.4 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast in patches Generally rough track geometry with 4 locations at a near D7 top Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094887&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094887 | C01-BU-GA-YUKAN-39.730km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.076 | KM | 791312 | Goonyella | YUKAN | BLACK MTN | 1.076 | KM | GA02ML39 | 0.7299 | GA02ML40 | 0.8 | KM |  |  |  |  | 39.73 | 40.8 | 2025-06-30 | UP |  |  |  | 3.5 | 4.4 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | Severely fouled ballast in patches Generally rough track geometry with several near D7 top defects Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 191 Created Melissa Durnsford 11/07/2022: Uploaded Site Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094888&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094888 | C01-BU-GA-YUKAN-45.354km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.151 | KM | 2143834 | Goonyella | YUKAN | BLACK MTN | 2.1509 | KM | GA02ML45 | 0.3539 | GA02ML47 | 0.5 | KM |  |  |  |  | 45.354 | 47.5 | 2024-06-30 | UP |  |  |  | 4 | 5 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast in patches D7 top defects at 46.3, 46.5, 46.6, 47.1, D7 twist defects at 45.7, 45.8 Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104040&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104040 | C01-BU-GA-YUKAN-37.814km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.87 | KM | 639815 | Goonyella | YUKAN-BLACK MTN | YUKAN-BLACK MTN | 0.8699 | KM | GA02ML37 | 0.8139 | GA02ML38 | 0.677 | KM |  |  |  |  | 37.814 | 38.677 | 2024-06-30 | UP |  |  |  | 3 | 4.2 |  | 4.2 |  | 12.6 | 185 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | FY22 Residual Scope Replan Comments: Mixture of fouling from 20-30 to 60+. Geometry near D7 in multiple locations. Likely that two mud holes will have to be addressed in short term if not already. New notification created to split from 2000052402 as FY22 work order attached and contains actuals. This notification is for execution in FY24 by C01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094858&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094858 | C14 NL Unallocated | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.5 | KM | 1994211 | Newlands |  |  | 2.5 | KM | NL01ML2 | 0.501 | NL01ML5 | 0 | KM |  |  |  |  | 0 | 2.5 | 2024-06-30 |  |  |  |  | 5 | 2 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094859&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094859 | C14 MA Unallocated | MA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.5 | KM | 1991374 | Moura |  |  | 2.5 | KM | MA01ML2 | 0.5 | MA01ML5 | 0.0219 | KM |  |  |  |  | 2.5 | 5 | 2024-06-30 |  |  |  |  | 5 | 2 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094857&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094857 | C14 GA Unallocated | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.5 | KM | 2031701 | Goonyella |  |  | 2.1699 | KM | GA01ML8 | 0.33 | GA01ML10 | 0.4929 | KM |  |  |  |  | 8 | 10.5 | 2024-06-30 |  |  |  |  | 5 | 3.5 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094856&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094856 | C14 BW Unallocated | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 4 | KM | 3180907 | Blackwater |  |  | 4 | KM | BW01ML534 | 0.2899 | BW01ML538 | 0.2889 | KM |  |  |  |  | 534.29 | 538.29 | 2024-06-30 |  |  |  |  | 5 | 3.5 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103690&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103690 | C14-BU-GA-BOILINGB-65.9000km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.04 | KM | 88709 | Goonyella | BOILINGB | BALOOK | 0.04 | KM | GA02ML65 | 0.9 | GA02ML65 | 0.9399 | KM |  |  |  |  | 65.9 | 65.94 | 2024-06-30 | UP |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly fouled ballast on average, some severe fouling and some moderate Rough track geometry, with seven near or at D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104107&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104107 | C14-BU-GA-BRAESIDE-114.300km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.23 | KM | 195477 | Goonyella | BRAESIDE | MINDI | 0.23 | KM | GA02ML114 | 0.2999 | GA02ML114 | 0.53 | KM |  |  |  |  | 114.3 | 114.53 | 2023-06-30 | UP |  |  |  | 4 | 4.4 |  | 4.4 |  | 17.6 |  | 2021-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG |  | 20240630 | 22.03.2021 10:49:42 AUSQLD Tracy Holmes (R870040) Severely fouled, geometry moderate, coincides with track upgrade in Fy22 note 12.04.2021 16:23:17 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk REFER TO NOTIFICATION 2000074553 ORIGINAL NOTIFICATION HAD WORK ORDER AND ACTUALS RECORDED NEW NOTIFICATION CREATED TO CAPTURE FY22 RESIDUAL SCOPE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052411&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052411 | C14-BU-GA-COPPABELLA-157.746km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.383 | KM | 173499 | Goonyella | BROADLEA | BROADLEA | 0.383 | KM | GA02ML157 | 0.7459 | GA02ML158 | 0.13 | KM |  |  |  |  | 157.746 | 158.13 | 2022-06-30 | UP |  |  |  | 4 | 2.5 | 2 | 3 | 1 | 12 | 185 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Sat 30.10.2021 Tim Griffin (r878533) Ammended due to 28Oct FY22 Q3 <(>&<)> Q4 review. See attcahed file / email. FY22 Residual Scope Replan Comments: Near D7 top at 157.900 and 158.080km, fouling varies, generally in the 30-40% range.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094609&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094609 | C14-BU-BW-CALLE-536.350km-DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.45 | KM | 383832 | Blackwater | CALLEMONDAH | MT MILLER | 0.45 | KM | BW02ML536 | 0.3499 | BW02ML536 | 0.8 | KM |  |  |  |  | 536.35 | 536.8 | 2025-06-30 |  |  |  |  | 3.5 | 4.8 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to severely fouled ballast Moderately rough track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052459&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052459 | C14-BU-BW-CALLEMONDAH-536.850km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.745 | KM | 337485 | Blackwater | CALLEMONDAH-ROCKLANDS UP RD |  | 0.7449 | KM | BW01ML536 | 0.8499 | BW01ML537 | 0.5999 | KM |  |  |  |  | 536.85 | 537.6 | 2022-06-30 | UP |  |  |  | 3 | 4.9 |  | 4.9 |  | 14.7 | 185 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | FY22 Residual Scope Replan Comments: Approx 1/3 is 60%+, another 1/3 is 40-60% and remainder 20-30%. Unable to locate geometry for this section, assumed it's not great. Possilble option may be to deliver most fouled scope as C14 if C01 is not viable in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094853&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094853 | C14-BU-BW-DINGO-148km-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.45 | KM | 383672 | Blackwater | DINGO | UMOLO | 0.45 | KM | BW03ML148 | 0 | BW03ML148 | 0.45 | KM |  |  |  |  | 148 | 148.45 | 2024-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to severely fouled ballast Moderately rough track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094854&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094854 | C14-BU-BW-DUARINGA-110.90km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.3 | KM | 246587 | Blackwater | DUARINGA | WALLAROO | 0.2999 | KM | BW04ML110 | 0.9 | BW04ML111 | 0.2 | KM |  |  |  |  | 110.9 | 111.2 | 2024-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Near D7 top and twist defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104550&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104550 | C14-BU-BW-EDUNGALBA-83.670km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.065 | KM | 0 | Blackwater | EDUNGALBA | AROONA | 0.065 | KM | BW03ML83 | 0.67 | BW03ML83 | 0.7349 | KM |  |  |  |  | 83.67 | 83.735 | 2024-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Moderate track geometry, getting rough from about 84.0km Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 199 Created Melissa Durnsford 11/07/2022: Site Inspection Document Uploaded Refer to 2000094920, split for neutral section to be completed by C14 Excavator Undercutters
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094852&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094852 | C14-BU-BW-EDUNGALBA-84.870km-DN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.495 | KM | 415845 | Blackwater | EDUNGALBA | AROONA | 0.4949 | KM | BW03ML84 | 0.8699 | BW03ML85 | 0.1 | KM |  |  |  |  | 84.87 | 85.1 | 2024-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Rough track geometry with near D7 top defects at multiple locations
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094850&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094850 | C14-BU-BW-EPALA-577.850km-DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.486 | KM | 409443 | Blackwater | EPALA | EPALA | 0.4859 | KM | BW02ML577 | 0.8499 | BW02ML578 | 0.34 | KM |  |  |  |  | 577.85 | 578.34 | 2025-06-30 |  |  |  |  | 3.5 | 4.1 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Highly to severely fouled ballast Generally good track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094907&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094907 | C14-BU-BW-EPALA-581.000km-UP. | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.175 | KM | 157660 | Blackwater | EPALA | RAGLAN | 0.1749 | KM | BW01ML581 | 0 | BW01ML581 | 0.1749 | KM |  |  |  |  | 581 | 581.175 | 2024-06-30 | UP |  |  |  | 4 | 4.1 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | HIGH | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast D7 top defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Scope Change Request # 205 Created to split notification into 3. Require confirmation on why cutting out and in. Melissa Durnsford 12/07/2022: Site Inspection Document Uploaded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094928&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094928 | C14-BU-BW-GRACEMERE-13.500km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.185 | KM | 212640 | Blackwater | GRACEMERE | KABRA | 0.1849 | KM | BW04ML13 | 0.5 | BW04ML13 | 0.685 | KM |  |  |  |  | 13.5 | 13.685 | 2024-06-30 | UP |  |  |  | 3.8 | 3.4 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Minimal track geometry defects Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Documents Melissa Durnsford 11/07/2022: Scope Change Request # 188 Created
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103505&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103505 | C14-BU-BW-GRACEMERE-13.850km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.257 | KM | 295397 | Blackwater | GRACEMERE | KABRA | 0.257 | KM | BW04ML13 | 0.8499 | BW04ML14 | 0.1079 | KM |  |  |  |  | 13.85 | 14.108 | 2024-06-30 | UP |  |  |  | 3.75 | 3.35 | 2 | 3.6 | 1 | 13.5 | 185 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Severely fouled ballast Minimal track geometry defects
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103598&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103598 | C14-BU-GA-HATFIELD-54.816km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.104 | KM | 179679 | Goonyella | HATFIELD | BOILINGB | 0.1039 | KM | GA02ML54 | 0.8159 | GA02ML54 | 0.92 | KM |  |  |  |  | 54.816 | 54.92 | 2024-06-30 | UP |  |  |  | 3.3 | 5 | 2 | 4 | 1 | 13.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Ballast fouling varies, some severely fouled sections, moderately fouled on average but all rough Rough track geometry with D7 top and twist defects Split out for AT Site (to be completed C14)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104106&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104106 | C14-BU-GA-HATFIELD-58.450km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.437 | KM | 376325 | Goonyella | HATFIELD-BOLINGBROKE | HATFIELD-BOLINGBROKE | 0.4369 | KM | GA02ML58 | 0.45 | GA02ML58 | 0.887 | KM |  |  |  |  | 58.45 | 58.887 | 2022-06-30 |  |  |  |  | 4 | 5 | 2 | 4 | 1 | 16 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | FY22 Residual Scope Replan Comments: Sent to Zop to confirm 14.12.21 - Ballast fouling is moderate and high, geometry is poor. Historical formation site. Check formation and plan in FY24. REFER TO NOTIFICATION 2000052406 NEW NOTIFICATION CREATED TO CAPTURE FY22 RESIDUAL ACTUALS AND WORK ORDER ALREADY ATTACHED TO ORIGINAL NOTI
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104105&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104105 | C14-BU-GA-DALY BAY-7.095km-ARRIVAL. | GA-02BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.765 | KM | 621722 | Goonyella | HP11B/A PTS-DL11CD PTS | HP11B/A PTS-DL11CD PTS | 0.765 | KM | GA02BA7 | 0.095 | GA02BA7 | 0.8599 | KM |  |  |  |  | 7.095 | 7.86 | 2022-06-30 |  |  |  |  | 4 | 2.6 | 2 | 3 | 1 | 12 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Extended finish km for 1.006km in total length. Tim Griffin 2 July 2021. FY22 Residual Scope Replan Comments: 100m completed per notification 2000088163 21.702 - 21.802. 60%+ for 100% of scope. D7 and D1 tops. REFER TO NOTIFICATION 2000052392, SPLIT TO CAPTURE FY22 RESIDUAL SCOPE ORIGINAL NOTIFICATION HAD A WORK ORDER AND ACTUALS ATTACHED This notification is intended to be partly completed as fix on fail under noti 2000119578 - this notification requires updating.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094851&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094851 | C14-BU-BW-MARMOR-594.760km-DN. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.242 | KM | 205324 | Blackwater | MARMOR | BAJOOL | 0.2419 | KM | BW02ML594 | 0.76 | BW02ML595 | 0 | KM |  |  |  |  | 594.76 | 595 | 2025-06-30 |  |  |  |  | 3.5 | 4.1 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to moderately foulded ballast Near D7 top defects according to track geometry reports
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052456&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052456 | CU-BU-BW-TRYPHINIA-141.800km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.801 | KM | 608000 | Blackwater | ROCKLANDS-RANGAL UP RD |  | 0.801 | KM | BW04ML141 | 0.8 | BW04ML142 | 0.5999 | KM |  |  |  |  | 141.8 | 142.563 | 2028-06-30 |  |  |  |  | 4 | 3.35 | 2 | 4 | 1 | 16 | 185 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | FY22 Residual Scope Replan Comments: Fouling is moderate, high in isolated spots. Geometry is okay apart from one D7 top at 41.890km. Maintenance to identify any current mud holes, replan the rest in FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094893&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094893 | C14-BU-GA-TOOTOOLAH-134.900km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.667 | KM | 645237 | Goonyella | TOOTOOLAH | MORANBAH NTH JCT | 0.667 | KM | GA02ML134 | 0.9 | GA02ML135 | 0.5699 | KM |  |  |  |  | 134.9 | 135.57 | 2024-06-30 | UP |  |  |  | 3.5 | 4.7 | 2 | 4 | 1 | 14 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Moderately to severely fouled ballast (about 50/50 of scope) Moderately rough track geometry at either end 135.570-135.700 captured under fix on fail 2000097276 in FY23 - updated kms in FY24 renewal to remove overlap of scope (end changed from 135.700 to 135.570) PCR TBA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094891&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094891 | C14-BU-GA-WANDOO-86.900km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.698 | KM | 575481 | Goonyella | WANDOO | WAITARA | 0.6979 | KM | GA02ML86 | 0.9 | GA02ML87 | 0.5999 | KM |  |  |  |  | 86.9 | 87.6 | 2024-06-30 | UP |  |  |  | 4 | 5 | 2 | 4 | 1 | 16 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | FY24 C01 Scope captured by the C14 program instead
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094862&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094862 | C14-BU-GA-WANDOO-97.650km-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.388 | KM | 340754 | Goonyella | WANDOO | WAITARA | 0.388 | KM | GA02ML97 | 0.65 | GA02ML98 | 0.0299 | KM |  |  |  |  | 97.65 | 98.03 | 2025-06-30 |  |  |  |  | 3.8 | 5 | 2 | 4 | 1 | 15.2 | 185 | 2022-03-31 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Highly to severely fouled ballast D7 twist at bridge end according to track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052388&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052388 | C14-BU-GA-WOTONGA-175.050km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.2 | KM | 93538 | Goonyella | WOTONGA | WOTONGA | 0.2 | KM | GA01ML175 | 0.05 | GA01ML175 | 0.25 | KM |  |  |  |  | 175.05 | 175.25 | 2022-06-30 |  |  |  |  | 3.5 | 4.6 |  | 4.6 |  | 16.1 | 185 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | FY22 Residual Scope Replan Comments: AT site, D7 tops, severely fouled. Ballast drop to address very shallow ballast was recently completed, needs to be re-assessed for possible future year (FY24+) depending on how effective the ballast drop and resurfacing was
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104102&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000104102 | C14-BU-BW-WYCARBAH-37.300km-UP. | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.95 | KM | 751341 | Blackwater | WYCARBAH | WESTWOOD | 0.9499 | KM | BW04ML37 | 0.2999 | BW04ML38 | 0.25 | KM |  |  |  |  | 37.3 | 38.25 | 2022-06-30 |  |  |  |  | 4 | 3.35 | 2 | 4 | 1 | 16 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | FY22 RESIDUAL C01 SCOPE DEFERRED TO FY24 REFER TO NOTIFICATION 2000052451 NEW NOTIFICATION CREATED TO REPLACE ORIGINAL AS IT WAS ATTACHED TO A WORK ORDER AND COMPLETED
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094421&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094421 | C13 Turnout B/U MA Unallocated TO | MA-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 1 | TURNOUT | 165235 | Moura |  |  | 0 | KM | MA01ML0 | 0 | MA01ML0 | 0 | KM |  |  |  |  | 0 | 0 | 2024-06-30 | MAIN |  |  |  | 5 | 4 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | C13 Reactive Undercut for Moura
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094425&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094425 | C13 Turnout B/U NL Unallocated TO | NL-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 1 | TURNOUT | 166340 | Newlands |  |  | 0 | KM | NL01ML0 | 0 | NL01ML0 | 0 | KM |  |  |  |  | 0 | 0 | 2024-06-30 | MAIN |  |  |  | 5 | 4 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | C13 Reactive Undercut for Newlands
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094410&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094410 | C13 Turnout B/U GA Unallocated TO | GA-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 2 | TURNOUT | 332680 | Goonyella |  |  | 0 | KM | GA01ML8 | 0 | GA01ML8 | 0 | KM |  |  |  |  | 8 | 8 | 2024-06-30 | DOWN |  |  |  | 5 | 4 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | C13 Reactive Undercut for Goonyella Reactive allocation increased to 2 following removal of Red Mountain 7AB due to requiring formation renewal, post MRSB draft. PCR TBA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094395&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000094395 | C13 Turnout B/U BW Unallocated TO | BW-01ML | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 2 | TURNOUT | 330838 | Blackwater |  |  | 0 | KM | BW01ML534 | 0 | BW01ML534 | 0 | KM |  |  |  |  | 534 | 534 | 2024-06-30 | UP |  |  |  | 5 | 4 | 2 | 5 | 1 | 25 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | C13 Reactive Undercut for Blackwater
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094393&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094393 | C13 Turnout B/U Bajool 8CD. | TO000834 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165188 | Blackwater | BAJOOL | BAJOOL | 0 | KM | BW01ML606 | 0.464 | BW01ML606 | 0.464 | KM |  |  |  |  | 606.464 | 606.513 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 606.464 End: 606.513
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094394&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094394 | C13 Turnout B/U Balook ER1.2A. | TO000214 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165260 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.799 | GA01ML74 | 0.799 | KM |  |  |  |  | 74.799 | 74.832 | 2024-06-30 | DOWN |  |  |  | 4.3 | 5 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Start: 74.799 End: 74.532
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094356&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094356 | C13 Turnout B/U Blackridge 12AB. | TO000297 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166439 | Goonyella | BLACKRIDGE | BLACKRIDGE | 0 | KM | GA05ML86 | 0.9799 | GA05ML86 | 0.9799 | KM |  |  |  |  | 86.98 | 86.931 | 2024-06-30 | MAIN |  |  |  | 4.3 | 1.2 | 2 | 2.5 | 1 | 10.8 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | 2 large culverts directly after TO Start: 86.980 End: 86.931
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094397&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094397 | C13 Turnout B/U Blackwater ER5.2E. | TO000774 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127348 | Blackwater | BLACKWATER | BLACKWATER | 0 | KM | BW05PL189 | 0.199 | BW05PL189 | 0.199 | KM |  |  |  |  | 189.199 | 189.173 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2023): Uploaded Walkout Inspection Start: 89.199 End: 89.173
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094396&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094396 | C13 Turnout B/U Blackwater ER5.2D. | TO000773 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127348 | Blackwater | BLACKWATER | BLACKWATER | 0 | KM | BW05PL189 | 0.223 | BW05PL189 | 0.223 | KM |  |  |  |  | 189.223 | 189.248 | 2024-06-30 | PASSING LOOP |  |  |  | 4.3 | 3.2 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2023): Uploaded Walkout Inspection Start: 89.223 End: 89.248
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094398&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094398 | C13 Turnout B/U Bluff 10AB. | TO000653 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 164811 | Blackwater | BLUFF | BLUFF | 0 | KM | BW03ML169 | 0.042 | BW03ML169 | 0.042 | KM |  |  |  |  | 169.042 | 169.078 | 2024-06-30 | DOWN |  |  |  | 4.8 | 3.4 | 2 | 3.6 | 1 | 17.3 |  | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 169.042 End: 169.078
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094400&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094400 | C13 Turnout B/U Callemondah 213A. | TO001174 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW20YR0 | 0.4099 | BW20YR0 | 0.4099 | KM |  |  |  |  | 0.41 | 0.438 | 2024-06-30 | BALLOON |  |  |  | 4.6 | 2.6 | 2 | 3.3 | 1 | 15.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Start: 0.410 End: 0.438
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094401&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094401 | C13 Turnout B/U Callemondah 213B. | TO001156 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW17YR0 | 0.466 | BW17YR0 | 0.466 | KM |  |  |  |  | 0.466 | 0.439 | 2024-06-30 | APPROACH |  |  |  | 4.3 | 2.6 | 2 | 3.3 | 1 | 14.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Start: 0.466 End: 0.439
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094404&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094404 | C13 Turnout B/U Collinsville 12AB. | TO000182 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166340 | Newlands | COLLINSVILLE | COLLINSVILLE | 0 | KM | NL01ML77 | 0.1749 | NL01ML77 | 0.1749 | KM |  |  |  |  | 77.175 | 77.142 | 2024-06-30 | MAIN |  |  |  | 4.2 | 2.5 | 2 | 3.3 | 1 | 13.9 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Cut out prior to level crossing @ 77.180km Start: 77.175 End: 77.142
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094406&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094406 | C13 Turnout B/U Coppabella 46AB. | TO000275 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 128404 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA02ML147 | 0.5749 | GA02ML147 | 0.5749 | KM |  |  |  |  | 147.575 | 147.624 | 2024-06-30 | UP |  |  |  | 4.5 | 4.6 | 2 | 4.1 | 1 | 18.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie in with Coppabella 45AB undercut Start: 147.575 End: 147.624
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094405&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094405 | C13 Turnout B/U Coppabella 45AB. | TO000285 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 128404 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA02ML147 | 0.78 | GA02ML147 | 0.78 | KM |  |  |  |  | 147.78 | 147.828 | 2024-06-30 | UP |  |  |  | 4.8 | 4.6 | 2 | 4.1 | 1 | 19.7 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie in with Coppabella 46AB undercut Start: 147.780 End: 147.828
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094407&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094407 | C13 Turnout B/U Dingo 12CD. | TO000690 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165188 | Blackwater | DINGO | DINGO | 0 | KM | BW03ML140 | 0.7289 | BW03ML140 | 0.7289 | KM |  |  |  |  | 140.729 | 140.684 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 140.729 End: 140.684
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094409&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094409 | C13 Turnout B/U German Creek 9AB. | TO000408 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 128404 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA22ML131 | 0.8169 | GA22ML131 | 0.8169 | KM |  |  |  |  | 131.817 | 131.783 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie into German Creek 7AB Undercut Start: 131.817 End: 131.782
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094408&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094408 | C13 Turnout B/U German Creek 7AB. | TO000409 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 128404 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA22ML131 | 0.8279 | GA22ML131 | 0.8279 | KM |  |  |  |  | 131.828 | 131.862 | 2024-06-30 | BALLOON |  |  |  | 4.1 | 1.1 | 2 | 2.5 | 1 | 10.3 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie into German Creek 9AB Start: 131.828 End: 131.862
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094411&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094411 | C13 Turnout B/U Gracemere 12CD. | TO000662 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165188 | Blackwater | GRACEMERE | GRACEMERE | 0 | KM | BW03ML4 | 0.111 | BW03ML4 | 0.111 | KM |  |  |  |  | 4.111 | 4.038 | 2024-06-30 | DOWN |  |  |  | 4.2 | 3.4 | 2 | 3.6 | 1 | 15.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 4.111 End: 4.038
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094412&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094412 | C13 Turnout B/U Hay Point 11CD. | TO000567 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165260 | Goonyella | HAY POINT | HAY POINT | 0 | KM | GA02BA3 | 0.643 | GA02BA3 | 0.643 | KM |  |  |  |  | 3.643 | 3.68 | 2024-06-30 | BALLOON |  |  |  | 3.9 | 2.3 | 2 | 3.2 | 1 | 12.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | 5/8/22 Zane Hooton: Refer notification 2000088801. Pan-horn contact at this location. OHLE measures ok. Top defect as attached. This renewal will address root cause of pan-horn contact. Start: 3.643 End: 3.680
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094413&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094413 | C13 Turnout B/U Jilalan 48AB | TO000506 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | JILALAN | JILALAN | 0 | KM | GA01ML17 | 0.5859 | GA01ML17 | 0.5859 | KM |  |  |  |  | 17.586 | 17.617 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 17.586 End: 17.617
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094414&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094414 | C13 Turnout B/U Jilalan 82AB. | TO000511 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | JILALAN | JILALAN | 0 | KM | GA01ML22 | 0.634 | GA01ML22 | 0.634 | KM |  |  |  |  | 22.634 | 22.598 | 2024-06-30 | DOWN |  |  |  | 4.5 | 4.8 | 2 | 4.2 | 1 | 18.9 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 22.634 End: 22.598
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094415&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094415 | C13 Turnout B/U Jilalan 83AB. | TO000512 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | JILALAN | JILALAN | 0 | KM | GA01ML23 | 0.261 | GA01ML23 | 0.261 | KM |  |  |  |  | 23.228 | 23.261 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 23.228 End: 23.261
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094416&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094416 | C13 Turnout B/U Mallawa 8CD. | TO000355 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127645 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA02ML168 | 0.2 | GA02ML168 | 0.2 | KM |  |  |  |  | 168.2 | 168.154 | 2024-06-30 | UP |  |  |  | 4.1 | 2.4 | 2 | 3.2 | 1 | 13.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 168.200 End: 168.154
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094417&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094417 | C13 Turnout B/U Mallawa 9AB. | TO000208 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML168 | 0.28 | GA01ML168 | 0.28 | KM |  |  |  |  | 168.28 | 168.329 | 2024-06-30 | GA-01ML |  |  |  | 4.8 | 2.5 | 2 | 3.3 | 1 | 15.8 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 168.280 End: 168.329 De-linked from WO 80113149 as per request from C Franks - 08/06/2023
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094419&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094419 | C13 Turnout B/U McNaughton 7A. | TO000129 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166340 | Newlands | MCNAUGHTON | MCNAUGHTON | 0 | KM | NL04ML81 | 0.535 | NL04ML81 | 0.535 | KM |  |  |  |  | 81.535 | 81.571 | 2024-06-30 | MAIN |  |  |  | 3.2 | 1.7 | 2 | 2.8 | 1 | 9 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Turnout to 85.710km to exit and 81.615km on entry; leading in 81.484km to the turnout Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 81.535 End: 81.571
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094418&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094418 | C13 Turnout B/U Millennium Jct 7AB. | TO000386 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166439 | Goonyella | MILLENNIUM JCT | MILLENNIUM JCT | 0 | KM | GA03ML16 | 0.533 | GA03ML16 | 0.533 | KM |  |  |  |  | 16.533 | 16.58 | 2024-06-30 | MAIN |  |  |  | 4.5 | 2.8 | 2 | 3.4 | 1 | 15.3 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Culvert at 16.610 Start: 16.533 End: 16.580
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094424&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094424 | C13 Turnout B/U Mt Larcom 11CD. | TO000853 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | MOUNT LARCOM | MOUNT LARCOM | 0 | KM | BW01ML564 | 0.7089 | BW01ML564 | 0.7089 | KM |  |  |  |  | 564.709 | 564.756 | 2024-06-30 | UP |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Culvert nearby to TO Start: 564.709 End: 564.756
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094426&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094426 | C13 Turnout B/U Peak Downs ER1.2A. | TO000342 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166439 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA17ML45 | 0.008 | GA17ML45 | 0.008 | KM |  |  |  |  | 45.008 | 45.037 | 2024-06-30 | BALLOON |  |  |  | 4.6 | 1.1 | 2 | 2.5 | 1 | 11.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 45.008 End: 45.037
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094431&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094431 | C13 Turnout B/U Rocklands 9AB. | TO000718 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 120392 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML0 | 0.925 | BW03ML0 | 0.925 | KM |  |  |  |  | 0.925 | 0.877 | 2024-06-30 | DOWN |  |  |  | 3.9 | 4.5 | 2 | 4.1 | 1 | 16 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 0.925 End: 0.877
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094430&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094430 | C13 Turnout B/U Rocklands 12CD. | TO000832 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 120392 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW01ML631 | 0.63 | BW01ML631 | 0.63 | KM |  |  |  |  | 631.63 | 631.679 | 2024-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.6 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 631.630 End: 631.679
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094428&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094428 | C13 Turnout B/U Rocklands 12AB. | TO000760 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 120392 | Blackwater | ROCKLANDS | ROCKLANDS | 0.048 | KM | BW02ML631 | 0.7279 | BW02ML631 | 0.68 | KM |  |  |  |  | 631.73 | 631.78 | 2024-06-30 | DOWN |  |  |  | 3.5 | 4.5 | 2 | 4.1 | 1 | 14.35 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Rocklands 10AB Turnout (TO000666) undercut in FY23 as fix on fail. Removed from undercut program, replaced with Rocklands 12AB (TO000760). PCR 5531 under this same notification.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094429&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094429 | C13 Turnout B/U Rocklands 11AB. | TO000665 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 120392 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW01ML631 | 0.8469 | BW01ML631 | 0.8469 | KM |  |  |  |  | 631.847 | 631.885 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 631.847 End: 631.887
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094432&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094432 | C13 Turnout B/U Sagittarius 12AB | TO000733 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 164811 | Blackwater | SAGITTARIUS | SAGITTARIUS | 0 | KM | BW04ML191 | 0.8149 | BW04ML191 | 0.8149 | KM |  |  |  |  | 191.815 | 191.888 | 2024-06-30 | UP |  |  |  | 3.9 | 3.2 | 2 | 3.6 | 1 | 14 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Melissa Durnsford (07/07/2022): Uploaded Walkout Inspection Document Start: 191.815 End: 191.888
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094433&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094433 | C13 Turnout B/U South Walker 9AB. | TO000250 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 166439 | Goonyella | SOUTH WALKER JCT | SOUTH WALKER JCT | 0 | KM | GA01ML127 | 0.4889 | GA01ML127 | 0.4889 | KM |  |  |  |  | 127.489 | 127.541 | 2024-06-30 | DOWN |  |  |  | 4.2 | 4.7 | 2 | 4.1 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Culvert nearby to TO Start: 127.489 End: 127.541
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094434&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094434 | C13 Turnout B/U Waitara 10AB. | TO000222 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118760 | Goonyella | WAITARA | WAITARA | 0 | KM | GA01ML100 | 0.381 | GA01ML100 | 0.381 | KM |  |  |  |  | 100.381 | 100.417 | 2024-06-30 | DOWN |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 100.381 End: 100.417
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094435&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094435 | C13 Turnout B/U Waitara 11AB. | TO000315 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118760 | Goonyella | WAITARA | WAITARA | 0 | KM | GA02ML100 | 0.549 | GA02ML100 | 0.549 | KM |  |  |  |  | 100.549 | 100.594 | 2024-06-30 | UP |  |  |  | 4.3 | 4.4 | 2 | 4 | 1 | 17.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie in with Waitara 12BCB undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094436&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094436 | C13 Turnout B/U Waitara 12BC. | TO000223 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118760 | Goonyella | WAITARA | WAITARA | 0 | KM | GA01ML100 | 0.643 | GA01ML100 | 0.643 | KM |  |  |  |  | 100.594 | 100.644 | 2024-06-30 | DOWN |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Tie in with Waitara 11AB undercut Start: 100.594 End: 100.644
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094437&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094437 | C13 Turnout B/U Warren 7AB. | TO000699 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | WARREN | WARREN | 0 | KM | BW04ML27 | 0.3649 | BW04ML27 | 0.3649 | KM |  |  |  |  | 27.365 | 27.413 | 2024-06-30 | UP |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.8 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 27.364 End: 27.413
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094438&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094438 | C13 Turnout B/U Warren 7CD. | TO000621 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | WARREN | WARREN | 0 | KM | BW03ML27 | 0.541 | BW03ML27 | 0.541 | KM |  |  |  |  | 27.541 | 27.495 | 2024-06-30 | UP |  |  |  | 4.5 | 3.4 | 2 | 3.6 | 1 | 16.2 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 27.541 End: 27.495
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094439&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094439 | C13 Turnout B/U Westwood 11AB. | TO000620 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW03ML45 | 0.333 | BW03ML45 | 0.333 | KM |  |  |  |  | 45.333 | 45.376 | 2024-06-30 | DOWN |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.5 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification in process | RRIG |  | 20240630 | Start: 45.333 End: 45.376
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094440&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094440 | C13 Turnout B/U Westwood 7BC. | TO000670 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 127591 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW03ML47 | 0.505 | BW03ML47 | 0.505 | KM |  |  |  |  | 47.505 | 47.468 | 2024-06-30 | DOWN |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.4 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 47.505 End: 47.468
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094443&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094443 | C13 Turnout B/U Yukan 9AB. | TO000340 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.533 | GA02ML28 | 0.533 | KM |  |  |  |  | 28.533 | 28.564 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Ties into Yukan 10BC Undercut Culvert at 28.495km Start: 28.533 End: 28.564
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094441&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094441 | C13 Turnout B/U Yukan 10BC. | TO000339 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.6949 | GA02ML28 | 0.6949 | KM |  |  |  |  | 28.695 | 28.663 | 2024-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.1 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | HIGH | Notification completed | RRIG |  | 20240630 | Ties into Yukan 9AB and Yukan 7AB undercuts Start: 28.695 End: 28.663
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094442&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094442 | C13 Turnout B/U Yukan 7AB. | TO001222 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 118289 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.7169 | GA02ML28 | 0.7169 | KM |  |  |  |  | 28.717 | 28.755 | 2024-06-30 | UP |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 16.4 | 185 | 2022-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | HIGH | Notification completed | RRIG |  | 20240630 | Start: 28.717 End: 28.755
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110133&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110133 | C20-BR-BW-GEOTECH-FY24FORFY25 | BW | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 9 | EA | 90000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  |  |  | 25 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20240630 | Geotech (design) notification to be funded in FY24 for FY25 renewal scopes. Estimate of $10,000 per bridge, split by system (9 bridges in BW) To be co-ordinated with the geotech investigation with formation. Timing TBC, either before 1st or 2nd CAC workshop.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110018&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110018 | C20-BR-GA-GEOTECH-FY24FORFY25 | GA | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 1 | EA | 10000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  |  |  | 25 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20240630 | Geotech (design) notification to be funded in FY24 for FY25 renewal scopes. Estimate of $10,000 per bridge, split by system. To be co-ordinated with the geotech investigation with formation. Timing TBC, either before 1st or 2nd CAC workshop.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110135&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110135 | C20-BR-MA-GEOTECH-FY24FORFY25 | MA | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 1 | EA | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  |  |  | 25 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20240630 | Geotech (design) notification to be funded in FY24 for FY25 renewal scopes. Estimate of $10,000 per bridge, split by system. To be co-ordinated with the geotech investigation with formation. Timing TBC, either before 1st or 2nd CAC workshop.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110134&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110134 | C20-BR-NL-GEOTECH-FY24FORFY25 | NL | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 1 | EA | 10000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  |  |  | 25 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20240630 | Geotech (design) notification to be funded in FY24 for FY25 renewal scopes. Estimate of $10,000 per bridge, split by system. To be co-ordinated with the geotech investigation with formation. Timing TBC, either before 1st or 2nd CAC workshop.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043536&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043536 | C20-BR-BW-HUT CREEK-UP-572.934KM | BR101453-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.145 | KM | 612915 | Blackwater | AMBROSE | EPALA | 0.1 | KM | BW01ML572 | 0.935 | BW01ML573 | 0.08 | KM |  |  |  |  | 572.935 | 573.08 | 2024-06-30 | UP |  |  |  | 4.16 | 4.1 | 3 | 4.1 | 18 | 17.1 |  | 2022-03-31 | 2020-11-13 | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Deferred from FY22 to FY24 to align with relieving slab works and landholder issues Existing notification updatied and tech scope added One shoulder is highly to severely fouled in 2021 GPR FY24 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094373&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094373 | C20-BR-BW-ANDA HORSESHOE-UP-96.770KM | BR100278-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.12 | KM | 667963 | Blackwater | AROONA | DUARINGA | 0.1199 | KM | BW04ML96 | 0.77 | BW04ML96 | 0.89 | KM |  |  |  |  | 96.77 | 96.89 | 2024-06-30 | UP |  |  |  | 4.1 | 3.4 | 3 | 4 | 1 | 16.4 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | AN-DA UP Horseshoe Bridge Rollout Gracemere districts highest priority bridge in FY24 7th highest future condtion score, 6th highest CRA score of bridges in BW system. 58% fouled in 2021 GPR - source: fixed asset BI Geometry is Near D7 top towards the middle of the bridge at time of scoping Central line mainline, empty, moderate-high traffic, moderate tonnage. No record of previous rollout at time of scoping. FY24 priority 7/8 - for change context purposes, subject to change upon review of new data
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094372&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094372 | C20-BR-BW-BONE CREEK-UP-101.346KM | BR100039-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.179 | KM | 882631 | Blackwater | AROONA | DUARINGA | 0.1789 | KM | BW04ML101 | 0.3459 | BW04ML101 | 0.525 | KM |  |  |  |  | 101.346 | 101.525 | 2024-06-30 | UP |  |  |  | 4.6 | 3.4 | 4 | 4.3 | 1 | 19.8 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | 3rd highest future condtion score, 5th highest CRA score of bridges in BW system. 65% fouled in 2021 GPR - source: fixed asset BI Geometry is moderately rough top and twist at the time of scoping. Central line mainline, empty, moderate-high traffic, moderate tonnage. No record of previous rollout at time of scoping. FY24 priority 3/8 - for change context purposes, subject to change upon review of new data
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091297&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091297 | C20-BR-BW-CALLIOPE RIVER UP-537.672KM. | BR101331-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.357 | KM | 1700000 | Blackwater | CALLEMONDAH | MT MILLER | 0.3569 | KM | BW01ML537 | 0.672 | BW01ML538 | 0.029 | KM |  |  |  |  | 537.672 | 538.029 | 2024-06-30 |  |  |  |  | 4.5 | 4.8 | 3 | 4.9 | 1 | 22.1 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | MEDIUM | LOW | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | N4 notification for Calliope River Up Road raised for February Change Board. Tech scope attached - formation required one end (low km end, 600mm standard formation) FY24 1/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094380&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094380 | C20-BR-GA-GRASSTREE BEACH ROAD-UP-9.477K | BR200652-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.107 | KM | 623796 | Goonyella | DALRYMPLE XOVER PTS | PRAGUELANDS | 0.1069 | KM | GA02ML9 | 0.4769 | GA02ML9 | 0.5839 | KM |  |  |  |  | 9.477 | 9.584 | 2024-06-30 | UP |  |  |  | 4 | 4.6 | 3 | 4.4 | 1 | 17.6 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | 15% fouled in 2021 GPR, however 2020 is much higher- source fixed asset BI. Fouling has decreased considerably between 2020 and 2021 from fouled/highly fouled to moderately clean. Geometry at bridge ends is near D7 top at the time of scoping FY24 Mainline near ports, Very high traffic and MGT, loaded traffic Last rolled out in 2013 - 11 year cycle if completed in FY24 FY25 priority 2/4 - for change context purposes, subject to change upon review of new data Bridge strengthening earmarked for FY30 Revised Priority FY24 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094377&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094377 | C20-BR-MA-LEIXLIP CREEK-MAIN-30.154KM | BR400169-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.116 | KM | 610571 | Moura | GRAHAM | STIRRAT | 0.116 | KM | MA01ML30 | 0.1539 | MA01ML30 | 0.27 | KM |  |  |  |  | 30.154 | 30.27 | 2024-06-30 | MAIN |  |  |  | 4.3 | 1.3 | 3 | 3.2 | 1 | 13.8 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Depot comments - Rolled ballast - ends require constant attention, may need to take a look at the formation, has had a ballast drop at the low km end to lift it up
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094376&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094376 | C20-BR-BW-TARGINNIE ROAD-UP-546.478KM. | BR101404-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.124 | KM | 623137 | Blackwater | MT MILLER | YARWUN | 0.1239 | KM | BW01ML546 | 0.4779 | BW01ML546 | 0.6019 | KM |  |  |  |  | 546.478 | 546.602 | 2024-06-30 | UP |  |  |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Gracemere Superintendent priority for FY24 Fouling at 20% on average in 2021 GPR. Geometry moderately rough. Webmap shows consistent fouling yellow-orange through bridge, mud holes don't appear to be forming. FY24 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094374&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094374 | C20-BR-BW-WALTON CREEK-UP-163.638KM. | BR100129-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.101 | KM | 379812 | Blackwater | PARNABAL | WALTON | 0.101 | KM | BW04ML163 | 0.683 | BW04ML163 | 0.784 | KM |  |  |  |  | 163.683 | 163.784 | 2024-06-30 | UP |  |  |  | 4.4 | 3.4 | 3 | 4 | 1 | 17.6 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | 4th highest future condition score and 3rd highest CRA score of bridges in BW system. 45% fouled in 2021 GPR - source: fixed asset BI. Central line mainline - moderate-high traffic, empty track - moderate MGT. No record of previous rollout at time of scoping. FY24 priority 4/8 - for change context purposes, subject to change upon review of new data Both Walton Ck bridges are in FY24 - opportuntity to deliver two short bridges together
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094370&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094370 | C20-BR-BW-WALTON CREEK-DOWN-163.695KM. | BR100175-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.193 | KM | 289560 | Blackwater | PARNABAL | WALTON | 0.0769 | KM | BW03ML163 | 0.6949 | BW03ML163 | 0.772 | KM |  |  |  |  | 163.965 | 163.772 | 2024-06-30 | DOWN |  |  |  | 4.7 | 3.4 | 3 | 4 | 1 | 18.8 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | 2nd Highest future condition score and CRA of bridges in BW system. 68% fouled in 2021 GPR - source: fixed asset BI Central line mainline - Moderate-high traffic, loaded track - high MGT No record of previous rollout at time of scoping. FY24 priority 2/8 - for change context purposes, subject to change upon review of new data Both Walton Ck bridges are in FY24 - opportuntity to deliver two short bridges together FY24 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094339&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094339 | C20-BR-BW-BURNETT OVERPASS-DOWN-0.926KM | BR100576-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.088 | KM | 461099 | Blackwater | ROCKLANDS | STANWELL | 0.1059 | KM | BW03ML0 | 0.926 | BW03ML1 | 0.014 | KM |  |  |  |  | 0.926 | 1.014 | 2024-06-30 | DOWN |  |  |  | 5 | 3.4 | 3 | 4 | 1 | 20 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | The Highest future condition score and CRA of bridges in BW system. Rolled out in FY17 and already has mud holes / powdering ballast through the whole bridge - potential fix on fail risk! 76% fouled in 2021 GPR - source: fixed asset BI Central line mainline near NCL - High traffic, loaded track - high MGT FY24 priority 1/8 - for change context purposes, subject to change upon review of new data Previous bridge strengthening bridge. Needs a bridge renewal ultimately but that will be in FY26 at the earliest and the bridge won't last until then in its current state
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093916&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000093916 | FENCING & CORRIDOR SECURITY REACTIVE | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 450000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 4.1 | 1 | 5 | 1 | 25 |  | 2022-03-31 | 2022-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093915&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000093915 | FENCING & CORRIDOR SECURITY REACTIVE | GA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 400000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 3.8 | 1 | 5 | 1 | 25 |  | 2022-03-31 | 2021-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093918&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000093918 | FENCING & CORRIDOR SECURITY REACTIVE | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 250000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 2.1 | 1 | 5 | 1 | 25 |  | 2022-03-31 | 2022-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093917&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000093917 | FENCING & CORRIDOR SECURITY REACTIVE | NL | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 225000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 2.7 | 1 | 5 | 1 | 25 |  | 2022-03-31 | 2023-10-05 | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112783&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | NON-COAL | 002000112783 | Burngrove to Nogoa Fencing FY24 | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 60000 | Blackwater | BURNGROVE | NOGOA | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 202.36 | 263.15 | 2024-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | [5 empty] | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093047&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093047 | C05-FR-NL-ABERDEEN-38.000km. | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.135 | KM | 413454 | Newlands | ABERDEEN | BINBEE | 0.135 | KM | NL01ML38 | 0 | NL01ML38 | 0.135 | KM |  |  |  |  | 38 | 38.135 | 2023-09-30 | MAIN LINE |  |  |  | 4 | 1.7 | 2 | 4 | 1 | 16 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | Tim Griffin (r878533) 9 March 2022. Linked to N7 formation 2000087739 where Fix on Fail portion was undertaken on 19 April 2022 then aided by maintenance plan until July 2023 (FY24 Q1) Planned renewal. MD 14.03.2022: Tangent Track, Mares Nest Creek Bridge Splays (last long bearer) at 38.135, Dragging Equipment Detector <(>&<)> associated bonds at 38.159km Adjoins private landowner. Access at Level Crossing ID3290 Private Access Road off Mount Aberdeen Road. 11.05.2022 Tim Griffin (r878533) Assume 50% unsuitable (Max of 900mm) given poor historic drainage. 10.10.2022 B.Crozier R888068. Notification showing extents 38.000-38.250km. Scope estimate shows length of 135m. No formation on Mares Nest Creek bridge so updated location data to 135m.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090992&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000090992 | C05-FR-BW-AROONA-96.100km. | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.55 | KM | 1623499 | Blackwater | AROONA | DUARINGA | 0.55 | KM | BW03ML96 | 0.1 | BW03ML96 | 0.65 | KM |  |  |  |  | 96.1 | 96.65 | 2024-06-30 | DOWN |  |  |  | 4 | 4 | 2 | 4 | 1 | 16 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | 28.01.2022 Tim Griffin (r878533) Western End of Down Road at Aroona, noting that C14 ballast undercut FLOC TO 000631 (7C/D at BW03ML96.038km) done in FY22 to aid ballast height. Linked to N4 notification ballast height reduction 2000054902. Planned formation renewal starting at Western End (previously in 2021 under TSR by Civil Mtce Gracemere) noting Horseshoe Swamp Creek bridge locality and working back towards Rockhampton. 11.05.2022 Tim Griffin (r878533). Assume unsuitable to be 50% (Max of 900mm depth) due to flood plain of Dawson River.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077822&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000077822 | C05-FR-BW-AROONA-100.200km | BW-04ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 958780 | Blackwater | AROONA | DUARINGA | 0.4 | KM | BW04ML100 | 0.2 | BW04ML100 | 0.5999 | KM |  |  |  |  | 100.2 | 100.6 | 2024-06-30 | UP |  |  |  | 3.5 | 3 | 2 | 3 | 1 | 10.5 | 184 | 2022-03-31 |  | Formation Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | 11.05.2022 Tim Griffin (r878533). Assume 40% unsuitable to max of 900mm depth considering age of formation near Duaringa. 15/01/2024 Anthony Maskell (r869346): November 2023 closure impacted by rain and works were cancelled. Material has already been delivered to site. No Geotech information available as Geotech testing was not completed in FY24 NIL Reactive formation history evident in SAP at this location Geometry 100.500 - 100.900km has been consistently good 2021 – Current. Geometry 100.300 - 100.400km has been consistently poor 2021 – Current (at DED). Likely due to lack of preventative maintenance / resurfacing around wayside equipment. This location has been under TSR twice in 2023 (June <(>&<)> October, SR202306-005439 <(>&<)> SR202311-005822). Maintenance undercut 100.330 (10m) completed 09/06/2023 (2000111735) <(>&<)> prior to this a lift and pack 10/03/2023 – latest geometry Oct 2023 suggests issue persists. GPR suggests higher fouling at proposed revised location Opportunity exists to adjust planned formation scope to cover this location, strengthening the section through the wayside equipment. Original Scope: BW-04ML (Up) 100.500 - 100.900km (400m) (FY24 2000077822) Proposed remain in FY24 but amend to 100.200 – 100.600km. Execution in February 2024 - Change approved in December 2023 Change Board. END COMMENT
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077784&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000077784 | C05-FR-BW-BAJOOL-606.256km | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 0.37 | KM | 1470181 | Blackwater | BAJOOL | ARCHER | 0.3699 | KM | BW02ML606 | 0.256 | BW02ML606 | 0.626 | KM |  |  |  |  | 606.256 | 606.626 | 2024-06-30 | DOWN |  |  |  | 3.5 | 5 | 2 | 4 | 1 | 7 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | * 27.05.2021 10:50:27 AUSQLD Tracy Holmes (R870040) * Highest priority in section for formation renewal scope. Geometry issues exist at turnouts (double crossover), anacdotal evidence is that the issues are due to excessive ballast height. No geotechnical testing or ballast test pits have been taken to confirm. Further geotech testing to be completed in FY24 prior to future renewal plans to be developed in future years. END COMMENT 27.05.2021 10:50:27 AUSQLD Tracy Holmes (R870040) Highest priority in section 11.01.2022 Tim Griffin (r878533)Technical Scope and site photos obtained on 11 Jan 2022, noting formation renewal between FLCO BR101268 (6 Mile Creek) and Level Xing ID1776 (Magazine Road Crossing). See attachments. 11.05.2022 Tim Griffin (r878533) Assume 50% unsuitable to max depth of 900mm.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052735&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052735 | C05-FR-GA-BROADLEA-164.450km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.52 | KM | 1298478 | Goonyella | BROADLEA | BURTON DOWNS | 0.52 | KM | GA01ML164 | 0.45 | GA01ML164 | 0.9699 | KM |  |  |  |  | 164.45 | 164.97 | 2024-06-30 | DOWN |  |  |  | 3.5 | 4 | 2 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: Formation is on a curve >1000m. Corridor access points via LXID's 7028 and 3206. LXID7028 at 164.945km is inside the formation so would only be an access point for any material delivery and at the beginning of the renewal. The end marker has been extended from 164.945 to the 164.970 to include the level crossing at the 164.945km 03/02/2022 R888068 Ben Crozier - issue with start/end km in location tab showing total length of 210.913km long. Updated location tab to reflect start/end km from linear data on notification tab. 11.05.2022 Tim Griffin (r878533) Assume 50% (max depth of 900mm) unsuitable material due to curve track and level crossing mixture.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067365&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000067365 | C05-FR-MA-CLARKE-71.200km | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.3 | KM | 740310 | Moura | CLARKE | FRY | 0.2999 | KM | MA01ML71 | 0.2 | MA01ML71 | 0.5 | KM |  |  |  |  | 71.2 | 71.5 | 2024-06-30 | MAIN LINE |  |  |  | 4 | 3 | 2 | 3 | 1 | 12 | 184 | 2022-03-31 |  | Formation Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | 11.05.2022 Tim Griffin (r878533) Assume 50% unsuitable to a max depth of 900mm due to clay soil.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052736&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052736 | C05-FR-GA-INGSDON-22.250km. | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.8 | KM | 2342925 | Goonyella | INGSDON | RED MOUNTAIN | 0.802 | KM | GA03ML22 | 0.25 | GA03ML23 | 0.05 | KM |  |  |  |  | 22.25 | 23.05 | 2024-06-30 | MAIN LINE |  |  |  | 4 | 4 | 3 | 4 | 1 | 16 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: Corridor access point at 22.850km. Culvert 23.230km; Loc Box 23.000km <(>&<)> 22.600km + associated cables Tangent track 9.02.2022 Tim Griffin (r878533) identified and confirmed original Scope had 250m overlap across FY23 planned formation renewal (23km050m to 23km700m being 650m length), so agreed with Construction delivery and Network capacity and Luke Brownsey FY24 Scope still remaining at 800m, but commencing at 22.250km and finishing at 23.050km (Integrating with FY23 commencement). 11.05.2022 Tim Griffin (r878533) Assume 70% unsuitable (max depth of 900mm if not 'cement mud jacking' due to Red Mountain historic geoemetry and TSR impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092001&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000092001 | C05-FR-BW-MARMOR-604.512km. | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.16 | KM | 447526 | Blackwater | MARMOR | BAJOOL | 0.16 | KM | BW01ML604 | 0.512 | BW01ML604 | 0.672 | KM |  |  |  |  | 604.512 | 604.672 | 2024-06-30 | UP |  |  |  | 4 | 4 | 2 | 4 | 1 | 16 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | 17.02.2022 Tim Griffin (r878533) Formation renewal works tie into FY23 (Sept/Oct 2022) Bajool No10pts turnout renewal and associated drainage(Point Asset FLOC. Works to be undertaken beneath Port Alma road overpass along with drainage longnitudual culverts (Fieldsides) into Southern RCB culvert drainage at 604km500m. Close to overpass adutment foundations and restricted overhead clearance (4400mm height). See attached reports. 11.05.2022 Tim Griffin (r878533) Assume unsuitable to be 30% as per Standard Drawing due to undercut required for track lowering and to achieve design ballast depth, since rock underneath.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052732&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052732 | C05-FR-GA-PEAK DOWNS-57.100km. | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.275 | KM | 736962 | Goonyella | PEAK DOWNS | HARROW | 0.275 | KM | GA03ML57 | 0.1 | GA03ML57 | 0.375 | KM |  |  |  |  | 57.1 | 57.375 | 2024-06-30 | MAIN LINE |  |  |  | 3.5 | 4 | 2 | 3 | 1 | 10.5 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: Formation is on an embankment with reasonable access road side. BHP have a mining lease on the field side. Track is tangent alignment. 11.05.2022 Tim Griffin (r878533) Assume as per Standard Drawing requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052753&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052753 | C05-FR-NL-PRING-8.800km. | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 1015620 | Newlands | PRING | BUCKLEY | 0.4 | KM | NL01ML8 | 0.8 | NL01ML9 | 0.2 | KM |  |  |  |  | 8.8 | 9.2 | 2024-06-30 | MAIN LINE |  |  |  | 4 | 1.7 | 2 | 3 | 1 | 12 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: Formation will need to be completed in a system closure as there is no side access on NL-01ML. Access needs to be gained across the passing loop at Buckley. Track Magnet 9.154km, Signal + Bonding 8.740km. Tangent Track Corridor access via Mt Buckley Road LX ID3277 @ 11.850km 01/02/2022 R888068 Ben Crozier - issue with start/end km in location tab. Updated location tab to reflect start/end km from linear data on notification tab. 11.05.2022 Tim griffin (r878533) Assume 60% unsuitable (max depth of 900mm) due to poor drainage and cross flow runoff / levy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052731&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000052731 | C05-FR-GA-SARAJI-79.000km. | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.35 | KM | 1484162 | Goonyella | SARAJI | LAKE VERMONT | 0.3499 | KM | GA03ML79 | 0 | GA03ML79 | 0.3499 | KM |  |  |  |  | 79 | 79.35 | 2024-06-30 | MAIN LINE |  |  |  | 3.5 | 4 | 2 | 4.2 | 1 | 7 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG INIF |  | 20240630 | MD: OC Saraji to Lake Vermont Main Limited access as the formation is in a cutting with a narrow access road Corridor access at 78.401km LX ID3607 11.05.2022 Tim Griffin (r878533) Assume 40% unsuitable to max depth of 900mm.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133330&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000133330 | C05-FR-BW-WARREN-28.800km. | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.305 | KM | 1350000 | Blackwater | WARREN | WYCARBAH | 0.3049 | KM | BW03ML28 | 0.8 | BW03ML29 | 0.1 | KM |  |  |  |  | 28.8 | 29.1 | 2024-06-30 | DOWN |  |  |  | 4.8 | 3.4 | 3 | 4 | 1 | 19.3 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20240630 | New Formation Scope agreed in December 2023 Change Board. Current reactive measures (shear keys) completed in FY24 are not holding and full renewal is required. Formation Renewal requirements: Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. Clean, clear and reinstate drainage from 28.700km to 29.200km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to construction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): - Reuse existing rail - Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) - Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) - Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017. Past Reactive Works completed: 2000124939, 28.830 - 29.000km, Shear Key (Completed 2023) 2000114598, 29.050 - 29.075km, Shear Key (Completed 2023)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077789&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000077789 | C05-FR-BW-WARREN-30.150km. | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.3 | KM | 745758 | Blackwater | WARREN | WYCARBAH | 0.2999 | KM | BW03ML30 | 0.1499 | BW03ML30 | 0.45 | KM |  |  |  |  | 30.15 | 30.45 | 2024-06-30 | DOWN |  |  |  | 3.5 | 4 | 2 | 3 | 1 | 10.5 | 184 | 2022-03-31 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | HIGH | HIGH | Notification in process | RRIG INIF |  | 20240630 | 11.05.2022 Tim Griffin (r878533) Assume 80% unsuitable to max depth of 900-1200mm due to Kalpa flood plain soil history and water table level.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077816&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077816 | Formation C05 Reactive Works | BW | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 2064120 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 | 184 | 2022-03-31 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067408&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000067408 | Formation C05 Reactive Works | GA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1704222 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 | 184 | 2022-03-31 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077830&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077830 | Formation C05 Reactive Works | MA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1799490 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 3 | 5 | 1 | 25 | 188 | 2022-03-31 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | 450m of fix on fail at $3800/m
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067429&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000067429 | Formation C05 Reactive Works | NL | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 476335 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 3 | 5 | 1 | 25 | 184 | 2022-03-31 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | 100m at $4500/m
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077877&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000077877 | FORMATION GEOTECH DESIGN | BW | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 33416 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3.5 | 4 | 2 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification completed | SCPR |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077878&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000077878 | FORMATION GEOTECH DESIGN | GA | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 33416 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3.5 | 4 | 2 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification completed | SCPR |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077879&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000077879 | FORMATION GEOTECH DESIGN | MA | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 33416 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3 | 2 | 2 | 4 | 1 | 12 | 184 | 2022-03-31 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077880&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000077880 | FORMATION GEOTECH DESIGN | NL | CIVIL | FORMATION | GEOTECH | DESIGN | 1 | LUMPSUM | 33416 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3 | 2 | 1 | 3 | 1 | 6 | 184 | 2022-03-31 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification completed | SCPR |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077851&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000077851 | CIVIL GPR RUN BLACKWATER | BW | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 624000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 25 |  |  |  | 2022-03-31 |  | Ground Penetrating Radar | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 27.05.2021 11:50:37 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE. APPROX KM BASED ON FY21 SCOPE = 954.068KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077863&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000077863 | CIVIL GPR RUN GOONYELLA | GA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 590000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 25 |  |  |  | 2022-03-31 |  | Ground Penetrating Radar | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 27.05.2021 12:02:39 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE FOR FUTURE YEARS SCOPE HANDOVER. SCOPE BASED ON FY21 SUBMISSION IS 796.421KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077864&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000077864 | CIVIL GPR RUN MOURA | MA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 210000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 25 |  |  |  | 2022-03-31 |  | Ground Penetrating Radar | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 27.05.2021 12:02:40 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN SCOPE FOR GPR AS REQUIRED FOR BALLAST UNDERCUTTING SCOPE HANDOVER IN FUTURE YEARS. SCOPE FOR GPR FOR MOURA BASED ON GPR FY21 IS 246.07KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079939&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000079939 | C58-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 359898 | Blackwater | BW | BW | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  | LIKE FOR LIKE | LIKE FOR LIKE | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 |  | Level Crossing Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Reactive Works
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079970&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000079970 | C58-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 232875 | Goonyella | GA | GA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  | LIKE FOR LIKE | LIKE FOR LIKE | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 |  | Level Crossing Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Reactive Works. Notes on 20 March 2022 Future condition 5 and Criticality Index 5, CRA Index 25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079972&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000079972 | C58-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 74097 | Moura | MA | MA | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  | LIKE FOR LIKE | LIKE FOR LIKE | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 | 2022-03-31 | Level Crossing Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Reactive Works. 20 March 2022 notes. Future condition 5, Criticality Index 5, CRA Index 25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079971&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000079971 | C58-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 158778 | Newlands | NL | NL | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  | LIKE FOR LIKE | LIKE FOR LIKE | 5 | 5 | 2 | 5 | 1 | 25 |  | 2022-03-31 | 2022-03-31 | Level Crossing Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Reactive Works
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044025&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044025 | C58-LX-MA-CALLE-24.71km | LX005965 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 659076 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML24 | 0.7099 | MA01ML24 | 0.7099 | KM |  |  | 24.71 | 24.71 | 24.71 | 24.71 | 2024-06-30 | SINGLE |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.8 | 1.3 | 2 | 3 | 1 | 8.4 |  | 2022-03-31 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 15.01.2020 13:18:55 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY24 due to low priority * 31.03.2021 09:17:55 AUSQLD Sharbaree Biswas (R865006) * CONDITION ASSESMSNET DATA IN THE ATTACHMENT FOR THE DESIGN TEAM 31.03.2021 09:17:55 AUSQLD Sharbaree Biswas (R865006) CONDITION ASSESMSNET DATA IN THE ATTACHMENT FOR THE DESIGN TEAM 12 JULY 2021: discussion with Geoff O'Connor The crossing requires full reconstruction except rail replacement (there is already rail onsite). Geoff is meeting with the AM <(>&<)> the RAP engineer on 21 July. Rail replacement <(>&<)> renewal should be done at once. IFC DESIGN document has been added in SPM on 14 March 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068817&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000068817 | C58-LX-BW-CREW-20.86km | LX003457 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 659076 | Blackwater | CREW | MCKENZIE | 0 | KM | BW08ML20 | 0.8599 | BW08ML20 | 0.8599 | KM |  |  | 20.86 | 20.86 | 20.86 | 20.86 | 2024-06-30 | RILEYS CROSSING RD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.33 | 1.2 | 2 | 3 | 1 | 7 |  | 2022-03-31 | 2022-03-31 | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Inspected on 21 July 2021. To be renewed in FY24. Scope prepared. It is a public crossing but has height gauges with 5.1m overhead clearance. To be investigated by the design team whether to change the clearance to 5.2m and the height gauges to be removed. Waiting on the discussion with Colin and Ron. 20.03.2024 Survey still outstanding. General arrangement design to be provided. Standard design docs added. 27/10/22 Will Schuh updated condition to 3 in line with photo evidence. Requires ongoing work to improve inspectors condition ratings.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083374&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000083374 | C58-LX-GA-MT MCLAREN-61.902km | LX005841 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 405632 | Goonyella | MOUNT MCLAREN | BLACKRIDGE | 0 | KM | GA05ML61 | 0.925 | GA05ML61 | 0.925 | KM |  |  | 61.902 | 61.902 | 61.902 | 61.902 | 2024-06-30 | RUSSELL PARK ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.2 | 1.2 | 2 | 3 | 1 | 9.6 | 5657 | 2022-03-31 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | BODAN Panels to be used in lieu of asphalt. CR submitted 5657. FY24 MAJOR RENEWAL. Supporting documents have been added. Geotech inv estigation to be conducted by Civil Design on a separate trip (VS informed). It was not included in the first trip when ID3258 was completed. PCR 5124. DD30 added in SPM as the IFP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079980&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000079980 | C58-LX-BW-RANGAL-195.752km | LX020243 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 659076 | Blackwater | RANGAL | BURNGROVE | 0 | KM | BW03ML195 | 0.752 | BW03ML195 | 0.752 | KM |  |  | 195.755 | 195.755 | 195.752 | 195.752 | 2024-06-30 | EMERGENCY ACCESS ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 10 | 2.05 | 2 | 10 | 1 | 100 |  | 2022-03-31 | 2022-03-31 | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | FY24 Construction. DD30 has been added. DD50 issued 29.03.2022 20.03.2022 Notes This crossing has to be constructed in FY24 before the renewal of ID985. This crossing shall be used as the temporary access road during the renewal of ID985. Renewal - Strategic: New Construction Future condition 10, Criticality Index 10, CRA Index 100.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079997&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000079997 | C58-LX-BW-BLUFF-171.08km | LX005564 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML171 | 0.1039 | BW03ML171 | 0.1039 | KM |  |  | 171.08 | 171.08 | 171.08 | 171.08 | 2024-06-30 | UNNAMED ROAD |  |  |  | 3.06 | 3.35 | 2 | 3.64 | 1 | 11.13 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Design for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104894&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104894 | C58-LX-MA-CALLE-533.897km | LX000708 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 0 | Moura | CALLEMONDAH | YARWUN | 0 | KM | NC02ML533 | 0.893 | NC02ML533 | 0.893 | KM |  |  |  |  | 533.897 | 533.897 | 2024-06-30 | CALLEMONDAH DRIVE NCL |  |  |  | 3 | 4.8 | 2 | 4 | 1 | 12.6 | 5471 |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | PCR5471- the design of ID708 to be carried out with ID6090 in FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101048&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000101048 | C58-LX-NL-DURROBURRA-1159.574km | LX007195 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 49396 | Newlands | DURROBURRA | KAILI | 0 | KM | NC03ML1159 | 0.5729 | NC03ML1159 | 0.5729 | KM |  |  |  |  | 1159.574 | 1159.574 | 2024-06-30 | DRY CKEEK ROAD |  |  |  | 2.6 | 3.2 | 2 | 3.58 | 1 | 9.31 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101985&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000101985 | C58-LX-GA-HAY POINT-0.066km | LX006470 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA0 | 0.066 | GA01BA0 | 0.066 | KM |  |  |  |  | 0.066 | 0.066 | 2025-06-30 | HAY POINT RD |  |  |  | 2.16 | 3.2 | 2 | 3.58 | 1 | 7.73 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Placed in FY24 Design- fully scoped on 11 Aug 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101983&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000101983 | C58-LX-GA-HAY POINT-5.518km | LX020011 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA5 | 0.506 | GA01BA5 | 0.506 | KM |  |  |  |  | 5.518 | 5.518 | 2024-06-30 | ACCESS RD HAY PT ARRIVAL |  |  |  | 2.28 | 3.2 | 2 | 3.58 | 1 | 8.16 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101683&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000101683 | C58-LX-MA-PARANA-10.354km | LX006090 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Moura | PARANA | CALLEMONDAH | 0 | KM | MA01ML10 | 0.3569 | MA01ML10 | 0.3569 | KM |  |  |  |  | 10.354 | 10.354 | 2024-06-30 | CALLEMONDAH DRIVE |  |  |  | 4.2 | 3.2 | 2 | 3.58 | 1 | 15.04 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068850&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000068850 | C58-LX-BW-RAGLAN-588.78km | LX001717 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW01ML588 | 0.778 | BW01ML588 | 0.778 | KM |  |  | 588.78 | 588.78 | 588.78 | 588.78 | 2024-06-30 | TWELVE MILE ROAD |  |  |  | 3.18 | 1.3 | 2 | 2.59 | 1 | 8.24 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FY24 Design for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103557&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103557 | C58-LX-BW-WARREN-36.715km | LX001079 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Blackwater | WARREN | WYCARBAH | 0 | KM | BW03ML36 | 0.7099 | BW03ML36 | 0.7099 | KM |  |  |  |  | 36.715 | 36.715 | 2024-06-30 | ROSEWOOD ROSE |  |  |  | 2.9 | 3.4 | 2 | 4 | 1 | 10.6 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Update the DESIGN (Update the existing IFC) to match the new requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044009&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044009 | C58-LX-BW-ARCHER-619.35km. | LX003178 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 859655 | Blackwater | ARCHER | MIDGEE | 0 | KM | BW01ML619 | 0.3499 | BW01ML619 | 0.3499 | KM |  |  |  |  | 619.35 | 619.35 | 2024-06-30 | COMINO ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.4 | 4.1 | 2 | 4 | 1 | 13.6 | 3662 | 2022-03-31 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 21.01.2020 08:41:16 AUSQLD Sharbaree Biswas (R865006) * This crossing is being delayed to FY22 and the replacement is ID890 Toonda Road. * 09.03.2020 11:55:55 AUSQLD Sharbaree Biswas (R865006) * Moved again into FY23 as per funding restriction. * 09.03.2020 15:18:10 AUSQLD Sharbaree Biswas (R865006) * Moved back in FY22 as per funding allocation. * 11.12.2020 09:03:14 AUSQLD Sharbaree Biswas (R865006) * Pushed back to FY24 for other priority crossings. Moved back in FY22 as per funding allocation. 11.12.2020 09:03:14 AUSQLD Sharbaree Biswas (R865006) Pushed back to FY24 for other priority crossings. FY24 CONSTRUCTUON/RENEWAL TO BE as per the new formation extent. Standards are attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068819&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000068819 | C58-LX-GA-BURTON DOWNS-168.488km. | LX003258 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 859655 | Goonyella | BURTON DOWNS | MALLAWA | 0 | KM | GA01ML168 | 0.4879 | GA01ML168 | 0.4879 | KM |  |  | 168.488 | 168.488 | 168.488 | 168.488 | 2024-06-30 | BURTON MINE ACC RD (3 TRACKS) |  | AS PER AURIZON STD DESIGN | AS PER AURIZON STD DESIGN | 3.12 | 2.4 | 2 | 3 | 1 | 10.03 |  | 2022-03-31 | 2022-03-31 | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | RAP team feedback received on 14 July 2021: (1) This is the top priority from Goonyella Systems in FY24 (2) Ballast is heavily fouled (reference GPR data) (3) There is Top and Line Exceptions for both legs (Track Recording data) (4) The track at the balloon loop is not to be fully reconstructed but to be installed with flangeways and asphalt. The scope document has been amended and added in SPM. 20.03.2022 Survey still outstanding. Civil Design reported to have a standard design. General arrangement design to be provided before 31 March 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050538&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000050538 | C58-LX-GA-INGSDON-16.585km | LX003247 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1071360 | Goonyella | INGSDON | RED MOUNTAIN | 0 | KM | GA03ML16 | 0.5849 | GA03ML16 | 0.5849 | KM |  |  | 16.585 | 16.585 | 16.585 | 16.585 | 2024-06-30 | PRIVATE ACCESS ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.76 | 2.5 | 2 | 3 | 1 | 11.3 | 5328 | 2022-03-31 | 2021-10-05 | Level Crossing Renewals | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF | FY23 IN | 20240630 | * 09.03.2020 11:25:28 AUSQLD Sharbaree Biswas (R865006) * Pushed to FY23 due to funding restrict of $6m in FY22. * 24.03.2021 11:57:22 AUSQLD Sharbaree Biswas (R865006) * Criticality Adopted. * 12.04.2021 16:21:52 AUSQLD Jeremy Stevenson (R867415) * No design, geotech or BMF complete for this N4 - n eed to determine if it is std or bespoke design an * d if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve? * relocation decision is pending as mine is in the process of deciding the best option for there operation. If relocation is the option then Aurizon current standard shall be applicable. PCRs 5238 <(>&<)> 5240. The crossing is currently located at 16.585km, which shall be decommissioned and the crossing shall be relocated to 16.450km when the decision by Aurizon Legal is made.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068816&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000068816 | C58-LX-BW-RANGAL-196.038km | LX000985 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 859655 | Blackwater | RANGAL | BURNGROVE | 0 | KM | BW03ML196 | 0.0379 | BW03ML196 | 0.0379 | KM |  |  | 196.09 | 196.09 | 196.038 | 196.038 | 2024-06-30 | BMA MINE ACCESS RD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 2.2 | 2.85 | 2 | 3 | 1 | 8 |  | 2022-03-31 | 2022-03-31 | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | The new emergency crossing is ID20243 at the proposed location of 195.755km. This is to be confirmed by the survey and the design. Notes on 20 March 2022 Overall Condition 2.93 (from 2017) <(>&<)> Criticality factor 2.85, Performance Impact was taken as 2. Criticality Index was calculated as 3.77 (taken 4) and CRA Index was thus 14. MAJOR RENEWAL IN FY24. A new emergency crossing to be designed and constructed which shall be kept locked at all time (ID20143 has been allocated for this).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044012&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044012 | C58-LX-BW-WYCARBAH-43.06km | LX003196 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 859655 | Blackwater | WYCARBAH | WESTWOOD | 0 | KM | BW03ML43 | 0.0609 | BW03ML43 | 0.0609 | KM |  |  | 43.06 | 43.06 | 43.06 | 43.06 | 2024-06-30 | SPRING CREEK ROAD | BOTH | AS PER AURIZON STD DESIGN | AS PER AURIZON STD DESIGN | 2.82 | 3.35 | 2 | 4 | 1 | 11.28 |  | 2022-03-31 | 2022-03-31 | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 15.01.2020 10:40:30 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY21 to FY22 due to funding * 09.03.2020 11:28:41 AUSQLD Sharbaree Biswas (R865006) * Pushed to FY23 due to funding restriction of $6m in FY22. 09.03.2020 11:28:41 AUSQLD Sharbaree Biswas (R865006) Pushed to FY23 due to funding restriction of $6m in FY22. 20.03.2022 Standard design docs have been added. FY24 construction so the new formation and rail extents to be followed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135646&DY_MAB=X&~OKCODE=ONLI | FY24 | RIM Infrastructure | FUTURE SCOPE | RIM | 002000135646 | C58-LX-QAL-NC-04ML-1.125km | LX000785 | CIVIL | LEVEL CROSSINGS | PLANNING | PLANNING | 1 | SITE | 25000 | Moura | SOUTH GLADSTONE | QAL | 0 | KM | NC04ML1 | 0.127 | NC04ML1 | 0.127 | KM | 2 |  | 0.22 | 0.22 | 1.125 | 1.125 | 2024-06-30 | QAL ACCESS ROAD |  |  |  | 3.5 | 2.3 |  |  |  | 7.86 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105104&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000105104 | C58-LX-BW-CALLE-km | BW | CIVIL | LEVEL CROSSINGS | RMS CT REPLACEMENT | RENEWAL | 1 | SITE | 200000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 | 5441 |  |  | Level Crossing Other | STRATEGIC | LOW | LOW | MEDIUM | LOW | Outstanding notification | RRIG |  | 20240630 | New type-approved CT that has current carrying wire threaded through it rather than being wired into the circuit. This should prevent failure through most surges. Locations in Blackwater to be based on priorities with important LXs and the NCL given priority. The programme to replace CTs will continue in future years. This work came out of failure of RMS at Wuthung Rd where a train had authority to pass over a failed LX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105105&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000105105 | C58-LX-GA-HAY POINT-km | GA | CIVIL | LEVEL CROSSINGS | RMS CT REPLACEMENT | RENEWAL | 1 | SITE | 52000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 | 5441 |  |  | Level Crossing Other | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | RRIG |  | 20240630 | New type-approved CT that has current carrying wire threaded through it rather than being wired into the circuit. This should prevent failure through most surges. Locations in Blackwater to be based on priorities with important LXs and the NCL given priority. The programme to replace CTs will continue in future years. This work came out of failure of RMS at Wuthung Rd where a train had authority to pass over a failed LX.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122764&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000122764 | C58-LX-MA-EARLSFIELD-128.395km | LX006025 | CIVIL | LEVEL CROSSINGS | SIGNALLING | PLANNING | 1 | SITE | 25000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML128 | 0.396 | MA01ML128 | 0.396 | KM |  |  |  |  | 128.395 |  | 2024-06-30 | BILOELA JAMBIN ROAD |  |  |  | 10 | 1.1 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20240630 | Planning for Signal Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122765&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000122765 | C58-LX-MA-EARLSFIELD-0.225km | LX006554 | CIVIL | LEVEL CROSSINGS | SIGNALLING | PLANNING | 1 | SITE | 25000 | Moura | EARLSFIELD | CALLIDE | 0 | KM | MA02ML0 | 0.224 | MA02ML0 | 0.224 | KM |  |  |  |  | 0.225 |  | 2024-06-30 | EARLSFILED JAMBIN ROAD |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20240725 | Planning for Signal Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122767&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000122767 | C58-LX-GA-MALLAWA-168.486km | LX003258 | CIVIL | LEVEL CROSSINGS | SIGNALLING | PLANNING | 1 | SITE | 25000 | Goonyella | MALLAWA | ISAAC PLAINS | 0 | KM | GA01ML168 | 0.4859 | GA01ML168 | 0.4859 | KM |  |  |  |  | 168.486 |  | 2024-06-30 | BURTON MINE ACCESS RIAD |  |  |  | 10 | 2.4 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20240725 | Planning for Signal Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122766&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000122766 | C58-LX-GA-NORWICH PARK-120.756km | LX003629 | CIVIL | LEVEL CROSSINGS | SIGNALLING | PLANNING | 1 | SITE | 25000 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM |  |  |  |  | 120.756 |  | 2024-06-30 | BOOROONDARRA ROAD |  |  |  | 10 | 1.5 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20240725 | Planning for Signal Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091845&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000091845 | TRACK RENEWAL FIX ON FAIL | BW | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM | 935000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FoF/Reactive for Blackwater System - All rail/sleepers/ track upgrade reactive - GIJ Renewals - Slab track Renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091846&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000091846 | TRACK RENEWALS FIX ON FAIL | GA | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM | 935000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FoF / Reactive Rail Renewal for Goonyella System - All rail/sleepers/ track upgrade reactive - GIJ Renewals - Slab track Renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091847&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000091847 | TRACK RENEWALS FIX ON FAIL | MA | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM | 115000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FoF / Reactive for Rail Fix on Fail for Moura system - All rail/sleepers/ track upgrade reactive - GIJ Renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091848&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000091848 | TRACK RENEWALS FIX ON FAIL | NL | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM | 115000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | FoF / Reactive Rail Renewals for Newlands System - All rail/sleepers/ track upgrade reactive - GIJ Renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094100&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094100 | C17 NL ABERDEEN 44.873-46.124. | NL-01ML | CIVIL | RAIL |  | RENEWAL | 2.484 | RAIL KM | 877414 | Newlands | ABERDEEN | BINBEE | 1.2479 | KM | NL01ML44 | 0.8729 | NL01ML46 | 0.1239 | KM | 23 |  | 2.484 | 1.248 | 44.873 | 46.124 | 2024-06-30 | SINGLE | BOTH |  |  | 3.7 | 1.7 | 1 | 2.2 | 1 | 8.14 | 158 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | CUT IN: 44.873 CUT OUT: 44.124
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094369&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094369 | C17 NL ARMUNA 27.994-28.684. | NL-01ML | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 437224 | Newlands | ARMUNA | ABERDEEN | 0.6909 | KM | NL01ML27 | 0.9939 | NL01ML28 | 0.684 | KM | 13 |  | 1.404 | 0.691 | 27.994 | 28.684 | 2024-06-30 | SINGLE | BOTH |  |  | 3.5 | 1.7 | 1 | 2.2 | 1 | 7.7 | 157 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094364&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094364 | C17 NL ARMUNA 28.985-29.083 | NL-01ML | CIVIL | RAIL |  | RENEWAL | 0.216 | RAIL KM | 60743 | Newlands | ARMUNA | ABERDEEN | 0.096 | KM | NL01ML28 | 0.9849 | NL01ML29 | 0.083 | KM | 2 |  | 0.216 | 0.96 | 28.985 | 29.083 | 2024-06-30 | SINGLE | BOTH |  |  | 3.6 | 1.7 | 1 | 2.2 | 1 | 7.92 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071021&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000071021 | C17 GNY BLACK MOUNTAIN 43.06-43.61. | CV002921 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 468275 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.55 | KM | GA01ML43 | 0.0599 | GA01ML43 | 0.6099 | KM | 11 |  | 1.188 | 0.562 | 43.06 | 43.622 | 2024-09-30 | DOWN | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.65 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Can be pushed if capitally challenged
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070774&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070774 | C17 GNY BLACK MOUNTAIN 43.97 - 44.23. | CV002926 | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 223069 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.262 | KM | GA01ML43 | 0.9699 | GA01ML44 | 0.23 | KM | 5 |  | 0.54 | 0.262 | 43.97 | 44.23 | 2024-12-31 | DOWN | BOTH |  |  | 3 | 5 | 1 | 3.9 | 1 | 11.7 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058617&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058617 | C17 GA BLACK MOUNTIAIN 45.058-45.354. | CV002933 | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 217012 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.2959 | KM | GA02ML45 | 0.058 | GA02ML45 | 0.3539 | KM | 6 |  | 0.648 | 0.296 | 45.058 | 45.355 | 2024-06-30 | UP | BOTH |  |  | 4 | 5 | 1 | 3.9 | 1 | 15.6 | 245 |  |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Cut in to tie in FY23 2000070767, there will be left over rail here
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058620&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058620 | C17 GNY BLACK MOUNTAIN 46.715-47.150 | CV002938 | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 324785 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.443 | KM | GA02ML46 | 0.7149 | GA02ML47 | 0.1499 | KM | 8 |  | 0.864 | 0.443 | 46.715 | 47.15 | 2023-12-31 | UP | BOTH |  |  | 4 | 5 | 1 | 3.9 | 1 | 15.6 | 241 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Reduced to 6 rails based on construction recommendation- SCR234 increased to original amount of 8 rails following construction team discussion - SCR241
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094576&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094576 | C17 GNY BLACK MOUNTAIN 47.170-47.531 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 264666 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.3609 | KM | GA02ML47 | 0.17 | GA02ML47 | 0.531 | KM | 7 |  | 0.756 | 0.561 | 47.17 | 47.531 | 2024-12-31 | UP | BOTH |  |  | 3.2 | 5 | 1 | 3.9 | 1 | 12.5 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Cut in is to be after LX3505 and cut is at at TOS of 7A/B points
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070764&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070764 | C17 BOLINGBROKE 60.560-61.270. | CV002956 | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 489857 | Goonyella | BOLINGBROKE | BALOOK | 0.6959 | KM | GA02ML60 | 0.5629 | GA02ML61 | 0.27 | KM | 13 |  | 1.404 | 0.696 | 60.563 | 61.27 | 2024-06-30 | UP | BOTH |  |  | 3.2 | 5 | 1 | 3.9 | 1 | 12.48 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Can be pushed if capitally challenged
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071006&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000071006 | C17 BOLINGBROKE 60.750 - 61.300 | CV002957 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 341138 | Goonyella | BOLINGBROKE | BALOOK | 0.4849 | KM | GA01ML60 | 0.8 | GA01ML61 | 0.2969 | KM | 9 |  | 0.972 | 0.485 | 60.8 | 61.297 | 2024-12-31 | DOWN | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044330&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044330 | C17 GA Bolingbroke 66.300 - 67.100. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 611513 | Goonyella | BOLINGBROKE | BALOOK | 0.756 | KM | GA02ML66 | 0.342 | GA02ML67 | 0.085 | KM | 14 | 0 | 1.512 | 0.756 | 66.342 | 67.085 | 2024-03-30 | UP | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.65 | 38 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | * 20.02.2020 11:56:52 AUSQLD Milton Saha (R884640) * Wearing 7% per year. 25% remaining on HL May 19. Don't defer. * Rail wear. 805 radius curve. HH. Expiry 08/24 * 13.08.2020 10:32:12 AUSQLD Milton Saha (R884640) * Wearing 7% per year. 25% remaining on HL May 19. Don't defer. * Rail wear. 805 radius curve. HH. Expiry 08/24 * 23.03.2021 11:37:15 AUSQLD Sanjna Rajagopalan (R884639) * Pushed to FY24 - Q2 as per AC comments * Extended to 66/069 * SHELL NOTIFICATION YET TO BE CREATED * Tech Scope updated * Post walkout CY22: 66.342 - 67.085 Start at 67.085 and using 7 rails (108m) (and accounting for 13m equality), laying from west to east, the lower chainage end will be at 66.342km. This will put us further back into the tangent and remove taper rails from previous renewals.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070672&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070672 | C17 NL BRIABA 64.530 - 65.189. | CV003465 | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 558010 | Newlands | BRIABA | ALMOOLA | 0.659 | KM | NL03ML64 | 0.53 | NL03ML65 | 0.189 | KM | 12 |  | 1.296 | 0.659 | 64.53 | 65.19 | 2024-06-30 | DOWN | BOTH |  |  | 3.8 | 1.7 | 1 | 2.2 | 1 | 8.36 | 161 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094363&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094363 | C17 NL BUCKLEY 14.689-15.487. | NL-01ML | CIVIL | RAIL |  | RENEWAL | 1.62 | RAIL KM | 506192 | Newlands | BUCKLEY | ARMUNA | 0.8 | KM | NL01ML14 | 0.6889 | NL01ML15 | 0.4869 | KM | 15 |  | 1.62 | 0.8 | 14.689 | 15.487 | 2024-06-30 | SINGLE | BOTH |  |  | 3.5 | 1.7 | 1 | 2.2 | 1 | 7.7 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070700&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070700 | C17 BW CALLIOPE 537.681-539.259 | CV005856 | CIVIL | RAIL |  | RENEWAL | 2.7 | RAIL KM | 944686 | Blackwater | CALLEMONDAH | MOUNT MILLER | 1.227 | KM | BW01ML537 | 0.681 | BW01ML539 | 0.259 | KM | 25 |  | 2.7 | 1.227 | 537.681 | 539.259 | 2024-06-30 | UP | BOTH |  |  | 4 | 4.8 | 1 | 3.8 | 1 | 15.2 | 249 |  |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Please complete with 2000061440
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070709&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070709 | C17 BW CALLE YARD 536.329-536.734. | CV005849 | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 289517 | Blackwater | CALLEMONDAH YARD | CALLEMONDAH YARD | 0.405 | KM | BW01ML536 | 0.329 | BW01ML536 | 0.7339 | KM | 8 |  | 0.864 | 0.405 | 536.329 | 536.734 | 2024-03-31 | UP | BOTH |  |  | 3.5 | 4.8 | 1 | 3.8 | 1 | 13.3 | 168 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Cut in at T/O 293 B/C Pts (536.326km) Cut out at T/O 294 A/B Pts (536.740km) 536.330km GIJ 6 Bolt Left leg 536.474km GIJ 6 Bolt left leg 536.620km GIJ 6 Bolt left leg 536.720km Lubricator Post Site walkout: Proposed reduction in scope end point due to newly inserted closure rail on Left rail, length between welds and proximity of welds to turnout
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091939&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091939 | C17 BW CLINTON BLOOP 2.638-3.950. | BW-12BL | CIVIL | RAIL |  | RENEWAL | 2.7 | RAIL KM | 906194 | Blackwater | CLINTON BLOOP NO.2 | CLINTON BLOOP NO.2 | 1.312 | KM | BW12BL2 | 0.638 | BW12BL3 | 0.9499 | KM | 25 |  | 2.7 | 1.312 | 2.638 | 3.95 | 2024-06-30 | SINGLE | BOTH |  |  | 4.5 | 2.6 | 1 | 2.8 | 1 | 12.6 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Renewing due to corrosion
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070968&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070968 | C17 GNY COPPABELLA YARD 144.830- 145.438 | CV003372 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 338776 | Goonyella | COPPABELLA YARD | COPPABELLA YARD | 0.6099 | KM | GA02ML144 | 0.8299 | GA02ML145 | 0.438 | KM | 11 |  | 1.188 | 0.61 | 144.83 | 145.438 | 2024-12-31 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 | 244 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Post walk out - one extra rail was added.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070969&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070969 | C17 GNY COPPABELLA YARD 144.845-145.339 | CV003373 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 173831 | Goonyella | COPPABELLA YARD | COPPABELLA YARD | 0.4959 | KM | GA01ML144 | 0.8449 | GA01ML145 | 0.339 | KM | 9 |  | 0.972 | 0.496 | 144.845 | 145.339 | 2024-06-30 | DOWN | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058765&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058765 | C17 GA COPPABELLA YARD 143.636 - 144.238 | CV003371 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 533711 | Goonyella | COPPBELLA YARD | COPPABELLA YARD | 0.5979 | KM | GA02ML143 | 0.636 | GA02ML144 | 0.2379 | KM | 11 |  | 1.188 | 0.598 | 143.944 | 144.909 | 2024-06-30 | UP | BOTH |  |  | 3.8 | 4.6 | 1 | 3.7 | 1 | 14.06 | 5498 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Post site walkouts Part 1: L - 143.944 - 144.238 - 3 R - 143.944 - 144.238 - 3 Part 2: L - 143.636 - 143.909 - 2.5 R - 143.636 - 143.909 - 2.5 Section between both parts is a turnout
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070993&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070993 | C17 GNY PRAGUELANDS 13.775 - 14.407. | CV002843 | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 420143 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0.648 | KM | GA02ML13 | 0.775 | GA02ML14 | 0.4069 | KM | 12 |  | 1.296 | 0.648 | 13.775 | 14.407 | 2024-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | - Preference is FY24 Q3 - Criticality is FY25 Q2
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109214&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000109214 | C17 GA DALRYMPLE BAY 2.506-3.028. | GA-03BA | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 430421 | Goonyella | DALRYMPLE BAY ARRIVAL ROAD | DALRYMPLE BAY ARRIVAL ROAD | 0.5719 | KM | GA03BA2 | 0.506 | GA03BA3 | 0.028 | KM | 11 |  | 1.188 | 0.572 | 2.506 | 3.028 | 2025-06-30 | TRACK 3 ARRIVAL ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-03-31 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Notification completed | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058569&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058569 | C17 MA EARSFIELD 3.200-3.570. | CV007217 | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 428914 | Moura | EARLSFIELD | DAKENBA | 0.3699 | KM | MA02ML3 | 0.2 | MA02ML3 | 0.5699 | KM | 7 |  | 0.756 | 0.37 | 3.2 | 3.57 | 2024-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 | 171 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | ope increase from 2 Rails to 7 rails to cover full curve as discussed on site walkout Proposed BMF site <(>&<)> monument install in conjunction with Rail Renewal - additional costs to be estimated in FSC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070846&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070846 | C17 BW EDUNGALBA 86.850-87.190. | CV006212 | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 433751 | Blackwater | EDUNGALBA | AROONA | 0.381 | KM | BW04ML86 | 0.8499 | BW04ML87 | 0.19 | KM | 7 |  | 0.756 | 0.381 | 86.85 | 87.19 | 2024-06-30 | UP | BOTH |  |  | 4 | 3.35 | 1 | 3.2 | 1 | 12.8 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070812&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070812 | C17 MA FRY 82.831 - 83.343. | CV007018 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 296917 | Moura | FRY | MOUNT RAINBOW | 0.501 | KM | MA01ML82 | 0.8309 | MA01ML83 | 0.343 | KM | 9 |  | 0.972 | 0.501 | 82.831 | 83.343 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | - TO BE COMPLETED WITH ADJACENT SCOPES
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094043&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094043 | C17 MA FRY 83.343 - 83.828 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 287434 | Moura | FRY | MOUNT RAINBOW | 0.4849 | KM | MA01ML83 | 0.343 | MA01ML83 | 0.8279 | KM | 9 |  | 0.972 | 0.485 | 83.343 | 83.828 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | To be completed with adjacent scopes
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094044&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094044 | C17 MA FRY 83.828 - 84.243. | MA-01ML | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 251283 | Moura | FRY | MOUNT RAINBOW | 0.4239 | KM | MA01ML83 | 0.8279 | MA01ML84 | 0.2429 | KM | 8 |  | 0.864 | 0.424 | 83.828 | 84.243 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | To be completed with adjacent scopes
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094045&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094045 | C17 MA FRY 84.243 - 84.473 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 0.432 | RAIL KM | 136309 | Moura | FRY | MOUNT RAINBOW | 0.23 | KM | MA01ML84 | 0.2429 | MA01ML84 | 0.4729 | KM | 4 |  | 0.432 | 0.23 | 84.243 | 84.473 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 | 212 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | To be completed with adjacent scopes
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066852&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000066852 | C17 MA FRY 84.473 - 85.208 | CV007022 | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 425521 | Moura | FRY | MOUNT RAINBOW | 0.7179 | KM | MA01ML84 | 0.4729 | MA01ML85 | 0.1859 | KM | 14 |  | 1.512 | 0.74 | 84.473 | 85.208 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | To be completed with adjacent scopes
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043639&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043639 | C17 MA FRY 87.722 - 88.910. | MA-01ML | CIVIL | RAIL |  | RENEWAL | 2.376 | RAIL KM | 850725 | Moura | FRY | MOUNT RAINBOW | 1.1899 | KM | MA01ML87 | 0.7219 | MA01ML88 | 0.91 | KM | 22 | 0 | 2.376 | 1.19 | 87.72 | 88.91 | 2024-06-30 | MAIN | BOTH |  |  | 2.5 | 1.5 | 1 | 2 | 1 | 5 | 193 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | * 05.06.2020 09:28:10 AUSQLD Milton Saha (R884640) * Scope can be pushed passed FY23 to FY27 - reassess in FY25 * 25.03.2021 12:49:00 AUSQLD Sanjna Rajagopalan (R884639) * push to FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070860&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070860 | C17 BW GOGANGO 66.780-67.325. | CV006165 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 455521 | Blackwater | GOGANGO | GRANTLEIGH | 0.547 | KM | BW03ML66 | 0.78 | BW03ML67 | 0.325 | KM | 10 |  | 1.08 | 0.547 | 66.78 | 67.325 | 2023-12-31 | DOWN | BOTH |  |  | 4 | 3.4 | 1 | 3.2 | 1 | 12.8 | 170 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG | FY23 OUT | 20240630 | * 18.03.2021 14:38:04 AUSQLD Sanjna Rajagopalan (R884639) * Rail Renewal * 66.8km - 67.34km - both legs 10 rails total * Rail wear * Q2/Q3 - FY23 * 12.04.2021 16:22:28 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * * Scope cut out extended to use full lengths of rail allocated and remove additional 1995 SC rail from tangent.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043634&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043634 | C17 BW GRACEMERE 7.195-7.852. | BW-04ML | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 576529 | Blackwater | GRACEMERE | GRACEMERE | 0.657 | KM | BW04ML7 | 0.195 | BW04ML7 | 0.8519 | KM | 12 | 0 | 1.296 | 0.657 | 7.195 | 7.85 | 2024-06-30 | UP | BOTH |  |  | 4 | 3.35 | 1 | 3.2 | 1 | 12.8 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | * 19.02.2020 12:34:45 AUSQLD Milton Saha (R884640) * Reason: Rail wear is breaching limits * 19.02.2020 13:17:42 AUSQLD Milton Saha (R884640) * Execute Q3 FY22 Plan for executon any time FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070997&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070997 | C17 GA HATFIELD 49.373-49.800. | CV002800 | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 326257 | Goonyella | HATFIELD | BOLINGBROKE | 0.4269 | KM | GA02ML49 | 0.3729 | GA02ML49 | 0.8 | KM | 8 |  | 0.864 | 0.427 | 49.373 | 49.8 | 2024-06-30 | UP | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.65 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Scope starts at LLB ER.2B and finishes at LLB 11A/B
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058622&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058622 | C17 GA HATFIELD 49.885-50.530. | CV002943 | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 467610 | Goonyella | HATFIELD | BOLINGBROKE | 0.6119 | KM | GA02ML49 | 0.885 | GA02ML50 | 0.53 | KM | 12 |  | 1.296 | 0.612 | 49.885 | 50.53 | 2024-06-30 | UP | BOTH |  |  | 3.7 | 5 | 1 | 3.9 | 1 | 14.43 | 147 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Scope starts psst TOS of 11A/B post walkout notes: cut out location changed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071010&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000071010 | C17 GNY HATFIELD 50.260-51.086. | CV002945 | CIVIL | RAIL |  | RENEWAL | 1.728 | RAIL KM | 493368 | Goonyella | HATFIELD | BOLINGBROKE | 0.8279 | KM | GA01ML50 | 0.26 | GA01ML51 | 0.0859 | KM | 16 |  | 1.728 | 0.828 | 50.26 | 51.086 | 2023-12-31 | DOWN | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 | 182 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | cut out point ties in with FY22 scope and removes fatigue rail Scope reduced as it was covered in FY23 - SRC 182
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071005&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000071005 | C17 GNY HATFIELD 58.308 - 59.060 | CV002955 | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 442721 | Goonyella | HATFIELD | BOLINGBROKE | 0.7429 | KM | GA02ML58 | 0.3079 | GA02ML59 | 0.0599 | KM | 14 |  | 1.512 | 0.743 | 58.308 | 59.06 | 2024-03-31 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | post walkout notes: cut-in point changed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058628&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058628 | C17 GNY HATFIELD 56.192-56.893. | CV002952 | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 417695 | Goonyella | HATFILED | BOLINGBROKE | 0.7009 | KM | GA02ML56 | 0.192 | GA02ML56 | 0.893 | KM | 13 |  | 1.404 | 0.701 | 56.192 | 56.893 | 2024-06-30 | UP | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.7 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071109&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000071109 | C17 BW MARMOR 591.715 - 592.478. | CV005927 | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 615195 | Blackwater | MARMOR | BAJOOL | 0.765 | KM | BW01ML591 | 0.7149 | BW01ML592 | 0.4779 | KM | 14 |  | 1.512 | 0.765 | 591.715 | 592.478 | 2024-06-30 | UP | BOTH |  |  | 4 | 4.1 | 1 | 3.6 | 1 | 14.4 | 169 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Post Site Walkout: Site Walkout Data Sheet Minimum cut out 591.715km. Proposed increase by 1 rail to remove standard carbon rail with numerous welds on Southern end of scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091607&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091607 | C17 BW PHOUSE APPROACH 534.417-534.730. | BW-14YR | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 406961 | Blackwater | POWERHOUSE APPROACH | POWERHUOSE APPROACH | 0.313 | KM | BW14YR534 | 0.4169 | BW14YR534 | 0.7299 | KM | 6 |  | 0.648 | 0.313 | 534.417 | 534.73 | 2024-06-30 | SINGLE | BOTH |  |  | 3.8 | 0.9 | 1 | 1.4 | 1 | 5.32 | 167 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Cut in at T.O.S of 271A and cut out at back of 276A Rail transitions from 60kg to 53kg to 47kg at approx. 534.468km Transition from 47kg to 53kg at 534.656km 4 bolt GIJ Left leg at 534.677km Transitions from 53kg to 60kg at 534.715km Redundant 4 bolt GIJ Right leg at 534.727km Proposed scope change start chainage amended to cut in at end of stockrails TOS 271A pts as measured on site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070725&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070725 | C17 GNY JILALAN 19.500 - 19.770 | CV002859 | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 195807 | Goonyella | PRAGUELANDS | JILALAN | 0.3019 | KM | GA02ML19 | 0.46 | GA02ML19 | 0.762 | KM | 5 |  | 0.54 | 0.302 | 19.5 | 19.77 | 2024-09-30 | UP | BOTH |  |  | 3.5 | 4.8 | 1 | 3.8 | 1 | 13.3 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | - FY25 Q1 - can be pushed if capitally challenged.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070732&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070732 | C17 GA PRAGUELANDS 15.001-15.550. | CV002844 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 355955 | Goonyella | PRAUGELANDS | JILALAN | 0.549 | KM | GA02ML15 | 0.001 | GA02ML15 | 0.55 | KM | 10 |  | 1.08 | 0.549 | 15.001 | 15.55 | 2023-09-30 | UP | BOTH |  |  | 3 | 4.6 | 1 | 3.7 | 1 | 11.1 | 235 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG | FY23 OUT | 20240630 | * 19.03.2021 13:33:35 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail Only * 15.001 - 15.596 * UP Road - both legs - 11 rails total * * Cables attached to both rails at 15.330km * Flash Butt Welds 15.580km Low-Leg * Flash Butt Welds 15.579km High-Leg * 12.04.2021 16:22:36 AUSQLD Jeremy Stevenson (R867415) * Technical Scope attached, scope combined for a tot al site * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070687&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070687 | C17 GA WANDOO 86.742 - 87.121. | CV003006 | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 472608 | Goonyella | WANDOO | WAITARA | 0.377 | KM | GA02ML86 | 0.7419 | GA02ML87 | 0.1209 | KM | 7 |  | 0.756 | 0.377 | 86.742 | 87.121 | 2024-12-31 | UP | BOTH |  |  | 3 | 5 | 1 | 3.9 | 1 | 11.7 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Can be pushed if capitally challenged
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070865&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070865 | C17 BW WESTWOOD 49.506-50.293. | CV006129 | CIVIL | RAIL |  | RENEWAL | 1.62 | RAIL KM | 586121 | Blackwater | WESTWOOD | WINDAH | 0.785 | KM | BW03ML49 | 0.506 | BW03ML50 | 0.2929 | KM | 15 |  | 1.62 | 0.785 | 49.506 | 50.293 | 2024-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 | 145 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073636&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000073636 | C17 BW WESTWOOD 52.655-52.910. | TN000427 | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 190396 | Blackwater | WESTWOOD | WINDAH | 0.255 | KM | BW03ML52 | 0.655 | BW03ML52 | 0.91 | KM | 5 |  | 0.54 | 0.255 | 52.655 | 52.91 | 2023-12-31 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 11.2 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Tangent has been excluded from previous rail renewals at each extent. 52.105 - 52.668km (18/09/2018) 52.908 - 54.221km (29/09/2017) Rail is in good condition other than rail wear Poor site access - on embankment Undercut required from 52.800 to west at time of site inspection. Ballast condition to be assessed again closer to rail renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070710&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070710 | C17 BW YARWUN 550.900-551.428. | CV005701 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 367543 | Blackwater | YARWUN | ALDOGA | 0.524 | KM | BW01ML550 | 0.9 | BW01ML551 | 0.4279 | KM | 10 |  | 1.08 | 0.524 | 550.9 | 551.428 | 2023-09-30 | UP | BOTH |  |  | 4.5 | 4.1 | 1 | 3.5 | 1 | 15.75 | 174 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Post walkouts - extended on lower chainage side to tie in with FY22 Re rail - SRC 174
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058709&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058709 | C17 BW YARWUN 552.324 - 552.500. | CV005705 | CIVIL | RAIL |  | RENEWAL | 0.324 | RAIL KM | 122748 | Blackwater | YARWUN | ALDOGA | 0.1759 | KM | BW01ML552 | 0.324 | BW01ML552 | 0.5 | KM | 3 |  | 0.32 | 0.176 | 552.324 | 552.5 | 2023-12-31 | UP | BOTH |  |  | 3.5 | 4.1 | 1 | 3.5 | 1 | 12.25 | 175 |  |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Post site walkout - addition of this curve as only right leg of CV005705 was renewed in FY21. Create an overall more reliable asset - SRC 175
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058710&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058710 | C17 BW YARWUN 552.500-553.613 | CV005708 | CIVIL | RAIL |  | RENEWAL | 0.216 | RAIL KM | 79260 | Blackwater | YARWUN | ALDOGA | 0.113 | KM | BW01ML552 | 0.5 | BW01ML552 | 0.6129 | KM | 2 |  | 0.216 | 0.113 | 552.5 | 552.613 | 2023-12-31 | UP | BOTH |  |  | 3.5 | 4.1 | 1 | 3.5 | 1 | 12.25 | 175 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Equality 552km 960.42 = 553km post Complete with adjacent Scopes Post sitewalkouts - added 3 more rails as only right leg of CV005705 was renewed in FY21. Create an overall more reliable asset - SRC 175
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058711&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058711 | C17 BW YARWUN 552.613 - 552.720 | CV005709 | CIVIL | RAIL |  | RENEWAL | 0.216 | RAIL KM | 75052 | Blackwater | YARWUN | ALDOGA | 0.1069 | KM | BW01ML552 | 0.6129 | BW01ML552 | 0.7199 | KM | 2 |  | 0.216 | 0.107 | 552.613 | 552.72 | 2023-12-31 | UP | BOTH |  |  | 3.5 | 4.1 | 1 | 3.5 | 1 | 12.25 | 175 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Equality 552km 960.42 = 553km post Complete with adject scopes Post Sitewalkouts - addition of 3 rails as only right leg of CV005705 was renewed in FY21. Create an overall more reliable asset
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058712&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000058712 | C17 BW YARWUN 552.720 - 553.065. | CV005712 | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 217440 | Blackwater | YARWUN | ALDOGA | 0.3099 | KM | BW01ML552 | 0.7199 | BW01ML553 | 0.065 | KM | 6 |  | 0.648 | 0.31 | 552.72 | 553.065 | 2023-12-31 | UP | BOTH |  |  | 3.5 | 4.1 | 1 | 3.5 | 1 | 12.25 | 175 | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Equality 552km 960.42 = 553km post Complete with adjacent scopes Post Sitewalkouts - addition of 3 rails as only right leg of CV005705 was renewed in FY21. Create an overall more reliable asset - SRC 175
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070970&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070970 | C17 GA YUKAN 35.496-36.049. | CV002886 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 512904 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.553 | KM | GA01ML35 | 0.4959 | GA01ML36 | 0.049 | KM | 10 |  | 1.08 | 0.553 | 35.496 | 36.049 | 2024-06-30 | DOWN | BOTH |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 |  | 2022-03-31 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | - Preference is Q4 FY24 - Criticality is Q3 FY25
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073856&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000073856 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ BW | BW | CIVIL | RAIL LUBRICATION |  | RENEWAL | 1 | LUMPSUM | 50000 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 10 |  | 5 |  | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG | FY23 OUT | 20240630 | * 09.03.2021 19:04:59 AUSQLD Tracy Holmes (R870040) * Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Goonyella Main. The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073855&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000073855 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ GA | GA | CIVIL | RAIL LUBRICATION |  | RENEWAL | 1 | LUMPSUM | 50000 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 10 |  | 5 |  | 25 |  | 2022-03-31 |  | Permanent Way -Other | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG | FY23 OUT | 20240630 | * 09.03.2021 19:04:47 AUSQLD Tracy Holmes (R870040) * Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Goonyella Main. The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092086&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000092086 | C18 BW BAJOOL FORK 0.023 - 0.210. | BW-08FK | CIVIL | SLEEPERS |  | RENEWAL | 260 | SLEEPERS | 580357 | Blackwater | BAJOOL EASTERN ANGLE | BAJOOL EASTERN ANGLE | 0.1869 | KM | BW08FK0 | 0.0229 | BW08FK0 | 0.2099 | KM |  | 260 |  | 0.187 | 0.023 | 0.21 | 2024-06-30 | FORK |  |  |  | 4.4 | 4.1 | 1 | 3.5 | 1 | 15.4 |  | 2022-03-31 |  | Sleeper Renewal | LIKE FOR LIKE | MEDIUM | LOW | HIGH | MEDIUM | Notification in process | RRIG |  | 20240630 | Renew with Low Profile sleepers Full depth sleepers currently through LX20149 Transition Sleepers required for turnout/catchpoints
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044291&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | NON-COAL | 002000044291 | C18 BW MAIN BURNGROVE 257.950 - 260.080. | BW-03ML | CIVIL | SLEEPERS |  | RENEWAL | 4500 | SLEEPERS | 2920500 | Blackwater | BURNGROVE | NOGOA | 3.0849 | KM | BW03ML257 | 0 | BW03ML260 | 0.08 | KM | 0 | 4500 |  | 3.085 | 257 | 260.08 | 2023-06-30 | MAIN | NONE |  |  | 4 | 1.7 | 1 | 2.1 | 1 | 8.5 | 5828 | 2021-03-31 | 2021-10-05 | Sleeper Renewal | LIKE FOR LIKE | HIGH | HIGH | MEDIUM | HIGH | Notification in process | SCPR | FY23 IN NON MRSB | 20240630 | * 30.03.2021 12:12:08 AUSQLD Sanjna Rajagopalan (R884639) * sleeper renewal * * 233.570 - 235.770km * total 3212 sleepers * continuation of previous works to eliminate timber * fatigue scope * Q4 * 06.04.2021 10:04:43 AUSQLD Sanjna Rajagopalan (R884639) * Changed kms to 2.2km as it had the wrong track kms original scope was 258.730 - 260.100 - approx. 2000 sleepers. Due to waterfall affects from incompleted sope in FY23 new scope is between 257km - 260.080 approx. 4500 sleepers. Tying into FY23 Job. Change Captured in PCR 5828
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092909&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092909 | TUNNEL SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY | CUTTING | DESIGN | 1 | LUMPSUM | 50000 | Blackwater | TUNNEL | EDUNGALBA | 0.1 | KM | BW03ML75 | 0.8 | BW03ML75 | 0.9 | KM |  |  |  |  | 75.8 | 75.9 | 2023-12-31 |  |  |  |  | 3.5 | 3 | 1 | 4 | 1 | 14 |  | 2022-03-31 | 2021-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | RRIG | FY24 IN | 20240630 | 07.02.2022 Tim Griffin (r878533) $50,000 Design and Cost Estimate for TUNNEL slope stability on Blackwater System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092921&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092921 | WESTWOOD SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY | CUTTING | DESIGN | 1 | LUMPSUM | 125000 | Blackwater | WYCARBAH | WESTWOOD | 0.11 | KM | BW03ML44 | 0.465 | BW03ML44 | 0.5749 | KM |  |  |  |  | 44.465 | 44.575 | 2023-10-30 |  |  |  |  | 3.5 | 1 | 1 | 3 | 1 | 3 |  | 2022-03-31 | 2021-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | RRIG | FY23 IN | 20240630 | 07.02.2022 Tim Griffin (r878533) $125,000 Design and Cost Estimate for WESTWOOD slope stability on Blackwater System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077569&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077569 | Structures Reactive Works | BW | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 127023 | Blackwater | BW |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 22.05.2021 08:49:51 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. 14/12/21 Reduced to $564k as closer to delivery year
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077635&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077635 | Structures Reactive Works | GA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 89023 | Goonyella | GA |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 22.05.2021 08:56:46 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. 14/12/21 Reduced to $564k as closer to delivery year 15/9/22 EB Reduced to 89,023 to include additional design scope at GA-196.040km as found as reactive scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077568&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077568 | Structures Reactive Works | MA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 63511 | Moura | MA |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 22.05.2021 08:48:40 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. 14/12/21 Reduced to $526k as closer to delivery year
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077639&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000077639 | Structures Reactive Works | NL | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 63511 | Newlands | NL |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 22.05.2021 09:03:22 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. 14/12/21 Reduced to $526k as closer to delivery year
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043881&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000043881 | 4759 Structures Renewal. | CU101399 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 550000 | Blackwater | RAGLAN |  | 0 | KM | BW01ML584 | 0.8269 | BW01ML584 | 0.8269 | KM |  |  |  |  | 584.83 |  | 2022-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 | 5637 | 2020-03-06 | 2020-11-13 | Culvert Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | SCPR |  | 20240630 | * 10.03.2020 08:30:48 AUSQLD Peter Rayner (R003851) * Defect - horizontal cracking in units 1,4. severe cracking in base slab, arch walls and moderate horz cracking in walls and ceiling. - Proposed Renewal - Remove and replace with large RCBC's
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092314&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092314 | Structures Design | BR300424 | CIVIL | STRUCTURES | BRIDGE STRENGTHENING | DESIGN | 1 | SITE | 33416 | Newlands | ARMUNA | BUCKLEY | 0.0379 | KM | NL01ML14 | 0.5899 | NL01ML14 | 0.628 | KM |  |  |  |  | 14.6 |  | 2026-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 | 184 | 2022-03-31 |  | Bridges Design | STRATEGIC |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Propped 60 kph Speed restriction overload 26.5-27.5TAL, Under load capacity Proposed: Strengthening in accordance with Fryessinet Recommendation in 4/8/20 report. Based on freyssinet report 1.4M to Structural Strengthening and approx 4M to replace Drawing: Risk: Reason: Strategic
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129717&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000129717 | Bridge 22.650km BYAA DEADMAN Creek #1 | BR300154 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS | DESIGN | 1 | SITE | 340529 | Newlands | ARMUNA | BUCKLEY | 0.049 | KM | NL01ML22 | 0.6159 | NL01ML22 | 0.665 | KM |  |  |  |  | 22.65 |  | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20240630 | Defect: Close inspections of cracks and detailed scope of repairs to pier cracks and bearing pad movement. Design install of handrai ls/platforms on LHS and RHS of bridge and removal of concrete platforms. Proposed: Install new handrails and platforms. Inspect bearing pads and pier cracks. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094219&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094219 | Structures Design | BR101090 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | DESIGN | 1 | SITE | 33416 | Blackwater | CREW | MACKENZIE | 0.445 | KM | BW08ML16 | 0.7119 | BW08ML17 | 0.158 | KM |  |  |  |  | 16.95 |  | 2025-06-30 |  |  | REL SLAB & HANDRAILS |  | 10 | 10 |  | 0.1 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Design | STRATEGIC |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Top of line issues suggesting possible relieving slba issue. Also strategic for Handrails. Proposed: Remove and Replace Relieving Slabs <(>&<)> Install Handrails Both sides <(>&<)> Remove concrete platforms. Drawing: Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094281&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094281 | Structures Design | BR200652 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | DESIGN | 1 | SITE | 33416 | Goonyella | DALRYMPLE | PRAGUELANDS | 0.048 | KM | GA02ML9 | 0.505 | GA02ML9 | 0.553 | KM |  |  |  |  | 9.514 |  | 2025-06-30 |  |  | REL SLAB & HANDRAILS |  |  |  |  | 0.1 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Top of line issues suggesting possible Relieving slab and Handrails Proposed: Remove and Replace Relieving Slabs <(>&<)> Install Handrails Both sides <(>&<)> Remove concrete platforms. Drawing: Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126274&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000126274 | Bridge 191.190km WTMN Isaac River | BR200866 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | DESIGN | 1 | SITE | 50000 | Goonyella | MORANBAH NORTH | WOTONGA | 0.1449 | KM | GA01ML191 | 0.115 | GA01ML191 | 0.26 | KM |  |  |  |  | 191.19 |  | 2024-06-30 |  |  | REL SLAB & HANDRAILS |  | 0 | 10 | 4 | 0 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20240630 | Defect: No Handrails LHS or RHS, to be designed for rollout install. HIgh bridge and long therefore high risk. some top of line issues on entry and exit of bridge. Proposed: Install new handrails and remove concrete platforms and install relieving slabs. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093963&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000093963 | Structures Renewal | BR101453 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | RENEWAL | 1 | SITE | 701485 | Blackwater | AMBROSE | EPALA | 0.0459 | KM | BW01ML573 | 0.006 | BW01ML573 | 0.0519 | KM |  |  |  |  | 572.99 |  | 2024-06-30 |  |  | REPLACE REL SLAB & LHS HR |  | 0 | 10 | 4 | 0 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect: Relieving slab failing on high chainage side, visible from abutment and install handrails on LHS. Confirm Proposed: Remove and Replace Relieving slabs both ends of the bridge and install handrails on LHS in Rollout Drawing: Risk: Mod-High Reason: Relieving slab has severe cracking in the ends of the abutment. Top alignment issues have also been observed which is causing faster deterioration of the ballast on the bridge. Higher maintenance costs until relieving slab resolved. the handrails are strategic scope for bridges on the CQCN.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094282&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000094282 | Structures Renewal | BR200652 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & RELEIVING | RENEWAL | 1 | SITE | 670000 | Goonyella | DALRYMPLE | PRAGUELANDS | 0.048 | KM | GA02ML9 | 0.505 | GA02ML9 | 0.553 | KM |  |  |  |  | 9.514 |  | 2025-06-30 |  |  | REMOVE & REPLACE AND NEW |  | 10 | 10 |  | 0.1 | 1 | 100 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Defect: Top of line issues suggesting possible Relieving slab and Handrails Proposed: Remove and Replace Relieving Slabs <(>&<)> Install Handrails Both sides <(>&<)> Remove concrete platforms. Drawing: Risk: Mod Reason: Moved to FY24 renewal to align with Bridge Rollout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089570&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089570 | Structures Design | BR101312 | CIVIL | STRUCTURES | BRIDGE-RELIEVING SLAB | DESIGN | 1 | SITE | 33416 | Blackwater | ARCHER | MIDGEE | 0.048 | KM | BW01ML618 | 0.8329 | BW01ML618 | 0.881 | KM |  |  |  |  | 618.85 |  | 2026-06-30 | UP RD |  |  |  | 3.5 | 4.1 | 4 | 4.5 | 1 | 15.9 | 184 | 2022-03-31 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Top of rail height issues, North relieving slab and supporting ballast wall failed with severe cracking in RS and ballast wall. North relieving slab had 160-200mm fall and 100mm higher than bridge surface. Lifting with teratek to have 75-80mm fall but still 100mm higher than deck and change drainage from RS to match formation with 5-10mm fall west to east. Monitor 6 monthly after injection in Nov 2020. Proposed: North relieving slab needs to be replaced in next bridge rollout. This will also need to include the re-construction of ballast wall support the relieving slab. Recommend remove all and reinstall. Eg saw cut ballast wall and dowel in required reinf and precast relieving slab. Craneage likely required. If north and south both replaced, estimate will need to be increased. Drawing: Risk: High
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092316&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092316 | Structures Design | BR101606 | CIVIL | STRUCTURES | BRIDGE-RELIEVING SLAB | DESIGN | 1 | SITE | 33416 | Blackwater | YARWUN |  | 0.08 | KM | BW01ML546 | 0.132 | BW01ML546 | 0.2119 | KM |  |  |  |  | 546.17 |  | 2026-06-30 |  |  |  |  | 4 | 4.9 | 4 | 4.7 | 1 | 19 | 184 | 2022-03-31 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Relieving Slab sinking on low chainage end, fall of 220mm. Ballast drain installed as interim fix but needs to be replaced as cracked at ballast wall as well. Proposed: Remove and replace Low Chainage relieving slab. Ensure drainage is designed and improvement to subgrade. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090333&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000090333 | Structures Design | CU200687 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33416 | Goonyella | BALOOK | WANDOO | 0 | KM | GA01ML78 | 0.6899 | GA01ML78 | 0.6899 | KM |  |  |  |  | 78.69 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.8 | 3 | 4.5 | 1 | 15.6 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Moderate corrosion thoughout culvert, with rocks starting to cause risk of localised holes in CMP. Proposed: CIPP Lining Drawing: Risk: Mod-High Reason: Moderate corrosion, could last longer, however main risk here is waiting too long and localised holed allows undermining of CMP and fatser corrosion rates. Lining now will remove need of closure and give live to this asset with only a few years left to another 50 years.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089485&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089485 | Structures Design | CU400411 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33416 | Moura | BELLDEEN | EARLSFIELD | 0 | KM | MA01ML136 | 0.05 | MA01ML136 | 0.05 | KM |  |  |  |  | 136.05 |  | 2026-06-30 |  |  |  |  | 4 | 1.3 | 3 | 3.2 | 1 | 12.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Severe corrosion on invert of CMP. Poorly constructed lining has failed and will be making corrosion worse. Proposed: CIPP line to be confirmed during Hydrology design. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044239&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000044239 | Structures Design | CU200939 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33416 | Goonyella | BOLINGBROKE | HATFIELD | 0 | KM | GA01ML58 | 0.8199 | GA01ML58 | 0.8199 | KM |  |  |  |  | 58.82 |  | 2026-06-30 |  |  |  |  | 3.5 | 5 | 3 | 4.5 | 1 | 15.8 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: severe corrosion on outlet side widening. Holes in CMP. Proposed: CMP CIPP Lining. Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089483&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089483 | Structures Design | CU100848 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33416 | Blackwater | KENMARE | KINROLA | 0 | KM | BW06ML18 | 0.22 | BW06ML18 | 0.22 | KM |  |  |  |  | 18.22 |  | 2026-06-30 |  |  |  |  | 3.5 | 2.6 | 3 | 3.7 | 1 | 13.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: severe corrosion in invert of inlet and outlet. Proposed: CIPP Lining Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084979&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084979 | Structures Renewal | CU400121 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 94100 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML168 | 0.8299 | MA01ML168 | 0.8299 | KM |  |  |  |  | 168.83 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate to severe corrosion 4-8 o'clock throughout Proposed - CMP CIPP Line <(>&<)> Replace head walls Drawing - Risk: Mod-High Reason: CIPP is the cheapest renewal option based on past experience and achieves the 30TAL wiuth 50 year life without creating a track closure, so before severe corrosion turn to large cracks, deformed shape and sizes of collapse CIPP is extremely good alternative, delaying only increase risk of remove and replace required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084955&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084955 | Structures Renewal | CU200844 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 162531 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0 | KM | GA01ML43 | 0.0299 | GA01ML43 | 0.0299 | KM |  |  |  |  | 43.03 |  | 2025-06-30 |  |  | CIPP | CIPP | 4 | 5 | 3 | 4.5 | 1 | 18 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Severe corrosion in invert for 12m from outlet and moderate to severe corrosion for remainder, total section loss at outlet. Proposed - CIPP LIne or Remove <(>&<)> Replace Drawing - Risk: Mod-High Reason: CIPP is the cheapest renewal option based on past experience and achieves the 30TAL wiuth 50 year life without creating a track closure, so before severe corrosion turn to large cracks, deformed shape and sizes of collapse CIPP is extremely good alternative, delaying only increase risk of remove and replace required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084953&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084953 | Structures Renewal | CU200663 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 217548 | Goonyella | BLACK MOUNTAIN | YUKAN | 0 | KM | GA01ML33 | 0.7399 | GA01ML33 | 0.7399 | KM |  |  |  |  | 33.74 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Severe corrosion in culvert throughout, likely under track, decent cover. Proposed - CIPP Lining Risk: Mod-High Reason: CIPP is the cheapest renewal option based on past experience and achieves the 30TAL wiuth 50 year life without creating a track closure, so before severe corrosion turn to large cracks, deformed shape and sizes of collapse CIPP is extremely good alternative, delaying only increase risk of remove and replace required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085026&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085026 | Structures Renewal | CU201240 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 151696 | Goonyella | DALRYMPLE | PRAGUELANDS | 0 | KM | GA01ML10 | 0 | GA01ML10 | 0 | KM |  |  |  |  | 10 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 4.6 | 3 | 4.4 | 1 | 15.4 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate to severe corrosion corrosion through out invert of culvert. Proposed - CIPP Lining Risk: Mod-High Reason: CIPP is the cheapest renewal option based on past experience and achieves the 30TAL wiuth 50 year life without creating a track closure, so before severe corrosion turn to large cracks, deformed shape and sizes of collapse CIPP is extremely good alternative, delaying only increase risk of remove and replace required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043824&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043824 | Structures Renewal | CU100269 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 422947 | Blackwater | EDUNGALBA | TUNNEL | 0 | KM | BW03ML80 | 0.8309 | BW03ML80 | 0.8309 | KM |  |  |  |  | 80.8 |  | 2024-06-30 |  |  | CIPP | CIPP | 3.5 | 3.8 | 3 | 4.2 | 1 | 14.7 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 25.09.2020 19:01:44 AUSQLD Edward Brooks (R884255) * Defect:Notification <(>&<)> Moderate cracking <(>&<)> spalling in some units, circumference cracking in middles of Cells 2<(>&<)>3 * * Propose: Heaps of cover, CIPP lining windening only.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092307&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092307 | Structures Design | CU200410 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 33416 | Goonyella | GERMAN CREEK | OAKY CREEK | 0.02 | KM | GA03ML144 | 0.5999 | GA03ML144 | 0.5799 | KM |  |  |  |  | 144.58 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.1 | 3 | 3.1 | 1 | 10.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: CMP under acces rd crushing <(>&<)> need to be replaced. moderate corrosion just above invert lining. 2m cover Proposed: Confirm CIPP with manufacturer is not possible to go to 1800. concrete line, if hydro suitable Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089484&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089484 | Structures Design | CU400022 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 33416 | Moura | QAL JUNCTION | CALLEMONDAH | 0 | KM | MA01ML2 | 0.8499 | MA01ML2 | 0.8499 | KM |  |  |  |  | 2.85 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.1 | 3 | 3.1 | 1 | 10.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Severe coorosion formed above the concrete invert Proposed: Concrete Line or Remove <(>&<)> Replace Confirm with Hydro Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043460&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000043460 | Structures Design | CU200825 | CIVIL | STRUCTURES | CMP-ELIMINATE | DESIGN | 1 | SITE | 33416 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0 | KM | GA01ML42 | 0.7149 | GA01ML42 | 0.7149 | KM |  |  |  |  | 42.715 |  | 2025-06-30 |  |  |  |  | 3.5 | 5 | 3 | 4.5 | 1 | 15.8 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Regularly full of silt and appeasr to full to nearby culvert at 42.730. Proposed: Elimination, Grout <(>&<)> Fill. Drawing: Risk: Reason: Maintenance costs of regular de-silting.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043830&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | NON-COAL | 002000043830 | 4706 Structures Renewal. | CU100715 | CIVIL | STRUCTURES | NON-MRSB RCBC | RENEWAL | 1 | SITE | 450382 | Blackwater | COMET | YAMALA | 0 | KM | BW03ML238 | 0.879 | BW03ML238 | 0.879 | KM |  |  |  |  | 238.88 |  | 2025-06-30 |  |  |  |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.3 | 3542 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR | NON MRSB | 20240630 | * 12.05.2020 16:25:13 AUSQLD Edward Brooks (R884255) * Defect: Severe cracks in wall and ceiling, culvert pumping under empty train. Designed planned for FY21 * Estimated renewal: Remove and replace with similar size culvert, to be confirmed during design stage. * Scope brought forward from FY23 to align scope and budget for FY22. 11/2/21 EB Scope deferred to FY24 due to change to non-MRSB and no longer taking the coal loaded traffic on this line.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091921&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | NON-COAL | 002000091921 | Structures Design | CU100177 | CIVIL | STRUCTURES | NON-MRSB-RCBC-ELIMINATE | DESIGN | 1 | SITE | 33416 | Blackwater | BURNGROVE-NOGOA |  | 0 | KM | BW03ML224 | 0.2999 | BW03ML224 | 0.2999 | KM |  |  |  |  | 224.3 |  | 2026-06-30 |  |  |  |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.3 |  | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | NON MRSB | 20240630 | NON-MRSB Scope Defect - Completely filled with material been like that for a number of years, does not appears to be required however as on side of road, need confirmed by hydro. Renewal - Complete hydro to confirm Eliminate and grout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093505&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093505 | Structures Design | CU300135 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Newlands | ALMOOLA | COLLINSVILLE | 0 | KM | NL01ML74 | 0.0899 | NL01ML74 | 0.0899 | KM |  |  |  |  | 74.09 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 2.5 | 3 | 3.7 | 1 | 13 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: numerous circumference cracking severe greater than 1mm up to 20mm. Horizontal crack in roof also which is a concern Proposed: Remove <(>&<)> Replace RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043843&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000043843 | Structures Design | CU101231 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | AMBROSE | EPALA | 0 | KM | BW01ML573 | 0.34 | BW01ML573 | 0.34 | KM |  |  |  |  | 573.34 |  | 2026-06-30 |  |  |  |  | 4 | 4.1 | 3 | 4.3 | 1 | 17 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 20.10.2020 16:31:12 AUSQLD Edward Brooks (R884255) * Defect: Propped all cells unit8-14. Poor patching is starting to spall again. Loaded trains now running on DN rd which is not propped * Proposed: Remove and replace Up Rd Side only.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089458&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089458 | Structures Design | CU101325 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | AMBROSE | EPALA | 0 | KM | BW01ML573 | 0.9599 | BW01ML573 | 0.9599 | KM |  |  |  |  | 573.96 |  | 2026-06-30 |  |  |  |  | 3.5 | 4.1 | 3 | 4.3 | 1 | 14.9 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Pumping under loaded trains Proposed: Remove and Replace Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093872&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093872 | Structures Design | CU100581 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | AROONA | EDUNGALBA | 0.05 | KM | BW03ML86 | 0.1 | BW03ML86 | 0.05 | KM |  |  |  |  | 86.05 |  | 2026-06-30 |  |  | REMOVE & REPLACE RCBC |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Insitu original, RCBC on WL. Seevere spalling in ceiling of precast units. Proposed: Check Hydro for area, however likely Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093503&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093503 | Structures Design | CU201071 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0 | KM | GA01ML46 | 0.3599 | GA01ML46 | 0.3599 | KM |  |  |  |  | 46.36 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 5 | 3 | 4.5 | 1 | 18.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Sinking Units 100mm in Cells 1 and 2. temporarily lined with HDPE Proposed: Remove <(>&<)> Replace RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089489&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089489 | Structures Design | CU100645 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML189 | 0.2899 | BW03ML189 | 0.2899 | KM |  |  |  |  | 189.29 |  | 2025-06-30 |  |  |  |  | 4.5 | 3.2 | 3 | 4 | 1 | 17.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Sinking approximately 100, severe cracking longitudanlly and partially failed in sections. Outlet may be into storm water drain on Cap Highway Proposed: Remove and Replace. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089488&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089488 | Structures Design | CU100348 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | BOONAL |  | 0 | KM | BW03ML179 | 0.6099 | BW03ML179 | 0.6099 | KM |  |  |  |  | 179.61 |  | 2026-06-30 |  |  |  |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Very mixed types. But severe cracking and gaps in the RCP section. Pumping at one of the RCPs. Proposed: Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043841&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000043841 | Structures Design | CU200544 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Goonyella | BUNDOORA |  | 0 | KM | GA03ML130 | 0.6999 | GA03ML130 | 0.6999 | KM |  |  |  |  | 130.7 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.3 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: severe spalling in units 2 <(>&<)> 3. Proposed: Remove and Replace RCBC Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089433&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089433 | Structures Design | CU400098 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Moura | BYELLEE | STOWE | 0 | KM | MA01ML23 | 0.6999 | MA01ML23 | 0.6999 | KM |  |  |  |  | 23.7 |  | 2024-06-30 |  |  |  |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: LHS extention is heavily corroded to replace or line Proposed: Remove <(>&<)> Replace Risk: Mod-High Reason: Risk of pumping and overloading at this location as CMP is not compliant with cover over rigid pipe. Will deteriorate faster. And corosion will also increase risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093871&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093871 | Structures Design | CU101725 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | CURRAGH |  | 0 | KM | BW12ML7 | 0.08 | BW12ML7 | 0.08 | KM |  |  |  |  | 7.08 |  | 2026-06-30 |  |  | REMOVE & REPLACE RCBC |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect; Insitu section had moderate cracking in ceiling and severe vertical cracking in walls and along base slab. Propose: Remove <(>&<)> Replace likely, Can CIPP be considered for this size of RCP? Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089456&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089456 | Structures Design | CU100332 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | DUARINGA |  | 0 | KM | BW03ML104 | 0.65 | BW03ML104 | 0.65 | KM |  |  |  |  | 104.65 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: pumping under dn track. Proposed: Remove and replace Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093501&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093501 | Structures Design | CU400402 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.25 | MA01ML89 | 0.25 | KM |  |  |  |  | 89.25 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Found during Hydro Study of Mt Rainbow Proposed: Remove and replace - No major issues observed during site visit continue to monitor performance, siltation and downstream scour. If Aurizon wishes for culvert to have immunity remove and replace with 900 x 600mm RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093502&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093502 | Structures Design | CU400255 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.5699 | MA01ML89 | 0.5699 | KM |  |  |  |  | 89.57 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Found during Hydro Study of Mt Rainbow Proposed: Additional Culverts - Consider additional barrels to structure to achieve 1% TOR immunity. 3/1200 x 600mm RCBC's required to achieve immunity. Potential to investigate options of regrading the upstream table drain. Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104575&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104575 | Structures Design | CU200720 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 38000 | Goonyella | GOONYELLA |  | 0 | KM | GA01ML196 | 0.04 | GA01ML196 | 0.04 | KM |  |  |  |  | 196.04 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.4 | 3 | 3.2 | 1 | 12.9 | 192 |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect - Severe spalling in most legs, with exposed corroded reinf. Proposed - Remove and Replace or Concrete line. Risk - High Reason - Severe corrosion in walls and requires propping to hold until Fy26. Reactive scope for poor condition structure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083858&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000083858 | Structures Design | CU300512 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Newlands | HAVILAH | NEWLANDS | 0.0299 | KM | NL01ML141 | 0.8 | NL01ML141 | 0.77 | KM |  |  |  |  | 141.77 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 10.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect - 15mm crack in base slab under unit 2. 5-20mm laterally displace unit 1-6. Appears to be M160 load rating based on ceiling thickness Proposed - Remove and Replace with RCBC Risk - Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089492&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089492 | Structures Design | CU101415 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | MIDGEE | ROCKLANDS | 0 | KM | BW01ML625 | 0.19 | BW01ML625 | 0.19 | KM |  |  |  |  | 625.19 |  | 2026-06-30 |  |  |  |  | 4 | 4.5 | 3 | 4.4 | 1 | 17.5 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Moderate to sever spalling in ceiling of units in Cells 2,3 and units sunk approx 40mm and minor pumping under loaded train. Proposed: Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041749&DY_MAB=X&~OKCODE=ONLI | FY24 | Dual Traffic | FUTURE SCOPE | COAL | 002000041749 | Structures Design | CU101500 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | MIDGEE | ROCKLANDS | 0 | KM | BW01ML625 | 0.7299 | BW01ML625 | 0.7299 | KM |  |  |  |  | 625.73 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4 | 3 | 4.2 | 1 | 16 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG |  | 20240630 | * 07.08.2019 15:28:11 AUSQLD Jeremy Stevenson (R867415) * Reinforced Concrete Box Culvert FY21 Construct 1 / 1220 x 450 RCBC with Widening Right * 19.10.2020 09:38:23 AUSQLD Edward Brooks (R884255) * Defect - head wall too small for ballast and failing. Units 5 to end dropped 50mm in unit 6 all spans. * Proposed - Remove and replace with 4 cells 1200x900. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090332&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000090332 | Structures Design | CU200401 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Goonyella | RED MOUNTAIN | WINCHESTER | 0 | KM | GA03ML25 | 0.7299 | GA03ML25 | 0.7299 | KM |  |  |  |  | 25.73 |  | 2027-06-30 |  |  |  |  | 3.5 | 2.1 | 3 | 3.5 | 1 | 12.4 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Pumping under loaded trains, which has caused legs of box to spall and have some areas of exposed reinforcement. Unable to repair pumping and is progressively getting worse each inspection. Proposed: Remove and Replace Drawing: Risk: Mod-High Reason: Pumping is tytpically linked to a structural deficiency in the structure or subgrade. Once started it is difficult and expensive to repair and generally will not last. the pumping damages the units and base under the track first and eventually impacts top of line which we have seen recently on OC line. If left top of line issues expected and emergency works likely.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093262&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093262 | Structures Design | CU100423 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | ROCKLANDS |  | 0 | KM | BW03ML3 | 0.3699 | BW03ML3 | 0.3699 | KM |  |  |  |  | 3.37 |  | 2026-06-30 |  |  | REPLACE WITH BRIDGE - UNICELL |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: CU100423 with strengthening steel beams on ceiling. Pumping severely 15-20mm under loaded train, sheared bolted in strengthening steel. Proposed: Remove and Replace. Ideally with bridge or unibox. Cost comparison. Drawing: Risk: High Reason: Pumping could lead to derailments and high likelihood of top of alignment issue with track and regular resurfacing requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000116349&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000116349 | Structures Design | CU101543 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 39000 | Blackwater | ROCKLANDS |  | 0 | KM | BW01ML632 | 0.16 | BW01ML632 | 0.16 | KM |  |  |  |  | 632.16 |  | 2025-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 4.5 | 3 | 4.4 | 1 | 19.8 | 5620 |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Defect - Culvert impacted <(>&<)> collapsed by Formation renewal machinery in April 2023. Grouted one cell and severe cracks in second cell. This is on the Central line fork section of the line and a critical section of the North coast-Central line connection infr astructure. Severe impact to waterway. Proposed Remove and Replace RCBC Risk: High Reason: High risk as the impact from the machinery has collapsed one cell completely and the other cell has severe cracks. This is a critical section of the track connecting central line with north coast line and therefore important to get replaced as soon as possible. Cell has been grouted to allow traffic to continue but severe impact to waterway. High risk of track washout and second cell collpasing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084077&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000084077 | Structures Design | CU400140 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Moura | STIRRAT |  | 0 | KM | MA01ML59 | 0.91 | MA01ML59 | 0.91 | KM |  |  |  |  | 59.91 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Corrosion under invert lining an issue. Lining separated from steel pipe. FY19 Stirrat-Clarje flood study Proposed: Remove and replace with RCBC (CIPP could be considered however concrete invert lining be good to remove) Risk: Moderate Reason: Corrosion around invert lining is visibal at top, but expecte dto be worse behind lining. Mderate risk of crushing as corrosio in side walls and this will impact track alignment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093504&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093504 | Structures Design | CU201138 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Goonyella | WAITARA |  | 0 | KM | GA01ML98 | 0.9899 | GA01ML98 | 0.9899 | KM |  |  |  |  | 98.99 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.7 | 3 | 4.4 | 1 | 17.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Unit 5 Pumping under loaded traffic. Regular severe spalling and exposed corroded reinf. Proposed: Remove <(>&<)> Replace RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090221&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000090221 | Structures Design | CU100495 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | WALLAROO |  | 0 | KM | BW03ML115 | 0.63 | BW03ML115 | 0.63 | KM |  |  |  | 115.63 | 115.63 | 115.63 | 2026-06-30 | BW-CL |  |  |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Full of ballast and misalignment issues suggesting the culvert is sinking. Proposed: Remove <(>&<)> Replace, confirm if required in hydro. Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093866&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093866 | Structures Design | CU100457 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33416 | Blackwater | WESTWOOD | WINDAH | 0 | KM | BW03ML47 | 0.6999 | BW03ML47 | 0.6999 | KM |  |  |  |  | 47.7 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: insitu severe spalling and corroded reinforcement. In need of propping Proposed: Remove <(>&<)> Replace RCBC Final: Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084877&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084877 | Structures Renewal. | CU101205 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 945215 | Blackwater | ARCHER | BAJOOL | 0 | KM | BW01ML609 | 0.63 | BW01ML609 | 0.63 | KM |  |  |  |  | 609.63 |  | 2025-06-30 |  |  |  |  | 3.5 | 4.5 | 3 | 4.4 | 1 | 15.4 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Crack in haunch 2-1 spalling at base and some movement in culvert 3-4. Minimal cover with M160 units, likely pumping under loaded, but not observed. Proposed Remove and Replace 3/1200x900 RCBC 6 units long Risk: Mod-High Reason: Dropping units and haunches cracks and being rated for M160 loading are all signs of significant risk of collapse due to overloading the deisgn capcaity of 15-16TAL when operating 26.5TAL.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083945&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000083945 | Structures Renewal. | CU100132 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 919628 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML174 | 0.78 | BW03ML174 | 0.78 | KM |  |  |  |  | 174.78 |  | 2024-06-30 |  |  |  |  | 4 | 3.4 | 3 | 4 | 1 | 16 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect: Moderate to Severe cracking in ceiling of 300A culverts. Severe cracks in base slab. Looks to be old base slab. RCBC crack is present in ceiling EB confirmed with remote inspection. be good to keep good units for reuse if possible in construction. Proposed: Remove and Replace with 1200x900, drawing AUR-Q-0804-4028 Risk - Mod-High Reason: Ceiling crack through middle of ceiling suggests structural failure of unit. This will deteriorate faster now exposed to water and corrosion in steel. Likely will start to pump in time which will directly impact track alignment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083859&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000083859 | Structures Renewal. | CU100947 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 305337 | Blackwater | CALLEMONDAH |  | 0 | KM | BW52CR1 | 0.04 | BW52CR1 | 0.04 | KM |  |  |  |  | 1.04 |  | 2024-06-30 |  |  |  | 3.5WX1.2H RCBC, 5 UNITS LONG | 3.5 | 1 | 3 | 3 | 1 | 10.5 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect: Spalling in Roof Large steel pipes from local industry are completely compromising the hydro for this culvert. Look to grout up and install new culvert. Contact owners of pipes. Proposed: Remove <(>&<)> Replace 3.5Wx1.2H RCBC, 5 units long Risk: High Reason: Risk of collapse as coastal environment and exposed reinforcement in spalled ceiling will corrode at a relatively high rate. Reason: Risk of collapse as coastal environment and exposed reinforcement in spalled ceiling will corrode at a relatively high rate. planning of closures to meet the E2E Requirements
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084108&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084108 | Structures Renewal. | CU101219 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2084221 | Blackwater | CALLEMONDAH |  | 0 | KM | BW01ML540 | 0.14 | BW01ML540 | 0.14 | KM |  |  |  |  | 540.14 |  | 2025-06-30 |  |  |  |  | 4 | 1 | 3 | 3 | 1 | 12 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - base slab cracked at cell 4-6,7, cell 1-6, cell 2-5,6, pumping shown in base slab cell 4-6 <(>&<)> 7. cracks in Cell 3-7 - Proposed Renewal - Remove <(>&<)> Replace RCBC Risk: Mod-High Reason: Units under track in cells 3 <(>&<)> 4 have sunk due to base slab failure and pumping under loaded train approx 2-4mm which will directly related to pumping in track risk track alignment issues. Pumping units has minor cracks in midspan of ceiling which will deteriorate faster with continual pumping and increases risk fo collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084956&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084956 | Culvert Renewal Renewal OC 94.350km. | CU200599 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 870215 | Goonyella | DYSART | STEPHENS | 0 | KM | GA03ML94 | 0.3499 | GA03ML94 | 0.3499 | KM |  |  |  |  | 94.35 |  | 2025-06-30 |  |  |  |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Defect - Unit 2 in all cells are pumping and with horizontal severe cracking in haunches and vertically down middle of walls. Leg thickness stated to be 60mm only. Proposed - Remove and Replace 5/1900x900 RCBC 8.42m Long Drawing - AUR-Q-0854-4041 Risk: High Reason: Pumping and severe cracks in haunches is direct link to overloaded structure andhigh risk of collapse or movement unexpectedly. High risk of track impacts on this culvert
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084900&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084900 | Structures Renewal. | CU101411 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1014860 | Blackwater | EPALA |  | 0 | KM | BW01ML577 | 0.4199 | BW01ML577 | 0.4199 | KM |  |  |  |  | 577.42 |  | 2025-06-30 |  |  |  |  | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - All cells Units 8-10 Sinking and Pumping under loaded trains. Proposed Renewal - Remove <(>&<)> Replace 3/1200x900 RCBC 15.636m Long Drawing AUR-Q-0854-4039 Risk: High Reason: Pumping and sinking under loaded train directly lead to track stability issue which will lead to speed restrictions and delays if work not completed at correct time.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085017&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085017 | Structures Renewal. | CU300042 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 715965 | Newlands | KAILI |  | 0 | KM | NL02ML13 | 0.04 | NL02ML13 | 0.04 | KM |  |  |  |  | 13.04 |  | 2025-06-30 |  |  |  |  | 2.5 | 1.7 | 3 | 3.4 | 1 | 8.5 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Heavily silted regularly. Near saltwater, confirm hydro for removal Proposed - Grout <(>&<)> Divert if hydro confirms. Otherwise will be pushed out. Drawing - Risk: Moderate Reason: Moderate risk to this one, mainly in due to the regular maintenance costs of cleaning silt from culvert and location being right beside the bridge. Does not appear to be required, so if it can be eliminated it will stay in scope for renewal, otherwise will be removed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084950&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084950 | Structures Renewal. | CU101597 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 779249 | Blackwater | MIDGEE | ROCKLANDS | 0 | KM | BW01ML626 | 0.08 | BW01ML626 | 0.08 | KM |  |  |  |  | 626.08 |  | 2024-06-30 |  |  |  | R&R 2 / 1200X900 RCBC | 3.5 | 4.5 | 3 | 4.4 | 1 | 15.4 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Severe cracking in insitu culvert and base slab under Dn Rd Proposed Remove and Replace 2 / 1200x900 RCBC Risk: Moderate Reason: Severe cracking in ceiling <(>&<)> base slab of insitu section need to be monitored as risk of collapse, however deterioration rate slower than others and could be pushed to FY25/26, but not longer
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083116&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000083116 | Structures Renewal | CU200413 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 490498 | Goonyella | MILLENNIUM JUNCTION |  | 0 | KM | GA03ML16 | 0.4199 | GA03ML16 | 0.4199 | KM |  |  |  |  | 16.42 |  | 2024-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 2.8 | 3 | 3.8 | 1 | 17.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect: units misaligned, ballasting falling through joints and undermining sleeper stability. Speed restriction required. Temporary rings or hdpe required until renewal Proposed: Remove and Replace RCBC Pipe through culvert owned by Daunia Quarry, to be contacted prior to renewal Risk: High Reason: Track stability has been compromised in this location with edge of sleeper exposed from falling ballast into culvert. temporary measures dramatically reduce the capacity of the waterway and increase the risk of track washout during weather event. All these put above rail operation at high risk of disruptions.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085998&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085998 | Structures Renewal. | CU400049 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 675162 | Moura | PARANA |  | 0 | KM | MA01ML6 | 0.46 | MA01ML6 | 0.46 | KM |  |  |  |  | 6.46 |  | 2025-06-30 |  |  |  |  | 4 | 1 | 3 | 3 | 1 | 12 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect: Severe corrosion above concrete invert lining from 3 to 9 oclock. Proposed: Concrete line or remove and replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080312&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000080312 | Structures Renewal. | CU201298 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 756237 | Goonyella | PEAK DOWNS |  | 0 | KM | GA17ML45 | 0.3599 | GA17ML45 | 0.3599 | KM |  |  |  |  | 45.36 |  | 2024-06-30 |  |  |  |  | 4.5 | 1.2 | 3 | 3.1 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect: FLOOR INVERT CORROSION. and hole formed between access rd and track suggesting severe corrosion. Both cells partially collapsed under access rd. Proposed: Remove and Replace with RCBC. Mine pipe through cell is not live and can be removed during construction, confirmed by PD Mine 26/7/21. Risk: Mod-High Reason: not immediate risk, but coming closer to FY24, this culvert will be in risk of scouring and track impacts to movement in the pipes. Also if we do not catch this cmp now it will require a track closure to remove and replace. Plan now is for it to be CIPP lined.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094128&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000094128 | Structures Renewal | CU100709 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 878380 | Blackwater | RANGAL |  | 0 | KM | BW03ML195 | 0.6999 | BW03ML195 | 0.6999 | KM |  |  |  |  | 195.7 |  | 2024-06-30 |  |  | REMOVE & REPLACE |  | 0 | 10 | 3 | 0 | 1 | 100 | 184 | 2022-03-31 |  | Culvert Renewals | STRATEGIC | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect: Being replaced as part of a Level crossing (temp) formation replacement extends to this culvert and hydro for this culvert suggests fall should be in opposite direction to how it is flowing currently. Efficiency of replace now will be the savings in formation and track rebuild as this will form part of teh level crossing upgrade. Proposed: Remove and Replace RCBC Drawing: Risk: Mod Reason: More a strategic scope to improve drainage through the corridor by correctly natural water flow through this culvert. Also saves an additional culvert being installed through teh temp level crossing and extensive earthworks to get drainage to work against the flow of the land. Efficiency in delivery for this culvert as well,as the costs of formation and track rebuild will be included in Level crossing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070098&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000070098 | Structures Renewal. | CU100505 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 928317 | Blackwater | SAGITTARIUS |  | 0 | KM | BW03ML193 | 0.91 | BW03ML193 | 0.91 | KM |  |  |  |  | 193.91 |  | 2024-06-30 |  |  |  |  | 3.5 | 2.9 | 3 | 3.9 | 1 | 13.7 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 30.12.2020 17:08:35 AUSQLD Edward Brooks (R884255) * Defect: CULVERTS UNIT/S DROPPED in units 8 and 9, 80 and 15mm respectively. Spalling in legs of 300A units at base. Sever cracks in base slab. * Proposed: Replace culvert on the Dn Rd side only. Approximately 6 units from north side. Patch repair spalling in 300A units. Seal any crack or inspect if greater than 0.3mm. * Risk: Mod-High * Reason: Unit 9 is very poor condition, sinking 70 and moderate haunch crack suggesting this unit could faul or drop further and compromise hydro of culvert and increase risk of track washout. The collapse or further sinking could cause derailment and additional resurfacing. further sinking could cause derailment and additional resurfacing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084076&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084076 | Structures Renewal. | CU400456 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 585600 | Moura | STIRRAT |  | 0 | KM | MA01ML60 | 0.8199 | MA01ML60 | 0.8199 | KM |  |  |  |  | 60.82 |  | 2024-06-30 |  |  |  |  | 4 | 1.1 | 3 | 3.5 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect: Longitudinal cracks in base and haunch cracking in cells 2 and 3. D7 track defect constantly occuring on this asset, making it higher priority to get replaced. FY19 Stirrat-Clarje flood study Proposed: Remove and Replace RCBC as subgrade appears to be compromised as base slab failed. Risk: High Reason: Track stability has been an issue for local districts team and ATIS is stating a D7 defect each run and therefore this is a priority piece of work to get renewed as soon as possible. High risk of customer impacts if this scope is deferred.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084978&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084978 | WTA Culvert Renewal 98.920KM. | CU201052 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 3161021 | Goonyella | WAITARA |  | 0 | KM | GA01ML98 | 0.92 | GA01ML98 | 0.92 | KM |  |  |  |  | 98.92 |  | 2025-06-30 |  |  |  | R&R 9 / 2400X1200 RCBC | 4 | 4.7 | 3 | 4.4 | 1 | 17.6 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - all cells propped from units 8-14, cracked in hog in unit 4 most spans and pumping on typically all spans for units 3-5/6. severely corroded steel bea for propping at U12-13. Proposed - Remove <(>&<)> Replace 9 / 2400x1200 RCBC Drawing - Risk: Mod-High Reason: Significant haunch cracking and numerous pumping culverts is the biggest risk here. Culvert is under capacity for the track loading of 26.5TAL and the pumping will deteriorate the concrete quicker. Think condition is more a 3.5-4 rather that 4.5 stated by inspector. end unit central cracking is also a concern as this could suggest reinf internally is flexing and cracking the surrounding concrete which would support the large section of faling repaired spalling. pumping will deteriorate the ballast and track alignment above and cuase risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043690&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043690 | Structures Renewal. | CU101375 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1646365 | Blackwater | YARWUN |  | 0 | KM | BW01ML550 | 0 | BW01ML550 | 0 | KM |  |  |  |  | 550 |  | 2024-06-30 |  |  |  | R&R 4/1500X1200 RCBC | 4 | 4.9 | 3 | 4.5 | 1 | 18 | 184 | 2022-03-31 | 2019-11-29 | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 03.04.2020 11:06:22 AUSQLD Edward Brooks (R884255) * "Cracked and pumping base slab under culvert units 6 to 9 with broken concrete upstand on the near side possibly due to poor foundation. Area of pumping base slab is approximately under the up track. * Spalling to leg of unit 9 on the near side. * Breaking of the seating mortar of units 6 to 9 and spalling to legs on the near side of units 8 and 9 - Remove and replace 4/1500x900 partial replacement or tunnelline as between two new culvert cells. " Due to clash with turnout above and to allow redesign and replanning of work, renewal now planned for delivery in FY24. PCR to be submitted by PM. 15/2/22 EB Advised by Das estimate for this work will be greater than $1M, therefore adjusted estimate in N4 accordingly.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110501&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000110501 | Structures Renewal | CU101579 | CIVIL | STRUCTURES | RCBC-BRIDGE-S1 | RENEWAL | 1 | SITE | 3635000 | Blackwater |  |  | 0 | KM | BW01ML613 | 0.07 | BW01ML613 | 0.07 | KM |  |  |  |  | 613.08 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.5 | 3 | 4 | 1 | 17.5 | 5543 |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Stage 1 Construction Defect - Severe pumping on cells 1 <(>&<)> 28. Cell 1 severely cracked legs. Cell 24-28 appear to have dropped approx 50mm. This is second time dropped after being lifted almost 100mm previously with subgrade injections. Proposed Remove and Replace RCBC Risk: High Reason: High risk of collapse and track undermining due to severe pumping of the units, deferment would lead to speed restruction re quirements and delays to customer services. 15/2/22 EB Design was not completed by March 2022, therefore construction delivery pushed from FY24 to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092312&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092312 | Structures Design | CU300333 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | DESIGN | 1 | SITE | 33416 | Newlands | PRING |  | 0 | KM | NL01ML4 | 0.44 | NL01ML4 | 0.44 | KM |  |  |  |  | 4.44 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.8 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Spalling in multiple units in multiple locations. Holds water for much of the year. Proposed: Concrete Lining confirmed by Hydro. If remove and replace, invert raising may be beneficial as holds water a lot of the year. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084818&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084818 | Structures Renewal | CU101575 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 636939 | Blackwater | ALDOGA |  | 0 | KM | BW01ML556 | 0.05 | BW01ML556 | 0.05 | KM |  |  |  |  | 556.05 |  | 2025-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate Cracking in haunches Proposed Renewal - Concrete Line 300mm +150mm Fish baffle on far legs. Risk: Mod-High Reason: Needs to be concrete lined at same time as 556.110 to maintain consistency and prevent future pumping of the track which will impact alignment and increase risk of loss of track stability.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084819&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084819 | Structures Renewal. | CU101431 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 1852292 | Blackwater | ALDOGA |  | 0 | KM | BW01ML556 | 0.11 | BW01ML556 | 0.11 | KM |  |  |  |  | 556.11 |  | 2025-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate cracking throughout majority of unit in haunches, ceiling and vertical moderate cracks in legs unit 1-1 <(>&<)> 10-3 Proposed Renewal - Concrete Line 300mm +150mm Fish baffle on far legs. Risk: High Reason: Ceiling cracks in many of these units and pumping under loaded track, high risk of track impacts. and prevent future pumping of the track which will impact alignment and increase risk of loss of track stability.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084951&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084951 | Structures Renewal | CU200984 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 2162267 | Goonyella | HAY POINT |  | 0 | KM | GA03BA4 | 0.508 | GA03BA4 | 0.508 | KM |  |  |  |  | 4.5 |  | 2024-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 2.6 | 3 | 3.7 | 1 | 13 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - RHS from centre insitu section has moderate to severe spalling on ceiling and legs. Proposed - Concrete Lining Risk: Moderate Reason: Spalling in ceiling and walls shows that units are overloaded and deteriorating faster and at risk of track impacting defects. Concrete lining will eliminate need for closure and provide full strength structure for 30TAL. Cost -benefit hevily in favour of this work as maintenance costs will only continue to escalate
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089487&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089487 | Structures Design | CU100032 | CIVIL | STRUCTURES | RCBC-ELIMINATE | DESIGN | 1 | SITE | 33416 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML177 | 0.4199 | BW03ML177 | 0.4199 | KM |  |  |  |  | 177.12 |  | 2025-06-30 |  |  | ELIMINATE |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Blocked with concrete, need to confirm hydrology if needs to be replaced. Proposed: Eliminate or remove and replace. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000098640&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000098640 | Structures Design | CU100331 | CIVIL | STRUCTURES | RCBC-ELIMINATE | DESIGN | 1 | SITE | 38000 | Blackwater | DUARINGA |  | 0 | KM | BW03ML103 | 0.8699 | BW03ML103 | 0.8699 | KM |  |  |  |  | 103.87 |  | 2025-06-30 |  |  | ELIMINATE |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 165 |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect - Sinking and badly misaligned. Last inspection had trouble finding this asset. Bit of confusion about km as 103.930 has been deleted in SAP, so need to check both km locations for this culvert and model both in hydro as both likely eliminated. M160 culvert as well. Proposed - Eliminate preferred as inlet has been blocked for a long time. Otherwise remove and replace. Risk - Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084901&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084901 | Structures Renewal | CU101182 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 437594 | Blackwater | MARMOR | RAGLAN | 0 | KM | BW01ML591 | 0.01 | BW01ML591 | 0.01 | KM |  |  |  |  | 591.01 |  | 2025-06-30 |  |  |  |  | 3.5 | 4.9 | 3 | 4.5 | 1 | 15.8 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Unit 5 dropped 100mm suggesting base slab failure under track Proposed Renewal - Remove <(>&<)> Replace RCBC Risk: Mod-High Reason: Waterway severely compromised with sinking of unit by 100mm. This increases the risk of track washout and the sinking will require regular ballast top up causing higher maintenance costs and high risk of track alignment issues. Remote inspection CR O - 1, S - 1, BC - 1, Spalling, Severe, Roof x 3. Mod spalling, near and far legs. WR1 - 1, S - 1, BC - 6 Displaced Movement, Severe, 100mm,Suspect CBS has failed, Exposed rio in roof WR1 - 1, S - 1, BC - 7, Displaced Movement, Severe, 100mm, Suspect CBS has failed Reinspected on the 30/06/2022 Seems to be no change have noticed its marked up for an undercut New remote inspection 28/11/2023 CR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089434&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089434 | Structures Design | CU100571 | CIVIL | STRUCTURES | RCBC-STRENGTHEN | DESIGN | 1 | SITE | 33416 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML132 | 0.8199 | BW03ML132 | 0.8199 | KM |  |  |  |  | 132.82 |  | 2024-06-30 |  |  |  |  | 3 | 3.4 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Reinforced Concrete Box Culvert FY20 Design 8 / 1520 x 1530 RCBC with Widening Left Defect: Cracks in haunches throughout culverts Proposed: Crabon Fibre strengthening recommended from AECOM report in FY20. Detailed design of Carbon fibre strengthening to be completed in FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092315&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000092315 | Structures Design | BR300147 | CIVIL | STRUCTURES | RCBC-UNIBOX | DESIGN | 1 | SITE | 33416 | Newlands | ARMUNA | BUCKLEY | 0.014 | KM | NL01ML15 | 0.683 | NL01ML15 | 0.6969 | KM |  |  |  |  | 15.7 |  | 2026-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 |  | 2022-03-31 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Propped bridge. 50kph Speed restriction to all loaded traffic, Under load capacity Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. To be confirmed again during design stage. Drawing: Risk: Reason: Strategic
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085024&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085024 | Structures Renewal. | BR300248 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 1962159 | Newlands | ARMUNA | BUCKLEY | 0.021 | KM | NL01ML12 | 0.1849 | NL01ML12 | 0.2059 | KM |  |  |  |  | 12.2 |  | 2025-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect - 59 kph Speed restriction overload 26.5-27.5TAL, Under load capacity Proposed - Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Drawing - Risk: High Reason: Strategic scope due to long term speed restriction due to these structures being under load capacity for the current 26.5TAL.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085025&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085025 | Structures Renewal. | BR300239 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 2229654 | Newlands | ARMUNA | BUCKLEY | 0.021 | KM | NL01ML12 | 0.227 | NL01ML12 | 0.2479 | KM |  |  |  |  | 12.23 |  | 2025-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect - 59 kph Speed restriction overload 26.5-27.5TAL, Under load capacity Proposed - Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Drawing - Risk: High Reason: Strategic scope due to long term speed restriction due to these structures being under load capacity for the current 26.5TAL.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084954&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000084954 | Culvert Renewal Renewal OC 34.420km. | CU200377 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 1937041 | Goonyella | PEAK DOWNS | WINCHESTER | 0 | KM | GA03ML34 | 0.4199 | GA03ML34 | 0.4199 | KM |  |  |  |  | 34.42 |  | 2024-06-30 |  |  |  | R&R 4/2400X2400 RCBC UNICELL | 4 | 2.1 | 3 | 3.5 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Large gap between units and severe crack in base slab. Gap increased 5-10mm in last three years from SC. Culverts pumping side to side suggesting subgrade issues. Proposed - Remove and Replace 4/2400x2400 RCBC Unicell lift 300mm Drawing - AUR-Q-0854-4043 Risk: Mod-High Reason: Gap opening up is greatest risk and difficult to maintain as it will continue to open up. Increasing approx 5-10mm every 2 years and large enough for material to fall through and undermine track stablity leading to restrictions or closure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089486&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000089486 | Structures Design | CU200762 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 33416 | Goonyella | BALOOK | BOLINGBROKE | 0 | KM | GA01ML68 | 0.65 | GA01ML68 | 0.65 | KM |  |  |  |  | 68.65 |  | 2026-06-30 |  |  |  |  | 4 | 5 | 3 | 4.5 | 1 | 18.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Widening right severely corroded in invert and defomred in shape. Corrosion visible from outside face as well. Proposed: Replace failing windening Right CMP with RCP preferrably. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094594&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094594 | Structures Design | CU400194 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 33416 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML80 | 0.0899 | MA01ML80 | 0.0899 | KM |  |  |  |  | 80.09 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 3 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Invert of CMP completely corroded and miss-shapped on the ends. Unsure due to shape of CMP whether CIPP will be option on this, so selected replace above to be conservative. Proposed: CIPP line or remove and replace confirm in design Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085010&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085010 | Structures Renewal. | CU300082 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 719080 | Newlands | KAILI |  | 0 | KM | NL02ML6 | 0.75 | NL02ML6 | 0.75 | KM |  |  |  |  | 6.75 |  | 2024-06-30 |  |  | CIPP | R&R 1/1350 RCP | 3.5 | 3.2 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate to severe corrosion above invert lining. Proposed - CMP CIPP Line Final Design - Remove <(>&<)> Replace 1/1350 RCP Drawing - Risk: Mod-High Reason: CIPP is the cheapest renewal option based on past experience and achieves the 30TAL wiuth 50 year life without creating a track closure, so before severe corrosion turn to large cracks, deformed shape and sizes of collapse CIPP is extremely good alternative, delaying only increase risk of remove and replace required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090620&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000090620 | Structures Design | CU300438 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33416 | Newlands | ALMOOLA | COLLINSVILLE | 0 | KM | NL01ML75 | 0.45 | NL01ML75 | 0.45 | KM |  |  |  |  | 75.45 |  | 2025-06-30 |  |  |  |  | 4.5 | 2.5 | 3 | 3.7 | 1 | 16.7 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Severe cracking in Ceiling of all units and some side cracka nd circumference cracking. Very poor condition Proposed: CIPP lining if hydro allows. Drawing: Risk: High Reason: Severe cracking in ceiling will only worsen and cannot be repaired. High risk of collapse. Lining with CIPP will save track closure and provide 50 years more life.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091002&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000091002 | Structures Design | CU300611 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33416 | Newlands | MCNAUGHTON |  | 0 | KM | NL04ML83 | 0.28 | NL04ML83 | 0.28 | KM |  |  |  |  | 83.28 |  | 2025-06-30 |  |  |  |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.4 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: Severe cracking in ceiling of pipe under the track units 3, 4. Poly pipe in cell 1 and disconnected steel pipe in cell 2. concrete worn under poly pie and exposed reinf most units. Proposed: CIPP lining if hydro allows, otherwise remove and replace. Drawing: Risk: High Reason: Severe cracking in ceiling will only worsen and cannot be repaired. High risk of collapse. Lining with CIPP will save track closure and provide 50 years more life.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052586&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000052586 | Structures Design | CU100285 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33416 | Blackwater | UMOLO |  | 0 | KM | BW03ML142 | 0.6999 | BW03ML142 | 0.6999 | KM |  |  |  |  | 142.7 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 3.35 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 26.02.2020 15:43:17 AUSQLD Peter Rayner (R003851) * Defect - Notif 2000024905 cracking throughout pipes under up road. Minor to mod cracks in 1-1,1-2,11-4,12-5,15-1,21-2 severe in 1.2 - Proposed Renewal - 0
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093848&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093848 | Structures Design | CU100509 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33416 | Blackwater | WESTWOOD | WYCARBAH | 0 | KM | BW03ML45 | 0.4799 | BW03ML45 | 0.4799 | KM |  |  |  |  | 45.48 |  | 2026-06-30 |  |  | CIPP |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2022-03-31 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect: PIPE UNIT/S CRACKED cell 1 unit 7 cracked 45.480km 45.480km pipe is cracked in unit 7 needs to be renewed or proped. Pumping in both cells at unit 7. Cracks appears to have gotten bigger in last 12 months. Proposed: CIPP lining if hydro allows. Drawing: Risk: High Reason: Lining with CIPP will save track closure and provide 50 years more life.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085021&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085021 | Structures Renewal | CU300342 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 75280 | Newlands | ABERDEEN | ARMUNA | 0 | KM | NL01ML30 | 0.3499 | NL01ML30 | 0.3499 | KM |  |  |  |  | 30.35 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.9 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate misalignment off small pipe through out. Check hydro for grouting. Good cover for a 900 pipe jack Proposed - CIPP line if Hydro suitable (FY24). Remove and Replace with larger 1/900 RCP (FY26) Final - CIPP confirmed in design Drawing - Risk: Moderate Reason: Misalignment will gradually make this culvert redundant as it is very small, so if it can be aliminate it would be preferred, otherwise CIPP is hoped to be installed before misalignment is too bad to repair.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083941&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000083941 | Structures Renewal | CU100305 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 941002 | Blackwater | AROONA | DUARINGA | 0 | KM | BW03ML99 | 0.64 | BW03ML99 | 0.64 | KM |  |  |  |  | 99.64 |  | 2024-06-30 |  |  | CIPP | CIPP | 3.5 | 3.35 | 3 | 4 | 1 | 14 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - Moderate horiz cracking in units 2 all cells. LHS head wall severely cracked. Proposed Renewal - Berolina Lining Risk - Mod-High Reason - Horizontal cracking in RCP is highest risk of collapse as first sign of crushing leading to collapse. Time to collapse variable, however mod-high rsik of deteriorating faster than other assets due to current cracked condition. This can also not be repair. Lining is cheapest method to avoid closure time.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085022&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085022 | Structures Renewal | CU300276 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 75280 | Newlands | BINBEE | BRIABA | 0 | KM | NL01ML53 | 0.64 | NL01ML53 | 0.64 | KM |  |  |  |  | 53.64 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.9 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - severe cracks in outlet RCP units. Crcaks throughout in bottom of pipe Proposed - RCP CIPP Lining or remove and replace. Drawing - Risk: Mod-High Reason: Severe cracks in RCP are high risk of collapse which will have track impacts like clousre or restrictions.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085023&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085023 | Structures Renewal | CU300161 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 163107 | Newlands | COLLINSVILLE |  | 0 | KM | NL01ML77 | 0.75 | NL01ML77 | 0.75 | KM |  |  |  |  | 77.75 |  | 2025-06-30 |  |  | CIPP | CIPP | 3 | 2.5 | 3 | 3.7 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect - circumference cracking in unreinforced pipe leading to misalignment and drainage issues and undermining around the units. Proposed - CP CIPP Lining Drawing - Risk: Mod-High Reason: Misalignmemt and cracking concrete pipes allows water to flow through cracks and behind the units undermining the stability of the units and eventually the track.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093507&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093507 | Structures Renewal | CU100054 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 319924 | Blackwater | KABRA |  | 0 | KM | BW03ML14 | 0.22 | BW03ML14 | 0.22 | KM |  |  |  |  | 14.22 |  | 2024-06-30 |  |  | CIPP LINE | CIPP | 3.5 | 4 | 3 | 4.2 | 1 | 14.7 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Defect: Moderate crack in ceiling and walls of RCP. Proposed: CIPP Lining Risk: Mod-High Reason: Cracking in the ceiling and sides of the RCP are structural cracks and risk of collapse is moderate to high. If collapses it will be removed and replace requiring track closure, CIPP will not require closure and cost less.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085050&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085050 | Structures Renewal | CU101309 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 108354 | Blackwater | MARMOR | RAGLAN | 0 | KM | BW01ML597 | 0.2899 | BW01ML597 | 0.2899 | KM |  |  |  |  | 597.29 |  | 2025-06-30 |  |  | CIPP | CIPP | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Defect - Severe Cracks in all RCP, needs sleeving Proposed - RCP CIPP line Drawing - Risk: High Reason: Culvert with severe cracking and increased risk of collapse, will save significant costs if CIPP lined now without a closure before worsening.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081470&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000081470 | Structures Renewal | CU100267 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 2609381 | Blackwater | UMOLO |  | 0 | KM | BW03ML143 | 0.8 | BW03ML143 | 0.8 | KM |  |  |  |  | 143.8 |  | 2024-06-30 |  |  | CIPP | CIPP | 4 | 3.35 | 3 | 4 | 1 | 16 | 184 | 2022-03-31 | 2020-11-13 | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | 26.02.2020 15:43:48 AUSQLD Peter Rayner (R003851) Defect - Notif 2000024906 Cracked regularly through first 2-3 units in LHS RCP's Proposed Renewal - Investigate CIPP lining of LHS RCP's as this may be a substantial cost savings in construction and avoid track closures. Note there is a significant step in old to new RCP's. Risk - High Reason: Currently these LHS RCP's are on a 6 monthly inspection frequency to ensure any significant change in cracking is occuring. Risk with these cracking in the top half of the RCP is that they will start to deform in shape and this will cause track alignment issues and due to there size may collapse. Aim is to Line to culvert before collapse to prevent a track closure and interuption to train paths. Should not be deferred.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103752&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103752 | Structures Design | CU101306 | CIVIL | STRUCTURES | RCP-LINE | DESIGN | 1 | SITE | 38000 | Blackwater | MOUNT LARCOM |  | 0 | KM | BW01ML564 | 0.8299 | BW01ML564 | 0.8299 | KM |  |  |  |  | 564.83 |  | 2026-06-30 |  |  | CIPP OR PVC LINE |  | 3 | 1.7 | 3 | 3.4 | 1 | 10.1 | 272 |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Defect - Horizontal minor to moderate cracking in units C1-3,4,5,6, C2-4 ,5,6, C3-3,5,6, C4-3,4,5. Looking at renewal options now as Turnout above being renewed in FY26. Note Mast looks to be impacted by remove and replace Proposed - Tentative in FY26 for Remove and Replace as turnout replaced above, however first prefernce is to look at lining options for this asset so it can be held unti FY28-30 before renewal Risk - Moderate for Remove and Replace in FY26 Reason - Included in FY26 because turnout above is being renewed and to prevent damaging this in the future a remove and replace will be better for the rail over time but also more cost effective as two assets being upgraded at the same time minimised track and formation material removal at least on one occasion.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097486&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097486 | C21 NL TU COLLINSVILLE 77.203 - 78.296. | NL-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.09 | TRACK KM | 1737464 | Newlands | ALMOOLA | COLLINSVILLE | 1.0909 | KM | NL01ML77 | 0.203 | NL01ML78 | 0.2959 | KM | 20 | 1600 | 2.16 | 1.09 | 77.203 | 78.296 | 2023-12-31 | SINGLE | BOTH |  |  | 4 | 2.5 | 1 | 2.7 | 1 | 10.8 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent Notification RAIL NOTIFICATION; 2000093413 (77.210 - 78.290) SLEEPER NOTIFICATION:2000093414 (77.210 - 78.270) RAIL AND SLEEPERS REQUIRED AFTER LX3301 AND FINISH AT TOS 10A/B Post walkouts: 77.203km - 77.290km - Rail 77.203km - 77.296km - Sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097487&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097487 | C21 NL TU BIRALEE 93.431 - 93.811. | NL-05SD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.38 | TRACK KM | 848301 | Newlands | BIRALEE | BIRALEE | 0.38 | KM | NL05SD93 | 0.4309 | NL05SD93 | 0.811 | KM | 7 | 555 | 0.76 | 0.38 | 93.431 | 93.811 | 2024-06-30 | BAD ORDER SIDING | BOTH |  |  | 4 | 1 | 1 | 1.5 | 1 | 6 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG | FY23 OUT | 20240630 | Parent Notification: Rail Notification 2000074995 (93.431 - 93.811) Sleeper Notification 2000093429 (93.431 - 93.811) 24.03.2021 16:04:38 AUSQLD Sanjna Rajagopalan (R884639) TRACK UPGRADE - B.O.S 93.431 - 93.811 7 rails total - both legs Existing rail is 41kg - cascade with 53kg rail TU to commence at LLB and continue to stop block, 41kg stop block can be re-used, skim of ballast required - 555 sleepers sleeper notification:2000093429
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097528&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097528 | C21 TU GA BRAESIDE 118.025 - 119.987. | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.959 | TRACK KM | 1982324 | Goonyella | BRAESIDE | MINDI | 1.959 | KM | GA02ML118 | 0.025 | GA02ML119 | 0.9869 | KM | 36 | 670 | 3.924 | 1.962 | 118.025 | 119.987 | 2024-06-30 | UP | BOTH |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent notification rail notification 2000054648 (118.025 - 119.987) sleeper notification 2000092320 (118.293 - 118.747) 670slprs 03.04.2020 12:21:50 AUSQLD Milton Saha (R884640) Scoped in Oct last year. Scope ties into reverse curves at ~118km (Re-rail Nov 2017) and runs out at Mindi BOS turnout (ER1A). 32 Rails GA-02ML (Defect Heavy section - multiple TD's of different sizes) Priority is Q1 FY23 23.03.2021 15:31:56 AUSQLD Sanjna Rajagopalan (R884639) MOVED TO FY25 Q2 - As per AC comments Tie into FY22 TU Ending at 118.025km Sleeper notification 2000092320
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097522&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097522 | C21 TU GA BROADLEA 158.283 - 159.876. | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.594 | TRACK KM | 1333778 | Goonyella | BROADLEA | CARBOROUGH DOWNS | 1.594 | KM | GA01ML158 | 0.2829 | GA01ML159 | 0.876 | KM | 30 | 1340 | 3.186 | 1.593 | 158.283 | 159.876 | 2024-06-30 | DOWN | BOTH |  |  | 3.5 | 2.5 | 1 | 2.7 | 1 | 9.45 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent Notification rail 2000092321 (158.283 - 159.876) sleeper 2000092322 (158.289 - 159.200) RRP 158.283km (LLB 7CD pts) - 159.876km (FY22 scope start) > replace 60kg BHP 1987 SC fatigue rail GIJ; > 1x 60kg 4 bolt @158.375km LR (Signal BL27/44) - replace > 1x 60kg 4 bolt @158.375km RR (Signal BL28/43) - replace Comments; Driven by fatigue, patch left behind Sleeper Notification:2000092322
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097525&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097525 | C21 GA CARABOROUGH DWNS 160.202 -163.120 | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.916 | TRACK KM | 2439960 | Goonyella | CARBOROUGH DOWNS | BURTON DOWNS | 2.9159 | KM | GA01ML160 | 0.202 | GA01ML163 | 0.1199 | KM | 54 | 3210 | 5.832 | 2.916 | 160.202 | 163.12 | 2024-06-30 | DOWN | BOTH |  |  | 3.8 | 2.4 | 1 | 2.7 | 1 | 10.26 | 243 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent Notification rail 2000092330 (160.020 -163.120) Sleeper Notification: 2000092332 (160.202 - 163.120) RRP 160.202km (FY21 scope end) - 163,120 (Start of FY23 scope) > Replace 60kg BHP 1987 SC fatigue rail GIJ; > 1x 60kg 6 bolt @ 160.477km LR (Signal CD16/18) - replace > 1x 60kg 6 bolt @ 160.477km LR (Signal CD16/18) - replace > 1x 60kg 6 bolt @ 161.038km LR (Signal CD25/23) - keep > 1x 60kg 6 bolt @ 161.039km LR (Signal CD25/23) - keep > 1x 60kg 6 bolt @ 167.616km RR (Signal MA14/29) - keep > 1x 60kg 6 bolt @ 167.615km LR (Signal MA13/30) - keep Wayside equipment; > DED @ 160.735km > Axle counter RR @ 161km > Magnet @ 164.931km > Axle counter RR @ 167.656km Level Crossings: replace Dn rd signage <(>&<)> install flangeways > LX ID3209 @ 161.850km > LX ID7028 @ 164.950km > LX ID3206 @ 166.875km Comments; Driven by 163.119km Exp FY25, take opportunity to renew entire section whilst mobilised Descoped due to oportunity to execute with formation renewal. 1st section - 160.202km (FY21 scope end) - 163.120km = 3210 sleepers - 54 rails - 2000097525 2nd section 163.830km (FY23 scope end) - 164.970 = 1656 sleepers - 21 rails
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097526&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097526 | C21 GA CARABOROUGH DWNS 163.830 -164.970 | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.134 | TRACK KM | 1938072 | Goonyella | CARBOROUGH DOWNS | BURTON DOWNS | 1.1339 | KM | GA01ML163 | 0.8299 | GA01ML164 | 0.9699 | KM | 21 | 1656 | 2.268 | 1.134 | 163.83 | 167.843 | 2024-06-30 | DOWN | BOTH |  |  | 3.8 | 2.4 | 1 | 2.7 | 1 | 10.26 | 243 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20240630 | Parent Notification Rail: 2000092333 (163.830 - 167.843) Sleeper:2000029334 (163.830 - 167.843) RRP 163.830 (FY23 Scope end) - 167.843km (LLB 12CD pts) > Replace 60kg BHP 1987 SC fatigue rail GIJ; > 1x 60kg 6 bolt @ 167.616km RR (Signal MA14/29) - keep > 1x 60kg 6 bolt @ 167.615km LR (Signal MA13/30) - keep Wayside equipment; > Magnet @ 164.931km > Axle counter RR @ 167.656km Level Crossings: replace Dn rd signage <(>&<)> install flangeways > LX ID7028 @ 164.950km > LX ID3206 @ 166.875km Comments; Driven by 163.119km Exp FY25, take opportunity to renew entire section whilst mobilised Descoped due to oportunity to execute with formation renewal. 1st section - 160.202km (FY21 scope end) - 163.120km = 3210 sleepers - 54 rails - 2000097525 2nd section 163.830km (FY23 scope end) - 164.970 = 1656 sleepers - 21 rails
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097488&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097488 | C21 TU NL HAVILAH 129.737-131.178. | NL-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.442 | TRACK KM | 2072825 | Newlands | COCKOOL | HAVILAH | 1.4419 | KM | NL01ML129 | 0.7369 | NL01ML131 | 0.1779 | KM | 27 | 2106 | 2.902 | 1.442 | 129.54 | 130.991 | 2024-06-30 | SINGLE | BOTH |  |  | 3.5 | 1.4 | 1 | 1.9 | 1 | 6.65 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent Notification rail 2000094258 (129.540 - 130.991) sleeper 2000096926 (129.540 - 130.986) Post site walkot 129.737km - 131.178km - Rail 129.737km - 131.177km - Sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092087&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000092087 | C21 DURAINGA SIDING 104.152-104.777. | BW-10SD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.625 | TRACK KM | 1023988 | Blackwater | DUARINGA SIDING | DUARINGA SIDING | 0.625 | KM | BW10SD104 | 0.1519 | BW10SD104 | 0.777 | KM | 12 | 831 | 1.296 | 0.625 | 104.152 | 104.777 | 2024-06-30 | SINGLE | BOTH |  |  | 4.4 | 3.35 | 1 | 3.2 | 1 | 14.08 | 194 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | Replace with 28T LPC Replace timber sleepers on Duaringa 10Pts Crossover (BW-76XR) Replace timber sleepers between T.O.S 10B Pts to T.O.S ER2.2B Replace timber sleepers between ER2.2B to ER1.2A Replace timber sleepers between ER1.2A to 9A Pts Was sleepers only but changed to track upgrade - SCR 189
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097527&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097527 | C21 TU BW EDUNGALBA 87.800-94.195. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 6.354 | TRACK KM | 7678648 | Blackwater | EDUNGALBA | AROONA | 6.2949 | KM | BW03ML87 | 0.8589 | BW03ML94 | 0.159 | KM | 116 | 7210 | 12.528 | 6.39 | 87.8 | 94.159 | 2024-06-30 | DOWN | BOTH |  |  | 3.6 | 3.35 | 1 | 3.2 | 1 | 11.52 | 177 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20250707 | Parent Notification rail notification - 2000092329 Sleeper notification - 2000092390 Post sitewalkout: Change in quantity: Rail 110 to 116 total (cut out 1992 BHP SC rail on higher chainage end. Tie into 2013 ONE steel Change in quantity: Sleepers 8750 to (6760 + 190 + 260 = 7210). As assessed by CM on site to account for Fast clip sleeper that have already been replaced with e-clip SRC 177
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092216&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000092216 | C21 BW GORDONSTONE 4.852-6.622. | BW-10ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.769 | TRACK KM | 2750379 | Blackwater | GORDONSTONE | YAN YAN | 1.7689 | KM | BW10ML4 | 0.8519 | BW10ML6 | 0.6219 | KM | 33 | 2580 | 3.456 | 1.769 | 4.852 | 6.622 | 2024-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 | 188 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification completed | RRIG |  | 20240630 | 2580 Sleepers 33 Rails Cut in point to start at end of FY22 job(3.393km - 4.858km) Cut out to tie in at Cuddenson Road level Crossing This used to be sleepers only - we have changed to track upgrade to remove defect rails at the same location - SRC 188
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104467&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000104467 | C21 TU PEAK DOWNS 46.982-47.084. | GA-17ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.107 | TRACK KM | 157800 | Goonyella | PEAK DOWNS BALLOON | PEAK DOWNS BALLOON | 0.1069 | KM | GA17ML46 | 0.9819 | GA17ML47 | 0.084 | KM | 2 | 65 | 0.216 | 0.107 | 46.982 | 47.084 | 2023-06-30 |  | BOTH |  |  | 3.5 | 1.1 | 1 | 1.8 | 1 | 5.5 | 5618 |  |  | Track Upgrade | [5 empty] | Outstanding notification | NWSC |  | 20240630 | TO BE FUNDED VIA FOF Start of concrete slab @ 47.079km Meridian Weigher @ 47.058km Rail encased in concrete @ 47.041km - 47.013km Concrete Spill Detector @ 47.011km DED @ 47.000km Weigh Bridge @ 46.992km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129850&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic |  | COAL | 002000129850 | C21 Peak Downs Balloon Loop | GA-17ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.168 | TRACK KM | 914417 | Goonyella | PEAK DOWNS BALLOON LOOP ENTRY | PEAK DOWNS BALLOON LOOP ENTRY | 2.168 | KM | GA17ML47 | 0.079 | GA17ML49 | 0.2399 | KM | 7 | 3154 | 0.756 | 2.168 | 47.079 | 49.24 | 2024-06-30 | ENTRY ROAD | BOTH |  |  | 4 | 1.1 | 1 | 1.6 | 1 | 6.4 | [9 empty] | Outstanding notification | NWSC |  | 20240630 | Rail Component - 47.079 - 47.450 - 7 rails total Sleeper Component - 47.079km - 49.240km - 3154 sleepers Job is to remove severly corroded rail - web and foot with lamination and pieces breaking away. Replacing existing eclips with new as they are fully corodded and no longer fit for service and aslo replacing existing fist clip sleepers with pandrol e clip sleepers. Scope is to be completed with below two undercutting jobs: • 45.660km - 45.730km Exit Road (2000100985) • 45.670km - 45.770km Entry Road (2000033215) Please see attachments for email background
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097305&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097305 | C21 GA PRAGUELANDS 16.059 - 16.869. | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.62 | TRACK KM | 638282 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0.81 | KM | GA02ML16 | 0.0589 | GA02ML16 | 0.8689 | KM | 15 |  | 1.62 | 0.81 | 16.059 | 16.869 | 2023-09-30 | UP | BOTH |  |  | 3.8 | 4.6 | 1 | 3.7 | 1 | 14.06 |  | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | PARENT NOTIFICATION: CHILD,,RAIL ,,2000063281 C17 GA PRAGUELANDS 16.059-16.869 CHILD,,SLEEPER 2000092335 C18 GA PRAGUELANDS 16.105-16.398 13.08.2020 14:40:47 AUSQLD Milton Saha (R884640) 1. Plain Creek Up Rd 2. 16.063 -16.873 Q4 FY22 3. Side wear brought forward 4. Tech Scope to be double checked and confirmed with AC 16.10.2020 08:45:07 AUSQLD Milton Saha (R884640) After Inspection RRP & SRC GA16.059km-16.869km Praguelands km UP Q4 FY22 Change: Partial SRC added + Refined start/end KM - (16.059 – 16.869km Rail) , (16.105 – 16.398km Sleepers). Changed to track upgrade Reason: 427 Cracked sleepers to be added to scope after inspection Notes: Construction Date is 16th of Feb 2022 02.03.2021 22:40:50 AUSQLD Sanjna Rajagopalan (R884639) MOVED TO FY24 This site was planned for renewal in Q3 FY22 (based on original trend for failure), however as it currently stands is trending to last 2yrs beyond this if the side wear remains stable. Delay this to FY24 to achieve a 4yr cycle rather than the current 2yr cycle. > Created PCR 02/03/2021 as per AC Email sent on 18/02/2021 > Ammended Tech Scope to say TU > There was 2 x tech scope only difference was one had as M3 monitor and the other M6 Monitor - went with M3 Monitor as indicated in the Email AC sent 18/02/2021 > Moved Tech Scope from RR FY22 folder to TU FY24 Folder RE RAIL NOTIFICATION 2000063281 Removing sleepers from scope as condition of sleepers can wait renewal Construction teams commented on access constraits Will do sleepers at a future date as rail is every 5 years
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100145&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100145 | C21 BW WESTWOOD 48.627km - 49.386km. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.756 | TRACK KM | 808446 | Blackwater | WESTWOOD | WINDAH | 0.756 | KM | BW03ML48 | 0.627 | BW03ML49 | 0.386 | KM | 14 | 1125 | 1.512 | 0.756 | 48.627 | 49.386 | 2024-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 11.2 |  |  |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | RRIG |  | 20240630 | Parent Notification: 2000090738 - Sleepers Added rail to this scope and made it into a track upgrade.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097398&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000097398 | C21 TU BW WESTWOOD 54.221-55.110. | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.889 | TRACK KM | 950673 | Blackwater | WESTWOOD | WINDAH | 0.889 | KM | BW03ML54 | 0.221 | BW03ML55 | 0.1199 | KM | 17 | 436 | 1.836 | 0.879 | 54.221 | 55.11 | 2023-09-30 | DOWN | BOTH |  |  | 4.5 | 3.35 | 1 | 3.2 | 1 | 14.4 | 176 | 2022-03-31 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification completed | NWSC |  | 20240630 | Parent Notification RAIL NOTIFICATION - 2000058504 (54.221 - 54.630) SLEEPER NOTIFICATION 2000091655 (54.590 - 54.850) Post site walkout: Rail: 54.221 - 55.120 - 17 rails Sleepers: 54.590 - 54.850 <(>&<)> 55.075 - 55.110 - 436 sleepers SRC 176
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101837&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  | COAL | 002000101837 | C21 GA Saraji Loadout 68.108 - 68.227. | GA-18ML | CIVIL | TRACK UPGRADE |  | RENEWALS | 0.119 | TRACK KM | 175497 | Goonyella | SARAJI LOADOUT | SARAJI LOADOUT | 0.1189 | KM | GA18ML68 | 0.1079 | GA18ML68 | 0.227 | KM | 3 |  | 0.324 | 0.119 | 68.108 | 68.227 | 2023-06-30 | SINGLE | BOTH |  |  | 4 | 1.1 | 1 | 1.5 | 1 | 6 | 5724 |  |  | Track Upgrade | [5 empty] | Notification completed | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044392&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044392 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 2500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044007&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044007 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 3000000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | 01 OCT 2021 K ALEX ROHWEDER - INCREASE FIX ON FAIL (C16) FUNDING AT GA TO $2.75 MILLION FROM $2.5 MILLION. TO FRELECT THE FY21 AND FY22 FIX ON FAIL TREND.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044393&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044393 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 500000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044394&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044394 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | LUMPSUM | 500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094146&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094146 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ BE 9A | TO000948 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1370000 | Moura | BYELLEE | BE 9A | 0.0509 | KM | MA01ML13 | 0.924 | MA01ML13 | 0.8729 | KM |  |  |  |  | 13.924 |  | 2024-06-30 |  |  |  |  | 4 | 3.5 | 4 | 3.5 |  | 12.25 |  | 2022-03-31 |  | Turnout Renewals | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL BE9A
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073333&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000073333 | TURNOUTS ¦ CONSTRUCT ¦ UPGRADE ¦ 250/251 | TO001145 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 2748000 | Blackwater | CALLEMONDAH | CH250/251 STAGE4 | 0.032 | KM | BW12YR535 | 0.8359 | BW12YR535 | 0.804 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 |  |  | 0 |  | 100 |  | 2022-03-31 |  | Turnout Renewals | BESPOKE DESIGN | MEDIUM | LOW | HIGH | LOW | Notification in process | RRIG |  | 20240630 | * 01.03.2021 10:11:47 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Relates to PCR4745 * 22.03.2021 21:10:37 AUSQLD Lachlan Prescott (R881571) * Added $1.3m deferred from FY23 to new total $3.562m 03.04.2022 Alex Rohweder (R87234) FY24 CONSTRUCTION - CONTINUATION FROM PREVIOUS YEARS - STAGED CONSTRUCTION WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094147&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094147 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL MI ER1.2A | TO000310 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1559000 | Goonyella | MINDI MI | ER1.2A | 0.032 | KM | GA02ML120 | 0.003 | GA02ML120 | 0.035 | KM |  |  |  |  | 120.003 |  | 2024-06-30 |  |  |  |  | 3.5 | 4.8 |  | 4.8 |  | 16.8 |  | 2022-03-31 |  | Turnout Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | LOW | Notification completed | RRIG |  | 20240630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ER1.2A
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073334&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000073334 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ PD12A/B | TO000391 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1400000 | Goonyella | PEAK DOWNS | PD12A/B | 0.049 | KM | GA05PL45 | 0.891 | GA05PL45 | 0.8419 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 3.5 | 2.1 | 4 | 3.9 |  | 13.7 |  | 2022-03-31 |  | Turnout Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG | FY23 OUT | 20240630 | * 01.03.2021 10:11:47 AUSQLD Tracy Holmes (R870040) * See attachment for more details
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074738&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000074738 | TURNOUTS ¦ DESIGN ¦ EARLY DESIGN ¦ WA45A | TO000698 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 100000 | Blackwater | WARREN | 45A | 0.0359 | KM | BW04ML25 | 0.541 | BW04ML25 | 0.505 | KM |  |  |  |  | 24.536 | 24.5 | 2024-06-30 |  |  |  |  | 3.5 | 3.5 |  |  |  | 14.35 | 4881 | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20240630 | * 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) * Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) 22.03.2021 21:25:23 AUSQLD Lachlan Prescott (R881571) Placeholder for $200k of FY23 design for FY24 construction (FY24 program to be finetuned) William Schuh - Design of 45pts and 46pts with complex overhead reconfigurations 0130432022 Alex Rohweder PCR 4881 Design in FY24, starting from the remaining DD30 to IFC. FY24 Design, FY27 Construction completion TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ WR45A 11/01/2023 Alex Rohweder (R972340) Early Design, FY28 Construction, with FY25 design, FY24 Design budget adjusted to 50% off the total design budget = $ 100,000 out of $ 200 ,000.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094999&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094999 | TURNOUTS ¦ DESIGN ¦ EARLY DESIGN ¦ WR46A | TO000697 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 59500 | Blackwater | WARREN | 46A | 0.0379 | KM | BW04ML25 | 0.444 | BW04ML25 | 0.406 | KM |  |  |  |  | 25.444 |  | 2024-06-30 | [5 empty] | 3.5 |  |  |  | 14.35 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG |  | 20240630 | TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ WR46A Early Design FY24,Construction FY28 (may required pre-construction), Bundle with WA45A. Design budget adjusted to 50% off the total design budget = $ 59,500 out of $ 119,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. PCR 4881 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118304&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118304 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 259A | TO001127 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 48820 | Blackwater | CALLEMONDAH | CH 259A | 0.0359 | KM | BW07YR536 | 0.0519 | BW07YR536 | 0.016 | KM | [6 empty] | 2024-05-27 |  |  | POINTS & X 60KG/M 12 CS SNX EO |  | 4 | 3.5 | 4 |  |  | 15.4 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 30.09.2020 07:09:06 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044001 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118301&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118301 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 260A | TO001136 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 49160 | Blackwater | CALLEMONDAH | CH 260A | 0.035 | KM | BW10YR536 | 0.0919 | BW10YR536 | 0.057 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 3.5 | 4 |  |  | 15.4 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 30.09.2020 07:08:45 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044000 12/05/2022 Alex Rohweder (R872340) Asset condition and criticality reviewed. To best manage the asset reliability and interlocking renewal collaboration, defer DESIGN to FY28 and to have it constructed in FY30. Turnout asset can be sufficiently maintained via C16 and C10, confirmed with Terry Callaghan local track inspector. Monitor Through Road Rail condition in FY28, and if required, plan rail renewal in conjunction with turnout renewal in FY30 (with Rail asset management team). ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118431&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000118431 | TURNOUTS ¦ DESIGN ¦ IFC ¦ EC12A | TO000139 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 12100 | Newlands | EAGLEFIELD CK | EC12A | 0.0459 | KM | NL01ML201 | 0.909 | NL01ML201 | 0.9549 | KM | [6 empty] | 2024-05-27 |  |  | POINTS & X 60KG/M 12 CS SNX EO | OPTION 3 | 3.5 | 2 | 4 |  |  | 12.25 | 4882 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 28.02.2020 13:41:53 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:05:34 AUSQLD Lachlan Prescott (R881571) To be moved to FY25 pending PCR4882 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118305&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118305 | TURNOUTS ¦ DESIGN ¦ IFC ¦ EC7A | TO000141 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 12100 | Newlands | EAGLEFIELD CK | EC7A | 0.0459 | KM | NL01ML204 | 0.111 | NL01ML204 | 0.065 | KM | [6 empty] | 2022-06-30 |  |  | POINTS & X 60KG/M 12 CS SNX TG | OPTION 3 | 3.5 | 2 | 4 |  |  | 12.25 | 4882 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 28.02.2020 13:41:40 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:05:35 AUSQLD Lachlan Prescott (R881571) To be moved to FY25 pending PCR4882 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118196&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118196 | TURNOUTS ¦ DESIGN ¦ IFC ¦ MMER1.3A | TO000879 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 17940 | Blackwater | MT MILLER | MM ER1.3A | 0.024 | KM | BW20ML0 | 0.451 | BW20ML0 | 0.4269 | KM | [6 empty] | 2024-05-27 |  |  |  |  | 4 | 3.5 | 2 |  |  | 14.8 | 5289 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 28.02.2020 13:40:03 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:03:09 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 ALEX ROHWEDER (R872340) SWAP THE DESIGN SCOPE WITH MT. MILLER ER1.2A TO DESIGN IN FY23, AND TO CONSTRUCT IN FY25. REASON: ASSET CRITICALITY. PCR 5289 APPROVED. Alex Rohweder (R87234) Multi year Design notifications are created per FY. DESIGN - IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118300&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118300 | TURNOUTS ¦ DESIGN ¦ IFC¦ MMER2.3B | TO000861 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 59500 | Blackwater | MT MILLER | MM ER2.3B | 0.035 | KM | BW01ML541 | 0.635 | BW01ML541 | 0.67 | KM | [6 empty] | 2024-05-27 |  |  |  |  | 4 | 3.5 | 3 |  |  | 16.4 | 5289 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | 28.02.2020 13:40:16 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution 10.05.2021 11:03:10 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 ALEX ROHWEDER (R872340) SWAP THE DESIGN SCOPE WITH MT. MILLER ER2.3B TO DESIGN IN FY23, AND TO CONSTRUCT IN FY25. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. REASON: ASSET CRITICALITY. PCR 5289 APPROVED.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118438&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118438 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WA 7AB | TO000317 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 31880 | Goonyella | WAITARA | WA 7AB | 0.0459 | KM | GA02ML98 | 0.0369 | GA02ML98 | 0.083 | KM | [6 empty] | 2024-07-31 |  |  |  |  | 3 | 4.4 | 5 |  |  | 14.4 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240731 | 30.09.2020 07:07:41 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043323 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy) 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5668 Recommended change from PM notification/s due dates revised to • IFP due 1st December 2023 (FY24) • IFC due 31st July 2024 (FY25 Q1) Reason: : priority is Design team produce all IFCs for TO construction in FY24 (these are WIP) Note: WA 7AB <(>&<)> WA9A construction remains
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118408&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118408 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WA 9A | TO000368 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 83700 | Goonyella | WAITARA | WA 9A | 0.0369 | KM | GA02PL98 | 0.168 | GA02PL98 | 0.2049 | KM | [6 empty] | 2024-07-31 |  |  |  |  | 3 | 5 | 4 |  |  | 14.4 |  | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240731 | 30.09.2020 07:08:20 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043324 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) 27/07/2023 Alex Rohweder (R872340) Extend the IFC due date as per the planned construction dates. PCR - 5668 Recommended change from PM notification/s due dates revised to • IFP due 1st December 2023 (FY24) • IFC due 31st July 2024 (FY25 Q1) Reason: : priority is Design team produce all IFCs for TO construction in FY24 (these are WIP) Note: WA 7AB <(>&<)> WA9A construction remains
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118714&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000118714 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WO12A/B | TO000319 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 131400 | Goonyella | WANDOO | WO12A/B | 0.048 | KM | GA02ML86 | 0.058 | GA02ML86 | 0.1059 | KM | [6 empty] | 2024-05-27 |  |  |  |  | 4 | 5 | 4 |  |  | 19.2 |  | 2024-05-27 | 2023-06-30 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20240527 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 27/07/2023 Alex Rohweder (R872340) Extend the IFP and IFC due date as per the planned construction dates. PCR - 5670 Recommended change from PM - IFP due 30th Nov 2023 (FY24); - IFC due 27th May 2024 (FY24) Why: OHLE <(>&<)> Signalling IFPs not developed Signalling requesting additional information from the Asset Manager to progress the drawings Asset Mgr has confirmed IFC is due in FY24 (ie early due to construction complexity)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065623&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000065623 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BK ER1.2A | TO000214 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 83500 | Goonyella | BALOOK | BK ER1.2A | 0 | KM | GA01ML74 | 0.802 | GA01ML74 | 0.802 | KM | [6 empty] | 2024-02-27 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240430 | * 30.09.2020 07:10:35 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044005 TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ BK ER1.2A 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. RBM to SNX. FY24 Design budget adjusted to 50% off the total design budget = $83 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094136&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094136 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HD 12C/D | TO000207 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | HATFIELD | 12C/D | 0.049 | KM | GA01ML49 | 0.922 | GA01ML49 | 0.8729 | KM |  |  |  |  | 49.8 | 49.751 | 2025-02-27 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 3 | 5 |  |  |  | 16.8 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ HD 12C/D Alex Rohweder (R872340) 28.03.2024 PCR - 5877 Push out IFP deliverable from FY24 to FY25 and subsequently push out IFC <(>&<)> Construction dates. IFP to FY25, IFC to FY26 and Construct in FY27. Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with HD 12A/B and HD 11A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 28.03.2024 PCR - 5877 Push out IFP deliverable from FY24 to FY25 and subsequently push out IFC <(>&<)> Construction dates. IFP to FY25, IFC to FY26 and Construct in FY27.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123286&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000123286 | TURNOUTS ¦ DESIGN ¦ IFP ¦ PS 12A/B | TO000471 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | PRAGUELANDS | PS 12A/B | 0.05 | KM | GA02ML14 | 0.4769 | GA02ML14 | 0.527 | KM |  |  |  |  | 14.377 | 14.427 | 2024-02-27 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 3.5 | 5 | 4 |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ PS 12A/B 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8C/D FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123283&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000123283 | TURNOUTS ¦ DESIGN ¦ IFP ¦ PS 12C/D | TO000441 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | PRAGUELANDS | PS 12C/D | 0.049 | KM | GA01ML14 | 0.5779 | GA01ML14 | 0.529 | KM |  |  |  |  | 14.377 | 14.427 | 2024-02-27 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 3.5 | 5 | 4 |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ PS 12C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8C/D FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094137&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094137 | TURNOUTS ¦ DESIGN ¦ IFP ¦ PS 8A/B | TO000442 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | PRAGUELANDS | PS 8 A/B | 0.05 | KM | GA01ML14 | 0.3589 | GA01ML14 | 0.4089 | KM |  |  |  |  | 14.377 | 14.427 | 2024-02-27 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 3.5 | 5 | 4 |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ PS 8A/B 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8C/D FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103739&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103739 | TURNOUTS ¦ DESIGN ¦ IFP ¦ PS 8C/D | TO000470 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | PRAGUELANDS | PS 8C/D | 0.0459 | KM | GA02ML14 | 0.455 | GA02ML14 | 0.4089 | KM |  |  |  |  | 14.472 | 14.426 | 2024-02-27 |  |  |  |  | 3 | 5 | 4 |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240227 | 30.09.2020 07:10:35 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044005 TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ PS 8C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081422&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000081422 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WO12A/B | TO000319 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 131400 | Goonyella | WANDOO | WO12A/B | 0.048 | KM | GA02ML86 | 0.058 | GA02ML86 | 0.1059 | KM | [6 empty] | 2023-11-30 |  |  |  |  | 4 | 5 | 4 |  |  | 19.2 | 5670 | 2023-11-30 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20231130 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 27/07/2023 Alex Rohweder (R872340) Extend the IFP and IFC due date as per the planned construction dates. PCR - 5670 Recommended change from PM - IFP due 30th Nov 2023 (FY24); - IFC due 27th May 2024 (FY24) Why: OHLE <(>&<)> Signalling IFPs not developed Signalling requesting additional information from the Asset Manager to progress the drawings Asset Mgr has confirmed IFC is due in FY24 (ie early due to construction complexity) Note: WO 12A/B construction remains unchanged being FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044395&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044395 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 250000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044008&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044008 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 250000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044396&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044396 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 50000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044397&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000044397 | TURNOUTS ¦ SIG ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | SIG | REACTIVE WORKS | 1 | LUMPSUM | 50000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2022-03-31 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094334&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094334 | NL HBD DESIGN BRIABA 54.5 KM | ST008820-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41872 | Newlands | BRIABA |  | 0 | KM | NL01ML54 | 0.5 | NL01ML54 | 0.5 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 16 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094335&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094335 | NL HBD DESIGN COCKOOL 116.98 KM | ST008840-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41872 | Newlands | COCKOOL |  | 0 | KM | NL01ML116 | 0.9799 | NL01ML116 | 0.9799 | KM | [6 empty] | 2024-06-30 | [13 empty] | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094333&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094333 | MA HBD DESIGN DUMGREE 112.0 KM | ST005260-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41872 | Moura | DUMGREE |  | 0 | KM | MA01ML112 | 0 | MA01ML112 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 16 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104109&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104109 | T54-AP-GA-69.43 KM | ST009230-29 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41000 | Blackwater | T54-AP-GA |  | 0 | KM | BW08ML69 | 0.4299 | BW08ML69 | 0.4299 | KM |  |  |  |  | 69.43 | 69.43 | 2024-03-31 |  |  |  |  | 4 | 2 | 3 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Design HBD PHOENIX MDS Upgrade 69.54 Lilyvale
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104121&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104121 | T54-AP-GA-173.81 KM | ST005400-07 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41000 | Goonyella | T54-AP-GA |  | 0 | KM | GA01ML173 | 0.8169 | GA01ML173 | 0.8169 | KM |  |  |  |  | 173.81 | 173.81 | 2024-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Design of HBD HWD PHOENIX MDS Upgrade 173.81 km Wotonga
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104103&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104103 | T54-AP-NL-158.6 KM | ST008330-07 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41000 | Newlands | T54-AP-NL |  | 0 | KM | NL01ML158 | 0.5999 | NL01ML158 | 0.5999 | KM |  |  |  |  | 158.6 | 158.6 | 2023-12-30 |  |  |  |  | 4 | 2 | 3 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Design HBD PHOENIX MDS Upgrade at 158.6 km Leichardt Range
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104108&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104108 | T54-AP-NL-206.6 KM | ST008410-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 41000 | Newlands | T54-AP-NL |  | 0 | KM | NL01ML206 | 0.5999 | NL01ML206 | 0.5999 | KM |  |  |  |  | 206.6 | 206.6 | 2023-12-30 |  |  |  |  | 4 | 2 | 3 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Design HBD PHOENIX MDS Upgrade 206.6 km Eaglefield Creek
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075325&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000075325 | CL110 HBD DUARINGA - BLUFF | ST005230-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 794000 | Blackwater | DUARINGA | BLUFF | 0 | KM | BW03ML110 | 0.069 | BW03ML110 | 0.069 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 31.03.2021 08:43:10 AUSQLD Scott Andrews (R003573) * RENEW DUAL TRACK HBD AT DUARINGA - WALLAROO CL110
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043600&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043600 | Asset Protection HBD Renewal Marmor | ST005250-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 768000 | Blackwater | MARMOR |  | 0 | KM | BW01ML597 | 0.752 | BW01ML597 | 0.752 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 29.03.2021 19:27:11 AUSQLD Scott Andrews (R003573) * RENEW DUAL TRACK HBD AT MARMOR NC598
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075322&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000075322 | CL192 SAGITTARIUS HBD RENEWAL | ST005210-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 797000 | Blackwater | SAGITTARIUS |  | 0 | KM | BW03ML192 | 0.0109 | BW03ML192 | 0.0109 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 31.03.2021 08:15:39 AUSQLD Scott Andrews (R003573) * RENEW DUAL TRACK HBD AT MARMOR NC598 * 31.03.2021 08:22:59 AUSQLD Scott Andrews (R003573) * SITE IS SAGITTARIUS CL192 (NOT MARMOR)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075323&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000075323 | ASSET PROTECTION RENEWAL HBD UMOLO | ST002240-02 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | SITE | 794000 | Blackwater | UMOLO |  | 0 | KM | BW03ML152 | 0.171 | BW03ML152 | 0.171 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 | 2021-10-05 | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 31.03.2021 08:22:07 AUSQLD Scott Andrews (R003573) * RENEW DUAL TRACK HBD AT UMOLO CL152
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085755&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085755 | BW LX CCTV RENEWAL BLACKWATER | LX000661-13 | CONTROL SYSTEMS | ASSET PROTECTION | LX CCTV | DESIGN | 1 | SITE | 12000 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML189 | 0.6179 | BW03ML189 | 0.6179 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 | 3 | 3 | 1 | 12 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085753&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085753 | BW LX CCTV RENEWAL DINGO | LX000746-08 | CONTROL SYSTEMS | ASSET PROTECTION | LX CCTV | DESIGN | 1 | SITE | 12000 | Blackwater | DINGO |  | 0 | KM | BW03ML141 | 0.26 | BW03ML141 | 0.26 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 | 3 | 3 | 1 | 12 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085756&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085756 | MA LX CCTV RENEWAL GLADSTONE | LX000786-34 | CONTROL SYSTEMS | ASSET PROTECTION | LX CCTV | RENEWAL | 1 | SITE | 12000 | Moura | GLADSTONE |  | 0 | KM | NC02ML529 | 0.5659 | NC02ML529 | 0.5659 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 | 3 | 3 | 1 | 12 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085754&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000085754 | GA MAINLINE PAN CAM DESIGN | GA | CONTROL SYSTEMS | ASSET PROTECTION | MAINLINE PAN CAN | DESIGN | 1 | UNIT | 150000 | Goonyella | WANDOO |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 4 | 3 | 3 | 1 | 15 | 149 | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103931&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103931 | T54-AP-BW-30.5 KM Kalapa DN WSS Design | ST009570-29 | CONTROL SYSTEMS | ASSET PROTECTION | MAINLINE WEIGHER | DESIGN | 1 | SITE | 100000 | Blackwater | KALAPA WAYSIDE COND MONIT SITE |  | 0 | KM | BW03ML30 | 0.4799 | BW03ML30 | 0.4799 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | LOW | HIGH | Outstanding notification | RRIG |  | 20240630 | Renew Dn Road Mainline Weigher at Kalapa
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053167&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000053167 | NE RailBAM Kaili Renewal | ST008760-01 | CONTROL SYSTEMS | ASSET PROTECTION | RAILBAM | RENEWAL | 1 | UNIT | 370000 | Newlands | KAILI |  | 0 | KM | NL02CR8 | 0.5999 | NL02CR8 | 0.5999 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 | 3 | 3 | 1 | 12 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103938&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103938 | ASSET PROTECTION WEATHER STN 102.9 KM | ST009160 | CONTROL SYSTEMS | ASSET PROTECTION | WEATHER STATION | RENEWAL | 1 | SITE | 50000 | Blackwater | WEATHER STN 102.9 KM |  | 0 | KM | BW06ML102 | 0.9 | BW06ML102 | 0.9 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Renew Weather Station at 102.9 km Bauhinia Branch
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103940&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103940 | ASSET PROTECTION WEATHER STN 72.0 KM | ST006920 | CONTROL SYSTEMS | ASSET PROTECTION | WEATHER STATION | RENEWAL | 1 | SITE | 50000 | Blackwater | WEATHER STN 72.0 KM |  | 0 | KM | BW06ML72 | 0.1 | BW06ML72 | 0.1 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Renew RMS Weather Station at 72.0 km on Bauhania Branch
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103939&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103939 | ASSET PROTECTION WEATHER STN 86.0 KM | ST009150 | CONTROL SYSTEMS | ASSET PROTECTION | WEATHER STATION | RENEWAL | 1 | SITE | 50000 | Blackwater | WEATHER STN 86.0 KM |  | 0 | KM | BW06ML86 | 0 | BW06ML86 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Renew RMS Weather Station at 86.0 km on Bauhinia Branch
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094184&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094184 | BW WEIGHER DESIGN BOORGOON | ST002460-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 68810 | Blackwater | BOORGOON | BOORGOON | 0 | KM | BW23ML2 | 0.23 | BW23ML2 | 0.23 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 16 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093737&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093737 | NL WEIGHER DESIGN MCNAUGHTON | NL | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 40000 | Newlands | MCNAUGHTON | MCNAUGHTON | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094185&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094185 | MA WEIGHBRIDGE DESIGN MOURA MINE | ST003790-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | DESIGN | 1 | SITE | 68810 | Moura | MOURA MINE | MOURA MINE | 0 | KM | MA04ML3 | 0.7079 | MA04ML3 | 0.7079 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 16 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093738&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093738 | MA WEIGHBRIDGE RENEWAL BOUNDARY HILL | ST007810-07 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 1305510 | Moura | BOUNDARY HILL | BOUNDARY HILL | 0 | KM | MA03ML2 | 0.7299 | MA03ML2 | 0.7299 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093764&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093764 | NL WEIGHBRIDGE RENEWAL CALLIDE | ST003490-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 1300909 | Moura | CALLIDE | CALLIDE | 0 | KM | MA07ML14 | 0.0529 | MA07ML14 | 0.0529 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093739&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093739 | GA WEIGHBRIDGE RENEWAL ISAAC PLAINS | ST007180-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE | RENEWAL | 1 | SITE | 1022222 | Goonyella | ISAAC PLAINS | ISAAC PLAINS | 0 | KM | GA11ML4 | 0.256 | GA11ML4 | 0.256 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102216&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | FUTURE SCOPE | COAL | 002000102216 | CSI CER Design Callemondah | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | PLANNING | 1 | SITE | 50000 | Blackwater | CALLEMONDAH SER | CALLEMONDAH SER | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078675&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000078675 | CSI Equipment Room Renewal Sandhurst | ST006390 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Blackwater | SANDHURST MWR | SANDHURST MWR | 0 | KM | BW61CR0 | 0 | BW61CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG |  | 20240630 | * 10.06.2021 16:27:10 AUSQLD Peter Rayner (R003851) * Replace Equipment Room
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078707&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000078707 | CSI Dehydrator Design NL | ST005350-29 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | DESIGN | 1 | SITE | 5000 | Newlands | BRIABA |  | 0 | KM | NL09CR0 | 0 | NL09CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 18:20:24 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site Replace all Dehydrators at this site with a new Puregas unit
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078710&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078710 | CSI Dehydrator Design BW | ST005950-17 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | DESIGN | 1 | SITE | 5000 | Blackwater | CAPELLA |  | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | * 10.06.2021 18:21:22 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site Contact: Alex Gainsford 0488 013 524 Dehydrator Renewal - Maintenance team to identify all sites that need renewal In the Blackwater System WBSE: iv.00822.e.h.bw.06.co.et
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078708&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000078708 | CSI Dehydrator Design GA | ST005900-35 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | DESIGN | 1 | SITE | 5000 | Goonyella | SARINA MWR | SARINA MWR | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 18:20:43 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085402&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000085402 | CSI Generator Renewal | ST008920 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 120000 | Goonyella | BRAESIDE MI EAST |  | 0 | KM | GA01ML104 | 0.2999 | GA01ML104 | 0.2999 | KM |  |  |  |  | 104.322 |  | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085401&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085401 | CSI Generator Renewal | ST005350-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 120000 | Newlands | BRIABA MW |  | 0 | KM | NL01ML58 | 0 | NL01ML58 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078696&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078696 | CSI Generator Renewal | ST005280-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 120000 | Blackwater | CROCKER PEAK |  | 0 | KM | BW03ML214 | 0 | BW03ML214 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 17:27:45 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085409&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000085409 | CSI Generator Renewal | ST005610 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 140000 | Moura | SPECIMEN HILL | SPECIMEN HILL | 0 | KM | MA15CR0 | 0 | MA15CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100576&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000100576 | CSI Optical Fibre Design | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | DESIGN | 1 | LUMPSUM | 50000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100577&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000100577 | CSI Optical Fibre Design | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | DESIGN | 1 | LUMPSUM | 50000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086509&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000086509 | CSI OF Renewal | ST004580-17 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2000 | METERS | 188620 | Goonyella | BROADLEA SER |  | 2.0859 | KM | GA01ML156 | 0.264 | GA01ML154 | 0.17 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086533&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000086533 | CSI OF Renewal | ST007210-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3000 | METERS | 282930 | Goonyella | CARBOROUGH DOWNS |  | 159.2769 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086532&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000086532 | CSI OF Renewal | ST007210-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3800 | METERS | 358378 | Goonyella | CARBOROUGH DOWNS | BROADLEA MI0 | 3.777 | KM | GA01ML161 | 0.777 | GA01ML158 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078616&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078616 | CSI OF Renewal | ST004210-21 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3034 | METERS | 303400 | Blackwater | GOGANGO CER TO GRANTLEIGH FSS |  | 5.581 | KM | BW03ML84 | 0.65 | BW03ML89 | 0.5 | KM |  |  |  |  | 61.22 | 63.804 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 15:23:10 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046578&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046578 | CSI OF Renewal | ST004740-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4600 | METERS | 433826 | Goonyella | GON-SER TO RIV-SER O/F CABLE |  | 4.6699 | KM | GA13ML195 | 0.4 | GA13ML200 | 0.07 | KM |  |  |  |  | 195.4 | 200.07 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086530&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000086530 | CSI OF Renewal | ST007220-17 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3600 | METERS | 339516 | Goonyella | ISAAC PLAINS SER | MALLAWA SER | 3.567 | KM | GA01ML171 | 0.9 | GA01ML168 | 0.32 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086531&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000086531 | CSI OF Renewal | ST004800-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6700 | METERS | 631877 | Goonyella | MALLAWA SER | CARBOROUGH DOWNS TSC | 6.5439 | KM | GA01ML168 | 0.32 | GA01ML161 | 0.777 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046839&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046839 | CSI OF Renewal | ST007050-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6300 | METERS | 594153 | Goonyella | MLJ-SER TO REM-TSC OF CABLE |  | 2.89 | KM | GA03ML16 | 0.5709 | GA03ML19 | 0.467 | KM |  |  |  |  | 13.23 | 19.46 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046596&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046596 | CSI OF Renewal | ST006770-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 94310 | Goonyella | REM-AT0 TO WCH-SER O/F CABLE |  | 1.03 | KM | GA03ML30 | 0.02 | GA03ML31 | 0.048 | KM |  |  |  |  | 30.02 | 31.05 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046595&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046595 | CSI OF Renewal | ST005040-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6400 | METERS | 603584 | Goonyella | REM-SER TO REM-AT0 O/F CABLE |  | 6.4 | KM | GA03ML23 | 0.6199 | GA03ML30 | 0.02 | KM |  |  |  |  | 23.62 | 30.02 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046840&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046840 | CSI OF Renewal | ST000720-26 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4600 | METERS | 433826 | Goonyella | REM-TSC TO REM-SER OF CABLE |  | 4.16 | KM | GA03ML19 | 0.467 | GA03ML23 | 0.6199 | KM |  |  |  |  | 19.46 | 23.62 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078609&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078609 | CSI OF Renewal | ST007790-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6659 | METERS | 532720 | Blackwater | SPRING CK AT TO WESTWOOD SER |  | 7.312 | KM | BW03ML40 | 0.4249 | BW03ML47 | 0.7359 | KM |  |  |  |  | 40.342 | 46.694 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:27:05 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078610&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078610 | CSI OF Renewal | ST007750-47 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6333 | METERS | 506640 | Blackwater | WESTWOOD TSC TO WINDAH AM |  | 7.0259 | KM | BW03ML48 | 0.069 | BW03ML55 | 0.0899 | KM |  |  |  |  | 49.176 | 55.093 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:27:48 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078612&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078612 | CSI OF Renewal | ST002140-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4571 | METERS | 365680 | Blackwater | WINDAH AM | GOGANGO CER | 0.51 | KM | BW03ML55 | 0.0899 | BW03ML55 | 0.5999 | KM |  |  |  |  | 57.655 | 61.22 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:29:14 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078611&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078611 | CSI OF Renewal | ST002140-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1270 | METERS | 101600 | Blackwater | WINDAH AT TO WINDAH SER |  | 0.51 | KM | BW03ML55 | 0.0899 | BW03ML55 | 0.5999 | KM |  |  |  |  | 55.093 | 56.194 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:28:31 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085522&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085522 | CSI OF Renewal | ST005120-19 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2200 | METERS | 207482 | Goonyella | WOTONGA SR1 | ISAAC PLAINS SER | 2.387 | KM | GA01ML174 | 0.08 | GA01ML171 | 0.6999 | KM |  |  |  |  | 174.08 | 171.7 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046581&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000046581 | CSI OF Renewal | ST000770-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6000 | METERS | 565860 | Goonyella | WOT-SR2 TO WOT-AT0 O/F CABLE |  | 9.65 | KM | GA01ML175 | 0.197 | GA01ML184 | 0.8469 | KM |  |  |  |  | 175.19 | 184.84 | 2024-06-30 | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078608&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000078608 | CSI OF Renewal | ST004480-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1731 | METERS | 138480 | Blackwater | WYCARBAH SER TO SPRING CK AT |  | 4.307 | KM | BW03ML36 | 0.115 | BW03ML40 | 0.4249 | KM |  |  |  |  | 38.879 | 40.342 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  | 2021-10-05 | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 10.06.2021 14:26:17 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108607&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000108607 | CSI Optical Fibre Renewal | ST007210-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1500 | METRES | 141465 | Goonyella | CARBOROUGH DOWNS JUNCTION CER | CARBOROUGH DOWNS TSC | 3.777 | KM | GA01ML161 | 0.777 | GA01ML158 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | [8 empty] | Telecommunication Asset | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108609&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000108609 | CSI Optical Fibre Renewal | ST007220-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3200 | METRES | 301792 | Goonyella | ISAAC PLAINS JUNCTION SER | ISAAC PLAINS BALLOON CER | 169.4 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | [8 empty] | Telecommunication Asset | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085341&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085341 | CSI Radome Renewal | MA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | LUMPSUM | 54000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | RADOME Cover Renewal - Maintenance team to nominate a replacement location - In the Moura System Contact: Alex Gainsford 0488 013 524 WBSE: IV.00822.e.h.ma.02.co.et
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085345&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085345 | CSI Radome Renewal FY24 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | LUMPSUM | 54000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20240630 | RADOME Cover Renewal - Maintenance team to nominate a replacement location - In the Blackwater System Contact: Alex Gainsford 0488 013 524 WBSE: IV.00822.e.h.bw.09.co.et
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085343&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085343 | CSI Radome Renewal FY24 | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | LUMPSUM | 54000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085344&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000085344 | CSI Radome Renewal FY24 | ST009550-23 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | LUMPSUM | 54000 | Goonyella | MORANBAH MWR | MORANBAH MWR | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078676&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078676 | CSI Structure Design | ST005350-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | DESIGN | 1 | SITE | 15000 | Newlands | BRIABA |  | 0 | KM | NL09CR0 | 0 | NL09CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:28:16 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078677&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078677 | CSI Structure Design | ST005920-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | DESIGN | 1 | SITE | 15000 | Goonyella | GOONYELLA |  | 0 | KM | GA01ML198 | 0.23 | GA01ML198 | 0.23 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:29:22 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078681&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078681 | CSI Structure Renewal | ST006380-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 30000 | Goonyella | BLAIR ATHOL |  | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:33:43 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078682&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078682 | CSI Structure Renewal | ST005950-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 30000 | Blackwater | CAPELLA |  | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:34:49 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078679&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078679 | CSI Structure Renewal | ST005280-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 30000 | Blackwater | CROCKER PEAK |  | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:31:33 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078680&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078680 | CSI Structure Renewal | ST005510-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 30000 | Blackwater | GREGORY |  | 0 | KM | BW08ML62 | 0.2469 | BW08ML62 | 0.2469 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:32:38 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078678&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078678 | CSI Structure Renewal | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 30000 | Blackwater | WALLAROO |  | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:30:27 AUSQLD Peter Rayner (R003851) * Renew Telecommunications Structure
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103934&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103934 | Data Comms Appliance DNA Mackay | ST005810-65 | CONTROL SYSTEMS | DATA COMMS | APPLIANCE DNA | RENEWAL | 1 | UNIT | 150000 | Goonyella | MACKAY |  | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | RRIG |  | 20240630 | Renew DNA Applicance Mackay
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103933&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103933 | Data Comms Appliance DNA Rocky 2 | ST005490-KJ | CONTROL SYSTEMS | DATA COMMS | APPLIANCE DNA | RENEWAL | 1 | UNIT | 150000 | Blackwater | ROCKHAMPTON |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | RRIG |  | 20240630 | Renew DNA Appliance Rocky 2
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103932&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000103932 | Data Comms Applicance DNA Rocky 1 | ST005490-KI | CONTROL SYSTEMS | DATA COMMS | APPLIANCE DNA | RENEWAL | 1 | UNIT | 150000 | Blackwater | ROCKHAMPTON |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | RRIG |  | 20240630 | Renew Rocky DNA Appliance 1
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085682&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085682 | Data Network Renewal BW | BW | CONTROL SYSTEMS | DATA COMMS | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 700000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | HIGH | HIGH | HIGH | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085661&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085661 | Data Network Renewal GA | GA | CONTROL SYSTEMS | DATA COMMS | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 850000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | HIGH | HIGH | HIGH | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085701&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085701 | Data Network Renewal MA | MA | CONTROL SYSTEMS | DATA COMMS | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 50000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | HIGH | HIGH | HIGH | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085684&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085684 | Data Network Renewal NL | NL | CONTROL SYSTEMS | DATA COMMS | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | HIGH | HIGH | HIGH | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074215&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000074215 | SIG_Interlocking Renewal - CH Stg1E_Des | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN | 1 | UNIT | 1268395 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 16.03.2021 17:25:49 AUSQLD Robert Love (R111379) * Complete the design phase of Callemondah Stage 1E - Commissioning the final cabling to GE OC West
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074216&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000074216 | SIG_Interlocking Renewal - CH Stg1F_Des | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN | 1 | UNIT | 1721501 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 16.03.2021 17:30:10 AUSQLD Robert Love (R111379) * Complete the design phase of Callemondah Stage 1F - commission the new hut GE OC East.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065500&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000065500 | SIG_Interlocking Renewal - CH Stg2A_Des | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN & ORDER | 1 | UNIT | 3800000 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 28.09.2020 10:38:28 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 2) * 16.03.2021 18:00:57 AUSQLD Robert Love (R111379) * Completion of second (2 of 3) phase of design and principal testing of the Callemondah Interlocking data, as per Callemondah Strategy Stage 2A. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074214&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000074214 | SIG_Interlocking Renewal - CH Stg1F_Pln | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | PLANNING | 1 | UNIT | 112160 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | RRIG | FY23 IN | 20240630 | * 16.03.2021 17:13:54 AUSQLD Robert Love (R111379) * Complete the planning phase for Callemondah Stage 1F - Commissioning of GE OC East.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065498&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000065498 | SIG_Interlocking Renewal - CH Stg1D_Com | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 1268395 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 28.09.2020 10:37:04 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 1D)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085111&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085111 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 1 | UNIT | 17500 | Newlands | ABBOT POINT | EAGLEFIELD CREEK | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace existing Newlands System Maintenance PC with Aurizon IT PC. PC to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PC to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085112&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085112 | SIG_Diagnostic_Computer_NL_Briaba_Com | ST002730-19 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 1 | UNIT | 17500 | Newlands | BRIABA | BRIABA | 0 | KM | NL01ML57 | 0.8 | NL01ML57 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace existing Briaba (NL) Maintenance PC with Aurizon IT PC. PC to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085119&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085119 | SIG_Diagnostic Computer_MA_Com | MA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 24000 | Moura | GLADSTONE | MOURA MINE | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace 2 existing Moura System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085116&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085116 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 81400 | Goonyella | HAY POINT | NORTH GOONYELLA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085117&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085117 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 9 | UNIT | 180300 | Blackwater | MOUNTLARCOM | GREGORY | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace 9 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065472&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000065472 | SIG_Interlocking Renewal - WO_Des | ST004050-02 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN | 1 | STATION | 1358441 | Goonyella | WANDOO | WANDOO | 0 | KM | GA01ML85 | 0.917 | GA01ML85 | 0.917 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 | 5709 | 2023-09-01 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20250630 | * 28.09.2020 10:18:53 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105159&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105159 | SIG_Interlocking Renewal_BW_ME_Pln | ST004310-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | SITE | 59000 | Blackwater | MIDGEE | MIDGEE | 0 | KM | BW01ML624 | 0.5899 | BW01ML624 | 0.5899 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | Replace Midgee Interlocking
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065474&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000065474 | SIG_InterlockingRenewal_GA_Braeside_Pln | ST004540-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 78960 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA01ML107 | 0.6949 | GA01ML107 | 0.6949 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH |  | MEDIUM | MEDIUM | Outstanding notification | RRIG | FY23 IN | 20240630 | * 28.09.2020 10:20:04 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060293&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060293 | SIG_Replace FOP signal_BW_BL16_Com | ST000600-D1 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | BAJOOL | BAJOOL | 0 | KM | BW01ML603 | 0.8 | BW01ML603 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 2 |  | 2 |  | 9 |  | 2022-03-31 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | MEDIUM | HIGH | MEDIUM | HIGH | Outstanding notification | RRIG INIF |  | 20240630 | * 23.06.2020 12:56:11 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094288&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094288 | SIG_Interlocking Renewal - MA_AE_Des | ST003290-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1014547 | Moura | ANNANDALE | ANNANDALE | 0 | KM | MA01ML0 | 0.1 | MA01ML0 | 0.1 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20240630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares. This is to get the circuits completed. Data design is to be started but to be completed in FY25 which may cause revisions of circuits to match data.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085455&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000085455 | C58-LX-GA-BLACKRIDGE-km | LX000663 | CONTROL SYSTEMS | LEVEL CROSSINGS | HOUSING REPLACEMENT | DESIGN | 1 | SITE | 58000 | Goonyella | BLACKRIDGE | BLACKRIDGE | 0 | KM | GA05ML80 | 0.68 | GA05ML80 | 0.68 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4.5 | 3 | 2 | 3 | 1 | 13.5 |  | 2022-03-31 |  | Other Control Sys Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | RRIG |  | 20240630 | Design the replacement of the 4 location cases, defunct power supplies and defunct track circuits at Ken Logan Rd Level Crossing with a standard LX hut. Change track circuits to axlecounters. Use a standard power setup.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085446&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000085446 | SIG_Points Impr_M23A Contact Rem_GA_Des | GA | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | DESIGN | 13 | UNIT | 195000 | Goonyella | SARAJI | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Design for the removal ofthe contactor from the following (13) M23A machines: Saraji SI12A Pts, SI12B Pts, SI7A Pts, SI7B Pts, SI9A Pts; Dysart DT12A Pts, DT12B Pts, DT7A Pts; Norwich Park NP8A PTs. This is to create spares of unsupported contactor relays and renew old machines in the field.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060079&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060079 | Replace M23A Mark1 point machines | TO000230-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML142 | 0.752 | GA01ML142 | 0.752 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 23.06.2020 12:22:23 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060077&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060077 | Replace M23A Mark1 point machines | TO000259-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML142 | 0.7029 | GA01ML142 | 0.7029 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 3 |  | 3 |  | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 23.06.2020 12:22:03 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060078&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060078 | Replace M23A Mark1 point machines | TO000464-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA02ML142 | 0.802 | GA02ML142 | 0.802 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 3 |  | 3 |  | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 23.06.2020 12:22:14 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060103&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060103 | Replace M23A Mark1 point machines | TO000235-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA01ML195 | 0.1529 | GA01ML195 | 0.1529 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630 | * 23.06.2020 12:26:07 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060105&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060105 | Replace M23A Mark1 point machines | TO000452-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA01ML195 | 0.4169 | GA01ML195 | 0.4169 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630 | * 23.06.2020 12:26:27 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060104&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060104 | Replace M23A point machines | TO000235-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA01ML195 | 0.1529 | GA01ML195 | 0.1529 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630 | * 23.06.2020 12:26:17 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060106&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060106 | Replace M23A point machines | TO000452-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69599 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA01ML195 | 0.4169 | GA01ML195 | 0.4169 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630 | * 23.06.2020 12:26:35 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060115&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060115 | SIG_Replace M23A_GA_IN12A_Com | TO000361-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69566 | Goonyella | INGSDON | INGSDON | 0 | KM | GA03ML13 | 0.2369 | GA03ML13 | 0.2369 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 23.06.2020 12:27:59 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060146&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000060146 | SIG_Replace M23A_GA_MA8A_Com | TO000234-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 69566 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML168 | 0.1019 | GA01ML168 | 0.1019 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 23.06.2020 12:33:15 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129664&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | REACTIVE RENEWALS | COAL | 002000129664 | SIG_Power Res_DSE509 Replace_Bidgerley | ST005700-03 | CONTROL SYSTEMS | POWER RESILIENCE | ALT & CONT PANEL & UPS | RENEWAL | 1 | UNIT | 70000 | Goonyella | BIDGERLEY |  | 0 | KM | GA06ML8 | 0.008 | GA06ML8 | 0.008 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  |  |  | Power Resilience | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Replace the DSE509 genset controller at Bidgerley with a like for like board solution. Board will be used at other DSE509 sites to replace the board at minimum cost. This is for the design and commissioning of the replacement within one year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129618&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | REACTIVE RENEWALS | COAL | 002000129618 | SIG_Power Res_DSE509 Replace_Millennium | ST007050-02 | CONTROL SYSTEMS | POWER RESILIENCE | ALT & CONT PANEL & UPS | RENEWAL | 1 | UNIT | 70000 | Goonyella | BIDGERLEY | MILLENNIUM | 0 | KM | GA03ML16 | 0.5699 | GA03ML16 | 0.5699 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  |  |  | Power Resilience | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Replace the DSE509 genset controller at Millennium with a like for like board solution. Board will be used at other DSE509 sites to replace the board at minimum cost. This is for the design and commissioning of the replacement within one year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129619&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | REACTIVE RENEWALS | COAL | 002000129619 | SIG_Power Res_DSE509 Replace_Stowe | ST003860-02 | CONTROL SYSTEMS | POWER RESILIENCE | ALT & CONT PANEL & UPS | RENEWAL | 1 | UNIT | 70000 | Moura | STOWE |  | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  |  |  | Power Resilience | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Replace the DSE509 genset controller at Stowe with a like for like board solution. Board will be used at other DSE509 sites to replace the board at minimum cost. This is for the design and commissioning of the replacement within one year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065517&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000065517 | SIG_Power Renewal_SI Replace - AL_Com | ST008620-17 | CONTROL SYSTEMS | POWER RESILIENCE | SI REPLACEMENT | RENEWAL | 1 | STATION | 90000 | Newlands | ALMOOLA |  | 0 | KM | NL01ML71 | 0.921 | NL01ML71 | 0.921 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Power Resilience | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | * 28.09.2020 10:53:30 AUSQLD Peter Rayner (R003851) * Replace old SI unit with new Eltec inverter. Update configuration to improve reliability.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065511&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000065511 | SIG_Power Renewal_SI Replace - BE_Com | ST002690-18 | CONTROL SYSTEMS | POWER RESILIENCE | SI REPLACEMENT | RENEWAL | 1 | STATION | 90000 | Newlands | BINBEE |  | 0 | KM | NL01ML45 | 0.9549 | NL01ML45 | 0.9549 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Power Resilience | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 28.09.2020 10:49:48 AUSQLD Peter Rayner (R003851) * Replace old SI unit with SI from Inventory. Update configuration to improve reliability. * 16.04.2021 16:48:00 AUSQLD Robert Love (R111379) * Replace old SI unit with new Eltec inverter. This will leave 3 SI units for spares for existing installations. *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065514&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000065514 | SIG_Power Renewal_SI Replace - BA_Com | ST002730-20 | CONTROL SYSTEMS | POWER RESILIENCE | SI REPLACEMENT | RENEWAL | 1 | STATION | 90000 | Newlands | BRIABA |  | 0 | KM | NL01ML57 | 0.8 | NL01ML57 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Power Resilience | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | * 28.09.2020 10:51:36 AUSQLD Peter Rayner (R003851) * Replace old SI unit with new Eltec inverter. Update configuration to improve reliability.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130889&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000130889 | SIG_Power Res_GA_Batteries FY24_Ren | GA | CONTROL SYSTEMS | POWER RESILIENCE | SIGNALLING BATTERY BANK | RENEWAL | 6 | SITE | 70000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 4 |  | 4 |  | 20 |  |  |  | Other Control Sys Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Funding to replace the 6 battery banks. Sites chosen by Maintenance are Riverside (Recycle Yard Rd LX 12V), Blair Athol (SER 24V), Moranbah (SER2 48V INV), 2x Dal Bay (SER1 48V INV, SER2 48V INV), Hay Point (SER 48V INV).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133923&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000133923 | Sig_Power Res_NL_Batteries FY24_Ren | NL | CONTROL SYSTEMS | POWER RESILIENCE | SIGNALLING BATTERY BANK | RENEWAL | 3 | SITE | 10000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 4 |  | 4 |  | 20 |  |  |  | Other Control Sys Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20240630 | Funding to replace the 3 battery banks. Sites chosen by Maintenance are Durraburra (Smith St LX), 2x Birralee Lax Rd LX (12V R, 12V L).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129785&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000129785 | T29-PR-BW-Sig Battery Bank | BW | CONTROL SYSTEMS | POWER RESILIENCE | SIGNALLING BATTERY BANK | RENEWAL | 2 | UNIT | 25000 | Blackwater | BW SYSTEM |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Power Resilience Minor | [5 empty] | Outstanding notification | NWSC |  | 00000000 | Replace Faulty Signalling Battery Banks
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043733&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000043733 | SIG_Train Detection_BW_Warren_CSEE_Des | ST005190-08 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 1 | STATION | 2395224 | Blackwater | WARREN | WARREN | 0 | KM | BW03ML25 | 0.4749 | BW03ML25 | 0.4749 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 4 | 4 | 4 | 1 | 18 |  | 2021-03-31 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | 30.08.2022: Rob Love - Rescheduled due to resources and re-estimated based on better unit rating. 19.09.2022 Delayed until FY26 commissioning. CSEE Tracks and any other tracks in the station are to be replaced with axlecounters. Thales axlecounters is the expected technology. It should not be connected to the ACE in adjacent stations in order to limit the number of stations requiring updating in one commissioning. There are 3 DEDs near Warren that are to be included in the scope. Tracks to Kabra are to be included in the design. All spares of CSEE track components are to go into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104707&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104707 | SIG_Train Detection_BW_Warren_CSEE_Pln | ST005190-08 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | PLANNING | 1 | SITE | 230000 | Blackwater | WARREN | WARREN | 0 | KM | BW03ML25 | 0.4749 | BW03ML25 | 0.4749 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 4 | 4 | 4 | 1 | 18 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | CSEE Tracks and any other tracks in the station are to be replaced with axlecounters. Thales axlecounters is the expected technology. It should not be connected to the ACE in adjacent stations in order to limit the number of stations requiring updating in one commissioning. There are 3 DEDs near Warren that are to be included in the scope. Tracks to Kabra are to be included in the design. All spares of CSEE track components are to go into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065524&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000065524 | SIG_Train Detection_GA_IsaacPlainsML_Com | ST007220 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLE COUNTER | RENEWAL | 1 | SITE | 1406605 | Goonyella | ISAAC PLAINS | ISAAC PLAINS | 0 | KM | GA01ML171 | 0.9 | GA01ML171 | 0.9 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | HIGH | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20240630 | * 28.09.2020 10:57:58 AUSQLD Peter Rayner (R003851) * Replace all TCs with FAdC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103817&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103817 | SIG_Train Detection_GA_Mallawa_ML_Des | ST001210 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 1375000 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML167 | 0.92 | GA01ML167 | 0.92 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20240630 | Replace all track circuits (primarily 26 defunct ML tracks) with 25 axlecounter tracks. Axlecounter is to be Frauschser.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103818&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103818 | SIG_Train Detection_GA_PeakDowns_ML_Des | ST000940 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 200000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.9529 | GA03ML43 | 0.9529 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20240630 | Replace 7 ML track circuits in the balloon loop (freq E,F,G,H) with 2 Frauscher or Thales tracks. Preference is for Frauscher but there is a Thales axlecounter used for a semi-attached level crossing. This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103865&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103865 | SIG_Train Detection_GA_Millennium_ML_Pln | ST007030 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 94866 | Goonyella | MILLENNIUM JUNCTION | MILLENNIUM JUNCTION | 0 | KM | GA03ML16 | 0.7229 | GA03ML16 | 0.7229 | KM |  |  |  |  | 16.723 | 16.723 | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  | 2023-09-01 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Replace all track circuits (primarily defunct 13 ML tracks and 1 AzS350U axlecounter track around part of the loop) with 16 new axlecounter tracks. New axlecounters are to be Frauschser. The axlecounter block to Ingsdon is to remain.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103977&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103977 | SIG_Train Detection_GA_Saraji_ML_Pln | ST000930 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 66000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML64 | 0.755 | GA03ML64 | 0.755 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Replace 10 ML track circuits in the balloon loop (freq E,F,G,H) with 3 Frauscher. This interlocking is relay based and hence the resetting of the 3 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085418&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000085418 | SIG_Train Detection_MA_Dumgree_S600_Pln | ST003300-02 | CONTROL SYSTEMS | TRAIN DETECTION | S600 AC | PLANNING | 1 | UNIT | 50000 | Moura | DUMGREE | ANNANDALE | 0 | KM | MA01ML109 | 0.7269 | MA01ML109 | 0.7269 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Plan the replacement of the Dumgree-Anandale Siemens AzS600 axlecounter block with the standard axlecounter used for new works on the Moura System.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085417&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000085417 | SIG_Train Detection_MA_MtRainbowS600_Pln | ST003610-02 | CONTROL SYSTEMS | TRAIN DETECTION | S600 AC | PLANNING | 1 | UNIT | 114259 | Moura | MOUNT RAINBOW | DUMGREE | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | Plan for the replacement of the Siemens S600 axlecounter from Mount Rainbow to Dumgree with the axlecounter used for new works on the Moura System.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091497&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000091497 | CS Transmission DMR Planning | BW | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | PLANNING | 1 | LINK | 80000 | Blackwater | ALL |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078683&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078683 | CS Transmission Renewal | ST005580-22 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 150000 | Moura | MAURICE HILL/GOLDING |  | 0 | KM | NC07CR0 | 0 | NC07CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:35:55 AUSQLD Peter Rayner (R003851) * Renew DMR Link
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078684&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078684 | CS Transmission Renewal | ST005580-41 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 150000 | Moura | MAURICE HILL/GRAHAM |  | 0 | KM | NC07CR0 | 0 | NC07CR0 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:37:00 AUSQLD Peter Rayner (R003851) * Renew DMR Link
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078637&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078637 | MA Belldeen-Moura HBD Site renew DC PS | ST005270-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Moura | BELLDEEN-MOURA HBD |  | 0 | KM | MA01ML160 | 0 | MA01ML160 | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:45:41 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078648&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078648 | CS Transmission Renewal | ST001730-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | COPPABELLA PSC 145.4KM |  | 0 | KM | GA01ML145 | 0.381 | GA01ML145 | 0.381 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:57:35 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078661&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078661 | CS Transmission Renewal | ST007660-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | COPPABELLA SR4 |  | 0 | KM | GA03ML3 | 0.795 | GA03ML3 | 0.795 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:11:52 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078643&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078643 | CS Transmission Renewal | ST007600-71 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | DALRYMPLE BAY FS |  | 0 | KM | GA01BA1 | 0.6899 | GA01BA1 | 0.6899 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:52:08 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085175&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085175 | CS Power Supply Renewal | ST008130-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Blackwater | EDUNGALBA ATS |  | 0 | KM | BW03ML88 | 0.902 | BW03ML88 | 0.902 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085174&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085174 | CS Power Supply Renewal | ST007760-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Blackwater | EDUNGALBA TSC |  | 0 | KM | BW03ML80 | 0.08 | BW03ML80 | 0.08 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078638&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078638 | CS Transmission Renewal | ST003660-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Moura | FRY |  | 0 | KM | MA01ML73 | 0.0509 | MA01ML73 | 0.0509 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:46:43 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046735&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000046735 | Tele Pwr Supply Renewal Graham SER | ST003710-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 42000 | Moura | GRAHAM SER | GRAHAM SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 28.59 | 28.59 | 2024-06-30 | ALL |  |  |  | 4 | 1.3 |  | 1.3 |  | 5.2 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078649&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078649 | CS Transmission Renewal | ST007640-48 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | GRASSTREE TSC |  | 0 | KM | GA01ML9 | 0.5999 | GA01ML9 | 0.5999 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:58:41 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078659&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078659 | CS Transmission Renewal | ST001260-11 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | INGSDON ATS 11.7KM |  | 0 | KM | GA03ML11 | 0.7399 | GA03ML11 | 0.7399 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:09:41 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078660&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078660 | CS Transmission Renewal | ST008030-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | INGSDON PSC 13.2KM |  | 0 | KM | GA03ML13 | 0.23 | GA03ML13 | 0.23 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:10:46 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078641&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078641 | CS Transmission Renewal | ST007220-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | ISAAC PLAINS JUNCTION SER |  | 0 | KM | GA01ML171 | 0.9 | GA01ML171 | 0.9 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:49:58 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078642&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078642 | CS Transmission Renewal | ST007590-29 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | JILALAN TSC |  | 0 | KM | GA02YR22 | 0.3499 | GA02YR22 | 0.3499 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:51:03 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078645&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078645 | CS Transmission Renewal | ST008780-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | LAKE VERMONT ATS 11.3KM |  | 0 | KM | GA19ML11 | 0.2999 | GA19ML11 | 0.2999 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:54:20 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078644&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078644 | CS Transmission Renewal | ST007550-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | LAKE VERMONT JUNCTION SER |  | 0 | KM | GA03ML87 | 0.017 | GA03ML87 | 0.017 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:53:15 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078640&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078640 | CS Transmission Renewal | ST007050-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | MILLENNIUM JUNCTION SER |  | 0 | KM | GA03ML16 | 0.5699 | GA03ML16 | 0.5699 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:48:52 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085171&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085171 | CS Power Supply Renewal | ST003760-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Moura | MOUNT RAINBOW |  | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078646&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078646 | CS Transmission Renewal | ST006770-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | RED MOUNTAIN ATS 30KM |  | 0 | KM | GA03ML30 | 0.02 | GA03ML30 | 0.02 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:55:25 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078647&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078647 | CS Transmission Renewal | ST005060-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | SARAJI SER |  | 0 | KM | GA03ML67 | 0.01 | GA03ML67 | 0.01 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:56:30 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085172&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085172 | CS Power Supply Renewal | ST003830-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Moura | STIRRAT |  | 0 | KM | MA01ML39 | 0.404 | MA01ML39 | 0.404 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078636&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078636 | Tele Pwr Supply Renewal Stowe SER | ST003860-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 29000 | Moura | STOWE SER |  | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 15:44:39 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085176&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085176 | CS Power Supply Renewal | ST005150-36 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Blackwater | UMOLO SER |  | 0 | KM | BW03ML148 | 0.507 | BW03ML148 | 0.507 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085173&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085173 | CS Power Supply Renewal | ST005790-29 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 32000 | Goonyella | WAITARA MW |  | 0 | KM | GA01ML100 | 0.45 | GA01ML100 | 0.45 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078686&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000078686 | CS Transmission Renewal | ST005490-JP | CONTROL SYSTEMS | TRANSMISSION | REVELOC | RENEWAL | 1 | SITE | 400000 | Blackwater | ROCKHAMPTON |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:39:12 AUSQLD Peter Rayner (R003851) * Renew REVELOC Application (Implementation)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093774&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093774 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 10 | SITE | 140000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093773&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093773 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 10 | SITE | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093772&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093772 | CS Transmission SDH to IP | NL | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 10 | SITE | 140000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085247&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085247 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 1 | BLACKWATER 1 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | RRIG |  | 20240630 | Duaringa FSS Labour IV.00822.e.h.bw.22.co.et Procurement IV.00822.e.h.bw.22.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126055&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126055 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 1 | BLACKWATER 1 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630 | Duaringa FSS Labour IV.00822.e.h.bw.22.co.et Procurement IV.00822.e.h.bw.22.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126183&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126183 | (ProcurmentCS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 2 | BLACKWATER 2 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20240630 | Labour IV.00822.e.h.bw.23.co.et Procurement IV.00822.e.h.bw.23.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100622&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100622 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 2 | BLACKWATER 2 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.23.co.et Procurement IV.00822.e.h.bw.23.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100623&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100623 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 3 | BLACKWATER 3 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.24.co.et Procurement IV.00822.e.h.bw.24.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126184&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126184 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 3 | BLACKWATER 3 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100624&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100624 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 4 | BLACKWATER 4 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.25.co.et Procurement IV.00822.e.h.bw.25.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126185&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126185 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 4 | BLACKWATER 4 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20240630 | Labour IV.00822.e.h.bw.25.co.et Procurement IV.00822.e.h.bw.25.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100625&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100625 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 5 | BLACKWATER 5 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126186&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126186 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 5 | BLACKWATER 5 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100626&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100626 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 6 | BLACKWATER 6 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.27.co.et Procurement IV.00822.e.h.bw.27.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126187&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126187 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 6 | BLACKWATER 6 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630 | Labour IV.00822.e.h.bw.27.co.et Procurement IV.00822.e.h.bw.27.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100627&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100627 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 7 | BLACKWATER 7 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.28.co.et Procurement IV.00822.e.h.bw.27.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126189&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126189 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 7 | BLACKWATER 7 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630 | Labour IV.00822.e.h.bw.28.co.et Procurement IV.00822.e.h.bw.27.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100629&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100629 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 8 | BLACKWATER 8 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.bw.29.co.et Procurement IV.00822.e.h.bw.29.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126230&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126230 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Blackwater | BLACKWATER 8 | BLACKWATER 8 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630 | Labour IV.00822.e.h.bw.29.co.et Procurement IV.00822.e.h.bw.29.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085248&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000085248 | MKY CER Battery Procurement 1. | ST005860-11 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 1 | GOONYELLA 1 | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Mackay CER battery procurment WO # 1 Procurement IV.00822.e.h.ga.24.pr.01. Order placed with logistics officer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100631&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000100631 | MKY CER Battery Procurement 2. | ST005860-62 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 2 | GOONYELLA 2 | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | MKY CER Battery Procurement 2 Procurement IV.00822.e.h.ga.25.pr.01 Order placed with logistics officer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100632&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000100632 | MKY CER Battery Procurement 3. | ST005860-63 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 3 | GOONYELLA 3 | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | MKY CER Battery Procurement 3 Procurement IV.00822.e.h.ga.26.pr.01 Order placed with logistics officer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100633&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000100633 | MKY CER Battery Procurement 4. | ST005860-64 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 4 | GOONYELLA 4 | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | MKY CER Battery Procurement 4 Procurement IV.00822.e.h.ga.27.pr.01 Order placed with logistics officer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100637&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | BASELOAD | COAL | 002000100637 | CD Junction Battery Procurement. | ST007210-23 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 7 | GOONYELLA 7 | 0 | KM | GA01ML160 | 0.788 | GA01ML160 | 0.788 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Carborough Downs Junction Battery Procurement Procurement IV.00822.e.h.ga.30.pr.01 Order placed with logistics officer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100638&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100638 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | GOONYELLA 8 | GOONYELLA 8 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100635&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100635 | MKY UPS Battery Procurement 1. | ST005860-C6 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | MACKAY CER | MACKAY CER | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | MKY UPS Battery Procurement 1 Procurement IV.00822.e.h.ga.28.pr.01. Purchase order raised with Admin team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100636&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100636 | MKY UPS Battery Procurement 2. | ST005860-C7 | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Goonyella | MACKAY CER | MACKAY CER | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | MKY UPS Battery Procurement 2 Procurement IV.00822.e.h.ga.29.pr.01 Purchase order reaised with Admin team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100621&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100621 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Moura | MOURA 1 | MOURA 1 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Labour IV.00822.e.h.ma.12.co.et Procurement IV.00822.e.h.ma.12.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126231&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126231 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Moura | MOURA 1 | MOURA 1 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630 | Labour IV.00822.e.h.ma.12.co.et Procurement IV.00822.e.h.ma.12.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085251&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085251 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Moura | MOURA 2 | MOURA 2 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | Telecommunication Batteries Renewal - Maintenance team to nominate a replacement location - In the Moura System Contact: Alex Gainsford 0488 013 524 Labour IV.00822.e.h.ma.13.co.et Procurement IV.00822.e.h.ma.13.pr.01
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126233&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000126233 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Moura | MOURA 2 | MOURA 2 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085250&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085250 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Newlands | NEWLANDS 1 | NEWLANDS 1 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100630&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000100630 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 11000 | Newlands | NEWLANDS 2 | NEWLANDS 2 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085475&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085475 | CS TETRA RADIO | ST004890 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 400000 | Goonyella |  |  | 0 | KM | GA05ML59 | 0.025 | GA05ML59 | 0.025 | KM | [6 empty] | 2024-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085462&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085462 | CS TETRA RADIO | ST006120 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 300000 | Blackwater | BLACKWATER MW | BLACKWATER MW | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085468&DY_MAB=X&~OKCODE=ONLI | FY24 | RIM Infrastructure | STRATEGIC | COAL | 002000085468 | CS TETRA RADIO | ST009280 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 100000 | Goonyella | CAVAL RIDGE | CAVAL RIDGE | 0 | KM | GA24ML6 | 0.5889 | GA24ML6 | 0.5889 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118033&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000118033 | CS TETRA RADIO | ST006020-23 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 100000 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML144 | 0.0519 | GA01ML144 | 0.0519 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | NWSC |  | 20240729
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085469&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085469 | CS TETRA RADIO | ST003030-02 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 100000 | Blackwater | ENSHAM | ENSHAM | 0 | KM | BW11ML13 | 0.1499 | BW11ML13 | 0.1499 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085461&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085461 | CS TETRA RADIO - FIRMWARE UPDATE | ST005860 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 250000 | Goonyella | MACKAY | MACKAY | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085472&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085472 | CS TETRA RADIO | ST007310 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 700000 | Goonyella | MINDI FSS | MINDI FSS | 0 | KM | GA01ML116 | 0.221 | GA01ML116 | 0.221 | KM | [6 empty] | 2025-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085473&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085473 | CS TETRA RADIO | ST009960 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 400000 | Goonyella | MORANBAH CER | MORANBAH CER | 0 | KM | GA05ML10 | 0.9 | GA05ML10 | 0.9 | KM | [6 empty] | 2024-06-30 | [13 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000097203&DY_MAB=X&~OKCODE=ONLI | FY24 | Dual Traffic | STRATEGIC | COAL | 002000097203 | CS TETRA RADIO | ST003740 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 320000 | Blackwater | MOUNT MILLER | MOUNT MILLER | 0 | KM | BW01ML540 | 0.93 | BW01ML540 | 0.93 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085460&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085460 | CS TETRA RADIO - FIRMWARE UPDATE | ST005490 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 250000 | Blackwater | ROCKHAMPTON | ROCKHAMPTON | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085464&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085464 | CS TETRA RADIO | ST009530-01 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 340000 | Blackwater | ROLLESTON AT7 | ROLLESTON AT7 | 0 | KM | BW06ML103 | 0.65 | BW06ML103 | 0.65 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085471&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085471 | CS TETRA RADIO | ST006670 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 340000 | Goonyella | SOUTH WALKER JUNCTION | SOUTH WALKER JUNCTION | 0 | KM | GA01ML127 | 0.4799 | GA01ML127 | 0.4799 | KM | [6 empty] | 2025-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085463&DY_MAB=X&~OKCODE=ONLI | FY24 | Coal Traffic | STRATEGIC | COAL | 002000085463 | CS TETRA RADIO | ST003260 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 300000 | Blackwater | YAN YAN SER | YAN YAN SER | 0 | KM | BW08ML50 | 0.8639 | BW08ML50 | 0.8639 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043414&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000043414 | Dig Telem BW Renewal | ST006470 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 9 | UNIT | 800000 | Blackwater | ROCKHAMPTON ADMIN 5TH FLR |  | 0 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW | HIGH | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085029&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085029 | UTC DTC Renewal BW | BW | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 840000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | UTC DTC | STRATEGIC | LOW | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085053&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085053 | UTC DTC Renewal GA | GA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 840000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | UTC DTC | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053189&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000053189 | UTC DTC Renewal MA | MA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 105000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | UTC DTC | STRATEGIC | LOW | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085060&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000085060 | UTC DTC Renewal NL | NL | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 315000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | UTC DTC | STRATEGIC | LOW | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085191&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085191 | OVERHEAD¦GOONYELLA PORTS OHL¦RENEWAL | GA-0912 | ELECTRICAL | OVERHEAD | GOONYELLA PORTS OHL RENEWAL | RENEWAL | 1 | SITE | 4000000 | Goonyella | DALRYMPLE BAY | HAY POINT | 9.6679 | KM | DL/-0/068/DR1 | 0 | GA/9/600/D | 0 | KM |  |  |  |  | 0 | 9.6 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Goonyella Ports Overhead Line Renewal | STRATEGIC | LOW | HIGH | HIGH | HIGH | Outstanding notification | RRIG INIF |  | 20240630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. 24/08/22: Estimate updated following development of Class 4 estimate. Refer to PCR 5347. 7/9/22: Estimate updated following SCR 275 submitted on 7/9/22 to remove SP7 and include SP8. 13.01.2023 PCR 5559. A portion of scope will not be achieved due to the high risk of not securing external entities to complete the scope item relating to the insulated overlaps. Budget reduced to $4M.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094958&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094958 | T30-OH-HEADSPAN-Dysart-90.258km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.258 | 90.258 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094959&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094959 | T30-OH-HEADSPAN-Dysart-90.313km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.313 | 90.313 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094960&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094960 | T30-OH-HEADSPAN-Dysart-90.371km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.371 | 90.371 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094961&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094961 | T30-OH-HEADSPAN-Dysart-90.428km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.428 | 90.428 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094962&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094962 | T30-OH-HEADSPAN-Dysart-90.473km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.473 | 90.473 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094963&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000094963 | T30-OH-HEADSPAN-Dysart-90.509km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 90000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.509 | 90.509 | 2024-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2022-03-31 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | HIGH | LOW | HIGH | Notification in process | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093694&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093694 | SECTION INSULATOR-BROADLEA | SQ020268 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | DESIGN | 1 | UNIT | 25000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA/155/987/U | 0 | GA/155/987/U | 0 | KM |  |  |  |  | 155.987 | 155.987 | 2024-06-30 |  |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 11.55 |  | 2022-03-31 |  | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103011&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000103011 | SECTION INSULATOR - BROADLEA | SQ020262 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | DESIGN | 1 | UNIT | 25000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA/156/001/D | 0 | GA/156/001/D | 0 | KM |  |  |  |  | 156.001 | 156.001 | 2025-06-30 |  |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 11.55 |  |  |  | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | HI25 SI to be replaced with insulated overlap
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074784&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000074784 | SECTION INSULATOR - ROCKLANDS | SQ020177 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | DESIGN | 1 | UNIT | 10000 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM |  | 0 |  | 0 | [5 empty] | 631.581 | 631.581 | 2024-06-30 |  |  |  |  | 3.5 | 4.5 | 2 | 4.1 | 1 | 14.35 |  | 2022-03-31 |  | Section Insulator and Neutral Section Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000076197&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000076197 | Overhead Reactive Works | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM | 800000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 |  | 2022-03-31 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 21.04.2021 10:07:16 AUSQLD Nigel McDowell (R885053) * Small components reactive works. Estimate includes $200,000 deferred from FY23. 13.01.2023 PCR 5558. Budget reduced from $1.2M to $800k.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000076196&DY_MAB=X&~OKCODE=ONLI | FY24 |  | REACTIVE RENEWALS | COAL | 002000076196 | Overhead Reactive Works | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM | 300000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 |  | 2022-03-31 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | * 21.04.2021 10:03:25 AUSQLD Nigel McDowell (R885053) * Small components reactive works. Estimate includes $200,000 deferred from FY23. 12.01.2023 PCR 5556: Reduce to $300k. As Goonyella Ports rusty component would be the priority for both possession and resources within the Goonyella system. $300k does allow for some work.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110900&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110900 | Termination Portal Design Blair Athol | SQ020483 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0.032 | KM | BA/108/190/UL | 0 | BA/108/222/DL | 0 | KM | [11 empty] | 4 | 1.2 | 3 | 3 | 1 | 12.4 |  |  |  | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110901&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110901 | Termination Portal Design Burton | SQ020476 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | BURTON | BURTON | 0.035 | KM | BN/3/582/L | 0 | BN/3/617/L | 0 | KM | [11 empty] | 4 | 0.9 | 3 | 3 | 1 | 12 |  |  |  | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110902&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110902 | Termination Portal Design German Creek | SQ020473 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.07 | KM | GC/134/233/L | 0 | GC/134/303/L | 0 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 1.2 | 3 | 3 | 1 | 12.4 |  |  |  | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110903&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110903 | Termination Portal Design Goonyella | SQ020479 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | GOONYELLA | GOONYELLA | 0.033 | KM | GA/198/196/DL | 0 | GA/198/229/DL | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110904&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110904 | Termination Portal Design Moorvale | SQ020466 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | MOORVALE | MOORVALE | 0.035 | KM | MP/5/473/L | 0 | MP/5/508/L | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110905&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110905 | Termination Portal Design Nth Goonyella | SQ020481 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0.0379 | KM | NG/217/207/L | 0 | NG/217/245/L | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110906&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110906 | Termination Portal Design Norwich Park | SQ020471 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | NORWICH PARK | NORWICH PARK | 0.034 | KM | NP/111/194/L | 0 | NP/111/228/L | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110907&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110907 | Termination Portal Design Oaky Creek | SQ020474 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | OAKY CREEK | OAKY CREEK | 0.0359 | KM | OC/152/847/L | 0 | OC/152/883/L | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110908&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000110908 | Termination Portal Design Riverside | SQ020480 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | DESIGN | 2 | STRUCTURES | 10000 | Goonyella | RIVERSIDE | RIVERSIDE | 0.0299 | KM | RE/203/506/L | 0 | RE/203/536/L | 0 | KM | [6 empty] | 2024-06-30 | [13 empty] | Termination Portals | [5 empty] | Outstanding notification | NWSC |  | 20240630 | PCR 5555. New notification for design ($10k).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105124&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105124 | AT¦BURNGROVE AT2¦DESIGN | ST000070-16 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Blackwater | BURNGROVE | BURNGROVE | 0 | KM | BW03ML202 | 0.5 | BW03ML202 | 0.5 | KM | [5 empty] | 202.5 | 2024-06-30 |  |  | 202.5 |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105123&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105123 | AT¦GERMAN CREEK AT1¦DESIGN | ST000760-08 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM |  |  |  |  | 136.433 | 136.433 | 2024-06-30 |  |  |  |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | STRATEGIC |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105122&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105122 | AT¦GERMAN CREEK AT2¦DESIGN | ST000760-09 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM |  |  |  |  | 136.433 | 136.433 | 2024-06-30 |  |  |  |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | STRATEGIC |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105126&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105126 | AT¦GRANTLEIGH AT2¦DESIGN | ST000210-21 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | STRATEGIC |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105125&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105125 | AT¦GRANTLEIGH AT3¦DESIGN | ST000210-22 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | STRATEGIC |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105121&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105121 | AT¦NORWICH PARK AT1¦DESIGN | ST001400-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 10000 | Goonyella | NORWICH PARK | NORWICH PARK | 0 | KM | GA03ML115 | 0.4 | GA03ML115 | 0.4 | KM |  |  |  |  | 105.126 | 105.126 | 2024-06-30 |  |  |  |  | 10 | 10 |  |  | 1 | 100 |  |  |  | Autotransformer Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | RRIG |  | 20240630 | 13-09-23 EK: This notification is to be deleted and removed-duplication
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105116&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000105116 | AT¦BOLINGBROKE AT1¦RENEWAL | ST001330-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML65 | 0.933 | GA01ML65 | 0.933 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Notification in process | NWSC |  | 20240630 | 9/6/23: Moved from FY27 to FY24. Refer PCR 5595.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112945&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000112945 | AT¦BUNDOORA ATS AT1¦RENEWAL | ST001420-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Goonyella | BUNDOORA ATS | BUNDOORA ATS | 0 | KM | GA03ML126 | 0.2 | GA03ML126 | 0.2 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Notification completed | NWSC |  | 20250205 | Swap into FY24. Refer to PCR 5595. IV.00825.E.A.GA.03.CO JP 09/08/2023 AT INSTALLED AND COMMISSIONED. ISOLATOR TO BE INSTALLED AT FUTRURE DATE.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000076185&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000076185 | AT¦CALLEMONDAH FS - AT3¦RENEWAL | ST000120-25 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Blackwater | CALLEMONDAH FS - AT3 | CALLEMONDAH FS | 0 | KM | BW01ML537 | 0.1429 | BW01ML537 | 0.1429 | KM |  |  |  |  | 537.143 | 537.143 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Autotransformer Renewal | STRATEGIC | LOW | LOW | LOW | LOW | Notification completed | RRIG |  | 20240630 | WBSE: IV.00825.E.A.BW.01.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050185&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000050185 | AT¦GRANTLEIGH FS - AT1¦RENEWAL | ST000210-20 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Blackwater | GRANTLEIGH FS - AT1 | GRANTLEIGH FS | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 | 2021-10-05 | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | RRIG | FY23 IN | 20240630 | * 01.06.2020 20:46:47 AUSQLD Emma-Kate Clyburn (R870828) * Site to be confirmed in Jan 2021 * 18.03.2021 08:58:32 AUSQLD Dhavalkumar Patel (R866429) * * Site confirmed - ST000210-20 GRANTLEIGH FS - AT1 * 12.04.2021 16:21:38 AUSQLD Jeremy Stevenson (R867415) * Current procurement contract will expire in FY23 - need to discuss this in FY23. (design implementat * ion for FY23 for reduction in cost with optimised design) - scope is low but as the design is being optimised in FY23 there may be change to scope on AT), duration is medium due to AT failures elsewhe * re in the system. Callemondah FS AT4 failed in service - Due to this Rangal FS AT1 pushed into FY23 (from FY22) and Grantleigh FS AT1 pushed into FY24 (from FY23). WBSE: IV.00825.E.A.BW.02.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112944&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000112944 | AT¦Mt McLaren Blackridge ATS AT1¦RENEWAL | ST001340-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Goonyella | MOUNT MCLAREN BLACKRIDGE | MOUNT MCLAREN BLACKRIDGE | 0 | KM | GA05ML65 | 0.9649 | GA05ML65 | 0.9649 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Notification completed | NWSC |  | 20240630 | Refer Noti 2000107278. Bushing failure, AT out of service. Swap into FY24. 9/6/23: Moved into FY24 scope. Refer PCR 5595.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094229&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000094229 | AT¦WALTON ATS - AT1¦RENEWAL | ST001970-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 710000 | Blackwater | WALTON ATS AT1 | WALTON ATS | 0 | KM | BW03ML162 | 0.202 | BW03ML162 | 0.202 | KM |  |  |  |  | 162.202 | 162.202 | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Autotransformer Renewal | STRATEGIC | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | WBSE: IV.00825.E.A..BW.03.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081065&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000081065 | BLUFF PSC DC/DC CONVERTER CW 171.018KM | ST001840-03 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | SITE | 15000 | Blackwater | BLUFF | BLUFF | 0 | KM | BW03ML171 | 0.0179 | BW03ML171 | 0.0179 | KM |  |  |  |  | 171.018 | 171.018 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.2 |  | 2022-03-31 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG INIF |  | 20240630 | INSTALL DC/DC CONVERTER WBSE: IV.00825.E.F.BW.01.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081066&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000081066 | BOONAL PSC DC/DC CONVERTER 181.338KM | ST001850-03 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | SITE | 15000 | Blackwater | BOONAL | BOONAL | 0 | KM | BW03ML181 | 0.338 | BW03ML181 | 0.338 | KM |  |  |  |  | 181.338 | 181.338 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.2 |  | 2022-03-31 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG INIF |  | 20240630 | INSTALL DC/DC CONVERTER WBSE: IV.00825.E.F.BW.02.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044545&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044545 | TRYPHINIA 125.714 km DC/DC CONVERTER | ST001950-05 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | SITE | 26000 | Blackwater | TRYPHINIA | TRYPHINIA | 0 | KM | BW03ML125 | 0.7139 | BW03ML125 | 0.7139 | KM |  |  |  |  | 125.7 | 125.7 | 2024-06-30 |  |  |  |  | 3 | 3.35 | 0.5 | 2.9 | 1 | 8.7 |  | 2022-03-31 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG |  | 20240630 | * 02.03.2021 14:08:24 AUSQLD Adrian Barnes (R886902) * Telecomms charger here, so install dc/dc converter and decommission power sys. charger. WBSE: IV.00825.E.F.BW.04.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044546&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000044546 | WALLAROO 111.074 km DC/DC CONVERTER | ST001940-05 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | SITE | 26000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML111 | 0.0739 | BW03ML111 | 0.0739 | KM |  |  |  |  | 111.074 | 111.074 | 2024-06-30 |  |  |  |  | 3 | 3.35 | 0.5 | 2.9 | 1 | 8.7 |  | 2022-03-31 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Notification in process | RRIG |  | 20240630 | * 02.03.2021 14:07:32 AUSQLD Adrian Barnes (R886902) * Telecomms charger here, so install dc/dc converter and decommission power sys. charger. WBSE: IV.00825.E.F.BW.05.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104673&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000104673 | POWER SYSTEMS¦LV EARTHING¦DESIGN | GA | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | DESIGN | 1 | UNIT | 20000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3 | 4.7 | 0.5 | 3.6 | 1 | 10.8 |  |  |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Develop standard design for TSC LV Earthing. This design will apply to 8 sites to be renewed in FY26: 002000094385 Red Rock 002000094386 German Creek 002000094387 Yan Yan 002000094388 Villafranca 002000094389 Moranbah South 002000094390 Saraji 002000094391 South Walker 002000094392 Red Mountain
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091898&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000091898 | MI/OHW Design 601/2 Black Mountain | SQ030213 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 59853 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA/40/770/U | 0 | GA/40/770/U | 0 | KM |  |  |  |  | 40.77 | 40.77 | 2024-06-30 |  |  |  |  | 3.44 | 5 | 2 | 4.2 | 1 | 17.2 |  | 2022-03-31 |  | Motorised Isolator Renewal | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY24 OUT | 20240630 | 15/2/2022: This Design N4 created as an addition to existing Renewal N4 for notification 2000044495 which will be executed in FY25. The MI design will be executed in FY24. 6/3/2022 R.Licis: Concept design and design cost only attached to notification. N4 class updated with estimate
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094260&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094260 | MI/OHW Design 902/3 Jilalan | SQ030556 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 11851 | Goonyella | JILALAN | JILALAN | 0.0459 | KM | GA/23/150/DM | 0 | GA/23/196/DM | 0 | KM |  |  |  |  | 23.196 | 23.196 | 2024-06-30 |  |  |  |  | 3.4 | 4.8 | 2 | 4.2 | 1 | 14.28 |  | 2022-03-31 |  | Motorised Isolator Renewal | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG | FY24 OUT | 20240630 | 28/3/2022 R.Licis: This is an OHW design N4 notification to relocate isolator 902/3 on mast GA/23/150/DM to portal leg GA/23/196/DM (access road side, SER side). Design to be done in FY24 and construction in FY25. See wiring layout markup for concept design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094355&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094355 | MI/OHW Design 101A/102G Rockland | ST000160-03 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 8166 | Blackwater | ROCKLAND | ROCKLAND | 0 | KM | BW03ML1 | 0.558 | BW03ML1 | 0.558 | KM |  |  |  |  | 1.553 | 1.553 | 2024-06-30 |  |  |  |  | 4.8 | 4.5 | 2 | 4.1 | 1 | 19.68 |  | 2022-03-31 |  | Motorised Isolator Renewal | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is an N4 OHW Design Only to raise MI box 101A/102G atCW/1/558/U to walkway access same surface height of Rockland TSC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094277&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000094277 | MI/OHW Design 551A/552E Rockland | ST000160-06 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 8166 | Blackwater | ROCKLAND | ROCKLAND | 0 | KM | BW03ML1 | 0.553 | BW03ML1 | 0.553 | KM |  |  |  |  | 1.553 | 1.553 | 2024-06-30 |  |  |  |  | 3.35 | 4.5 | 2 | 4.1 | 1 | 13.74 |  | 2022-03-31 |  | Motorised Isolator Renewal | BESPOKE DESIGN | LOW |  | LOW | LOW | Notification in process | RRIG |  | 20240630 | 28/3/2022 R.Licis: This is an N4 OHW Design Only to raise MI box 551A/552E to walkway access same surface height of Rockland TSC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091920&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091920 | MI Renewal 851/8 Bluff | SQ030479 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 73160 | Blackwater | BLUFF | BLUFF | 0 | KM | CW/170/995/H1 | 0 | CW/170/995/H1 | 0 | KM |  |  |  |  | 170.995 | 170.995 | 2024-06-30 |  |  |  |  | 3.94 | 3.35 | 2 | 3.6 | 1 | 14.18 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 created for FY24 8/3/2022 R.Licis: Inspected scope attached. 5/6/2023 R.Licis: Scope F4 non-polluted Type WBSE: IV.00825.E.C.BW.02.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074283&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000074283 | MI Renewal 862/3 Boonal | SQ030703 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 70623 | Blackwater | BOONAL | BOONAL | 0 | KM | CW/178/246/D | 0 | CW/178/246/D | 0 | KM |  |  |  |  | 178.246 | 178.246 | 2024-06-30 |  |  |  |  | 2.9 | 3.4 | 2 | 3.7 | 1 | 10.73 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 OUT | 20240630 | * 31.03.2021 19:19:49 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 8/3/2022 R.Licis: Inspected scope attached 5/6/2023 R.Licis: Scope type F4 double non-polluted WBSE: IV.00825.E.C.BW.01.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074284&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000074284 | MI Renewal 862/2 Boonal | SQ030476 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 70623 | Blackwater | BOONAL | BOONAL | 0 | KM | CW/181/332/D | 0 | CW/181/332/D | 0 | KM |  |  |  |  | 181.332 | 181.332 | 2024-06-30 |  |  |  |  | 2.6 | 3.4 | 2 | 3.7 | 1 | 9.62 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG | FY23 OUT | 20240630 | * 31.03.2021 19:19:54 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 8/3/2022 R.Licis: Inspected Scope attached. Design required (FY24) and Renewal in FY25 25/3/2022 R.Licis: Scope moved back to FY24. Design not required. Scope will be F4 type. In addition, isolator paddle to be shifted slightly to fit new MVT MI as OPGW box is next to it. See attachment for solution. 31/3/2022 Longer backing flat will be required once the isolator paddle is moved. WBSE: IV.00825.E.C.BW.01.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091894&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091894 | MI Renewal 142/5 Dingo | SQ030459 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 65139 | Blackwater | DINGO | DINGO | 0 | KM | CW/140/611/D | 0 | CW/140/611/D | 0 | KM |  |  |  |  | 140.611 | 140.611 | 2024-06-30 |  |  |  |  | 3.44 | 3.35 | 2 | 3.6 | 1 | 12.38 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 created for FY24 8/3/2022 R.Licis: Inspected Scope attached. 5/6/2023 R.Licis: Scope C Type WBSE: IV.00825.E.C.BW.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091893&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091893 | MI Renewal 141/2 Dingo | SQ030461 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 70767 | Blackwater | DINGO | DINGO | 0 | KM | CW/140/741/U | 0 | CW/140/741/U | 0 | KM |  |  |  |  | 140.741 | 140.741 | 2024-06-30 |  |  |  |  | 3.94 | 3.35 | 2 | 3.6 | 1 | 14.18 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 created for FY24 8/3/2022 R.Licis: Inspected Scope attached. 5/6/2022 R.Licis: Scope F4 Type (Non-polluted) WBSE: IV.00825.E.C.BW.03.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091919&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091919 | MI Renewal 812/3 Warren | SQ030537 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 73160 | Blackwater | WARREN | WARREN | 0 | KM | CW/25/280/D | 0 | CW/25/280/D | 0 | KM |  |  |  |  | 25.28 | 25.28 | 2024-06-30 |  |  |  |  | 3.44 | 3.35 | 2 | 3.6 | 1 | 12.4 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 created for FY24 8/3/2022 R.Licis: Scope and Inspection form attached 5/6/2023 R.Licis: Scope Type F4 non-polluted WBSE: IV.00825.E.C.BW.05.CO
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091914&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091914 | MI Renewal 112/2 Windah West | SQ030017 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 61228 | Blackwater | WINDAH WEST | WINDAH WEST | 0 | KM | CW/57/692/D | 0 | CW/57/692/D | 0 | KM |  |  |  |  | 57.692 | 57.692 | 2024-06-30 |  |  |  |  | 3.44 | 3.35 | 2 | 3.6 | 1 | 12.4 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 for FY24 created 11/3/2022 R.Licis: Inspected Scope attached. 5/6/2023 R.Licis: Scope is C Type. WBSE: IV.00825.E.C.BW.06.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091915&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091915 | MI Renewal 111/4 Windah West | SQ030532 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 66856 | Blackwater | WINDAH WEST | WINDAH WEST | 0 | KM | CW/57/855/U | 0 | CW/57/855/U | 0 | KM |  |  |  |  | 57.857 | 57.857 | 2024-06-30 |  |  |  |  | 3.44 | 3.35 | 2 | 3.6 | 1 | 12.4 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 notification created for FY24. 8/3/2022 R.Licis: Scope and Inspection form attached. Note leave existing wiring arrangement AS IS but replace box and blade 5/6/2023 R.Licis: Scope Type F4 non-polluted WBSE: IV.00825.E.C.BW.06.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093008&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093008 | MI Renewal 181/5 Yan Yan | SQ030521 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 73917 | Blackwater | YAN YAN | YAN YAN | 0 | KM | GG/51/901/L | 0 | GG/51/901/L | 0 | KM |  |  |  |  | 52.055 | 52.055 | 2024-06-30 |  |  |  |  | 3.44 | 1 | 2 | 2.4 | 1 | 8.3 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG | FY25 OUT | 20240630 | 8/3/2022 R.Licis: N4 created for FY25. Inspected scope attached. 21/2/2022 R.Licis: Scope moved to FY24. 5/6/2023 R.Licis: Scope type F4 Non-polluted WBSE: IV.00825.E.C.BW.07.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091917&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000091917 | MI Renewal 181/7 Yan Yan | SQ030519 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 73917 | Blackwater | YAN YAN | YAN YAN | 0 | KM | GS/0/019/L | 0 | GS/0/019/L | 0 | KM |  |  |  |  | 52.137 | 52.137 | 2024-06-30 |  |  |  |  | 3.44 | 1 | 2 | 2.4 | 1 | 8.3 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification completed | RRIG | FY24 OUT | 20240630 | 15/2/2022 R.Licis: N4 created for FY24 5/6/2023 R.Licis: Scope Type F4 non-polluted WBSE: IV.00825.E.C.BW.07.CO 04/03/2024 T.Gurnett: Quality Assurance documents uploaded into work order. Completing this notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105330&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105330 | PSC RENEWAL¦INTERLOCKING UPGRADE¦DESIGN | GA | ELECTRICAL | POWER SYSTEMS | PSC SER INTEGRATION | DESIGN | 1 | UNIT | 20000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 3 | 5 | 0.5 | 3.7 | 1 | 11.1 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | Development of standard design for integration of PSC equipment into new SER buildings. Balook and Wandoo SER renewals currently planned for FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105402&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105402 | ALDOGA AT 555.876 PSC SITE DESIGN | ST001860-03 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 10000 | Blackwater | ALDOGA | ALDOGA | 0 | KM | BW01ML555 | 0.876 | BW01ML555 | 0.876 | KM |  |  |  |  | 555.876 | 555.876 | 2024-06-30 |  |  |  |  | 3.5 | 4.5 | 0.5 | 3.5 | 1 | 12.3 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105404&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105404 | DYSART 88.400 PSC SITE DESIGN | ST001750-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 10000 | Goonyella | DYSART | DYSART | 0 | KM | GA03ML88 | 0.4 | GA03ML88 | 0.4 | KM |  |  |  |  | 88.4 | 88.4 | 2024-06-30 |  |  |  |  | 3.5 | 1.1 | 0.5 | 1 | 1 | 3.5 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105403&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105403 | MARMOR 594.900 PSC SITE DESIGN | ST001880-03 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 10000 | Blackwater | MARMOR | MARMOR | 0 | KM | BW01ML594 | 0.9 | BW01ML594 | 0.9 | KM |  |  |  |  | 594.9 | 594.9 | 2024-06-30 |  |  |  |  | 3.5 | 4.9 | 0.5 | 3.7 | 1 | 13 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105273&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000105273 | MT MILLER 540.355 PSC SITE RENEWAL (DSN) | ST002080-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 10000 | Blackwater | MT MILLER | MT MILLER | 0 | KM | BW01ML540 | 0.3549 | BW01ML540 | 0.3549 | KM |  |  |  |  | 540.355 | 540.355 | 2024-06-30 |  |  |  |  | 3.5 | 4.8 | 0.5 | 3.6 | 1 | 12.6 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20240630 | No information within notification on what is required by teams, please advise of scope. LG 29/1/2024
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093729&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093729 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-29 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093740&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093740 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-30 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093741&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093741 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-31 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093669&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093669 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-32 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093750&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093750 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-33 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093751&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093751 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-34 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093752&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093752 | POWER SYSTEMS¦RELAYS¦DESIGN¦GRANTLEIGH | ST000210-35 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2024-06-30 |  |  |  |  | 3.5 | 3.35 | 0.5 | 2.9 | 1 | 10.15 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093722&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093722 | POWER SYSTEMS¦RELAYS¦DESIGN¦MT MCLAREN | ST000800-21 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2024-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093725&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093725 | POWER SYSTEMS¦RELAYS¦DESIGN¦MT MCLAREN | ST000800-22 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2024-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093726&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093726 | POWER SYSTEMS¦RELAYS¦DESIGN¦MT MCLAREN | ST000800-25 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2024-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093727&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093727 | POWER SYSTEMS¦RELAYS¦DESIGN¦MT MCLAREN | ST000800-26 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2024-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093728&DY_MAB=X&~OKCODE=ONLI | FY24 |  | FUTURE SCOPE | COAL | 002000093728 | POWER SYSTEMS¦RELAYS¦DESIGN¦MT MCLAREN | ST000800-27 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2024-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | RRIG |  | 20240630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093756&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093756 | POWER SYSTEMS¦RELAYS¦RENEWAL¦MORANBAHSTH | ST000780-16 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM |  |  |  |  | 19.976 | 19.976 | 2024-06-30 |  |  |  |  | 3.5 | 1.5 | 0.5 | 1.5 | 1 | 5.25 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Moranbah Sth TSC-Construction IV.00825.E.E.GA.02.CO TRN040 End: 30/06/2024 Add: 002000093757 002000093758
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093757&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093757 | POWER SYSTEMS¦RELAYS¦RENEWAL¦MORANBAHSTH | ST000780-17 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM |  |  |  |  | 19.976 | 19.976 | 2024-06-30 |  |  |  |  | 3.5 | 1.5 | 0.5 | 1.5 | 1 | 5.25 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Moranbah Sth TSC-Construction IV.00825.E.E.GA.02.CO TRN040 End: 30/06/2024 Add: 002000093756 00200003758
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093758&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093758 | POWER SYSTEMS¦RELAYS¦RENEWAL¦MORANBAHSTH | ST000780-18 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM |  |  |  |  | 19.976 | 19.976 | 2024-06-30 |  |  |  |  | 3.5 | 1.5 | 0.5 | 1.5 | 1 | 5.25 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Moranbah Sth TSC-Construction IV.00825.E.E.GA.02.CO TRN040 End: 30/06/2024 Add: 00200009376 2000093757
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093753&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093753 | POWER SYSTEMS¦RELAYS¦RENEWAL¦SARAJI | ST000740-10 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM |  |  |  |  | 71.271 | 71.271 | 2024-06-30 |  |  |  |  | 3.5 | 1.8 | 0.5 | 1.8 | 1 | 6.3 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Saraji TSC-Construction IV.00825.E.E.GA.03.CO TRN040 End: 30/06/2024 Include: 002000093754 002000093755
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093754&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093754 | POWER SYSTEMS¦RELAYS¦RENEWAL¦SARAJI | ST000740-11 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM |  |  |  |  | 71.271 | 71.271 | 2024-06-30 |  |  |  |  | 3.5 | 1.8 | 0.5 | 1.8 | 1 | 6.3 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Saraji TSC-Construction IV.00825.E.E.GA.03.CO TRN040 End: 30/06/2024 Include: 002000093753 002000093755
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093755&DY_MAB=X&~OKCODE=ONLI | FY24 |  | BASELOAD | COAL | 002000093755 | POWER SYSTEMS¦RELAYS¦RENEWAL¦SARAJI | ST000740-12 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 47000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM |  |  |  |  | 71.271 | 71.271 | 2024-06-30 |  |  |  |  | 3.5 | 1.8 | 0.5 | 1.8 | 1 | 6.3 |  | 2022-03-31 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | RRIG |  | 20240630 | FY24-Relays-Saraji TSC-Construction IV.00825.E.E.GA.03.CO TRN040 End: 30/06/2024 Include: 002000093754 FY24-Relays-Saraji TSC-Construction IV.00825.E.E.GA.03.CO TRN040 End: 30/06/2024 Include: 002000093753 002000093754
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121120&DY_MAB=X&~OKCODE=ONLI | FY24 |  |  |  | 002000121120 | Design Permanent Barrier-HV Cables | ST000150-09 | ELECTRICAL | POWER SYSTEMS | SMALL COMPONENTS | DESIGN | 1 | SITE |  | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01ML582 | 0.506 | BW01ML582 | 0.506 | KM | [26 empty] | Outstanding notification | AREQ |  | 20240629 | 27/06/23 EK: Design permanent barrier to protect incoming HV cables on Masts FS/RA/13 and FS/RA/14 from vehicle collision. The mechanical protection to be suitably design for use in the substation environment and will need to be risk-assessed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085316&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085316 | Traction Substation Renewals | BW | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 8 | SITE | 1820784 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Traction Substation Renewals | STRATEGIC | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. Estimate updated to $1,820,784 following SCR submitted on 9/8/22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085315&DY_MAB=X&~OKCODE=ONLI | FY24 |  | STRATEGIC | COAL | 002000085315 | Traction Substation Renewals | GA | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 14 | SITE | 3121649 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Traction Substation Renewals | STRATEGIC | LOW | LOW | HIGH | HIGH | Outstanding notification | RRIG |  | 20240630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. 7/9/22: Estimate updated to $3,121,649 following SCR submitted 9/8/22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103885&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000103885 | C60-ACP-BW-km | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 4.9 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103888&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000103888 | C60-ACP-GA-km | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 4.9 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103891&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000103891 | C60-ACP-MA-km | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 1.3 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103894&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000103894 | C60-ACP-NL-km | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 2.7 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120580&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120580 | C60-ACP-MA-BELLDEEN-156.087km | AP400037 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML156 | 0.0869 | MA01ML156 | 0.0869 | KM |  |  |  |  | 156.087 | 156.087 | 2025-06-30 |  |  |  |  | 10 | 10 | 2 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | AP400037 MA 156.087km Dawson Hwy Belldeen Access Point Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121159&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000121159 | C60-ACP-GA-DALY BAY-9.523km | AP200121 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA02ML9 | 0.523 | GA02ML9 | 0.523 | KM |  |  |  |  | 9.523 | 9.523 | 2025-06-30 |  |  |  |  | 10 | 10 | 2 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY25 ACCESS POINT DESIGN- IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120582&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000120582 | C60-ACP-BW-RAGLAN-591.798km | AP100303 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW02ML591 | 0.798 | BW02ML591 | 0.798 | KM |  |  |  |  | 591.798 | 591.798 | 2025-06-30 |  |  |  |  | 10 | 10 | 2 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | AP100303 at 591.798km Capricorn Highway (Marble Creek)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120583&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120583 | C60-ACP-NL-SONOMA-91.379km | AP300142 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Newlands | SONOMA | BIRRALEE | 0 | KM | NL01ML91 | 0.379 | NL01ML91 | 0.379 | KM |  |  |  |  | 91.379 | 91.379 | 2025-06-30 |  |  |  |  | 10 | 10 | 2 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Notification in process | NWSC |  | 20250630 | FY24 Design Bowen Development Road Birralee Desktop review limited due to no google street view in Newlands system beyond 29km. This Access Point is on TMR road corridor so will require road safety audit by an approved contractor (where further information will be gathered).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120584&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000120584 | C60-ACP-BW-ROCKLANDS-631.792km | BW-01CR | CIVIL | ACCESS POINTS | IFC - STAIRS | DESIGN | 1 | UNIT | 16890 | Blackwater | ROCKLANDS | ROCKLANDS | 96.337 | KM | BW01ML534 | 0.1519 | BW01ML632 | 0.9579 | KM |  |  |  |  | 631.792 | 631.792 | 2025-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | 28/3/2022 R.Licis: This is a Civil Design N4 notification created to renew an existing stairs (NCL 631k800 Down)connecting the access road at the top of embankment down to 551/5 isolator mast at N/631/792/D. The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Engineering) attached as well.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120585&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000120585 | C60-ACP-BW-ROCKLANDS-1.533km | BW-03CR | CIVIL | ACCESS POINTS | IFC - WALKWAY | DESIGN | 1 | UNIT | 4704 | Blackwater | ROCKLANDS | ROCKLANDS | 263.1309 | KM | BW03ML0 | 0 | BW03ML263 | 0.1499 | KM |  |  |  |  | 1.533 | 1.533 | 2025-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | 28/3/2022 R.Licis: This is a Civil Design Only N4 notification created to design a walkway platform from the top of embankment of Rockland TSC to mast CW/1/553/U The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Eng ineering) attached as well. Another design walkway associated to this noti is 2000094316 (also at Rockland TSC). Design Estimate attached was therefore halved.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120586&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000120586 | C60-ACP-BW-ROCKLANDS-1.588km | BW-03CR | CIVIL | ACCESS POINTS | IFC - WALKWAY | DESIGN | 1 | UNIT | 4704 | Blackwater | ROCKLANDS | ROCKLANDS | 263.1309 | KM | BW03ML0 | 0 | BW03ML263 | 0.1499 | KM |  |  |  |  | 1.588 | 1.588 | 2025-06-30 |  |  |  |  | 10 | 10 | 1 | 0.1 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | 28/3/2022 R.Licis: This is a Civil Design Only N4 notification created to design a walkway platform from the top of embankment of Rockland TSC to mast CW/1/558/U The design work to be done in FY24 and construction in FY25. Scope attached to noti and design estimate from Simon Larsen (Civil Eng ineering) attached as well.Another design walkway associated to this noti is 2000094315(also at Rockland TSC). Design Estimate attached was therefore halved.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114617&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114617 | C60-ACP-NL-ARMUNA-27.1km | AP300018 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands | ARMUNA | ABERDEEN | 0 | KM | NL01ML27 | 0.139 | NL01ML27 | 0.139 | KM |  |  |  |  | 27.1 | 27.1 | 2025-06-30 |  |  |  |  | 10 | 1.7 | 0.5 | 10 | 1 | 100 | 38 | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Survey works 2. Installation of signage 3. Construction of adequate drainage features 4. Road manager's approval 5. Construction of turning lanes.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114136&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000114136 | C60-ACP-BW-GLADSTONE-546.571km | AP100686 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater | GLADSTONE | MT LARCOM | 0 | KM | BW01ML546 | 0.5709 | BW01ML546 | 0.5709 | KM |  |  |  |  | 546.571 | 546.571 | 2025-06-30 |  |  |  |  | 10 | 4.8 | 0.5 | 10 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of slip/turning lanes 2. Installation of signage 3. Construction of adequate drainage works 4. Achieve road managers approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114615&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114615 | C60-ACP-MA-STIRRAT-45.25km | AP400052 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura | STIRRAT | CLARKE | 0 | KM | MA01ML45 | 0.251 | MA01ML45 | 0.251 | KM |  |  |  |  | 45.25 | 45.25 | 2025-06-30 |  |  |  |  | 10 | 1.3 | 0.5 | 10 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT DESIGN. Scope of renewal works may include: 1. Construction of turning lanes 2. Construction of drainage infrastructures as required 3. Installation of signage 4. Receive road manager's approval 4. Survey works
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114132&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114132 | C60-ACP-BW-WALLAROO-115.759km | AP100112 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater | WALLAROO | TRYPHINIA | 0 | KM | BW04ML115 | 0.761 | BW04ML115 | 0.761 | KM |  |  |  |  | 115.759 | 115.759 | 2025-06-30 |  |  |  |  | 10 | 3.35 | 0.5 | 10 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT DESIGN 1. Construction of slip and turning lanes 2. Construction of adequate drainage 3. Construction/installation of signage 4. Survey works 5. Achieve TMR/Council approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114140&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114140 | C60-ACP-GA-YUKAN-36.5km | AP200371 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML36 | 0.4799 | GA01ML36 | 0.4799 | KM |  |  |  |  | 36.5 | 36.5 | 2025-06-30 |  |  |  |  | 10 | 4.4 | 2 | 10 | 1 | 100 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 ACCESS POINT DESIGN. Scope may include: 1. Construction of slip/turning lanes 2. Installation of signage 3. Construction of drainage works 4. Road managers's approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115219&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115219 | Access Road Improvement Oaky Ck - Design | GA-03ML | CIVIL | ACCESS ROADS |  | DESIGN | 1 | SITE | 50000 | Goonyella | SARAJI JCT | LAKE VERMONT FORK (NTH JCT) | 0.6999 | KM | GA03ML81 | 0.8 | GA03ML81 | 0.1 | KM |  |  |  |  | 81.8 | 88.1 | 2025-06-30 | SINGLE |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068906&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000068906 | Access Roads Reactive | BW | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 340000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068907&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000068907 | Access Roads Reactive | GA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 340000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068909&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000068909 | Access Roads Reactive | MA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 140000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068908&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000068908 | Access Roads Reactive | NL | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 140000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115669&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115669 | C14 Adj C13 ML Exit Aldoga 11A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.06 | KM | 26730 | Blackwater | ALDOGA | ALDOGA | 0.0599 | KM | BW01ML553 | 0.505 | BW01ML553 | 0.445 | KM |  |  |  |  | 553.505 | 553.445 | 2025-06-30 | GA-02YR |  |  |  | 4.6 | 4.5 | 2 | 4.1 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order for noti-2000115668, C14 Adj C13 ML Lead Aldoga 11A/B where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115670&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115670 | C14 Adj C13 ML Divergent Aldoga 11A/B | BW-23YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 22275 | Blackwater | ALDOGA | ALDOGA | 0.05 | KM | BW23YR553 | 0.55 | BW23YR553 | 0.5999 | KM |  |  |  |  | 553.55 | 553.6 | 2025-06-30 | GA-02YR |  |  |  | 4.6 | 4.5 | 2 | 4.1 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115668&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115668 | C14 Adj C13 ML Lead Aldoga 11A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 22275 | Blackwater | ALDOGA | ALDOGA | 0.05 | KM | BW01ML553 | 0.552 | BW01ML553 | 0.6019 | KM |  |  |  |  | 553.552 | 553.602 | 2025-06-30 | GA-05PL |  |  |  | 4.6 | 4.5 | 2 | 4.1 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115678&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115678 | C14 Adj C13 ML Exit Aldoga 8A/B | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 22275 | Blackwater | ALDOGA | ALDOGA | 0.05 | KM | BW02ML555 | 0.8189 | BW02ML555 | 0.769 | KM |  |  |  |  | 555.819 | 555.769 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti- 2000115677, C14 Adj C13 ML Lead Aldoga 8A/B where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115677&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115677 | C14 Adj C13 ML Lead Aldoga 8A/B | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.011 | KM | 4900 | Blackwater | ALDOGA | ALDOGA | 0.0109 | KM | BW02ML555 | 0.8659 | BW02ML555 | 0.877 | KM |  |  |  |  | 555.866 | 555.877 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115680&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115680 | C14 Adj C13 ML Lead Aldoga 7C/D | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.011 | KM | 4900 | Blackwater | ALDOGA | ALDOGA | 0.0109 | KM | BW02ML555 | 0.877 | BW02ML555 | 0.888 | KM |  |  |  |  | 555.877 | 555.888 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115681&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115681 | C14 Adj C13 ML Exit Aldoga 7C/D | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.075 | KM | 33413 | Blackwater | ALDOGA | ALDOGA | 0.0749 | KM | BW02ML555 | 0.9399 | BW02ML556 | 0.0149 | KM |  |  |  |  | 555.94 | 556.015 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti-2000115680,C14 Adj C13 ML Lead Aldoga 7C/D where the FSCL is mapped to. Tie into the splay rails of Larcom Creek Bridge (BR101460)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115672&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115672 | C14 Adj C13 ML Exit Aldoga 7A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 22275 | Blackwater | ALDOGA | ALDOGA | 0.05 | KM | BW01ML555 | 0.9419 | BW01ML555 | 0.892 | KM |  |  |  |  | 555.942 | 555.892 | 2025-06-30 | GA-02YR |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order for noti-2000115671, C14 Adj C13 ML Lead Aldoga 7A/B where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115671&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115671 | C14 Adj C13 ML Lead Aldoga 7A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.035 | KM | 15592 | Blackwater | ALDOGA | ALDOGA | 0.035 | KM | BW01ML555 | 0.9879 | BW01ML556 | 0.0229 | KM |  |  |  |  | 555.988 | 556.023 | 2025-06-30 | GA-02YR |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Tie into the splay rails of Larcom Creek Bridge (BR101460)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115665&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115665 | C14 Adj C13 ML Lead Bajool 12C/D | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.098 | KM | 46126 | Blackwater | BAJOOL | BAJOOL | 0.098 | KM | BW02ML603 | 0.465 | BW02ML603 | 0.3669 | KM |  |  |  |  | 603.465 | 603.367 | 2025-06-30 | GA-05PL |  |  |  | 3.9 | 4.1 | 2 | 3.9 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut to back of signal BL27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115666&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115666 | C14 Adj C13 ML Exit Bajool 12C/D | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.066 | KM | 31064 | Blackwater | BAJOOL | BAJOOL | 0.066 | KM | BW02ML603 | 0.514 | BW02ML603 | 0.5799 | KM |  |  |  |  | 603.514 | 603.58 | 2025-06-30 | GA-05PL |  |  |  | 3.9 | 4.1 | 2 | 3.9 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti- 2000115665, C14 Adj C13 ML Lead Bajool 12C/D where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115675&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115675 | C14 Adj C13 ML Exit Bajool 12A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 23533 | Blackwater | BAJOOL | BAJOOL | 0.05 | KM | BW01ML603 | 0.515 | BW01ML603 | 0.465 | KM |  |  |  |  | 603.515 | 603.465 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.5 | 2 | 4.1 | 1 | 14.4 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115674&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115674 | C14 Adj C13 ML Lead Bajool 12A/B | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.021 | KM | 9884 | Blackwater | BAJOOL | BAJOOL | 0.021 | KM | BW01ML603 | 0.562 | BW01ML603 | 0.5829 | KM |  |  |  |  | 603.562 | 603.583 | 2025-06-30 | GA-02YR |  |  |  | 3.5 | 4.5 | 2 | 4.1 | 1 | 14.4 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti-2000115675, C14 Adj C13 ML Exit Bajool 12A/B where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115791&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115791 | C14 Adj C13 Black Mtn 12CD Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.098 | KM | 49742 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.098 | KM | GA01ML40 | 0.8699 | GA01ML40 | 0.9679 | KM |  |  |  |  | 40.87 | 40.968 | 2025-06-30 | GA-02ML |  |  |  | 4.2 | 5 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115789&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115789 | C14 Adj C13 Black Mtn 12CD Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.155 | KM | 78674 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.1549 | KM | GA01ML41 | 0.0149 | GA01ML41 | 0.17 | KM |  |  |  |  | 41.015 | 41.17 | 2025-06-30 | GA-42YR |  |  |  | 4.2 | 5 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti-2000115791, C14 Adj C13 Black Mtn 12CD Exit where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115657&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115657 | C14 Adj C13 ML Exit Bluff 9A/B | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.057 | KM | 31832 | Blackwater | BLUFF | BLUFF | 0.057 | KM | BW03ML170 | 0.917 | BW03ML170 | 0.8599 | KM |  |  |  |  | 170.917 | 170.86 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.4 | 2 | 3.7 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115658&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115658 | C14 Adj C13 ML Divergent Bluff 9A/B | BW-04PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.054 | KM | 30157 | Blackwater | BLUFF | BLUFF | 0.0539 | KM | BW04PL170 | 0.9539 | BW04PL170 | 0.9 | KM |  |  |  |  | 170.954 | 170.9 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.4 | 2 | 3.7 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115656&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115656 | C14 Adj C13 ML Lead Bluff 9A/B | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.149 | KM | 83211 | Blackwater | BLUFF | BLUFF | 0.169 | KM | BW03ML170 | 0.9539 | BW03ML171 | 0.1 | KM |  |  |  |  | 170.954 | 171.08 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.4 | 2 | 3.7 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115657,C14 Adj C13 ML Exit Bluff 9A/B where the FSCL is mapped to. Cut to LX5564
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115643&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115643 | C14 Adj C13 ML Divergent Bluff 7C/D | BW-91XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.005 | KM | 2792 | Blackwater | BLUFF | BLUFF | 0.055 | KM | BW91XR171 | 0.1749 | BW91XR171 | 0.23 | KM |  |  |  |  | 171.175 | 171.18 | 2025-06-30 | BW-22YR |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115642&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115642 | C14 Adj C13 ML Exit Bluff 7C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.075 | KM | 41885 | Blackwater | BLUFF | BLUFF | 0.0749 | KM | BW03ML171 | 0.1829 | BW03ML171 | 0.1079 | KM |  |  |  |  | 171.183 | 171.108 | 2025-06-30 | BW-22YR |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti 2000115641- C14 Adj C13 ML Lead Bluff 7C/D, where the FSCL is mapped to. Cut to LX5564
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115641&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115641 | C14 Adj C13 ML Lead Bluff 7C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 27923 | Blackwater | BLUFF | BLUFF | 0.05 | KM | BW03ML171 | 0.23 | BW03ML171 | 0.28 | KM |  |  |  |  | 171.23 | 171.28 | 2025-06-30 | BW-20YR |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115632&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115632 | C14 Adj C13 ML Lead Stowe 12A Pts | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 28385 | Moura | BYELLEE | STOWE | 0.0529 | KM | MA01ML24 | 0.315 | MA01ML24 | 0.3679 | KM |  |  |  |  | 24.315 | 24.368 | 2025-06-30 | BW-02ML |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115634&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115634 | C14 Adj C13 ML Diverg Stowe 12A Pts | MA-02PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.052 | KM | 27849 | Moura | BYELLEE | STOWE | 0.0519 | KM | MA02PL24 | 0.3679 | MA02PL24 | 0.4199 | KM |  |  |  |  | 24.368 | 24.42 | 2025-06-30 | BW-27XR |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115633&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115633 | C14 Adj C13 ML Exit Stowe 12A Pts | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 26778 | Moura | BYELLEE | STOWE | 0.05 | KM | MA01ML24 | 0.4099 | MA01ML24 | 0.46 | KM |  |  |  |  | 24.41 | 24.46 | 2025-06-30 | BW-02ML |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order for noti- 2000115632, C14 Adj C13 ML Lead Stowe 12A Pts where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115602&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115602 | C14 Adj C13 ML Divergent Callemondah 215 | BW-11XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.035 | KM | 22291 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.035 | KM | BW11XR0 | 0.065 | BW11XR0 | 0.1 | KM |  |  |  |  | 0.065 | 0.1 | 2025-06-30 | BW-01ML |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | Remove LX surface, complete undercut and reinstate once finished.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115630&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115630 | C14 Adj C13 ML Exit Callemondah 215A | BW-22YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 31845 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.05 | KM | BW22YR0 | 0.0929 | BW22YR0 | 0.1429 | KM |  |  |  |  | 0.093 | 0.143 | 2025-06-30 | BW-28XR |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | Remove LX surface, complete undercut and reinstate once finished.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115628&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115628 | C14 Adj C13 ML Divergent Callem 214A pts | BW-20YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.056 | KM | 35667 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.056 | KM | BW20YR0 | 0.3659 | BW20YR0 | 0.3099 | KM |  |  |  |  | 0.366 | 0.31 | 2025-06-30 | BW-01ML |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115625&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115625 | C14 Adj C13 ML Lead Calle 214A Pts | BW-20YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.004 | KM | 2547 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.004 | KM | BW20YR0 | 0.3659 | BW20YR0 | 0.3699 | KM |  |  |  |  | 0.366 | 0.37 | 2025-06-30 | BW-23YR |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | Cut to first long bearer of Callemondah 212B
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115627&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115627 | C14 Adj C13 ML Exit Callemondah 214A Pts | BW-08YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.012 | KM | 7642 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.012 | KM | BW08YR533 | 0.808 | BW08YR533 | 0.8199 | KM |  |  |  |  | 533.808 | 533.82 | 2025-06-30 | BW-01ML |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | Tie into Callemondah 401A Toe of Switch
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115734&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115734 | C14 Adj C13 Daly Bay 45AB Lead. | GA-04BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.107 | KM | 67225 | Goonyella | DAL BAY | DAL BAY | 0.1069 | KM | GA04BA3 | 0.8 | GA04BA3 | 0.907 | KM |  |  |  |  | 3.8 | 3.907 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115739&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115739 | C14 Adj C13 Daly Bay 45CD Exit | GA-03BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.015 | KM | 9424 | Goonyella | DAL BAY | DAL BAY | 0.0149 | KM | GA03BA3 | 0.9499 | GA03BA3 | 0.9649 | KM |  |  |  |  | 3.95 | 3.965 | 2025-06-30 | BW-91XR |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | 5209-C14 Adj C13 Daly Bay 45CD Exit This noti to be linked to the work order for noti 2000115737,C14 Adj C13 Daly Bay 45CD Lead where the FSCL has been mapped.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115735&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115735 | C14 Adj C13 Daly Bay 45AB Divergent | GA-03XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.008 | KM | 5026 | Goonyella | DAL BAY | DAL BAY | 0.008 | KM | GA03XR3 | 0.9519 | GA03XR3 | 0.9599 | KM |  |  |  |  | 3.952 | 3.96 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115742&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115742 | C14 Adj C13 Daly Bay 46AB Exit | GA-04BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.01 | KM | 6282 | Goonyella | DAL BAY | DAL BAY | 0.01 | KM | GA04BA3 | 0.9649 | GA04BA3 | 0.9749 | KM |  |  |  |  | 3.965 | 3.975 | 2025-06-30 | BW-54XR |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | 5209-C14 Adj C13 Daly Bay 46AB Exit Need to link to work order for noti 2000115740, C14 Adj C13 Daly Bay 46AB Lead where the FSCL was mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115737&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115737 | C14 Adj C13 Daly Bay 45CD Lead. | GA-03BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 30785 | Goonyella | DAL BAY | DAL BAY | 0.049 | KM | GA03BA4 | 0.0109 | GA03BA4 | 0.0599 | KM |  |  |  |  | 4.011 | 4.06 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115740&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115740 | C14 Adj C13 Daly Bay 46AB Lead. | GA-04BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.04 | KM | 36125 | Goonyella | DAL BAY | DAL BAY | 0.05 | KM | GA04BA4 | 0.0299 | GA04BA4 | 0.08 | KM |  |  |  |  | 4.03 | 4.088 | 2025-06-30 | BW-04ML |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115743&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115743 | C14 Adj C13 Daly Bay 47AB Lead. | GA-05BD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.052 | KM | 32670 | Goonyella | DALY BAY ARRIVAL RD 5 | DALY BAY ARRIVAL RD 5 | 0.0519 | KM | GA05BD3 | 0.9 | GA05BD3 | 0.9519 | KM |  |  |  |  | 3.9 | 3.952 | 2025-06-30 | BW-04ML |  |  |  | 3.9 | 2.6 | 2 | 3.3 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115745&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115745 | C14 Adj C13 Daly Bay 47AB Exit | GA-05BD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 30785 | Goonyella | DALY BAY ARRIVAL RD 5 | DALY BAY ARRIVAL RD 5 | 0.049 | KM | GA05BD4 | 0.001 | GA05BD4 | 0.05 | KM |  |  |  |  | 4.001 | 4.05 | 2025-06-30 | BW-39XR |  |  |  | 3.9 | 2.6 | 2 | 3.3 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | 5209-C14 Adj C13 Daly Bay 47AB Exit Need to link to the work order of noti 2000115743, C14 Adj C13 Daly Bay 47AB Lead where the FSCL has been mapped.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115744&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115744 | C14 Adj C13 Daly Bay 47AB Divergent | GA-04XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.059 | KM | 37068 | Goonyella | DALY BAY ARRIVAL RD 5 | DALY BAY ARRIVAL RD 5 | 0.079 | KM | GA04XR4 | 0.001 | GA04XR4 | 0.08 | KM |  |  |  |  | 4.001 | 4.06 | 2025-06-30 | BW-04ML |  |  |  | 3.9 | 2.6 | 2 | 3.3 | 1 | 15.2 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115648&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115648 | C14 Adj C13 ML Exit Dingo 2A Pts | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 34392 | Blackwater | DINGO | DINGO | 0.05 | KM | BW04ML141 | 0.686 | BW04ML141 | 0.7359 | KM |  |  |  |  | 141.686 | 141.736 | 2025-06-30 | MA-01ML |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115647&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115647 | C14 Adj C13 ML Lead Dingo 2A Pts | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 34392 | Blackwater | DINGO | DINGO | 0.05 | KM | BW04ML141 | 0.768 | BW04ML141 | 0.8179 | KM |  |  |  |  | 141.768 | 141.818 | 2025-06-30 | MA-02PL |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti 2000115648- C14 Adj C13 ML Exit Dingo 2A Pts where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115639&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115639 | C14 Adj C13 ML Exit Duaringa 7C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.059 | KM | 42193 | Blackwater | DUARINGA | DUARINGA | 0.0719 | KM | BW03ML104 | 0.9589 | BW03ML104 | 0.887 | KM |  |  |  |  | 104.959 | 104.9 | 2025-06-30 | BW-20YR |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut to LX750
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115638&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115638 | C14 Adj C13 ML Lead Duaringa 7C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.117 | KM | 83672 | Blackwater | DUARINGA | DUARINGA | 0.117 | KM | BW03ML105 | 0.003 | BW03ML105 | 0.1199 | KM |  |  |  |  | 105.003 | 105.12 | 2025-06-30 | BW-08CT |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti 2000115639- C14 Adj C13 ML Exit Duaringa 7C/D where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115659&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115659 | C14 Adj C13 ML Lead Edungalba 2B Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.006 | KM | 2652 | Blackwater | EDUNGALBA | EDUNGALBA | 0.008 | KM | BW03ML84 | 0.796 | BW03ML84 | 0.788 | KM |  |  |  |  | 84.796 | 84.79 | 2025-06-30 | GA-01ML |  |  |  | 4.3 | 3.8 | 2 | 3.8 | 1 | 16.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Tie in with Edungalba 12C/D
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115661&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115661 | C14 Adj C13 ML Divergent Edungalba 2B | BW-09SD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.044 | KM | 19450 | Blackwater | EDUNGALBA | EDUNGALBA | 0.0439 | KM | BW09SD84 | 0.796 | BW09SD84 | 0.8399 | KM |  |  |  |  | 84.796 | 84.84 | 2025-06-30 | GA-01ML |  |  |  | 4.3 | 3.8 | 2 | 3.8 | 1 | 16.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115660&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115660 | C14 Adj C13 ML Exit Edungalba 2B Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.084 | KM | 37133 | Blackwater | EDUNGALBA | EDUNGALBA | 0.084 | KM | BW03ML84 | 0.8309 | BW03ML84 | 0.915 | KM |  |  |  |  | 84.831 | 84.915 | 2025-06-30 | GA-01ML |  |  |  | 4.3 | 3.8 | 2 | 3.8 | 1 | 16.3 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115659, C14 Adj C13 ML Lead Edungalba 2B Pts to where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115663&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115663 | C14 Adj C13 ML Exit Edungalba 2A Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.081 | KM | 35807 | Blackwater | EDUNGALBA | EDUNGALBA | 0.081 | KM | BW03ML85 | 0.1409 | BW03ML85 | 0.0599 | KM |  |  |  |  | 85.141 | 85.06 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.8 | 2 | 3.8 | 1 | 15.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115664&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115664 | C14 Adj C13 ML Divergent Edungalba 2A | BW-09SD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.056 | KM | 24755 | Blackwater | EDUNGALBA | EDUNGALBA | 0.056 | KM | BW09SD85 | 0.1759 | BW09SD85 | 0.1199 | KM |  |  |  |  | 85.176 | 85.12 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.8 | 2 | 3.8 | 1 | 15.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115662&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115662 | C14 Adj C13 ML Lead Edungalba 2A Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.054 | KM | 23871 | Blackwater | EDUNGALBA | EDUNGALBA | 0.0539 | KM | BW03ML85 | 0.1759 | BW03ML85 | 0.23 | KM |  |  |  |  | 85.176 | 85.23 | 2025-06-30 | GA-01ML |  |  |  | 4.1 | 3.8 | 2 | 3.8 | 1 | 15.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order for the noti- 2000115663, C14 Adj C13 ML Exit Edungalba 2A Pts where the FSCL is mapped.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115756&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115756 | C14 Adj C13 Jilalan 7CD Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.026 | KM | 23456 | Goonyella | JILALAN | JILALAN | 0.0389 | KM | GA01ML17 | 0.3499 | GA01ML17 | 0.389 | KM |  |  |  |  | 17.363 | 17.389 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 16.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115754&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115754 | C14 Adj C13 Jilalan 7CD Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 8119 | Goonyella | JILALAN | JILALAN | 0.0089 | KM | GA01ML17 | 0.4209 | GA01ML17 | 0.4299 | KM |  |  |  |  | 17.421 | 17.43 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 16.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link to work order for noti-2000115756, C14 Adj C13 Jilalan 7CD Exit where the FSCL is mapped.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115751&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115751 | 5213-C14 Adj C13 Jilalan 46AB Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.012 | KM | 10825 | Goonyella | JILALAN | JILALAN | 0.0109 | KM | GA01ML17 | 0.4299 | GA01ML17 | 0.441 | KM |  |  |  |  | 17.43 | 17.442 | 2025-06-30 | GA-25CT |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 16.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115753&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115753 | C14 Adj C13 Jilalan 46AB Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.014 | KM | 12630 | Goonyella | JILALAN | JILALAN | 0.014 | KM | GA01ML17 | 0.4729 | GA01ML17 | 0.4869 | KM |  |  |  |  | 17.473 | 17.487 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 16.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link to the work order for noti- 2000115751, C14 Adj C13 Jilalan 46AB Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115752&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115752 | C14 Adj C13 Jilalan 46AB Diverget | GA-01YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.057 | KM | 51423 | Goonyella | JILALAN | JILALAN | 0.057 | KM | GA01YR17 | 0.4729 | GA01YR17 | 0.53 | KM |  |  |  |  | 17.473 | 17.53 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 16.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115781&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115781 | C14 Adj C13 Jilalan 81AB Divergent | GA-28CT | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.044 | KM | 39695 | Goonyella | JILALAN | JILALAN | 0.0439 | KM | GA28CT22 | 0.46 | GA28CT22 | 0.504 | KM |  |  |  |  | 22.046 | 22.504 | 2025-06-30 | GA-01PL |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115768&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115768 | C14 Adj C13 Jilalan Yard 11AB Lead | GA-02YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 12659 | Goonyella | JILALAN | JILALAN | 0.004 | KM | GA02YR22 | 0.16 | GA02YR22 | 0.164 | KM |  |  |  |  | 22.55 | 22.559 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.8 | 2 | 4.2 | 1 | 16.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115783&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115783 | C14 Adj C13 Jilalan Bypass 11AB Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 8119 | Goonyella | JILALAN | JILALAN | 0.0089 | KM | GA01ML22 | 0.55 | GA01ML22 | 0.559 | KM |  |  |  |  | 22.55 | 22.559 | 2025-06-30 | GA-01PL |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115785&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115785 | 5213- C14 Adj C13 Jil Bypass 11AB Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.012 | KM | 10825 | Goonyella | JILALAN | JILALAN | 0.012 | KM | GA01ML22 | 0.5929 | GA01ML22 | 0.6049 | KM |  |  |  |  | 22.593 | 22.605 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti- 2000115783, C14 Adj C13 Jilalan Bypass 11AB Lead where the FSCL has been mapped to. Ties right into the back of 82AB which is in FY24 - tie into FY24 work.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115772&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115772 | C14 Adj C13 Jilalan 84AB Divergent | GA-02YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 44205 | Goonyella | JILALAN | JILALAN | 0.049 | KM | GA02YR23 | 0.4099 | GA02YR23 | 0.459 | KM |  |  |  |  | 23.41 | 23.459 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.8 | 2 | 4.2 | 1 | 16.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115771&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115771 | C14 Adj C13 Jilalan 84AB Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.067 | KM | 60444 | Goonyella | JILALAN | JILALAN | 0.067 | KM | GA01ML23 | 0.4929 | GA01ML23 | 0.56 | KM |  |  |  |  | 23.493 | 23.56 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.8 | 2 | 4.2 | 1 | 16.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115766&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115766 | C14 Adj C13 Jilalan 106B Divergent | GA-03YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.022 | KM | 30945 | Goonyella | JILALAN YARD DOWN | JILALAN YARD DOWN | 0.0219 | KM | GA03YR22 | 0.0899 | GA03YR22 | 0.112 | KM |  |  |  |  | 22.09 | 22.112 | 2025-06-30 | GA-05BD |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115767&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115767 | C14 Adj C13 Jilalan 106B Exit | GA-02YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.022 | KM | 30945 | Goonyella | JILALAN YARD DOWN | JILALAN YARD DOWN | 0.0219 | KM | GA02YR22 | 0.0899 | GA02YR22 | 0.112 | KM |  |  |  |  | 22.09 | 22.112 | 2025-06-30 | GA-05BD |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115765&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115765 | C14 Adj C13 Jilalan 106B Lead | GA-03YR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.012 | KM | 16879 | Goonyella | JILALAN YARD DOWN | JILALAN YARD DOWN | 0.012 | KM | GA03YR22 | 0.1479 | GA03YR22 | 0.16 | KM |  |  |  |  | 22.148 | 22.16 | 2025-06-30 | GA-05BD |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 19 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Link this noti to the work order for noti- 2000115766, C14 Adj Jilalan 106B Divergent where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115644&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115644 | C14 Adj C13 ML Lead Kabra 12A/B | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.113 | KM | 66492 | Blackwater | KABRA | KABRA | 0.1 | KM | BW04ML13 | 0.3629 | BW04ML13 | 0.263 | KM |  |  |  |  | 13.363 | 13.25 | 2025-06-30 | BW-11YR |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115646&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115646 | C14 Adj C13 ML Divergent Kabra 12A/B | BW-54XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.107 | KM | 62962 | Blackwater | KABRA | KABRA | 0.1069 | KM | BW54XR13 | 0.3629 | BW54XR13 | 0.4699 | KM |  |  |  |  | 13.363 | 13.47 | 2025-06-30 | MA-01ML |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 | 257 | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Tie in Kabra 12C/D undercut
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115651&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115651 | C14 Adj C13 ML Exit Kabra 12C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.097 | KM | 57077 | Blackwater | KABRA | KABRA | 0.097 | KM | BW03ML13 | 0.4099 | BW03ML13 | 0.507 | KM |  |  |  |  | 13.41 | 13.507 | 2025-06-30 | BW-04ML |  |  |  | 3.5 | 3.4 | 2 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti with the work order for noti- 2000115650, C14 Adj C13 ML Lead Kabra 12C/D where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115645&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115645 | C14 Adj C13 ML Exit Kabra 12A/B | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.055 | KM | 32363 | Blackwater | KABRA | KABRA | 0.064 | KM | BW04ML13 | 0.4359 | BW04ML13 | 0.5 | KM |  |  |  |  | 13.445 | 13.5 | 2025-06-30 | MA-01ML |  |  |  | 3.5 | 3.35 | 2 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti- 2000115644, C14 Adj C13 ML Lead Kabra 12A/B where the FSCL is mapped to. Tie in with FY24 C14 (2000094928)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115650&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115650 | C14 Adj C13 ML Lead Kabra 12C/D | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.051 | KM | 30010 | Blackwater | KABRA | KABRA | 0.0609 | KM | BW03ML13 | 0.559 | BW03ML13 | 0.6199 | KM |  |  |  |  | 13.559 | 13.61 | 2025-06-30 | BW-04ML |  |  |  | 3.5 | 3.4 | 2 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Tie into Kabra 11/AB's Toe of Switch
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120467&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120467 | C14 Adj C13 Kaili 7C/D Exit | NL-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 51110 | Newlands | KAILI | KAILI | 0.05 | KM | NL02ML6 | 0.923 | NL02ML6 | 0.9729 | KM | [6 empty] | 2025-06-30 | MAIN |  | 6.923 | 6.973 | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order for noti- 2000120466, C14 Adj C13 Kaili 7C/D Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120466&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120466 | C14 Adj C13 Kaili 7C/D Lead | NL-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 9199 | Newlands | KAILI | KAILI | 0.0089 | KM | NL02ML6 | 0.884 | NL02ML6 | 0.893 | KM | [6 empty] | 2025-06-30 | MAIN |  | 6.884 | 6.893 | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Tie into Kaili 8A/B Adj C14
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120464&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120464 | C14 Adj C13 Kaili 8A/B Exit | NL-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 51110 | Newlands | KAILI | KAILI | 0.05 | KM | NL02ML6 | 0.8389 | NL02ML6 | 0.789 | KM |  |  |  |  | 6.839 | 6.879 | 2025-06-30 | MAIN |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order for noti- 2000120463, C14 Adj C13 Kaili 8A/B Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120463&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120463 | C14 Adj C13 Kaili 8A/B Lead | NL-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.009 | KM | 9199 | Newlands | KAILI | KAILI | 0.0089 | KM | NL02ML6 | 0.875 | NL02ML6 | 0.884 | KM |  |  |  |  | 6.875 | 6.884 | 2025-06-30 | MAIN |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Tie into Kaili 7C/D Adj C14
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120465&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120465 | C14 Adj C13 Kaili 8A/B Divergent | NC-13XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.008 | KM | 8177 | Newlands | KAILI | KAILI | 0.008 | KM | NC13XR1165 | 0.7159 | NC13XR1165 | 0.7239 | KM |  |  |  |  | 1165.716 | 1165.724 | 2025-06-30 | MAIN |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120503&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120503 | C14 Adj C13 Kaili 7C/D Divergent | NC-12XR | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.008 | KM | 8177 | Newlands | KAILI | KAILI | 0.008 | KM | NC12XR1165 | 0.878 | NC12XR1165 | 0.886 | KM |  |  |  |  | 1165.878 | 1165.886 | 2025-06-30 | CROSSOVER |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115719&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115719 | C14 Adj C13 Mallawa 7CD Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.072 | KM | 40380 | Goonyella | MALLAWA | MALLAWA | 0.0719 | KM | GA01ML167 | 0.75 | GA01ML167 | 0.8219 | KM |  |  |  |  | 167.75 | 167.822 | 2025-06-30 | BW-03ML |  |  |  | 4.5 | 2.4 | 2 | 3.2 | 1 | 14.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115717&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115717 | C14 Adj C13 Mallawa 7CD Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.061 | KM | 34211 | Goonyella | MALLAWA | MALLAWA | 0.0609 | KM | GA01ML167 | 0.894 | GA01ML167 | 0.9549 | KM |  |  |  |  | 167.894 | 167.955 | 2025-06-30 | BW-02ML |  |  |  | 4.5 | 2.4 | 2 | 3.2 | 1 | 14.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti- 2000115719, C14 Adj C13 Mallawa 7CD Exit where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115720&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115720 | C14 Adj C13 Mallawa 8AB Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.053 | KM | 29724 | Goonyella | MALLAWA | MALLAWA | 0.0529 | KM | GA01ML168 | 0.05 | GA01ML168 | 0.1029 | KM |  |  |  |  | 168.05 | 168.103 | 2025-06-30 | BW-03ML |  |  |  | 4.2 | 2.4 | 2 | 3.2 | 1 | 13.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115722&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115722 | C14 Adj C13 Mallawa 8AB Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 28042 | Goonyella | MALLAWA | MALLAWA | 0.05 | KM | GA01ML168 | 0.1499 | GA01ML168 | 0.2 | KM |  |  |  |  | 168.15 | 168.2 | 2025-06-30 | BW-03ML |  |  |  | 4.2 | 2.4 | 2 | 3.2 | 1 | 13.5 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti- 2000115720 , C14 Adj C13 Mallawa 8AB Lead, where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115711&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115711 | C14 Adj C13 Peak Downs ER.2D Lead | GA-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.043 | KM | 26437 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0429 | KM | GA05PL45 | 0.2899 | GA05PL45 | 0.333 | KM |  |  |  |  | 45.29 | 45.333 | 2025-06-30 | BW-02ML |  |  |  | 4.1 | 2.1 | 2 | 3.1 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115712&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115712 | C14 Adj C13 Peak Downs ER.2D Diverg | GA-20SD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.036 | KM | 22133 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0359 | KM | GA20SD45 | 0.3639 | GA20SD45 | 0.4 | KM |  |  |  |  | 45.364 | 45.4 | 2025-06-30 | BW-02ML |  |  |  | 4.1 | 2.1 | 2 | 3.1 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115713&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115713 | C14 Adj C13 Peak Downs ER.2D Exit | GA-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.036 | KM | 22133 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0459 | KM | GA05PL45 | 0.3639 | GA05PL45 | 0.4099 | KM |  |  |  |  | 45.364 | 45.4 | 2025-06-30 | BW-02ML |  |  |  | 4.1 | 2.1 | 2 | 3.1 | 1 | 12.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti- 2000115711, C14 Adj C13 Peak Downs ER.2D Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115724&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115724 | C14 Adj C13 Peak Downs ER.2E Diverg | GA-20SD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.02 | KM | 12296 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0599 | KM | GA20SD45 | 0.5799 | GA20SD45 | 0.64 | KM |  |  |  |  | 45.58 | 45.6 | 2025-06-30 | BW-05SD |  |  |  | 3.5 | 2.4 | 2 | 3.2 | 1 | 8.4 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115725&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115725 | C14 Adj C13 Peak Downs ER.2E Exit | GA-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.04 | KM | 24593 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.04 | KM | GA05PL45 | 0.5999 | GA05PL45 | 0.64 | KM |  |  |  |  | 45.6 | 45.64 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 2.4 | 2 | 3.2 | 1 | 8.4 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115723&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115723 | C14 Adj C13 Peak Downs ER.2E Lead | GA-05PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.047 | KM | 28897 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.047 | KM | GA05PL45 | 0.673 | GA05PL45 | 0.7199 | KM |  |  |  |  | 45.673 | 45.72 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 2.4 | 2 | 3.2 | 1 | 8.4 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti- 2000115725, C14 Adj C13 Peak Downs ER.2E Exit where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120460&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120460 | C14 Adj C13 Sonoma 9A Lead | NL-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 50122 | Newlands | SONOMA | SONOMA | 0.066 | KM | NL05ML0 | 0.9509 | NL05ML1 | 0.001 | KM |  |  |  |  | 0.951 | 1.001 | 2025-06-30 | BALLOON |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120461&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120461 | C14 Adj C13 Sonoma 9A Exit | NL-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 50122 | Newlands | SONOMA | SONOMA | 0.05 | KM | NL05ML1 | 0.0179 | NL05ML1 | 0.068 | KM |  |  |  |  | 1.034 | 1.084 | 2025-06-30 | BALLOON |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order of noti- 2000120460,C14 Adj C13 Sonoma 9A Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120462&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120462 | C14 Adj C13 Sonoma 9A Divergent | NL-05ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 50122 | Newlands | SONOMA | SONOMA | 0.05 | KM | NL05ML3 | 0.504 | NL05ML3 | 0.554 | KM |  |  |  |  | 3.501 | 3.551 | 2025-06-30 | BALLOON |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 8.75 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order of noti- 2000120460,C14 Adj C13 Sonoma 9A Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115636&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115636 | C14 Adj C13 ML Exit Stowe 7A Pts. | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 26778 | Moura | STOWE | GRAHAM | 0.05 | KM | MA01ML26 | 0.222 | MA01ML26 | 0.272 | KM |  |  |  |  | 26.222 | 26.272 | 2025-06-30 | BW-02ML |  |  |  | 3.9 | 1.3 | 2 | 2.6 | 1 | 10.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order of noti-2000115635, C14 Adj C13 ML Lead Stowe 7A Pts where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115635&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115635 | C14 Adj C13 ML Lead Stowe 7A Pts | MA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 26778 | Moura | STOWE | GRAHAM | 0.05 | KM | MA01ML26 | 0.3049 | MA01ML26 | 0.3549 | KM |  |  |  |  | 26.305 | 26.355 | 2025-06-30 | BW-02ML |  |  |  | 3.9 | 1.3 | 2 | 2.6 | 1 | 10.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115637&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115637 | C14 Adj C13 ML Divergent Stowe 7A Pts. | MA-02PL | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 26778 | Moura | STOWE | GRAHAM | 0.05 | KM | MA02PL26 | 0.4779 | MA02PL26 | 0.4279 | KM |  |  |  |  | 26.478 | 26.428 | 2025-06-30 | BW-02ML |  |  |  | 3.9 | 1.3 | 2 | 2.6 | 1 | 10.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115757&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115757 | C14 Adj C13 Tootoolah 8AB Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.14 | KM | 70074 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.14 | KM | GA01ML132 | 0.4699 | GA01ML132 | 0.6099 | KM |  |  |  |  | 132.47 | 132.61 | 2025-06-30 | GA-01ML |  |  |  | 3.6 | 4.7 | 2 | 4.1 | 1 | 14.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115759&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115759 | C14 Adj C13 Tootoolah 8AB Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.055 | KM | 27529 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.055 | KM | GA01ML132 | 0.655 | GA01ML132 | 0.7099 | KM |  |  |  |  | 132.655 | 132.71 | 2025-06-30 | GA-01ML |  |  |  | 3.6 | 4.7 | 2 | 4.1 | 1 | 14.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link noti to the work order for noti- 2000115757, C14 Adj C13 Tootoolah 8AB Lead where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115762&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115762 | C14 Adj C13 Tootoolah 12CD Exit | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.036 | KM | 18019 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.0359 | KM | GA01ML132 | 0.8399 | GA01ML132 | 0.876 | KM |  |  |  |  | 132.84 | 132.876 | 2025-06-30 | GA-04BA |  |  |  | 3.9 | 4.7 | 2 | 4.1 | 1 | 15.9 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115760&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115760 | C14 Adj C13 Tootoolah 12CD Lead | GA-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.049 | KM | 24525 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.049 | KM | GA01ML132 | 0.921 | GA01ML132 | 0.9699 | KM |  |  |  |  | 132.921 | 132.97 | 2025-06-30 | GA-04BA |  |  |  | 3.9 | 4.7 | 2 | 4.1 | 1 | 15.9 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Need to link this noti to the work order for noti-2000115762, C14 Adj C13 Tootoolah 12CD Exit, where the FSCL is mapped to.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115654&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115654 | C14 Adj C13 ML Exit Warren 101A Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 35316 | Blackwater | WARREN | WARREN | 0.05 | KM | BW03ML23 | 0.278 | BW03ML23 | 0.328 | KM |  |  |  |  | 23.278 | 23.328 | 2025-06-30 | GA-01ML |  |  |  | 4 | 3.4 | 2 | 3.7 | 1 | 14.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Check with Reagan for Extension
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115655&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115655 | C14 Adj C13 ML Divergent Warren 101A | BW-05SD | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.052 | KM | 36728 | Blackwater | WARREN | WARREN | 0.0519 | KM | BW05SD23 | 0.328 | BW05SD23 | 0.38 | KM |  |  |  |  | 23.328 | 23.38 | 2025-06-30 | GA-01ML |  |  |  | 4 | 3.4 | 2 | 3.7 | 1 | 14.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115653&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115653 | C14 Adj C13 ML Lead Warren 101A Pts | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.125 | KM | 88290 | Blackwater | WARREN | WARREN | 0.125 | KM | BW03ML23 | 0.3599 | BW03ML23 | 0.4849 | KM |  |  |  |  | 23.36 | 23.485 | 2025-06-30 | GA-01ML |  |  |  | 4 | 3.4 | 2 | 3.7 | 1 | 14.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti 2000115654- C14 Adj C13 ML Exit Warren 101A Pts where the FSCL is mapped to. Cut to Crossing (No LX ID?)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126845&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126845 | FY25 C01 Plant Depreciation - BW | BW | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -3123188 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126846&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126846 | FY25 C01 Plant Depreciation - GA | GA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -2325778 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126847&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126847 | FY25 C01 Plant Depreciation - MA | MA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -265803 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126849&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126849 | FY25 C01 Plant Depreciation - NL | NL | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -332254 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115883&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115883 | C01-BU-BW-AROONA-103.062KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.61 | KM | 1237505 | Blackwater | AROONA | DUARINGA | 1.935 | KM | BW03ML102 | 0.8399 | BW03ML104 | 0.8259 | KM |  |  |  |  | 103.062 | 104.664 | 2025-06-30 | DOWN |  |  |  | 4.8 | 3.35 | 2 | 3.6 | 1 | 17.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Duaringa 11AB up to tie into FY25 C14 adjacent near Duaringa 7CD. Cut through AT site at 103.900km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115876&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115876 | C01-BU-BW-BAJOOL-613.220KM-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.215 | KM | 2027455 | Blackwater | BAJOOL | ARCHER | 1.925 | KM | BW01ML613 | 0.1799 | BW01ML615 | 0.1 | KM |  |  |  |  | 613.22 | 615.43 | 2025-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.8 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Oaky Creek Bridge to Bajool AR1.2A. Cut through AT site at 615.150km. Notification split out 2000116911 to C14 (excavator undercutters to undercut through the AT Site). Lower chainage moved due to bridge end, higher chainage moved to match local formation job, if single line cut out @ 615.150 AT site. NOTIFICATION UPDATED- start, end marker, distance and noti description
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115895&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115895 | C01-BU-GA-BALOOK-74.700KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.151 | KM | 792835 | Goonyella | BALOOK | WANDOO | 1.1359 | KM | GA02ML74 | 0.6999 | GA02ML75 | 0.8599 | KM |  |  |  |  | 74.7 | 75.875 | 2025-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.2 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Balook 7A/B to Three Mile Ck Bridge
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115907&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115907 | C01-BU-GA-BALOOK-76.100KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.76 | KM | 523505 | Goonyella | BALOOK | WANDOO | 0.76 | KM | GA02ML76 | 0.1 | GA02ML76 | 0.8599 | KM |  |  |  |  | 76.1 | 76.86 | 2025-06-30 | UP |  |  |  | 4.3 | 4.8 | 2 | 4.2 | 1 | 18.2 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115895, where the FSCL is mapped to. Condition Based Cut from Three Mile Ck Bridge. At site at the 76.783km- originally C14 mainline scope, rolled over to C01.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123264&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000123264 | C01-BU-MA-BELLDEEN-155.600KM-MAIN. | MA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 6.605 | KM | 2220017 | Moura | BELLDEEN | MOURA MINE JCT | 6.605 | KM | MA01ML155 | 0.5999 | MA01ML162 | 0.2 | KM |  |  |  |  | 155.6 | 162.2 | 2025-06-30 | MAIN |  |  |  | 4 | 1.1 | 2 | 2.5 | 1 | 10 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | NWSC |  | 20250807 | Condition Based Cut from LX6045 to 50m from 4 Mile Ck Splays (BR400030) Other info: LX6047 - Public LX recently renewed in FY23. Potential to cut out (159.480km - 159.510km) LX6049 - Private LX (161.845km)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123265&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000123265 | C01-BU-MA-BELLDEEN-165.300KM-MAIN | MA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.501 | KM | 504503 | Moura | BELLDEEN | MOURA MINE JCT | 1.5009 | KM | MA01ML165 | 0.2999 | MA01ML166 | 0.8 | KM |  |  |  |  | 165.3 | 166.8 | 2025-06-30 | MAIN |  |  |  | 4 | 1.1 | 2 | 2.5 | 1 | 10 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order of noti-2000123264, where the FSCL is mapped to. Condition Based Cut from 165.300km to 166.800km Other info: LX6050 - Private LX (166.030km)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115893&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115893 | C01-BU-GA-BOLINGBROKE-60.600KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.499 | KM | 3148948 | Goonyella | BOLINGBROKE | BALOOK | 3.499 | KM | GA02ML60 | 0.5999 | GA02ML64 | 0.1 | KM |  |  |  |  | 60.6 | 64.1 | 2025-06-30 | UP |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from turnout Bolingbroke 12AB through to FY21 UC / bridge at 64.100km. Cut through crossing 5763 at 63.0km pending site considerations
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115894&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115894 | C01-BU-GA-BOLINGBROKE-72.400KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.051 | KM | 1412777 | Goonyella | BOLINGBROKE | BALOOK | 2.051 | KM | GA02ML72 | 0.4 | GA02ML74 | 0.45 | KM |  |  |  |  | 72.4 | 74.45 | 2025-06-30 | UP |  |  |  | 4.3 | 5 | 2 | 4.2 | 1 | 18.2 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115895, where the FSCL is mapped to. Condition Based Cut from 72.4km through to Balook 8C/D
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115898&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115898 | C01-BU-GA-BRAESIDE-110.230KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4.302 | KM | 2534210 | Goonyella | BRAESIDE | MINDI | 4.3019 | KM | GA02ML110 | 0.23 | GA02ML114 | 0.53 | KM |  |  |  |  | 110.23 | 114.53 | 2025-06-30 | UP |  |  |  | 5 | 4.4 | 2 | 4 | 1 | 21.3 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Cooper Creek Bridge through to FY22 UC Cut through AT site at 111km and crossing 5792 pending site considerations. Note: scope adjusted at bulk upload (shortened to account for bridge at low km end and past scope at high km end). Title corrected post bulk upload. 13.04.23
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115887&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115887 | C01-BU-GA-BRAESIDE-116.920KM-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.003 | KM | 2336220 | Goonyella | BRAESIDE | MINDI | 3.003 | KM | GA01ML116 | 0.92 | GA01ML119 | 0.92 | KM |  |  |  |  | 116.92 | 119.92 | 2025-06-30 | DOWN |  |  |  | 4.4 | 4.4 | 2 | 4 | 1 | 17.7 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | Condition Based Tie into FY23 Undercut at 116.92km (2000074515) through to FY22 UC at 119.92. Cut through crossing at 5795 pending site considerations
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125871&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000125871 | C01-BU-BW-BURNGROVE-0.400km-MAIN. | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4.911 | KM | 2884061 | Blackwater | BURNGROVE | CREW | 4.7629 | KM | BW08ML0 | 0.4 | BW08ML5 | 0.2 | KM |  |  |  |  | 0.4 | 5.2 | 2024-06-30 | MAINLINE |  |  |  | 3.5 | 1.2 | 2 | 3 | 1 | 10.5 | 185 | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Notification in process | NWSC |  | 20250630 | Highly fouled ballast with severe patches Moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 189 created - requires a split between C01 and C14 (0.050 - 0.400 C14; 0.400 - 5.200 C01)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115889&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115889 | C01-BU-GA-DALYBAY CROSSOVER-8.308KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.141 | KM | 1548172 | Goonyella | DALYBAY CROSSOVER | PRAGUELANDS | 1.129 | KM | GA02ML8 | 0.3499 | GA02ML9 | 0.4699 | KM |  |  |  |  | 8.308 | 9.44 | 2025-06-30 | UP |  |  |  | 5 | 4.6 | 2 | 4.1 | 1 | 22.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Daly Bay 9A/B to Grasstree Beach Rd Bridge Moved due to bridge end and points. NOTIFICATION UPDATED- start marker, end marker, distance and noti description
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074467&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000074467 | C01-BU-BW-DINGO-146.500KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.544 | KM | 1727326 | Blackwater | DINGO | UMOLO | 1.544 | KM | BW03ML146 | 0.5 | BW03ML148 | 0 | KM |  |  |  |  | 146.5 | 148 | 2025-06-30 |  |  |  |  | 4 | 3.35 | 2 | 3.35 | 1 | 13.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | * 22.03.2021 10:29:25 AUSQLD Tracy Holmes (R870040) * Charlevue Creek is @148.140km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115884&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115884 | C01-BU-BW-DUARINGA-105.600KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.179 | KM | 2443496 | Blackwater | DUARINGA | WALLAROO | 3.1789 | KM | BW03ML105 | 0.5999 | BW03ML108 | 0.7439 | KM |  |  |  |  | 105.6 | 108.744 | 2025-06-30 | DOWN |  |  |  | 4.3 | 3.35 | 2 | 3.6 | 1 | 15.3 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Start cut from Seven Mile CK Bridge and tie into FY21 UC at 108.744km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115881&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115881 | C01-BU-BW-GOGANGO-61.880KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.695 | KM | 2102170 | Blackwater | GOGANGO | GRANTLEIGH | 2.725 | KM | BW03ML60 | 0.8499 | BW03ML63 | 0.5709 | KM |  |  |  |  | 60.88 | 63.571 | 2025-06-30 | DOWN |  |  |  | 4.5 | 3.35 | 2 | 3.6 | 1 | 16.2 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Gogango Ck Bridge Rollout to FY21 undercutting scope at 63.571km. Cut through LX1814 pending CE and diversion considerations.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115878&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115878 | C01-BU-BW-GRACEMERE-9.630KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.536 | KM | 1385188 | Blackwater | GRACEMERE | KABRA | 1.4859 | KM | BW03ML9 | 0.63 | BW03ML11 | 0.1 | KM |  |  |  |  | 9.63 | 11.15 | 2025-06-30 | DOWN |  |  |  | 3.2 | 3.35 | 2 | 3.6 | 1 | 11.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti- 2000115877, Rocklands -Gracemere Down where the FSCL is mapped to. Condition Based Cut from Gracemere 80A to 11.100km where fouling improves before the curve. No reason for adjusting cut in/ cut out. NOTIFICATION UPDATED- end marker and distance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115890&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115890 | C01-BU-GA-HATFIELD-49.950KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.483 | KM | 1719075 | Goonyella | HATFIELD | BOLINGBROKE | 2.483 | KM | GA02ML49 | 0.9499 | GA02ML52 | 0.45 | KM |  |  |  |  | 49.95 | 52.45 | 2025-06-30 | UP |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 22.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Hatfield 12C/D through to Bolingbroke Ck. Cut through crossing 6475 at 50.780km pending site considerations.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115891&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115891 | C01-BU-GA-HATFIELD-52.670KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.34 | KM | 927733 | Goonyella | HATFIELD | BOLINGBROKE | 1.34 | KM | GA02ML52 | 0.67 | GA02ML54 | 0.0309 | KM |  |  |  |  | 52.67 | 54.031 | 2025-06-30 | UP |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 22.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115890, where the FSCL is mapped to. Condition Based Cut from Bolingbroke CK through to FY24 undercut. Cut through crossing 5757 at 53.220km pending site considerations
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115892&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115892 | C01-BU-GA-HATFIELD-55.850KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.541 | KM | 1759231 | Goonyella | HATFIELD | BOLINGBROKE | 2.611 | KM | GA02ML55 | 0.8499 | GA02ML58 | 0.45 | KM |  |  |  |  | 55.85 | 58.38 | 2025-06-30 | UP |  |  |  | 4.7 | 5 | 2 | 4.2 | 1 | 19.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115890, where the FSCL is mapped to. Condition Based Tie cut in with FY24 undercut at 55.850km (2000103599) through to FY24 UC at 58.45km Cut through crossing 5760 at 56.900km pending site considerations. Moved due to curve. NOTIFICATION UPDATED- end marker and distance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124805&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000124805 | C01-BU-NL-MCNAUGHTON JCT-82.250KM-MAIN | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.38 | KM | 185858 | Newlands | MCNAUGHTON JCT | SONOMA JCT | 0.38 | KM | NL01ML82 | 0.25 | NL01ML82 | 0.63 | KM |  |  |  |  | 82.25 | 82.63 | 2025-06-30 | MAIN |  |  |  | 4.3 | 2.4 | 2 | 3.2 | 1 | 13.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Notification in process | NWSC |  | 20250630 | Will need to link this noti to the work order of noti-2000115901, where the FSCL is mapped to. Condition Based Cut out prior to Coral Ck Bridge (BR300468)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115900&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115900 | C01-BU-NL-MCNAUGHTON JCT-82.825KM-MAIN | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.773 | KM | 867177 | Newlands | MCNAUGHTON JCT | SONOMA JCT | 1.7729 | KM | NL01ML82 | 0.8249 | NL01ML84 | 0.5999 | KM |  |  |  |  | 82.825 | 84.6 | 2025-06-30 | MAIN |  |  |  | 4.3 | 2.4 | 2 | 3.2 | 1 | 13.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti-2000115901, where the FSCL is mapped to. Condition Based Cut out prior to Sonoma 7A and Culverts (CU300501)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115888&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115888 | C01-BU-GA-MBH NTH JCT-186.050km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4.961 | KM | 1688045 | Goonyella | MORANBAH NORTH JUNCTION | WOTONGA | 4.961 | KM | GA01ML186 | 0.05 | GA01ML191 | 0.0299 | KM |  |  |  |  | 186.05 | 191.03 | 2025-06-30 | DOWN |  |  |  | 4.3 | 2.9 | 2 | 3.5 | 1 | 14.9 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Tie into FY24 Undercut at 186.05km (2000094877) through to Isaac River bridge. Cut through crossing 3224, 3225 and 3226km pending site considerations
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115875&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115875 | C01-BU-BW-RAGLAN-592.500KM-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.006 | KM | 2514015 | Blackwater | RAGLAN | MARMOR | 1.806 | KM | BW01ML592 | 0.5 | BW01ML594 | 0.2999 | KM |  |  |  |  | 592.5 | 594.5 | 2025-06-30 | UP |  |  |  | 4.3 | 4.9 | 2 | 4.2 | 1 | 17.9 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | MEDIUM | HIGH | MEDIUM | Notification in process | SCPR |  | 20250630 | Condition Based Cut in at FY23 undercut and cut out prior to Marmor 11C/D Scope extents changed during phase 2 workshop to reduce extents at high km end from 594.500 to 594.300 to not overlap with formation renewal planned (currently in FY25) noti 2000115202 - 200m reduction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115877&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115877 | C01-BU-BW-ROCKLANDS-4.400KM-DOWN. | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.512 | KM | 3167176 | Blackwater | ROCKLANDS | GRACEMERE | 3.3119 | KM | BW03ML4 | 0.45 | BW03ML8 | 0.8 | KM |  |  |  |  | 4.4 | 8.95 | 2025-06-30 | DOWN |  |  |  | 5.3 | 3.35 | 2 | 3.6 | 1 | 18.9 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Gracemere 11A/B to Gracemere 10C/D Cut through AT site at 8.860km. Split out the AT Site per new C14 notification 2000116910. No reason for adjusting cut in/ cut out. NOTIFICATION UPDATED- Start marker, end marker, distance and noti description
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115899&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115899 | C01-BU-GA-SARAJI JCT-65.400KM-MAIN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.011 | KM | 1963535 | Goonyella | SARAJI JCT | LAKE VERMONT JCT | 2.0459 | KM | GA03ML65 | 0.4 | GA03ML67 | 0.45 | KM |  |  |  |  | 65.4 | 67.415 | 2025-06-30 | MAIN |  |  |  | 4.9 | 1.6 | 2 | 2.8 | 1 | 13.8 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Saraji 9A/B/FY23 fix on fail through to Saraji 12A/B Note: FY24 scope that was deferred to FY25 due to delivery risk. Moved to the CT point due to trans and turnout. NOTIFICATION UPDATED- Start, end markers, distance and noti discription.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115901&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115901 | C01-BU-NL-SONOMA JCT-84.850KM-MAIN | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 7.428 | KM | 3633048 | Newlands | SONOMA JCT | BIRRALEE | 7.4279 | KM | NL01ML84 | 0.8499 | NL01ML92 | 0.28 | KM |  |  |  |  | 84.85 | 92.28 | 2025-06-30 | MAIN |  |  |  | 3.2 | 2.2 | 2 | 3.1 | 1 | 9.8 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut in after Sonoma 7A and cut out prior to Birralee 7A/B
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115882&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115882 | C01-BU-BW-TUNNEL-76.000km-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 6.022 | KM | 4230004 | Blackwater | TUNNEL | EDUNGALBA | 6.022 | KM | BW03ML76 | 0 | BW03ML82 | 0.2 | KM |  |  |  |  | 76 | 82.2 | 2025-06-30 | DOWN |  |  |  | 5 | 3.75 | 2 | 3.8 | 1 | 19.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Tunnel 7C/D up to tie into FY23 undercutting/track lowering at 82.200km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115897&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115897 | C01-BU-GA-WAITARA-100.650KM-UP. | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 7.045 | KM | 3663844 | Goonyella | WAITARA | BRAESIDE | 7.0449 | KM | GA02ML100 | 0.65 | GA02ML107 | 0.6999 | KM |  |  |  |  | 100.65 | 107.7 | 2025-06-30 | UP |  |  |  | 4.8 | 4.4 | 2 | 4 | 1 | 19.3 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20240711 | Condition Based Cut from Waitara 11A/B to Braeside 8C/D Cut through AT site at 103km and 104.3km Cut through LX 5790 at 104.8km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115886&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115886 | C01-BU-BW-WALLAROO-115.100KM-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.791 | KM | 2800784 | Blackwater | WALLAROO | TRYPHINIA | 3.7909 | KM | BW04ML115 | 0.1 | BW04ML119 | 0 | KM |  |  |  |  | 115.1 | 119 | 2025-06-30 | UP |  |  |  | 4.6 | 3.35 | 2 | 3.6 | 1 | 16.5 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Wallaroo 12AB through to 119km. Cut through crossing 5558 at 115.760km. Cut through substation at 118km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115885&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115885 | C01-BU-BW-WALLAROO-115.800KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 6.889 | KM | 3687899 | Blackwater | WALLAROO | TRYPHINIA | 6.889 | KM | BW03ML115 | 0.8 | BW03ML122 | 0.8 | KM |  |  |  |  | 115.8 | 122.8 | 2025-06-30 | DOWN |  |  |  | 4 | 3.35 | 2 | 3.6 | 1 | 14.4 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from ER1.2A turnout (and just after corssing 5558) through to FY22 UC at 122.8km. Cut through substation at 118km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115896&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115896 | C01-BU-GA-WANDOO-90.920KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.482 | KM | 3284333 | Goonyella | WANDOO | WAITARA | 5.482 | KM | GA02ML90 | 0.92 | GA02ML96 | 0.4 | KM |  |  |  |  | 90.92 | 96.4 | 2025-06-30 | UP |  |  |  | 4.3 | 5 | 2 | 4.2 | 1 | 17.9 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from FY21 scope at 90.92 through to FY24 C01 Scope (2000094892) Cut through LX 5781, 5782 and 5783 pending site considerations. Cut through AT site at 94.95km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115879&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115879 | C01-BU-BW-WARREN-31.930KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4.053 | KM | 2558366 | Blackwater | WARREN | WYCARBAH | 4.048 | KM | BW03ML31 | 0.9 | BW03ML35 | 0.9499 | KM |  |  |  |  | 31.93 | 35.985 | 2025-06-30 | DOWN |  |  |  | 4.8 | 3.35 | 2 | 3.6 | 1 | 17.1 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Start cut from Neerkol Ck Bridge to Wycarbah 11C/D Preference to cut through LX1775 pending community engagement and diversion considerations. Cut through AT site at 33.400km. No reason for adjusting cut in/ cut out- notification updated with km's.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115880&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115880 | C01-BU-BW-WESTWOOD-47.580KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 7.425 | KM | 3461944 | Blackwater | WESTWOOD | WINDAH | 7.4649 | KM | BW03ML47 | 0.54 | BW03ML55 | 0 | KM |  |  |  |  | 47.58 | 55 | 2025-06-30 | DOWN |  |  |  | 5 | 3.35 | 2 | 3.6 | 1 | 18.6 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | LOW | HIGH | HIGH | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Westwood 7B/C to Windah 11A/B Cut through LX1064 at 47.720km pending CE and diversion consideration. Cut through AT site at 49.200km. Change due to cut in on a curve. Undercut 49.270 to 50.300km FY23. Moved due o curve- UPDATE IN THE NOTIFICATION HAS BEEN MADE-changed the start marker and length, updated noti descitption
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115871&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115871 | C01-BU-BW-WIGGINS ISLAND-540.450KM-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.14 | KM | 1492336 | Blackwater | WIGGINS ISLAND | MT MILLER | 1.1299 | KM | BW01ML540 | 0.45 | BW01ML541 | 0.5799 | KM |  |  |  |  | 540.45 | 541.59 | 2025-06-30 | UP |  |  |  | 4.3 | 3.8 | 2 | 3.8 | 1 | 16.5 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from 50m off Mt Miller 11C/D to 50m off Mt Miller ER2.3B. Moved due to curve <(>&<)> ER. NOTIFICATION UPDATED- end marker and distance
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115905&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115905 | C01-BU-GA-WOTONGA-191.340KM-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.821 | KM | 279356 | Goonyella | WOTONGA | MORANBAH NORTH JCT | 0.8209 | KM | GA01ML191 | 0.34 | GA01ML192 | 0.14 | KM |  |  |  |  | 191.34 | 192.14 | 2025-06-30 | DOWN |  |  |  | 4.3 | 2.9 | 2 | 3.5 | 1 | 14.9 |  | 2023-10-13 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Will need to link this noti to the work order of noti- 2000115888, where the FSCL is mapped to. Condition Based Cut from Issac River Bridge to Moranbah 7A/B. Roll over C14 mainline into C01 project.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115909&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115909 | C14 BW Unallocted | BW | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 6 | KM | 4515351 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 5 | 5 | 1 | 25 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Condition Based Fix On Fail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115910&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115910 | C14 GA Unallocted | GA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 3.55 | KM | 3027666 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 5 | 5 | 1 | 25 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Condition Based Fix On Fail Assist in meeting corporate target. Not expected to need 4km of reactive scope. Completed >3km in FY23. Civil manager is ok with reducing this scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115911&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115911 | C14 MA Unallocted | MA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.5 | KM | 1878756 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 5 | 5 | 1 | 25 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Condition Based Fix On Fail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115912&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115912 | C14 NL Unallocted | NL | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 1 | KM | 1067833 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 5 | 5 | 1 | 25 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Condition Based Fix On Fail Assist in meeting corporate target. Not expected to need 4km of reactive scope. Only completed 410m in FY23. Civil manager is ok with reducing this scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000116911&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000116911 | C14-BU-BW-BAJOOL-615.100KM-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.31 | KM | 224734 | Blackwater | BAJOOL | ARCHER | 0.3099 | KM | BW01ML615 | 0.1 | BW01ML615 | 0.4099 | KM |  |  |  |  | 615.1 | 615.41 | 2025-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | NWSC |  | 20250630 | Originally C01 2000115876, split out to ensure AT site is undercut Cut through AT site at 615.150km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115908&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115908 | C14-BU-GA-DALY BAY-11.450KM-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.8 | KM | 527005 | Goonyella | DALY BAY CROSSOVER | PRAUGELANDS | 0.805 | KM | GA01ML11 | 0.45 | GA01ML12 | 0.25 | KM |  |  |  |  | 11.45 | 12.25 | 2025-06-30 | DOWN |  |  |  | 4.6 | 4.6 | 2 | 4.1 | 1 | 18.8 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Tie cut to FY23 C01 Scope (2000052335)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115904&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115904 | C14-BU-GA-HATFIELD-48.700KM-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.58 | KM | 459541 | Goonyella | HATFIELD | BOLINGBROKE | 0.5829 | KM | GA01ML48 | 0.6999 | GA01ML49 | 0.28 | KM |  |  |  |  | 48.7 | 49.28 | 2025-06-30 | DOWN |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from LX3506 to Hatfield ER1.2A
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115906&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115906 | C14-BU-GA-HATFIELD-59.730KM-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.73 | KM | 483712 | Goonyella | HATFIELD | BOLINGBROKE | 0.67 | KM | GA02ML59 | 0.7299 | GA02ML60 | 0.38 | KM |  |  |  |  | 59.73 | 60.44 | 2025-06-30 | UP |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Tie cut in to FY23 C14 Scope (2000074538) and cut out prior to Bolingbroke 8C/D. Increased to the 60.440km to encompass mudhole.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000116910&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000116910 | C14-BU-BW-GRACEMERE-8.800KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.15 | KM | 159425 | Blackwater | ROCKLANDS | GRACEMERE | 0.1499 | KM | BW03ML8 | 0.8 | BW03ML8 | 0.9499 | KM |  |  |  |  | 8.8 | 8.95 | 2025-06-30 | DOWN |  |  |  | 5.3 | 3.35 | 2 | 3.6 | 1 | 18.9 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | NWSC |  | 20250630 | Condition Based Cut from Gracemere 11A/B to Gracemere 10C/D Cut through AT site at 8.860km. Originally captured in C01 notification 2000115877
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115902&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115902 | C14-BU-BW-STANWELL-23.620KM-DOWN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.943 | KM | 605931 | Blackwater | STANWELL | WARREN | 0.9429 | KM | BW03ML23 | 0.6199 | BW03ML24 | 0.55 | KM |  |  |  |  | 23.62 | 24.55 | 2025-06-30 | DOWN |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.6 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Kabra 102B to Stewarts Ck Bridge
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115903&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115903 | C14-BU-BW-WARREN-36.250KM-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.795 | KM | 497773 | Blackwater | WARREN | WYCARBAH | 0.7449 | KM | BW04ML36 | 0.25 | BW04ML37 | 0 | KM |  |  |  |  | 36.25 | 37.05 | 2025-06-30 | UP |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14.1 |  | 2023-10-13 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Condition Based Cut from Wycarbah 12C/D to Wycarbah-Westwood ER1.2B
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126809&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000126809 | 4003 Burngrove-Mackenzie Mn | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 96577 | Blackwater |  |  | 78.1189 | KM | BW08ML0 | -0.0739 | BW08ML78 | 0.05 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126820&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126820 | 5000 Rocklands-Kabra Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 99272 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126821&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126821 | 5001 Warren-Westwood Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 79704 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126822&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126822 | 5002 Wycarbah-Windah Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 146016 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126824&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126824 | 5003 Windah-Grantleigh Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 52999 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126825&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126825 | 5004 Tunnel-Edungalba Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 118426 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126826&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126826 | 5005 & 5027 Aroona-Wallaroo Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 94178 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126827&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126827 | 5006 Duaringa-Tryphinia Up | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 74552 | Blackwater |  |  | 198.257 | KM | BW04ML0 | 0 | BW04ML198 | 0.2839 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126828&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126828 | 5007 Duaringa-Tryphinia Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 135476 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126829&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126829 | 5008 Callemondah-Yarwun Up | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 22419 | Blackwater |  |  | 96.1979 | KM | BW01ML534 | 0.2909 | BW01ML632 | 0.9579 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126830&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126830 | 5010 Raglan Yard-Bajool Up | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 39449 | Blackwater |  |  | 96.1979 | KM | BW01ML534 | 0.2909 | BW01ML632 | 0.9579 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126831&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126831 | 5011 Bajool-Archer Up | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 43559 | Blackwater |  |  | 96.1979 | KM | BW01ML534 | 0.2909 | BW01ML632 | 0.9579 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126844&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000126844 | 5012 McNaughton-Birrallee Mn | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 448401 | Newlands |  |  | 213.8779 | KM | NL01ML0 | 0 | NL01ML213 | 0.8269 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126833&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126833 | 5013 Hatfield Yard-Bollingbroke | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 125151 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126834&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126834 | 5014 Hatfield-Balook Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 68810 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126835&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126835 | 5015 Bolingbroke-Wandoo Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 77915 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126836&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126836 | 5016 Wandoo-Waitara Yard Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 107806 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126837&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126837 | 5017 Waitara-Braeside Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 138543 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126838&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126838 | 5018 Braeside-Mindi Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 84601 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126839&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126839 | 5019 Braeside-Mindi Dn | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 59055 | Goonyella |  |  | 210.913 | KM | GA01ML8 | 0.33 | GA01ML219 | 0.456 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126840&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126840 | 5020 & 5113 Wotonga-Moranbah North Mn | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 113706 | Goonyella |  |  | 210.913 | KM | GA01ML8 | 0.33 | GA01ML219 | 0.456 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126841&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000126841 | 5021 Saraji-Lake Vermont Mn | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 39547 | Goonyella |  |  | 153.918 | KM | GA03ML1 | 0.005 | GA03ML154 | 0.9979 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126842&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126842 | 5023 Daly Bay-Praguelands Up | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 22438 | Goonyella |  |  | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126832&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000126832 | 5024 Dingo-Parnabal Dn | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 30364 | Blackwater |  |  | 202.2439 | KM | BW03ML0 | 0 | BW03ML202 | 0.2849 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126843&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000126843 | 5025 Belldeen-Moura Mn | MA-01ML | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 379370 | Moura |  |  | 188.679 | KM | MA01ML2 | 0.4979 | MA01ML191 | 0.1499 | KM | [6 empty] | 2025-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115689&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115689 | C13 Turnout B/U Aldoga 11A/B | TO000570 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 131479 | Blackwater | ALDOGA | ALDOGA | 0.047 | KM | BW01ML553 | 0.505 | BW01ML553 | 0.552 | KM |  |  |  |  | 553.505 | 553.552 | 2025-06-30 | GA-04BA |  |  |  | 4.6 | 4.5 | 2 | 4.1 | 1 | 19 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115691&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115691 | C13 Turnout B/U Aldoga 8A/B | TO000898 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 131479 | Blackwater | ALDOGA | ALDOGA | 0.047 | KM | BW02ML555 | 0.8189 | BW02ML555 | 0.8659 | KM |  |  |  |  | 555.819 | 555.866 | 2025-06-30 | GA-04BA |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115692&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115692 | C13 Turnout B/U Aldoga 7C/D | TO000899 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 131479 | Blackwater | ALDOGA | ALDOGA | 0.0519 | KM | BW02ML555 | 0.888 | BW02ML555 | 0.9399 | KM |  |  |  |  | 555.888 | 555.94 | 2025-06-30 | GA-04BA |  |  |  | 4.2 | 4.5 | 2 | 4.1 | 1 | 17.3 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115690&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115690 | C13 Turnout B/U Aldoga 7A/B | TO000854 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 131479 | Blackwater | ALDOGA | ALDOGA | 0.0459 | KM | BW01ML555 | 0.9419 | BW01ML555 | 0.9879 | KM |  |  |  |  | 555.942 | 555.988 | 2025-06-30 | GA-04BA |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.3 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080081&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000080081 | C13 Turnout B/U Bajool 12A/B | TO000922 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 143959 | Blackwater | BAJOOL | BAJOOL | 0.047 | KM | BW01ML603 | 0.515 | BW01ML603 | 0.562 | KM |  |  |  |  | 603.515 | 603.562 | 2025-06-30 | BW-01ML |  |  |  | 3.5 | 4.5 | 2 | 4.5 | 1 | 15.8 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115795&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115795 | C13 Turnout B/U Black Mtn 12C/D | TO000448 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 267015 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0.048 | KM | GA01ML40 | 0.9679 | GA01ML41 | 0.0149 | KM |  |  |  |  | 40.968 | 41.015 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 5 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080077&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080077 | C13 Turnout B/U Bluff 7C/D | TO000651 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 146426 | Blackwater | BLUFF | BLUFF | 0.047 | KM | BW03ML171 | 0.1829 | BW03ML171 | 0.23 | KM |  |  |  |  | 171.183 | 171.23 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 | 2 | 3.35 | 1 | 11.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104197&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104197 | C13 Turnout B/U Stowe 12A Pts | TO000957 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 136062 | Moura | BYELLEE | STOWE | 0.042 | KM | MA01ML24 | 0.3679 | MA01ML24 | 0.4099 | KM |  |  |  |  | 24.368 | 24.41 | 2025-06-30 | MA-01ML |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104183&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104183 | C13 Turnout B/U Callemondah 215A Pts | TO001184 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 153338 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.0259 | KM | BW11XR0 | 0.065 | BW11XR0 | 0.0909 | KM |  |  |  |  | 0.065 | 0.091 | 2025-06-30 | BW-22YR |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.6 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104182&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104182 | C13 Turnout B/U Callemondah 214A Pts | TO001172 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 153338 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.029 | KM | BW08YR533 | 0.779 | BW08YR533 | 0.808 | KM |  |  |  |  | 533.779 | 533.808 | 2025-06-30 | BW-08YR |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.6 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080252&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080252 | C13 Turnout U/C Daly Bay 45A/B. | TO000489 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 132953 | Goonyella | DAL BAY | DAL BAY | 0.05 | KM | GA04BA3 | 0.9499 | GA04BA4 | 0.0109 | KM |  |  |  |  | 3.95 | 4.011 | 2025-06-30 | GA-04BA |  |  |  | 3.5 | 2.6 | 2 | 2.6 | 1 | 9.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Rough top and twist, near D7 (Feb 21) Needs to be grouped with 45CD and 46AB due to layout geography
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104250&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104250 | C13 Turnout U/C Daly Bay 47A/B. | TO000492 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 132953 | Goonyella | DALY BAY ARRIVAL RD 5 | DALY BAY ARRIVAL RD 5 | 0.049 | KM | GA05BD3 | 0.9519 | GA05BD4 | 0.001 | KM |  |  |  |  | 3.952 | 4.001 | 2025-06-30 | GA-05BD |  |  |  | 3.9 | 2.6 | 2 | 4.1 | 1 | 15.2 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080121&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080121 | C13 Turnout B/U Dingo 2A Pts | TO000721 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 192404 | Blackwater | DINGO | DINGO | 0.032 | KM | BW04ML141 | 0.7359 | BW04ML141 | 0.768 | KM |  |  |  |  | 141.736 | 141.768 | 2025-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 | 2 | 3.35 | 1 | 11.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080080&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080080 | C13 Turnout B/U Duaringa 7C/D | TO000577 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 199004 | Blackwater | DUARINGA | DUARINGA | 0.048 | KM | BW03ML105 | 0.003 | BW03ML104 | 0.9589 | KM |  |  |  |  | 105.003 | 104.959 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 | 2 | 3.35 | 1 | 11.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104227&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104227 | C13 Turnout B/U Kabra 12C/D | TO000677 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 203524 | Blackwater | GRACEMERE | KABRA | 0.0519 | KM | BW03ML13 | 0.507 | BW03ML13 | 0.559 | KM |  |  |  |  | 13.507 | 13.559 | 2025-06-30 | BW-03ML |  |  |  | 3.5 | 3.4 | 2 | 3.6 | 1 | 12.5 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080197&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080197 | C13 Turnout U/C Jilalan 7C/D | TO000569 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 145849 | Goonyella | JILALAN | JILALAN | 0.032 | KM | GA01ML17 | 0.389 | GA01ML17 | 0.4209 | KM |  |  |  |  | 17.389 | 17.421 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.6 | 1 | 16.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | D7 top, pair with adjacent with 46AB (Jan 2021)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080198&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080198 | C13 Turnout U/C Jilalan 46A/B | TO000438 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 145849 | Goonyella | JILALAN | JILALAN | 0.032 | KM | GA01ML17 | 0.441 | GA01ML17 | 0.4729 | KM |  |  |  |  | 17.441 | 17.473 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.6 | 1 | 16.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | D7 top, pair with adjacent 7CD (Jan 2021)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080210&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080210 | C13 Turnout U/C Jilalan Yard 11A/B | TO000434 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 239915 | Goonyella | JILALAN | JILALAN | 0.035 | KM | GA02YR22 | 0.164 | GA02YR22 | 0.199 | KM |  |  |  |  | 22.164 | 22.199 | 2025-06-30 | GA-02YR |  |  |  | 3.5 | 4.8 | 2 | 4.8 | 1 | 16.8 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | D7 top and near D7 twist (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115792&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115792 | C13 Turnout U/C Jilalan 81A/B | TO000509 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 145849 | Goonyella | JILALAN | JILALAN | 0.034 | KM | GA01ML22 | 0.504 | GA01ML22 | 0.538 | KM |  |  |  |  | 22.504 | 22.538 | 2025-06-30 | GA-02ML |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115793&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115793 | C13 Turnout B/U Jilalan Bypass 11A/B | TO000510 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 145849 | Goonyella | JILALAN | JILALAN | 0.034 | KM | GA01ML22 | 0.559 | GA01ML22 | 0.5929 | KM |  |  |  |  | 22.559 | 22.593 | 2025-06-30 | GA-01ML |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080222&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080222 | C13 Turnout U/C Jilalan 84A/B | TO000514 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 145849 | Goonyella | JILALAN | JILALAN | 0.034 | KM | GA01ML23 | 0.459 | GA01ML23 | 0.4929 | KM |  |  |  |  | 23.459 | 23.493 | 2025-06-30 | GA-01ML |  |  |  | 3.5 | 4.8 | 2 | 4.8 | 1 | 16.8 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Geometry moderately rough (Jan 2021)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104249&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104249 | C13 Turnout U/C Jilalan 106B | TO000118 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 239915 | Goonyella | JILALAN YARD DOWN | JILALAN YARD DOWN | 0.0359 | KM | GA02YR22 | 0.112 | GA02YR22 | 0.1479 | KM |  |  |  |  | 22.112 | 22.148 | 2025-06-30 | GA-02YR |  |  |  | 3.9 | 4.8 | 2 | 4.1 | 1 | 19 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080176&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080176 | C13 Turnout B/U Kabra 12A/B | TO000766 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 203524 | Blackwater | KABRA | KABRA | 0.0729 | KM | BW04ML13 | 0.3629 | BW04ML13 | 0.4359 | KM |  |  |  |  | 13.363 | 13.436 | 2025-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 | 2 | 3.35 | 1 | 11.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104225&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104225 | C13 Turnout B/U Warren 101A Pts | TO000675 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 203543 | Blackwater | KABRA | STANWELL | 0.032 | KM | BW03ML23 | 0.328 | BW03ML23 | 0.3599 | KM |  |  |  |  | 23.328 | 23.36 | 2025-06-30 | BW-03ML |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.3 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092130&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000092130 | C13 Turnout U/C Kaili 8A/B | TO000120 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165367 | Newlands | KAILI | KAILI | 0.0359 | KM | NL02ML6 | 0.8389 | NL02ML6 | 0.875 | KM |  |  |  |  | 6.839 | 6.875 | 2025-06-30 | NL-02ML |  |  |  | 3.5 | 2.5 | 2 | 2.5 | 1 | 8.75 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Melissa Durnsford - Meeting held with Newlands District Stakeholders on 21.02.2022. Priority for completion in FY25, ensuring 50m either side of the turnout is undercut in conjunction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092119&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000092119 | C13 Turnout U/C Kaili 7C/D | TO000121 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 165367 | Newlands | KAILI | KAILI | 0.0299 | KM | NL02ML6 | 0.893 | NL02ML6 | 0.923 | KM |  |  |  |  | 6.893 | 6.923 | 2025-06-30 | NL-02ML |  |  |  | 3.5 | 2.5 | 2 | 2.5 | 1 | 8.75 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Melissa Durnsford - Meeting held with Newlands District Stakeholders on 21.02.2022. Priority for completion in FY25, ensuring 50m either side of the turnout is undercut in conjunction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115726&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115726 | C13 Turnout U/C Mallawa 7C/D | TO000233 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 173350 | Goonyella | MALLAWA | MALLAWA | 0.0719 | KM | GA01ML167 | 0.8219 | GA01ML167 | 0.894 | KM |  |  |  |  | 167.822 | 167.894 | 2025-06-30 | BW-03ML |  |  |  | 4.5 | 2.4 | 2 | 3.2 | 1 | 14.5 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115727&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115727 | C13 Turnout U/C Mallawa 8A/B | TO000234 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 173350 | Goonyella | MALLAWA | MALLAWA | 0.047 | KM | GA01ML168 | 0.1029 | GA01ML168 | 0.1499 | KM |  |  |  |  | 168.103 | 168.15 | 2025-06-30 | BW-09SD |  |  |  | 4.2 | 2.4 | 2 | 3.2 | 1 | 13.5 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104246&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000104246 | C13 Turnout B/U Bajool 12C/D | TO000870 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 143959 | Blackwater | MARMOR | BAJOOL | 0.049 | KM | BW02ML603 | 0.465 | BW02ML603 | 0.514 | KM |  |  |  |  | 603.465 | 603.514 | 2025-06-30 | BW-02ML |  |  |  | 3.9 | 4.1 | 2 | 3.9 | 1 | 15.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115714&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115714 | C13 Turnout B/U Peak Downs ER.2D | TO000360 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 168113 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0309 | KM | GA05PL45 | 0.333 | GA05PL45 | 0.3639 | KM |  |  |  |  | 45.333 | 45.364 | 2025-06-30 | BW-44XR |  |  |  | 4.1 | 2.1 | 2 | 3.1 | 1 | 12.6 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000055914&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000055914 | C13 GOONYELLA T/O ER2.2E PEAK DOWNS. | TO000359 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 168113 | Goonyella | PEAK DOWNS ER2.2E |  | 0 | KM | GA05PL45 | 0.674 | GA05PL45 | 0.674 | KM |  |  |  |  | 45.674 | 45.674 | 2025-06-30 | GA-05PL |  |  |  | 3.5 | 2.4 | 2 | 2.4 | 1 | 8.4 | 4748 | 2023-10-13 | 2020-11-13 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | * 27.04.2020 10:48:55 AUSQLD Peter Rayner (R003851) * Peak Downs ER2.2E
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092131&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000092131 | C13 Turnout U/C Sonoma 9A | TO000183 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 239405 | Newlands | SONOMA | SONOMA | 0.033 | KM | NL05ML1 | 0.003 | NL05ML1 | 0.0359 | KM |  |  |  |  | 1.003 | 1.036 | 2025-06-30 | NL05ML |  |  |  | 3.5 | 2.5 | 2 | 2.5 | 1 | 8.75 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Melissa Durnsford - Meeting held with Newlands District Stakeholders on 21.02.2022. Priority for completion in FY25, ensuring 50m either side of the turnout is undercut in conjunction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104198&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104198 | C13 Turnout B/U Stowe 7A Pts. | TO000958 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 136062 | Moura | STOWE | GRAHAM | 0.033 | KM | MA01ML26 | 0.272 | MA01ML26 | 0.3049 | KM |  |  |  |  | 26.272 | 26.305 | 2025-06-30 | MA-01ML |  |  |  | 3.9 | 1.3 | 2 | 2.6 | 1 | 10.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115763&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115763 | C13 Turnout B/U Tootoolah 8A/B | TO000252 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 174167 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.0449 | KM | GA01ML132 | 0.6099 | GA01ML132 | 0.655 | KM |  |  |  |  | 132.61 | 132.655 | 2025-06-30 | GA-04BA |  |  |  | 3.6 | 4.7 | 2 | 4.1 | 1 | 14.6 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115764&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115764 | C13 Turnout B/U Tootoolah 12C/D | TO000254 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 174167 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0.0449 | KM | GA01ML132 | 0.876 | GA01ML132 | 0.921 | KM |  |  |  |  | 132.876 | 132.921 | 2025-06-30 | GA-04BA |  |  |  | 3.9 | 4.7 | 2 | 4.1 | 1 | 15.9 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104244&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104244 | C13 Turnout B/U Edungalba 2B Pts | TO000616 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150508 | Blackwater | TUNNEL | EDUNGALBA | 0.035 | KM | BW03ML84 | 0.796 | BW03ML84 | 0.8309 | KM |  |  |  |  | 84.796 | 84.831 | 2025-06-30 | BW-03ML |  |  |  | 4.3 | 3.8 | 2 | 3.8 | 1 | 16.3 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104243&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104243 | C13 Turnout B/U Edungalba 2A Pts | TO000615 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150508 | Blackwater | TUNNEL | EDUNGALBA | 0.035 | KM | BW03ML85 | 0.1409 | BW03ML85 | 0.1759 | KM |  |  |  |  | 85.141 | 85.176 | 2025-06-30 | BW-03ML |  |  |  | 4.1 | 3.8 | 2 | 3.8 | 1 | 15.7 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104223&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104223 | C13 Turnout B/U Bluff 9A/B | TO000652 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 146426 | Blackwater | WALTON | BLUFF | 0.0369 | KM | BW03ML170 | 0.917 | BW03ML170 | 0.9539 | KM |  |  |  |  | 170.917 | 170.954 | 2025-06-30 | BW-03ML |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.9 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | MEDIUM | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115116&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000115116 | C20-BR-BW-GEOTECH-FY25FORFY26 | BW | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 7 | SITE | 70000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115117&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000115117 | C20-BR-GA-GEOTECH-FY25FORFY26 | GA | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 2 | SITE | 20000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115118&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000115118 | C20-BR-MA-GEOTECH-FY25FORFY6 | MA | CIVIL | BRIDGE ROLLOUTS |  | DESIGN | 1 | SITE | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104179&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000104179 | C20-BR-BW-SIX MILE CK-UP-605.635KM | BR101279-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.054 | KM | 910492 | Blackwater | BAJOOL | ARCHER | 0.2159 | KM | BW01ML605 | 0.5789 | BW01ML605 | 0.795 | KM |  |  |  |  | 605.635 | 605.689 | 2025-06-30 | UP |  |  |  | 4.5 | 4.5 | 3 | 4.4 | 1 | 17.2 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 Moderate Priority Mud and very poor ballast profile shows in track video late 2022. - Deficient ballast throughout entire bridge. Mudhole / pumping sleeper at start of adbuntment on low Km end. Small top defects at bridge ends. " FY252/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115088&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115088 | C20-BR-BW-Six Mile Ck-Up-606.020KM | CU101761 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.032 | KM | 539551 | Blackwater | BAJOOL | ARCHER | 0.032 | KM | BW01ML606 | 0.016 | BW01ML606 | 0.048 | KM |  |  |  |  | 606.016 | 606.048 | 2025-06-30 | UP |  |  |  | 4.5 | 4.5 | 3 | 4.4 | 1 | 19.8 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Culvert with multiple mudholes. No splay rails present. Vegetation can be seen growing from the toe of ballast. Ballast profile is lacking (Not reaching the kerb) needs rollout rather than C01 or C14 in late 2022. Moderate top defects at each ends of the culvert. "
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104178&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000104178 | C20-BR-BW-OAKY CK-UP-613.020KM | BR101299-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.088 | KM | 411003 | Blackwater | BAJOOL | ARCHER | 0.201 | KM | BW01ML612 | 0.9799 | BW01ML613 | 0.1799 | KM |  |  |  |  | 612.98 | 613.18 | 2025-06-30 | UP |  |  |  | 4 | 4.5 | 3 | 4.4 | 1 | 16.5 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 Moderate Priority Culvert and bridge - Ed's replacing culvert with bridge. Check the lot is being done. Mud hole / pumping on high km end (late 2022 track video). Opportunity to co-ordinate with nearby replacment work on the Oaky Ck culverts. Considering the high impact if this bridge were to fail, it was originally been placed in FY25, with a potential to require fix on fail. Possible relieving slab issues. "
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115089&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115089 | C20-BR-BW-BW CK OVERFLOW-DOWN-186.610KM | CU100496 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.031 | KM | 184439 | Blackwater | BOONAL | BLACKWATER | 0.1849 | KM | BW03ML186 | 0.528 | BW03ML186 | 0.7129 | KM |  |  |  |  | 186.606 | 186.637 | 2025-06-30 | DOWN |  |  |  | 4.8 | 3.15 | 3 | 3.9 | 1 | 12.3 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Culvert with splays. Pumping. Losing material at abutment. Ed to review and is arranging rock washout protection. Nearby Blackwater creek at the 187km is also planned in FY25. Kerb raising installed. Skewed sleepr at low KM end of culvert. Powdering ballast around signials at both adbuntments. "
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104174&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104174 | C20-BR-BW-BLACKWATER CK-UP-187.018KM | BR100264-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.126 | KM | 749656 | Blackwater | BOONAL | BLACKWATER | 0.229 | KM | BW04ML186 | 0.9669 | BW04ML187 | 0.196 | KM |  |  |  |  | 187.018 | 187.144 | 2025-06-30 | UP |  |  |  | 4.3 | 3.2 | 3 | 3.9 | 1 | 13.4 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Complete in conjuntion with Blackwatter Ck Down Road Rollout (2000104173) Central line mainline - moderate-high traffic, empty track - moderate MGT. Track recording video from May 2022 shows deficient ballast over the bridge span. Mudhole with skewed sleepers can be seen at the high km end. Powdering ballast at 2 other locations suggest more mudholes forming. " FY25 1/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104173&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104173 | C20-BR-BW-BLACKWATER CK-DOWN-187.025KM | BR100194-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.112 | KM | 666361 | Blackwater | BOONAL | BLACKWATER | 0.064 | KM | BW03ML187 | 0.0439 | BW03ML187 | 0.1079 | KM |  |  |  |  | 187.025 | 187.137 | 2025-06-30 | DOWN |  |  |  | 4.2 | 3.2 | 3 | 3.9 | 1 | 13.4 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Complete in conjuntion with Blackwater Ck Up Road Rollout (2000104174) Track recording video from September 22 shows defiecent ballast throughout the entire bridge. Multiple mudholes forming on the bridge. Both bridge ends showing top defects from 10/22 Geometry Report. " FY25 1/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101461&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal GAPE Traffic | BASELOAD | COAL | 002000101461 | C20-BR-NL-EAGLEFIELD CK-MAIN-195.260KM. | BR300668-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.129 | KM | 454709 | Newlands | EAGLEFIELD CREEK | NORTH GOONYELLA | 0.129 | KM | NL01ML195 | 0.197 | NL01ML195 | 0.326 | KM |  |  |  |  | 195.197 | 195.326 | 2024-06-30 |  |  |  |  | 4 | 1.2 | 2 | 1.2 | 1 | 4.8 |  |  |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Notification in process | RRIG |  | 20240630 | EAGLEFIELD CK BRIDGE ROLLOUT BROUGHT FOWARD AS SCR INTO FY24 AFTER IT WAS IDENTIFIED TO HAVE MUD/PUMPING THROUGH THE BRIDGE IN MID 2022. TECH SCOPE ATTACHED DCPS TAKEN EARLY AUGUST - NO FORMATION REQUIRED FY24 1/3 PCR 5864 - no longer deliverable in FY24 due to changing closure regime. Rescheduled to Sep 2024 (FY25) - MOD ID updated. 30.01.24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115120&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115120 | C20-BR-BW- MIDDLE CREEK-UP-15.330KM | BR100266-91-02 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.045 | KM | 755267 | Blackwater | GRACEMERE | KABRA | 0.192 | KM | BW04ML15 | 0.276 | BW04ML15 | 0.468 | KM |  |  |  |  | 15.353 | 15.398 | 2025-06-30 | UP |  |  |  | 4.1 | 3.35 | 3 | 4 | 1 | 13.4 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Track video shows powdering ballast on bridge which suggests pumping / potential mudholes and defiecent ballast around splay rail on both bridge ends. TO 10m of the end of the bridge (High Km end). Powdering ballast on bridge suggests pumping / potential mudhole. Top and twist issues over entire bridge."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115087&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115087 | C20-BR-BW-NEERKOL CK-UP-21.360KM | BR100141-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.1 | KM | 1035725 | Blackwater | KABRA | WARREN | 0.2429 | KM | BW04ML21 | 0.2449 | BW04ML21 | 0.4879 | KM |  |  |  |  | 21.32 | 21.42 | 2025-06-30 | UP |  |  |  | 3.9 | 3.4 | 3 | 4 | 1 | 13.6 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | HIGH | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority 2022 GPR shows mostly severe fouling, a significant increase on 2021 GPR which was moderate, and 2020 which was missing data (Feb 2023 RC) Track recording video from May 2022 shows shy ballast across the bridge with rolling ballast on the LHS (Field) shoulder. The rolling ballast correlates with the moderate top and twist seen in the geometry report"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104165&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104165 | C20-BR-BW-STOCK CROSSING-MAIN-29.365KM | BR100862-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.07 | KM | 633226 | Blackwater | KENMARE | MEEMOOLOO | 0.17 | KM | BW06ML29 | 0.28 | BW06ML29 | 0.45 | KM |  |  |  |  | 29.365 | 29.435 | 2025-06-30 | MAIN |  |  |  | 4.2 | 2.3 | 3 | 3.6 | 1 | 9.6 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | " FY25 Moderate Priority Geometry is near D7 top in mid 2022 with large top defects on both ends of the bridge. 2 bay mudhole forming on the low Km end between adbuntment and splay rails. Shy ballast in LHS shoulder with small amount of vegetation. Small bridge with no hand rails installed. " FY25 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104166&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000104166 | C20-BR-BW-STOCK CROSSING-MAIN-71.903KM | BR100880-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.069 | KM | 659648 | Blackwater | MEEMOOLOO | STARLEE | 0.1719 | KM | BW06ML71 | 0.8169 | BW06ML71 | 0.9889 | KM |  |  |  |  | 71.903 | 71.972 | 2025-06-30 | MAIN |  |  |  | 4.4 | 2.3 | 3 | 3.6 | 1 | 10.2 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 High Priority Geometry at D1 top in May 2022, deteriorated from near D7 top in previous run. Shallow Ballast on Low KM side and around the splay rails on the High Km side, Gabion Baskets with coal fouling on the RHS. " FY25 1/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094378&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal GAPE Traffic | BASELOAD | COAL | 002000094378 | C20-BR-NL-SUTTOR CREEK-MAIN-178.276KM | BR300676-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.08 | KM | 879839 | Newlands | SUTTOR CREEK | EAGLEFIELD CREEK | 0.1819 | KM | NL01ML178 | 0.275 | NL01ML178 | 0.457 | KM |  |  |  |  | 178.276 | 178.356 | 2025-06-30 | MAIN |  |  |  | 4.6 | 1.3 | 3 | 3.2 | 1 | 14.6 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | "FY25 Moderate Priority Has very high fouling (79%), not impacting geometry due to the low tonnage profile. Bridge was originally put forward in FY24 but was replaced by Eaglefield Creek instead. Track Geometry reports from 10/22 show only moderate top defects at the bridge ends. Ballast deficient at low km end of bridge." Bridge removed from FY25 after it was flagged as being rolled out in 2017, records which weren't available at the time of scoping. Inspector agrees that it can be deferred. Deferred indefinitely. SCR TBA. Has very high fouling (79%), not impacting geometry too much at this point, thanks probably to the low tonnage profile Moved from FY24 into FY25 after it was identified Eaglefield Creek has mud/pumping through the bridge and needed to come into FY24. FY25 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115121&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115121 | C20-BR-BW-GOGANGO CK-DOWN-60.740KM | BR100050-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.267 | KM | 1118853 | Blackwater | WINDAH | GRANTLEIGH | 0.3709 | KM | BW03ML60 | 0.4859 | BW03ML60 | 0.8569 | KM |  |  |  |  | 60.532 | 60.799 | 2025-06-30 | DOWN |  |  |  | 4.1 | 3.35 | 3 | 4 | 1 | 13.4 |  | 2023-10-13 |  | Bridge Roll Out | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | FY25 Moderate Priority Rolling ballast can be seen throughout the entire bridge. Small amount of vegetation can be seen also in the shoulder of bridge ballast which suggests fouling. Crib material seems to be new on high km side of bridge suggesting a possible ballast drop. Long bridge.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115190&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115190 | FENCING & CORRIDOR SECURITY REACTIVE | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 0 | LUMPSUM | 1225000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115191&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115191 | FENCING & CORRIDOR SECURITY REACTIVE | GA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 0 | LUMPSUM | 1100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115192&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115192 | FENCING & CORRIDOR SECURITY REACTIVE | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 0 | LUMPSUM | 330000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115193&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115193 | FENCING & CORRIDOR SECURITY REACTIVE | NL | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 0 | LUMPSUM | 330000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112784&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | NON-COAL | 002000112784 | Burngrove to Nogoa Fencing FY25 | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 60000 | Blackwater | BURNGROVE | NOGOA | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 202.36 | 263.15 | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115206&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115206 | C05-FR-GA-BRAESIDE-119.080km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.3 | KM | 1743639 | Goonyella | BRAESIDE | MINDI | 0.2999 | KM | GA02ML119 | 0.08 | GA02ML119 | 0.38 | KM |  |  |  |  | 119.08 | 119.38 | 2025-06-30 | UP |  |  |  | 3.6 | 4.4 | 3 | 4.3 | 1 | 15.4 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 119.000km to 119.660km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 119.400km to 119.700km GA-02ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 30-50% (Refer attached Geotech report). The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Scope nominated by district, private cattle crossing LX5795 @ 119.100km 20.06.2023 Unsuitable material allowances updated, Geotech report attached and emailed to A/Construction Managment Leader 13.06.2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115205&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115205 | C05-FR-GA-BROADLEA-159km. | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.25 | KM | 1431049 | Goonyella | BROADLEA | MALLAWA | 0.25 | KM | GA01ML159 | 0 | GA01ML159 | 0.25 | KM |  |  |  |  | 159 | 159.25 | 2025-06-30 | DOWN |  |  |  | 3.9 | 2.5 | 3 | 3.7 | 1 | 14.5 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 158.810km to 159.370km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 159.250km to 159.600km GA-01ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • FY24 track upgrade 158.283km-159.876km (noti # 2000097522) • More top defects than twist – to be confirmed with DCPs. D7 top defects in 2022 geometry run
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115216&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115216 | C05-FR-NL-Buckley-15.540km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.35 | KM | 1721047 | Newlands | BUCKLEY | ARMUNA | 0.3499 | KM | NL01ML15 | 0.54 | NL01ML15 | 0.89 | KM |  |  |  |  | 15.54 | 15.89 | 2025-06-30 | SINGLE |  |  |  | 4.5 | 1.7 | 3 | 3.4 | 1 | 15.3 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 15.530km to 16.200km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 15.400 - 15.490km <(>&<)> 15.890 - 16.300km NL-01ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Formation failure <(>&<)> twist defect D7 at 14.100km (Covered by FY23 Scope) • Track geometry poor 15.480 - 15.750km (D7 Twist x3) • General subgrade material = Clay, no expected capping layer, typical soaked CBR of subgrade 2-3 • DCP test 2005/06 results: 13.500km = 5, 14.000km = 3, 14.500km = 3, 15.000km = 5, 15.500km = 2 • Merinda Depot feedback - Poor formation continues through to 18.400km Adjacent Site History: 13.950 - 14.000km Formation Renewal (IM FY22) (Notification Unknown) 14.000 - 14.050km No evidence of renewal - will need to be managed under FoF 14.050 - 14.070km Culvert 14.070 - 14.390km Formation Renewal (CM FY23) (002000052754) 14.410 - 14.440km Culvert (Renewed in FY21) 14.440 - 14.590km No evidence of renewal - will need to be managed under FoF 14.590 – 14.625km Bridge 14.600 - 14.825km Formation Renewal (CM FY22) (002000052263) 14.825 - 14.925km CM FY21? (Notification Unknown) 14.925 - 15.400km Formation Renewal (CM FY22) (002000064181) 15.400 - 15.490km No evidence of renewal - will need to be managed under FoF 15.490 - 15.540km Level Crossing – Formation Renewal to be completed in conjunction with future renewal 15.540 - 15.890km Proposed FY25 Renewal (002000115216)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115194&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115194 | C05-FR-BW-CALLEMONDAH-541.5km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.115 | KM | 787154 | Blackwater | CALLEMONDAH | MOUNT MILLER | 0.115 | KM | BW01ML541 | 0.5 | BW01ML541 | 0.6149 | KM |  |  |  |  | 541.5 | 541.615 | 2025-06-30 | UP |  |  |  | 4.5 | 4.8 | 3 | 4.2 | 1 | 18.9 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 541.490km to 541.700km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 541.200km to 541.500km (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50-70% (Refer attached Geotech report). The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Rerailed in FY22 (002000067298) 20.06.2023 Unsuitable Allowance updated, Geotech Report attached and emailed advice to Construction Manager. 09.08.2023 Reduced Additional DCP testing requirements from 541.200km to 541.615km to 541.200km to 541.500km as discussed with Construction Manager
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115195&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115195 | C05-FR-BW-MARMOR-604.809km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.706 | KM | 3605986 | Blackwater | MARMOR | BAJOOL | 0.7059 | KM | BW01ML604 | 0.809 | BW01ML605 | 0.515 | KM |  |  |  |  | 604.809 | 605.515 | 2025-06-30 | UP |  |  |  | 3.8 | 4.1 | 3.5 | 4.6 | 1 | 17.6 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 604.650km to 605.630km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Tie into formation completed in conjunction with Bajool Turnout renewal in FY23 (002000043305 / 80108263)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115215&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115215 | C05-FR-NL-Pring-5.100km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 2146489 | Newlands | PRING | BUCKLEY | 0.4 | KM | NL01ML5 | 0.1 | NL01ML5 | 0.5 | KM |  |  |  |  | 5.1 | 5.5 | 2025-06-30 | MAIN |  |  |  | 4.3 | 1.7 | 3 | 3.4 | 1 | 14.7 |  | 2023-10-13 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 5.070km to 6.030km RHS of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 4.700km to 5.100km, NL-01ML (Section adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Adjoins Notification 002000052751 (5.500km – 5.865km, FY23) • 3 x Reactive Formations completed 2017 – 2018 covering 5.861 - 5.961km <(>&<)> 6.031 - 6.254km. • Track geometry issues 5.1 - 5.2km, previously under TSR (D7 Twist), deteriorated from 2021 to 2022. • From 2005/06 Report: General subgrade material = Clay, no expected capping layer, typical soaked CBR of subgrade 3, DCP test result 3 @5.000km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077799&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077799 | Formation C05 Reactive Works | BW | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 3790343 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077832&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077832 | Formation C05 Reactive Works | GA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 3009978 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077831&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077831 | Formation C05 Reactive Works | MA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1599748 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077833&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077833 | Formation C05 Reactive Works | NL | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 535107 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077881&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077881 | FORMATION GEOTECH DESIGN | BW | CIVIL | FORMATION | GEOTECH | DESIGN | 0 | LUMPSUM | 44331 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077882&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077882 | FORMATION GEOTECH DESIGN | GA | CIVIL | FORMATION | GEOTECH | DESIGN | 0 | LUMPSUM | 44331 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077883&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077883 | FORMATION GEOTECH DESIGN | MA | CIVIL | FORMATION | GEOTECH | DESIGN | 0 | LUMPSUM | 44331 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077884&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077884 | FORMATION GEOTECH DESIGN | NL | CIVIL | FORMATION | GEOTECH | DESIGN | 0 | LUMPSUM | 44331 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077865&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077865 | CIVIL GPR RUN BLACKWATER | BW | CIVIL | GPR RUN |  | ASSESSMENT | 0 | LUMPSUM | 779592 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 27.05.2021 12:03:01 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE. APPROX KM BASED ON FY21 SCOPE = 954.068KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077866&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077866 | CIVIL GPR RUN GOONYELLA | GA | CIVIL | GPR RUN |  | ASSESSMENT | 0 | LUMPSUM | 699363 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 27.05.2021 12:03:02 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE FOR FUTURE YEARS SCOPE HANDOVER. SCOPE BASED ON FY21 SUBMISSION IS 796.421KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077862&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077862 | CIVIL GPR RUN NEWLANDS | NL | CIVIL | GPR RUN |  | ASSESSMENT | 0 | LUMPSUM | 234884 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Ground Penetrating Radar | LIKE FOR LIKE |  |  |  |  | Outstanding notification | RRIG |  | 20250630 | * 27.05.2021 12:02:45 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN SCOPE AS REQUIRED FOR SCOPING FUTURE YEARS. KILOMETRES FROM FY21 SCOPE WAS 282.556KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083395&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000083395 | C58-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 0 | LUMPSUM | 207532 | Blackwater | BW | BW | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 4.9 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083396&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000083396 | C58-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 0 | LUMPSUM | 76095 | Goonyella | GA | GA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5.1 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083397&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000083397 | C58-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 0 | LUMPSUM | 207532 | Moura | MA | MA | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 1.3 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 REACTIVE WORKS Moura Systems had the most FoF money needed. Two level crossings have been attended using the entire allocation form Moura and also from sources.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083398&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000083398 | C58-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 0 | LUMPSUM | 51883 | Newlands | NL | NL | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 2.7 | 2 | 5 | 1 | 25 |  | 2023-10-13 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120595&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120595 | C58-LX-BW-BLUFF-171.08km | LX005564 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28824 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML171 | 0.1029 | BW03ML171 | 0.1029 | KM |  |  | 171.08 | 171.08 | 171.08 | 171.08 | 2025-06-30 | UNNAMED ROAD |  |  |  | 3.06 | 3.35 | 2 | 3.64 | 1 | 11.13 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120597&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000120597 | C58-LX-MA-CALLE-533.897km | LX000708 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28824 | Moura | CALLEMONDAH | YARWUN | 0 | KM | NC02ML533 | 0.893 | NC02ML533 | 0.893 | KM |  |  |  |  | 533.897 | 533.897 | 2025-06-30 | CALLEMONDAH DRIVE NCL |  |  |  | 3 | 4.8 | 2 | 4 | 1 | 12.6 | 5471 | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | PCR5471- the design of ID708 to be carried out with ID6090 in FY24. FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120593&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000120593 | C58-LX-NL-DURROBURRA-1159.574km | LX007195 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 17294 | Newlands | DURROBURRA | KAILI | 0 | KM | NC03ML1159 | 0.5729 | NC03ML1159 | 0.5729 | KM |  |  |  |  | 1159.574 | 1159.574 | 2025-06-30 | DRY CKEEK ROAD |  |  |  | 2.6 | 3.2 | 2 | 3.58 | 1 | 9.31 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122946&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic |  | COAL | 002000122946 | C58-LX-MA-EARLSFIELD-128.396km | LX006025 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 32000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML128 | 0.396 | MA01ML128 | 0.396 | KM |  |  |  |  | 128.396 | 128.396 | 2026-06-30 | BILOELA JAMBIN ROAD |  |  |  | 3.4 | 1.1 | 2 | 3 | 1 | 10.2 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Pushed to FY26 renewal. AS per the mtg on 28 July 2022 with the IM team. FY25 Design for FY26 Delivery with the signal design in FY25 (N4 2000123395).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120599&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120599 | C58-LX-GA-HAY POINT-5.518km | LX020011 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28824 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA5 | 0.506 | GA01BA5 | 0.506 | KM |  |  |  |  | 5.518 | 5.518 | 2025-06-30 | ACCESS RD HAY PT ARRIVAL |  |  |  | 2.28 | 3.2 | 2 | 3.58 | 1 | 8.16 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120594&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120594 | C58-LX-MA-PARANA-10.354km | LX006090 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 40852 | Moura | PARANA | CALLEMONDAH | 0 | KM | MA01ML10 | 0.3569 | MA01ML10 | 0.3569 | KM |  |  |  |  | 10.354 | 10.354 | 2025-06-30 | CALLEMONDAH DRIVE |  |  |  | 4.2 | 3.2 | 2 | 3.58 | 1 | 15.04 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | To be designed with LX000708/Same design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120601&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000120601 | C58-LX-BW-RAGLAN-588.78km | LX001717 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28824 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW01ML588 | 0.778 | BW01ML588 | 0.778 | KM |  |  | 588.78 | 588.78 | 588.78 | 588.78 | 2025-06-30 | TWELVE MILE ROAD |  |  |  | 3.18 | 1.3 | 2 | 2.59 | 1 | 8.24 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135366&DY_MAB=X&~OKCODE=ONLI | FY25 | RIM Infrastructure | FUTURE SCOPE | RIM | 002000135366 | C40-LX-QAL-NC-04ML-1.125km | LX000785 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28000 | Moura | SOUTH GLADSTONE | QAL | 0 | KM | NC04ML1 | 0.127 | NC04ML1 | 0.127 | KM | 2 |  | 0.22 | 0.22 | 1.125 | 1.125 | 2026-06-30 | QAL ACCESS ROAD |  |  |  | 3.5 | 2.3 |  |  |  | 7.86 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | FY25 IFP <(>&<)> FY25 IFC for FY26 Renewal (Non-RIG)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120602&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000120602 | C58-LX-BW-WARREN-36.715km | LX001079 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28824 | Blackwater | WARREN | WYCARBAH | 0 | KM | BW03ML36 | 0.7099 | BW03ML36 | 0.7099 | KM |  |  |  |  | 36.715 | 36.715 | 2025-06-30 | ROSEWOOD ROSE |  |  |  | 2.9 | 3.4 | 2 | 4 | 1 | 10.6 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Update the DESIGN (Update the existing IFC) to match the new requirements. FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101686&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000101686 | C58-LX-MA-CALLE-16.416km | LX005753 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 28824 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML16 | 0.4179 | MA01ML16 | 0.4179 | KM |  |  |  |  | 16.416 | 16.416 | 2025-06-30 | JEFFERIES ROAD |  |  |  | 3.2 | 1.3 | 2 | 3 | 1 | 9.6 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Originally kept in FY26 Design for FY27 Renewal as per the mtg with Geoff O'Connor. Dec. 2022 Changed to FY25 Design for FY27 Renewal due to increased maintenance activities and poor formation witnessed during recent undercut in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111104&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000111104 | C58-LX-NL-COLLINSVILLE-77.186km | LX003301 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 28824 | Newlands | COLLINSVILLE | MCNAUGHTON | 0 | KM | NL01ML77 | 0.1859 | NL01ML77 | 0.1859 | KM |  |  |  |  | 77.186 | 77.186 | 2025-06-30 | BOWEN DEVELOPMENT ROAD |  |  |  | 3.3 | 2.5 | 2 | 3 | 1 | 10.6 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 Design for FY27 Renewal. This crossing is being put forward for alternative surface (Bodan preferably).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051942&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic |  | COAL | 002000051942 | C58-LX-MA-EARLSFIELD-128.4km | LX006025 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML128 | 0.399 | MA01ML128 | 0.399 | KM |  |  |  |  | 128.4 | 128.4 | 2026-06-30 | BILOELA JAMBIN ROAD |  |  |  | 3.4 | 1.1 | 2 | 3 | 1 | 10.2 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20240630 | FY25 Design (IFP) for FY26 Delivery (both Civil <(>&<)> Signal)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135347&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000135347 | C58-LX-MA-FRY-MA-01ML-89.560km | LX006516 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 43000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.56 | MA01ML89 | 0.56 | KM | 2 |  | 0.22 | 0.22 | 89.56 | 89.56 | 2025-06-30 | MAINTENANCE ACCESS ROAD |  |  |  | 4.17 | 2.66 | 2 | 3.34 | 1 | 10.8 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | PCR 5859 to include the design of LX6516
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101984&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000101984 | C58-LX-GA-JILALAN-28.84km | LX003500 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Goonyella | JILALAN | YUKAN | 0 | KM | GA01ML28 | 0.8409 | GA01ML28 | 0.8409 | KM |  |  |  |  | 28.84 | 28.84 | 2025-06-30 | BORGS ACCESS RD |  |  |  | 3.2 | 4.2 | 2 | 4 | 1 | 12.8 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 Design for FY27 Renewal. QR to be informed by the project team about this upcoming works. The Borgs (the property owner) to be advised by Community Engagement about the work in due course. Although there are seven tracks, renewal works to be completed for Goonyella Up and Down tracks only.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068851&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000068851 | C58-LX-BW-MT LARCOM-570.366km | LX000640 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 53538 | Blackwater | MOUNT LARCOM | EPALA | 0 | KM | BW01ML570 | 0.3639 | BW01ML570 | 0.3639 | KM |  |  | 570.366 | 570.366 | 570.366 | 570.366 | 2024-06-30 | DARTS CREEK ROAD |  |  |  | 3.16 | 4.1 | 2 | 3.92 | 1 | 12.39 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20240630 | PCR 5858 to align with the TO design. FY24 DESIGN for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101049&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000101049 | C58-LX-BW-MT LARCOM-576.77km | LX005586 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Blackwater | MT LARCOM | EPALA | 0 | KM | BW01ML576 | 0.771 | BW01ML576 | 0.771 | KM |  |  |  |  | 576.77 | 576.77 | 2025-06-30 | EPALA LANE |  |  |  | 3.2 | 4.1 | 2 | 4 | 1 | 12.8 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Crossing km was reviewed and found to be 576.773km. ID640 and ID1717 took priority in FY24 over ID5586. Moved ID5586 to FY25 Design based on the discussion on 11 July 2022 with the Gracemere district.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137969&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000137969 | C58-LX-GA-NORWICH PARK-120.716 | LX003629 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM | 2 |  |  |  | 120.756 |  |  | BOOROONDARRA ROAD |  |  |  | 10 | 1.5 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135365&DY_MAB=X&~OKCODE=ONLI | FY25 | RIM Infrastructure | FUTURE SCOPE | RIM | 002000135365 | C40-LX-QAL-NC-04ML-1.125km | LX000785 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 43000 | Moura | SOUTH GLADSTONE | QAL | 0 | KM | NC04ML1 | 0.127 | NC04ML1 | 0.127 | KM | 2 |  | 0.22 | 0.22 | 1.125 | 1.125 | 2025-06-30 | QAL ACCESS ROAD |  |  |  | 3.5 | 2.3 |  |  |  | 7.86 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | FY25 Design (IFP <(>&<)> IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103558&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000103558 | C58-LX-BW-WALTON-163.87km | LX005562 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML163 | 0.9569 | BW03ML163 | 0.9569 | KM |  |  |  |  | 163.87 |  | 2025-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 2 | 3.4 | 2 | 4 | 1 | 7.32 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FY25 DESIGN FOR FY27 CONSTRUCTION.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068847&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068847 | C58-LX-BW-BOORGOON-42.425km | LX006951 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 957514 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML42 | 0.4249 | BW06ML42 | 0.4249 | KM | 2 |  |  |  | 42.425 | 42.425 | 2025-06-30 | COMET ROLLESTON RD |  |  |  | 3.5 | 2.3 | 2 | 3 | 1 | 10.7 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | FY25 Renewal. DD50 Design Doc added in SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041548&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000041548 | C58-LX-MA-BOUNDARY HILL-125.2km | LX006022 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1325905 | Moura | BOUNDARY HILL | EARLSFIELD | 0 |  |  | 0 |  | 0 | KM | 2 |  | 125.2 | 125.2 | 125.2 | 125.2 | 2025-06-30 | EARLSFILED PIT ROAD |  |  |  | 4.4 | 1.3 | 2 | 3 | 1 | 13.2 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | * 07.08.2019 14:55:21 AUSQLD Jeremy Stevenson (R867415) * Earlsfield Pit Road FY21 Q3 Renewal Scope # * Moura Line Upgrade * Asset ID 6022 - Condition - * Public Crossing Asset ID 6022 - Condition is due to be completed in May 2022. Public Crossing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083379&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000083379 | C58-LX-BW-DUARINGA-115.758km | LX005558 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1438067 | Blackwater | DUARINGA | WALLAROO | 0 | KM | BW03ML115 | 0.758 | BW03ML115 | 0.758 | KM | 3 |  |  |  | 115.758 | 115.758 | 2025-06-30 | WABBLER ROAD |  |  |  | 4.3 | 3 | 2 | 4 | 1 | 17.2 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630 | FY25 MAJOR RENEWAL. DD50 Design Docs ADDED IN SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044071&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000044071 | C58-LX-BW-EPALA-579.84km | LX005587 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1348965 | Blackwater | EPALA | RAGLAN | 0 | KM | BW01ML579 | 0.8289 | BW01ML579 | 0.8289 | KM | 0 |  |  |  | 579.84 | 579.84 | 2025-06-30 |  |  |  |  | 3.5 | 4.1 | 2 | 4 | 1 | 14 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | DESIGN SHALL STAY IN FY23 BUT THE RENEWAL SHALL BE ADDED IN FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088578&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000088578 | C58-LX-GA-HAY POINT BALLOON-3.1km | LX007377 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1438067 | Goonyella | HAY POINT BALLOON | HAY POINT BALLOON | 0 | KM | GA01BA3 | 0.1 | GA01BA3 | 0.1 | KM | 4 |  | 3.1 | 3.1 | 3.1 | 3.1 | 2025-06-30 | MAINTENANCE ACCESS ROAD |  |  |  | 3.6 | 4.6 | 2 | 4 | 1 | 14.75 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | FY25 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088581&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000088581 | C58-LX-GA-INGSDON-10.935km. | LX003251 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1606310 | Goonyella | INGSDON | RED MOUNTAIN | 0 | KM | GA03ML10 | 0.935 | GA03ML10 | 0.935 | KM | 4 |  | 10.935 | 10.935 | 10.935 | 10.935 | 2025-06-30 | BARADA BARNA ROAD |  |  |  | 3.68 | 3.66 | 2 | 4 | 1 | 14.7 |  | 2023-10-13 |  | Level Crossing Renewals | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | FY25 RENEWAL. DD50 added in SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123395&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000123395 | C58-LX-MA-EARLSFIELD-128.395km | LX006025 | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 196002 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML128 | 0.396 | MA01ML128 | 0.396 | KM |  |  |  |  | 128.395 | 128.395 | 2025-06-20 |  |  |  | DESIGN SIGNAL | 10 | 1.1 | 2 | 10 | 1 | 100 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123399&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000123399 | C58-LX-MA-EARLSFIELD-0.225km | LX006554 | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 196002 | Moura | EARLSFIELD | CALLIDE | 0 | KM | MA02ML0 | 0.224 | MA02ML0 | 0.224 | KM |  |  |  |  | 0.225 | 0.225 | 2025-06-30 |  |  |  | DESIGN SIGNAL | 10 | 1 | 2 | 10 | 1 | 100 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110809&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000110809 | C17 BW AMBROSE 573.640 - 575.750 | BW-01ML | CIVIL | RAIL |  | RENEWAL | 4.212 | RAIL KM | 1449516 | Blackwater | AMBROSE | EPALA | 2.156 | KM | BW01ML573 | 0.64 | BW01ML575 | 0.75 | KM | 40 |  | 4.212 | 2.156 | 573.64 | 575.75 | 2025-06-30 | UP | BOTH |  |  | 4 | 4.1 | 1 | 3.5 | 1 | 16 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071056&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000071056 | C17 BW EPALA 575.810 - 576.753 | CV006590 | CIVIL | RAIL |  | RENEWAL | 1.944 | RAIL KM | 669007 | Blackwater | AMBROSE | EPALA | 0.9469 | KM | BW01ML575 | 0.81 | BW01ML576 | 0.753 | KM | 18 |  | 1.944 | 0.947 | 575.81 | 576.753 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 4.1 | 1 | 3.5 | 1 | 13.3 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut in at 12C/D Pts @ 575.810km Cut out at LX5586 @ 576.573km Removing worn 1991 BHP SC rail CV006590 worn to 19.5mm on high leg (7.12.22)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110803&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000110803 | C17 BW AROONA 96.470 - 96.713 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 355928 | Blackwater | AROONA | DUARINGA | 0.2429 | KM | BW03ML96 | 0.4699 | BW03ML96 | 0.7129 | KM | 5 |  | 0.54 | 0.243 | 96.47 | 96.713 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 12 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058735&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000058735 | C17 GA BALOOK 79.570 - 80.546 | CV002995 | CIVIL | RAIL |  | RENEWAL | 1.944 | RAIL KM | 879796 | Goonyella | BALOOK | WANDOO | 0.9789 | KM | GA02ML79 | 0.5699 | GA02ML80 | 0.546 | KM | 18 |  | 1.944 | 0.797 | 79.57 | 80.546 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.8 | 1 | 3.8 | 1 | 13.3 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070893&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070893 | C17 BW BLUFF 170.427 - 170.583 | CV006346 | CIVIL | RAIL |  | RENEWAL | 0.324 | RAIL KM | 229378 | Blackwater | BLUFF | BOONAL | 0.2389 | KM | BW03ML171 | 0.534 | BW03ML171 | 0.773 | KM | 3 |  | 0.324 | 0.156 | 170.427 | 170.583 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.4 | 1 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Complete with 2000071046
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071046&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071046 | C17 BW BLUFF 170.583 - 170.751 | CV007552 | CIVIL | RAIL |  | RENEWAL | 0.324 | RAIL KM | 229378 | Blackwater | BLUFF | BOONAL | 0.168 | KM | BW03ML170 | 0.5829 | BW03ML170 | 0.751 | KM | 3 |  | 0.324 | 0.168 | 170.583 | 170.751 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.4 | 1 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Complete with 2000070893
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114491&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal GAPE Traffic | BASELOAD | COAL | 002000114491 | C17 NL BRIABA 65.844 - 66.231 | NL-03ML | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 422360 | Newlands | BRIABA | ALMOOLA | 0.387 | KM | NL03ML65 | 0.8439 | NL03ML66 | 0.231 | KM | 8 |  | 0.864 | 0.387 | 65.844 | 66.231 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 1.7 | 1 | 2.2 | 1 | 8.36 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061440&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000061440 | C17 BW CALLEMONDAH 537.072 - 537.681 | CV005852 | CIVIL | RAIL |  | RENEWAL | 1.118 | RAIL KM | 540060 | Blackwater | CALLEMONDAH | MOUNT MILLER | 0.6089 | KM | BW01ML537 | 0.0719 | BW01ML537 | 0.681 | KM | 11 |  | 1.188 | 0.609 | 537.072 | 537.681 | 2025-06-30 | UP | BOTH |  |  | 4 | 4.8 | 1 | 3.8 | 1 | 15.2 | 209 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | 14/1/2023 Originally included to align with Calliope River Bridge works. Due to the need to complete independantly as a result of an AT location, can defer to FY25 Originally wanted to be completed with 002000070700 (Nov 22) This one needs the cut out to change to 537.681 - to tie into FY24 job - this is due to the BBR was bought into FY24 therefore the rail across the bridge was bought into FY24 - PCR was not changed approved before MRSB final submission hence 34 rails was submitted for FY25 submission (31/03/2025).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110805&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000110805 | C17 BW CLINTON SPUR 1.390 - 1.710 | BW-22YR | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 351073 | Blackwater | CLINTON SPUR | CLINTON SPUR | 0.32 | KM | BW22YR1 | 0.39 | BW22YR1 | 0.7099 | KM | 6 |  | 0.648 | 0.32 | 1.39 | 1.71 | 2025-06-30 | DOWN | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 11.2 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070999&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000070999 | C17 GA DALRYMPLE BAY 8.331 - 9.388 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 2.16 | RAIL KM | 917345 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 168.2899 | KM | GA02ML8 | 0.33 | GA02ML176 | 0.8179 | KM | 20 |  | 2.16 | 1.066 | 8.331 | 9.388 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 | 227 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | POST SITE WALKOUTS: "Split Scope into two notifications: First one wil be 8.331 - 9.388 - re rail only 10 pair rails second one will be 9.679 - 10.015 - 3 pair rail Reason for Change - Already 2 rails inserted from 9.388km to start of bridge. Grasstree beach rd Bridge planned to be rerailed with 2 pairs of rails in FY24 upto 9.676km Was 32 rails now 26 rails" SCR 227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118505&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000118505 | C17 GA DALRYMPLE BAY 9.679 - 10.015 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 552238 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0.335 | KM | GA02ML9 | 0.679 | GA02ML10 | 0.0149 | KM | 6 |  | 0.648 | 0.335 | 9.679 | 10.015 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 | 228 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | POST SITE WALKOUT Split Scope into two notifications: First one wil be 8.331 - 9.388 - re rail only 10 pair rails second one will be 9.679 - 10.015 - 3 pair rail Reason for Change - Already 2 rails inserted from 9.388km to start of bridge. Grasstree beach rd Bridge planned to be rerailed with 2 pairs of rails in FY24 upto 9.676km" SCR - 228
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070991&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070991 | C17 GA DALRYMPLE BAY 12.321-12.861 | CV002838 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 554101 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0.54 | KM | GA02ML12 | 0.321 | GA02ML12 | 0.8609 | KM | 10 |  | 1.08 | 0.54 | 12.321 | 12.861 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071132&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071132 | C17 BW DUARINGA 114.190 - 114.915 | CV006269 | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 669471 | Blackwater | DUARINGA | WALLAROO | 0.7249 | KM | BW03ML114 | 0.19 | BW03ML114 | 0.915 | KM | 14 |  | 1.512 | 0.725 | 114.19 | 114.915 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 3.4 | 1 | 3.2 | 1 | 12.16 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122405&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000122405 | C17 BW FISHERMANS LANDING 0.670 - 1.432 | BW-20ML | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 799086 | Blackwater | FISHERMANS LANDING | FISHERMANS LANDING | 0.762 | KM | BW20ML0 | 0.67 | BW20ML1 | 0.4319 | KM | 14 |  | 1.512 | 0.762 | 0.67 | 1.432 | 2025-06-30 | SINGLE | BOTH |  |  | 4 | 0.9 | 1 | 1.4 | 1 | 5.6 | 245 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Scope was originally identified as NON RIG at time of scope handover - since the RAB was checked and location is considered as RIG. SCR - 245
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111624&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111624 | C17 MA FRY 79.700 - 80.990 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 1.291 | RAIL KM | 732519 | Moura | FRY | MOUNT RAINBOW | 1.2909 | KM | MA01ML79 | 0.6999 | MA01ML80 | 0.9899 | KM | 24 |  | 2.572 | 1.201 | 79.7 | 80.99 | 2025-06-30 | SINGLE | BOTH |  |  | 4 | 1.3 | 1 | 1.8 | 1 | 7.2 | 207 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Removing 1996 /97 BHP Rail Field side flow on high leg. RCF on low leg Tie into start of FY23 re rail @ 80.985km LX6001 @ 80.076km Survey and Monuments required HD Insulators currently installed only on the field side of curve. Renew with HD insulators on Gauge side as well Changed from 80.985 to 80.900 at the cutout due to more accurate end from post site walkout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111625&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111625 | C17 MA FRY 85.210 - 86.125 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 1.832 | RAIL KM | 1039486 | Moura | FRY | MOUNT RAINBOW | 0.916 | KM | MA01ML85 | 0.2099 | MA01ML86 | 0.125 | KM | 17 |  | 1.832 | 0.916 | 85.21 | 86.125 | 2025-06-30 | SINGLE | BOTH |  |  | 4 | 1.3 | 1 | 1.8 | 1 | 7.2 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | CV007023 (85.241 - 85.640km) 300m Radius, Right CV007024 (85.652 - 86.021km) 302m Radius, Left Removing BHP 1996 / 97 Lubricator at 86.075km HD Insulators required for gauge side (already installed on field side) Survey and monument required
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111626&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111626 | C17 MA FRY 86.880 - 87.720 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 1.728 | RAIL KM | 980475 | Moura | FRY | MOUNT RAINBOW | 0.8389 | KM | MA01ML86 | 0.88 | MA01ML87 | 0.7199 | KM | 16 |  | 1.728 | 0.839 | 86.88 | 87.72 | 2025-06-30 | SINGLE | BOTH |  |  | 4 | 1.3 | 1 | 1.8 | 1 | 7.2 | 208 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | LOW | Notification in process | SCPR |  | 20250630 | Change cut out to 87.720 to tie into FY24 re rail - removes 1996 rail from mountain - known defect location - increase from 14 rails to 16 rails - FY24 Job 002000043639
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111691&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111691 | C17 BW GORDONSTONE 7.481 - 7.755 | BW-10ML | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 240914 | Blackwater | GORDONSTONE | GORDONSTONE | 0.274 | KM | BW10ML7 | 0.4809 | BW10ML7 | 0.755 | KM | 5 |  | 0.54 | 0.274 | 7.481 | 7.755 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111692&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111692 | C17 BW GORDONSTONE 7.790 - 8.100 | BW-10ML | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 289097 | Blackwater | GORDONSTONE | GORDONSTONE | 0.3079 | KM | BW10ML7 | 0.79 | BW10ML8 | 0.1 | KM | 6 |  | 0.648 | 0.308 | 7.79 | 8.1 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107947&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000107947 | C17 GA HATFIELD 50.530 - 51.079 | CV002946 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 625010 | Goonyella | HATFIELD | BOLINGBROKE | 0.55 | KM | GA02ML50 | 0.53 | GA02ML51 | 0.079 | KM | 11 |  | 1.188 | 0.55 | 50.53 | 51.079 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.65 | 234 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | POST WALKOUT - Changed cut in location from 50.600 to 50.530 as there is a re rail in FY24 finishing at 50.530. This increases the rail qty by 2
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070727&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070727 | C17 GA JILALAN 22.636 - 23.230 | CV002866 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 580726 | Goonyella | JILALAN | YUKAN | 0.4899 | KM | GA01ML22 | 0.636 | GA01ML23 | 0.23 | KM | 9 |  | 0.972 | 0.487 | 22.636 | 23.23 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 4.8 | 1 | 3.8 | 1 | 17 | 212 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Change end km due to not putting new rail onto back of turnout (removes height difference between new rail <(>&<)> old rail)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070699&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000070699 | C17 BW MARMOR 600.794 - 601.525 | CV005938 | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 620677 | Blackwater | MARMOR | BAJOOL | 0.6929 | KM | BW01ML600 | 0.794 | BW01ML601 | 0.525 | KM | 13 |  | 1.404 | 0.693 | 600.794 | 601.525 | 2025-09-30 | UP | BOTH |  |  | 3.5 | 4.1 | 1 | 3.9 | 1 | 13.65 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Lower chainage extents ties into RRP (25/05/2021) Higher chainage extents ties into Sisalana Rd LX 1006 which was renewed in FY21 Removing worn rail in curve and 1993 BHP 60kg S.C between curve and LX1006 Must be completed in Q1 FY25 - cannot push further - due to rail wear
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114430&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114430 | C17 GA MCARTHUR 138.600 - 139.296 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 630748 | Goonyella | MCARTHUR | COPPABELLA | 0.6939 | KM | GA02ML138 | 0.5999 | GA02ML139 | 0.2959 | KM | 13 |  | 1.404 | 0.694 | 138.6 | 139.296 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | BACK TO BACK SCOPES 137.180 - 138.600 - TU 27 rails + 2070 sleepers 138.600 - 139.296 - RR ONLY 13 rails 139.296 - 141.523 - TU 42 rails + 3251 sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114386&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114386 | C17 GA MINDI 126.405 - 127.024 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 615118 | Goonyella | MINDI | SOUTHWALKER | 0.6169 | KM | GA02ML126 | 0.405 | GA02ML127 | 0.024 | KM | 12 |  | 1.296 | 0.617 | 126.405 | 127.024 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Removing 1998 BHP SC Rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070986&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070986 | C17 GA JILALAN 16.980 - 17.311 | CV002850 | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 478161 | Goonyella | PRAGUELANDS | JILALAN | 0.328 | KM | GA02ML16 | 0.9799 | GA02ML17 | 0.3109 | KM | 6 |  | 0.684 | 0.326 | 16.98 | 17.311 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137783&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic |  |  | 002000137783 | C17 GA RIVERSIDE LOADOUT 203.465-203.527 | GA-14ML | CIVIL | RAIL |  | RENEWAL | 0.108 | RAIL KM | 50000 | Goonyella | RIVERSIDE LOADOUT | RIVERSIDE LOADOUT | 0.0619 | KM | GA14ML203 | 0.465 | GA14ML203 | 0.527 | KM | 1 |  | 0.108 | 0.62 | 203.465 | 203.527 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.1 | 1 | 1.6 | 1 | 5.6 | [9 empty] | Outstanding notification | NWSC |  | 00000000 | This scope is to replace rail at the same time as the mine complete's loadout structure renewal. This will be taken to change board for approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114387&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114387 | C17 GA SOUTHWALKER 127.064 - 127.247 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.432 | RAIL KM | 205039 | Goonyella | SOUTH WALKER | TOOTOOLAH | 0.1829 | KM | GA02ML127 | 0.064 | GA02ML127 | 0.2469 | KM | 4 |  | 0.432 | 0.183 | 127.064 | 127.247 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115599&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115599 | C17 GA SOUTHWALKER 130.217 - 132.667. | GA-02ML | CIVIL | RAIL |  | RENEWAL | 4.968 | RAIL KM | 1694820 | Goonyella | SOUTH WALKER | TOOTOOLAH | 2.447 | KM | GA02ML130 | 0.2169 | GA02ML132 | 0.667 | KM | 46 |  | 4.968 | 2.447 | 130.217 | 132.667 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 4.7 | 1 | 3.8 | 1 | 18 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114388&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114388 | C17 GA SOUTHWALKER 127.310 - 129.405 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 4.212 | RAIL KM | 1550995 | Goonyella | SOUTHWALKER | TOOTOOLAH | 2.1009 | KM | GA02ML127 | 0.3099 | GA02ML129 | 0.405 | KM | 39 |  | 4.212 | 2.095 | 127.31 | 129.405 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 | 215 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | "Scope change. Left rail will now be 127.310 - 129.405. Right Rail will now be 127.316 - 129.405km. Asset Manager to send Change Request. Reducing scope on Left rail at Lower chainage due to existing rail condition. Increasing scope on Higher Chainage to join on proposed FY25 Track Upgrade @129.405-130.217 UP RD"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118532&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000118532 | C17 GA SOUTHWALKER 132.716 - 132.818 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.216 | RAIL KM | 131200 | Goonyella | SOUTHWALKER | TOOTOOLAH | 0.1019 | KM | GA02ML132 | 0.7159 | GA02ML132 | 0.8179 | KM | 2 |  | 0.216 | 0.102 | 132.716 | 132.818 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 4.7 | 1 | 3.8 | 1 | 18 | 230 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | POST SITE WALKOUT - Scope addition of 2 rails to replace rail between 8C/D <(>&<)> 12A/B as requested by the inspectors as the rail within this section is the same as adjacent rail - fatigued SCR - 230
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108736&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000108736 | C17 GA SOUTHWALKER 132.870 - 133.153 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 393602 | Goonyella | SOUTHWALKER | TOOTOOLAH | 0.281 | KM | GA02ML132 | 0.8699 | GA02ML133 | 0.1529 | KM | 6 |  | 0.648 | 0.281 | 132.87 | 133.153 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110791&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000110791 | C17 BW WARREN 23.578 - 24.272 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 644054 | Blackwater | STANWELL | WARREN | 0.7069 | KM | BW03ML23 | 0.5779 | BW03ML24 | 0.272 | KM | 13 |  | 1.404 | 0.707 | 23.578 | 24.272 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 12 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | This one is between Warren 102B Pts and joins to 2014 RRP at 24.272km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061373&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000061373 | C17 BW WARREN 26.734 - 27.500 | CV006059 | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 701717 | Blackwater | STANWELL | WARREN | 0.769 | KM | BW03ML26 | 0.7339 | BW03ML27 | 0.5 | KM | 14 |  | 1.512 | 0.764 | 26.734 | 27.5 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 11.2 | 234 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cutting in at 26.734 and cutting out at Warren 7C/D Removing welds back at Turnout has increased the scope at higher chainage. No material changed required
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071148&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071148 | C17 BW TUNNEL 75.892 - 76.535 | CV006189 | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 561012 | Blackwater | TUNNEL | EDUNGALBA | 0.64 | KM | BW04ML75 | 0.892 | BW04ML76 | 0.535 | KM | 12 |  | 1.296 | 0.64 | 75.892 | 76.535 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 3.8 | 1 | 3.4 | 1 | 12.9 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071147&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071147 | C17 BW TUNNEL 75.964 - 76.537 | CV006188 | CIVIL | RAIL |  | RENEWAL | 1.188 | RAIL KM | 514261 | Blackwater | TUNNEL | EDUNGALBA | 0.5689 | KM | BW03ML75 | 0.9639 | BW03ML76 | 0.537 | KM | 11 |  | 1.188 | 0.569 | 75.964 | 76.537 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 3.75 | 1 | 3.4 | 1 | 14 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut in at T.O.S of #7C/D Curve located within cutting (76.057 - 76.385km) #7C/D Pts at lower chainage of re rail Previous re rail 75.950 - 76.572km (28/07/2014)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071140&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071140 | C17 BW TUNNEL 77.024 - 77.730 | CV006193 | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 539885 | Blackwater | TUNNEL | EDUNGALBA | 0.7059 | KM | BW04ML77 | 0.024 | BW04ML77 | 0.7299 | KM | 13 |  | 1.404 | 0.706 | 77.024 | 77.73 | 2025-06-30 | UP | BOTH |  |  | 4 | 3.75 | 1 | 3.4 | 1 | 13.6 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | * 18.03.2021 18:14:43 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail * 77.024km 77.726km * BW - 04ML - UP * Both Rails - 13 rails * Renewals driven by wear * Q1 or Q2
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058444&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000058444 | C17 BW TUNNEL 77.730 - 78.707 | CV006195 | CIVIL | RAIL |  | RENEWAL | 1.944 | RAIL KM | 747534 | Blackwater | TUNNEL | EDUNGALBA | 0.9779 | KM | BW04ML77 | 0.7299 | BW04ML78 | 0.7069 | KM | 18 |  | 1.944 | 0.978 | 77.73 | 78.707 | 2025-09-30 | UP | BOTH |  |  | 3.3 | 3.75 | 1 | 3.4 | 1 | 11.22 | 238 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Equality 77km 1008.22m = 78km post 09/07/2013 High leg / Left Replaced 9 rails with 60kg HH 77.734 - 78.652km Post walkout - changed cut out point to 78.707 - reducing 0.5rails on both legs. Reduced scope at higher chainage due to better access <(>&<)> no change in rail condition further into cutting. Future rerail to join at this location. SCR 238
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107764&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000107764 | C17 GA WAITARA 97.640 - 98.035 | CV003023 | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 495072 | Goonyella | WANDOO | WAITARA | 0.403 | KM | GA02ML97 | 0.64 | GA02ML98 | 0.035 | KM | 8 |  | 0.864 | 0.403 | 97.64 | 98.035 | 2025-12-31 | UP | BOTH |  |  | 3.5 | 5 | 1 | 3.9 | 1 | 13.65 | 214 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | POST SITE WALKOUT: Changed cut in from 97.664km to 97.640 to cut in near bridge end as the rail is better quality here and it allows to remove the need of taper rails and reduction in welds
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070868&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070868 | C17 BW WESTWOOD 52.910 - 54.221 | CV006137 | CIVIL | RAIL |  | RENEWAL | 2.7 | RAIL KM | 1047337 | Blackwater | WESTWOOD | WINDAH | 1.3189 | KM | BW03ML52 | 0.91 | BW03ML54 | 0.221 | KM | 25 |  | 2.7 | 1.319 | 52.91 | 54.221 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 3.4 | 1 | 3.2 | 1 | 13 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Two sopes in same area due to section of tangent inbetween being completed in FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107968&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000107968 | C17 BW WESTWOOD 51.396 - 52.655 | CV006136 | CIVIL | RAIL |  | RENEWAL | 2.592 | RAIL KM | 1028264 | Blackwater | WESTWOOD | WYCARBAH | 1.266 | KM | BW03ML51 | 0.396 | BW03ML52 | 0.655 | KM | 24 |  | 2.592 | 1.266 | 51.396 | 52.655 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 12 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Two scopes in same area - section of tanget inbetween is being done in FY24. Tying into previous re rail - located within curve
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061375&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000061375 | C17 BW WYCARBAH 43.826 - 44.960 | CV006104 | CIVIL | RAIL |  | RENEWAL | 2.268 | RAIL KM | 986743 | Blackwater | WYCARBAH | WESTWOOD | 1.135 | KM | BW04ML43 | 0.8259 | BW04ML44 | 0.9599 | KM | 21 |  | 2.268 | 1.135 | 43.826 | 44.96 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070728&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070728 | C17 GA YUKAN 30.423 - 31.068 | CV002872 | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 713981 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.642 | KM | GA02ML30 | 0.4229 | GA02ML31 | 0.068 | KM | 12 |  | 1.296 | 0.642 | 30.423 | 31.068 | 2025-03-31 | UP | BOTH |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 | 239 | 2023-10-13 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Post site walkout changes made to the cut out - as it is tangent track and is on a cycle renewal. Reduction in overall scope by 2 rails. SCR - 239
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109778&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000109778 | TRACK RENEWALS FIX ON FAIL | BW | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 315000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FoF/Reactive for Blackwater System - All rail/sleepers/ track upgrade reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109777&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000109777 | TRACK RENEWALS FIX ON FAIL | GA | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 315000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FoF / Reactive Rail Renewal for Goonyella System - All rail/sleepers/ track upgrade reactive - GIJ Renewals - Slab track Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109779&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000109779 | TRACK RENEWALS FIX ON FAIL | MA | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 35000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FoF/Reactive for Moura System - All rail/sleepers/ track upgrade reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109790&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000109790 | TRACK RENEWALS FIX ON FAIL | NL | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 35000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | FoF/Reactive for Newlands System - All rail/sleepers/ track upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114969&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000114969 | BW GIJ RENEWALS | BW | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 320000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114968&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000114968 | GA GIJ RENEWALS | GA | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 340000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115006&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115006 | NL GIJ RENEWALS | NL | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 80000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115005&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115005 | MA GIJ RENEWALS | MA | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 80000 | Moura | - |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Funding for GIJ renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115620&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115620 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ BW | BW | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS | 0 | LUMPSUM | 100680 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 10 | 1 | 5.2 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Goonyella Main. The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115621&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115621 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ GA | GA | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS | 0 | LUMPSUM | 80544 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 10 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Goonyella Main. The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115983&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115983 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ MA | MA | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS | 0 | LUMPSUM | 14484 | Moura | MOURA SYSTEM | MOURA SYSTEM | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 10 | 1 | 5 | 1 | 25 | 201 | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Moura. The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115982&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115982 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ NL | NL | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS | 0 | LUMPSUM | 20136 | Newlands | NEWLANDS SYSTEM | NEWLANDS SYSTEM | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 10 | 1 | 5 | 1 | 25 | 201 | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Strategic upgrade from 16-port applicator bars to 48-port applicator bars on Newlands The intention is to achieve better application to wheels and therefore better carry distance for the grease, including less splatter and wastage. These will be used in high tonnage locations with high grease consumption rates.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092192&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000092192 | C18 BW BAJOOL PASSLOOP 604.720 - 605.466 | BW-02PL | CIVIL | SLEEPERS |  | RENEWAL | 1185 | SLEEPERS | 1445376 | Blackwater | BAJOOL PASSING LOOP | BAJOOL PASSING LOOP | 0.7459 | KM | BW02PL604 | 0.7199 | BW02PL605 | 0.466 | KM |  | 1185 |  | 0.746 | 604.72 | 605.466 | 2024-06-30 | SINGLE |  |  |  | 4 | 4.5 | 1 | 3.7 | 1 | 14.8 |  | 2023-10-13 |  | Sleeper Renewal | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20250630 | Part 1: 604.720km (back off new location of T/O 10 Bajool) - 605.215km (Stop at the TOS of ER1) - need 820 new sleepers Part 2: 605.235km (Back of ER1) - 605.466km (Stop at LLB at 46A points) - need 338 new sleepers Will need 4 x transition sets
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137384&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic |  |  | 002000137384 | C18-SR-MA-Fry-73.600km-74.300km | MA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 1009 | SLEEPERS | 654841 | Moura | FRY | FRY | 0.6909 | KM | MA01ML73 | 0.5999 | MA01ML74 | 0.2999 | KM |  | 1009 |  | 0.691 | 73.6 | 74.3 | 2024-12-31 | SINGLE |  |  |  | 4 | 1.3 | 1 | 1.8 | 1 | 7.2 | [9 empty] | Outstanding notification | NWSC |  | 00000000 | DERAILMENT DAMAGED SLEEPERS REQUIRE RENEWAL. REPLACE ALL T28 SLEEPERS TO NEW FROM 73.600KM TO 74.300KM. PICTURES ATTACHED. LOCATION: FRY MAIN LINE 73.600KM - 74.300KM. PROTECTION: TOA.B CLOSURE WORKS FY16/18 TO FY23/25 SIGNALS. 1009 Sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115498&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115498 | C18 NL KAILI 1159.887 - 1160.234 | NC-03ML | CIVIL | SLEEPERS |  | RENEWAL | 507 | SLEEPERS | 372717 | Newlands | KAILI | DURROBURRA | 0.3449 | KM | NC03ML1159 | 0.887 | NC03ML1160 | 0.234 | KM |  | 507 |  | 1.272 | 1159.887 | 1160.234 | 2025-06-30 | SINGLE |  |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 231 | 2023-10-13 |  | Sleeper Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C18 NL KAILI 1158.964 - 1160.239 change to C18 NL KAILI 1159.887 - 1160.234 - 507 sleepers change due to the previous section is covered in a TU notification was 1862 sleepers -1355 sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115499&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115499 | C18 NL KAILI 1160.777 - 1161.090 | NC-03ML | CIVIL | SLEEPERS |  | RENEWAL | 457 | SLEEPERS | 295238 | Newlands | KAILI | DURROBURRA | 0.2959 | KM | NC03ML1160 | 0.777 | NC03ML1161 | 0.0899 | KM |  | 457 |  | 0.296 | 1160.777 | 1161.09 | 2025-06-30 | SINGLE |  |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 |  | 2023-10-13 |  | Sleeper Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113659&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | NON-COAL | 002000113659 | C18 BW MAIN BURNGROVE 255.630 - 257 | BW-03ML | CIVIL | SLEEPERS |  | RENEWAL | 2000 | SLEEPERS | 1298000 | Blackwater | NOGOA | YAMALA | 1.37 | KM | BW03ML255 | 0.63 | BW03ML257 | 0 | KM |  | 2000 |  | 1.372 | 255.63 | 257 | 2025-06-30 |  |  |  |  | 4 | 1.7 | 1 | 2.1 | 1 | 8.5 | 5828 |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20250630 | Approved as part of IAR - 2000 SLEEPERS PER YEAR original scope was 257.360 - 258.730 - approx. 2000 sleepers. Due to waterfall affects from incompleted sope in FY23 new scope is between 255,630km - 257km approx. 2000 sleepers. Tying into FY24 Job. Change Captured in PCR 5828
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093001&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000093001 | C38-SS-GA-BLACK MOUNTAIN-44.190KM | GA-01CR | CIVIL | SLOPE STABILITY | CUTTING | DESIGN | 1 | SITE | 125000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.065 | KM | GA01ML44 | 0.19 | GA01ML44 | 0.255 | KM |  |  |  |  | 44.19 | 44.255 | 2025-06-30 |  |  |  |  | 3 | 4 | 1 | 4 | 1 | 12 |  | 2023-10-13 |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | 04.03.2022 Tim Griffin (r8788533) Linked to FY23 Slope Stability Design N4 notification which requires design and costing to be completed by Q1FY23 (Sept 2022) so that construction delivery costs are accurate. See attached email to Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077855&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000077855 | C38-SS-GA-BLACK MOUNTAIN-42.621KM | GA-01CR | CIVIL | SLOPE STABILITY | DRAINAGE | DESIGN | 1 | SITE | 75000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.2449 | KM | GA01ML42 | 0.4 | GA01ML42 | 0.645 | KM |  |  |  |  | 42.4 | 42.645 | 2025-06-30 |  |  |  |  | 3 | 5 | 3 | 4 | 1 | 15 |  | 2023-10-13 |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | 03.08.2022 - W Schuh - Status set to New and moved to FY25 for design. 04.03.2022 Tim Griffin (r8788533) Linked to FY23 Slope Stability Design N4 notification which requires design and costing to be completed by Q1FY23 (Sept 2022) so that construction delivery costs are accurate. See attached email to Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092935&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000092935 | LALEHAM SINK HOLES | BW-13CR | CIVIL | SLOPE STABILITY | SINK HOLES | DESIGN | 1 | SITE | 100000 | Blackwater | BLACKWATER | KOORILGAH | 2.685 | KM | BW13ML7 | 0.9389 | BW13ML10 | 0.6199 | KM |  |  |  |  | 7.939 | 10.62 | 2025-06-30 |  |  |  |  | 3 | 2 | 1 | 2 | 1 | 6 |  | 2023-10-13 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR | FY24 IN | 20250630 | 21/02/2024 - Notifications 2000092936 <(>&<)> 2000092937 merged with notification 2000092935 as discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). This notification now encompasses the below locations: 7.939 - 8.006km (Originally 2000092935, remains FY25) 10.400 - 10.405km (Originally 2000092936 set to DLFL) 10.610 - 10.620km (Originally 2000092937 set to DLFL) 03.08.2022 - Will Schuh - Deferred to FY25. Consideration required if is capital or NMP. 07.02.2022 Tim Griffin (r878533) $100,000 Design and Cost Estimate for TUNNEL slope stability on Blackwater System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092913&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000092913 | BAUHINIA SINK HOLES | BW-06CR | CIVIL | SLOPE STABILITY | SINK HOLES | DESIGN | 1 | SITE | 75000 | Blackwater | MEMOOLOO | ROLLESTON | 14.4499 | KM | BW06ML88 | 0.3449 | BW06ML102 | 0.795 | KM |  |  |  |  | 88.345 | 102.795 | 2025-06-30 |  |  |  |  | 3 | 3 | 1 | 3 | 1 | 9 |  | 2023-10-13 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | REJC | FY24 IN | 20250630 | 21/02/2024 - Notifications 2000092911 <(>&<)> 2000092912 merged with notification 2000092913 as discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). This notification now encompasses the below locations: 88.345 - 88.355km (Originally 2000092911 set to DLFL) 101.890 - 101.910km (Originally 2000092912 set to DLFL) 102.785 - 102.795km (Originally 2000092913, remains FY25) 03.08.2022. Set to Rejected - location can be scoped along with notifications for 88.350 and 101.900km. Site scoping must consider NMP solutions and if this is capital. 07.02.2022 Tim Griffin (r878533) $75,000 Design and Cost Estimate for Bauhinia sink holes on Blackwater Branch System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077630&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077630 | Structures Reactive Works | BW | CIVIL | STRUCTURES |  | REACTIVE WORKS | 0 | LUMPSUM | 0 | Blackwater | BW |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 | 3541 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 22.05.2021 08:50:55 AUSQLD Edward Brooks (R884255) * 31.12.2020 08:19:50 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. Estimate 3 reactive design may be required in FY25 based on this being locked in 2 year prior to delivery. 2000120873 - 40k for design 2000123256 - 40k for design reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077636&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077636 | Structures Reactive Works | GA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 0 | LUMPSUM | 0 | Goonyella | GA |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 | 3541 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 22.05.2021 08:57:52 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. Estimate for 3 reactive design culverts to be incldued in this financial year 2000122760 40k culvert design 2000122761 75k bridge bearing design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077632&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077632 | Structures Reactive Works | MA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 0 | LUMPSUM | 0 | Moura | MA |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 | 3541 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 22.05.2021 08:53:36 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. Estimate 2 reactive design may be required in FY25 based on this being locked in 2 year prior to delivery.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077640&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000077640 | Structures Reactive Works | NL | CIVIL | STRUCTURES |  | REACTIVE WORKS | 0 | LUMPSUM | 0 | Newlands | NL |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 | 3541 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 22.05.2021 09:05:11 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works. Estimate 2 reactive design may be required in FY25 based on this being locked in 2 year prior to delivery.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086023&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086023 | B52 -ST-NL-Almoola-072.860km | CU300441 | CIVIL | STRUCTURES | ARCH-ELIMINATE | RENEWAL | 1 | SITE | 64552 | Newlands | ALMOOLA | COLLINSVILLE | 0 | KM | NL01ML72 | 0.8599 | NL01ML72 | 0.8599 | KM |  |  |  |  | 72.86 |  | 2026-06-30 |  |  | REMOVE & REPLACE | ELIMINATE & DIVERT | 3.5 | 2.5 | 3 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Defect: 60-70 gap between cracked arches. No deflection. Severe horzontal crack Proposed: Remove and Replace RCBC Final: Eliminate and Divert Drawing: Risk: Mod-High Reason: Very large circumference cracking present which will impact track alignment. Likely subgrade issues which cannot be repaired. High risk of future track impacts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119476&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000119476 | B12 -ST-BW-Archer-613.110km | BR101299 | CIVIL | STRUCTURES | BRIDGE | RENEWAL | 1 | SITE | 4770000 | Blackwater | ARCHER | BAJOOL | 0.042 | KM | BW01ML613 | 0.0859 | BW01ML613 | 0.128 | KM |  |  |  |  | 613.11 |  | 2026-06-30 |  |  | REMOVE & REPLACE | BRIDGE REOPLACEMENT | 3 | 4.5 | 4 | 4.6 | 1 | 13.8 | 240 | 2023-10-13 |  | Bridges Renewal | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20250630 | Defect: Include in Renewal of neighbouring pumping culverts. 50 years old original M220 structure. Strengthened previously to M270, however substructure never strengthened and aging. Efficiency and constructability benefits also with replacing bridge and only an additional 2 piles required as abutments end already required piles to support original design for 5 spans, instead of 7. So nominal cost impacts. Proposed: Remove and Replace Bridge Final: Bridge Drawing: Risk: Mod Reason: If left existing bridge, high risk that these two spans, abutments and piles will require renewal at a later stage which would be considerably more cost than replacing culverts and bridge together. Also some constructability benefits, not having to work around existing structures.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122761&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000122761 | B12 -ST-GA-Bolingbroke-052.570km | BR200004 | CIVIL | STRUCTURES | BRIDGE BEARING PAD | DESIGN | 1 | SITE | 82578 | Goonyella | BOLINGBROKE | HATFIELD | 0.1069 | KM | GA01ML52 | 0.5 | GA01ML52 | 0.6069 | KM |  |  |  |  | 52.57 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 5 | 3 | 4.8 | 1 | 16.8 | 246 | 2023-10-13 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Pier 6 bearing pad 50% fallen out, at risk of falling completely out and degrading girders. Plan for renewal in FY27 to avoid further damage. Proposed: Remove <(>&<)> Replace Bearing pads. Final: Drawing: Risk: HIgh Reason: If fall out, the time involved in replaced the pads if not planned may cause irrepairable damage to the bridge girder which will be far more expensive to renew than bearing pads.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124372&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000124372 | B12 -ST-BW-Aroona-101.450km | BR100239 | CIVIL | STRUCTURES | BRIDGE RELIEVING | DESIGN | 1 | SITE | 33031 | Blackwater | CL |  | 0.1559 | KM | BW03ML101 | 0.3579 | BW03ML101 | 0.514 | KM |  |  |  |  | 101.45 |  | 2027-06-30 |  |  | RELIEVING SLAB R&R |  | 3.5 | 3.4 | 4 | 4.3 | 1 | 15.1 |  | 2023-10-13 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Down Rd Relieveing slab failing to be put into Bridge rollout Proposed: Remove <(>&<)> Replace relieving slabs during next rollout. Final: Drawing: Risk: Mod-HIgh Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066494&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000066494 | B52 -ST-GA-Jilalan-020.310km | CU200324 | CIVIL | STRUCTURES | CIPP-RCP | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA02YR20 | 0.3099 | GA02YR20 | 0.3099 | KM |  |  |  |  | 20.31 |  | 2028-06-30 | MOD-HIGH |  | REMOVE AND REPLACE |  | 4 | 4.7 | 3 | 4.4 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | * 20.10.2020 16:01:15 AUSQLD Edward Brooks (R884255) * Defect: NCL Affected. Minor cracking in haunches and more severe in unit 16-3 * Proposed: CIPP lining or Remove and replace. Reason: Under yard and main line so high risk to busy part of the network. If we can line with CIPP then will avoid large remove <(>&<)> Replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109450&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000109450 | B52 -ST-GA-Balook-061.730km | CU201032 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | BOLINGBROKE |  | 0 | KM | GA01ML61 | 0.7299 | GA01ML61 | 0.7299 | KM |  |  |  |  | 61.73 |  | 2027-06-30 |  |  | CIPP |  | 4 | 5 | 3 | 4.5 | 1 | 18 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe waterway blocked from ballast and moderate corrosion throughout pipe. Proposed: CIPP LIning Final: Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100558&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100558 | B52 -ST-GA-Black Mountain-035.000km | CU200628 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA01ML35 | 0 | GA01ML35 | 0 | KM |  |  |  |  | 35 |  | 2028-06-30 |  |  |  |  | 3.5 | 1.2 | 3 | 3.1 | 1 | 10.9 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to sereve corrosion from 2 to 10 oclock. Proposed: CIPP Lining or remove and replace. Could be pushed in Fy28, if condition holds up in next few years. Highest risk of vehicle on acces rd Final: Drawing: Risk: Moderate Reason: Moderate to track however most severe corrosion in under the access rd which puts employees at risk iun vehicles. Yearly inspection to monitor risk, so mod-high risk to access rd users and mod to trackk.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100358&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100358 | B52 -ST-GA-Black Mountain-043.790km | CU200973 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA01ML43 | 0.79 | GA01ML43 | 0.79 | KM |  |  |  |  | 43.79 |  | 2027-06-30 |  |  | CIPP LINING |  | 3.5 | 2.6 | 3 | 3.7 | 1 | 13.1 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Localised section of severe corrosion and holes. Invert moderate to severe throughout Proposed: CIPP Lining Final: Drawing: Risk: Mod-High Reason: severe corrosion in cmp can often be too late to renew with a lining option which does not cause track disruptions. Therefore when assets are at moderate to severe corrosion this is a better time to line with CIPP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115974&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115974 | B52 -ST-GA-Balook-068.860km | CU200976 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA01ML68 | 0.8599 | GA01ML68 | 0.8599 | KM |  |  |  |  | 68.86 |  | 2027-06-30 |  |  | CIPP |  | 4 | 5 | 3 | 4.5 | 1 | 18 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to severe corrosion on invert of culvert from 4-8 oclock. RHS visibly worse than LHS Proposed: CIPP pending hydro Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115483&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115483 | B52 -ST-GA-South Walker-127.450km | CU201139 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA01ML127 | 0.45 | GA01ML127 | 0.45 | KM |  |  |  |  | 127.45 |  | 2027-06-30 |  |  | CIPP |  | 4 | 4.5 | 3 | 4.4 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to localised severe corrosion onlower half of culvert Proposed: CIPP lining pedning Hyrdo Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087568&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000087568 | B52 -ST-GA-Jilalan-019.084km | CU200948 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA-NG |  | 0 | KM | GA01ML19 | 0.084 | GA01ML19 | 0.084 | KM |  |  |  |  | 19.084 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.7 | 3 | 4.4 | 1 | 15.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to severe corrosion in invert and too small to maintain. Proposed: CIPP Line pending Hydro. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089459&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000089459 | B52 -ST-GA-Black Mountain-039.610km | CU200708 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA-NG |  | 0 | KM | GA01ML39 | 0.6099 | GA01ML39 | 0.6099 | KM |  |  |  |  | 39.61 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Inlet RHS severe to moderate corrosion but also half silted. Moderate spalling in drop chute. Remote shows severe corrosion in CMP invert at pit with large section of invert lost to corrosion. Proposed: CIPP Lining, need to confirm cipp will work with suck a large sectional loss at pit. Est based on remove and replace due to risk to cipp Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089457&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000089457 | B52 -ST-GA-Harrow-062.530km | CU200507 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Goonyella | GA-OC |  | 0 | KM | GA03ML62 | 0.53 | GA03ML62 | 0.53 | KM |  |  |  |  | 62.53 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.8 | 3 | 3.4 | 1 | 11.9 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to severe corrosion throughout culvert. Risk if left beyond FY27, that remove and replace will be required as corrosion too bad Proposed: CIPP lining to be confirmed by Hrdo. Drawing: Risk: High
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122760&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000122760 | B52 -ST-GA-Stephens-097.480km | CU200567 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 41839 | Goonyella | GA-OC |  | 0 | KM | GA03ML97 | 0.4799 | GA03ML97 | 0.4799 | KM |  |  |  |  | 97.48 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.4 | 3 | 3.7 | 1 | 14.8 | 246 | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Moderate to severe corrosion in invert of CMP. Needs to be lined prior to deteriorating. Proposed: CIPP pending Hydro Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115477&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000115477 | B52 -ST-MA-Parana-008.230km | CU400026 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Moura | MA |  | 0 | KM | MA01ML8 | 0.23 | MA01ML8 | 0.23 | KM |  |  |  |  | 8.23 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: severe corrosion with holes in invert adjoining RCP. RCP on WL. Proposed: CIPP Line pending hydro requirements. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115478&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115478 | B52 -ST-MA-Graham-033.530km | CU400079 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Moura | MA |  | 0 | KM | MA01ML33 | 0.53 | MA01ML33 | 0.53 | KM |  |  |  |  | 33.53 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: invert lining too low and not in widening. NMp look at lengthening. Moderate to severe corrosion up to half way. Proposed: CIPP line note partially concrete lined. Otherwise remove and replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114828&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114828 | B52 -ST-NL-Kaili-005.480km | CU300080 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 33466 | Newlands | NL |  | 0 | KM | NL02CR5 | 0.4799 | NL02CR5 | 0.4799 | KM |  |  |  |  | 5.48 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 3.2 | 3 | 4 | 1 | 14 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Pipe dropped under track and hevily silted on outlet. Small culvert Proposed: CIPP or Remove and replace or grout if not required in hydro Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090609&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000090609 | B52 -ST-NL-Almoola-075.450km | CU300438 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 63141 | Newlands | ALMOOLA | COLLINSVILLE | 0 | KM | NL01ML75 | 0.45 | NL01ML75 | 0.45 | KM |  |  |  |  | 75.45 |  | 2025-06-30 |  |  | CIPP | CIPP | 4.5 | 2.5 | 3 | 3.7 | 1 | 16.7 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20250630 | Defect: Severe cracking in Ceiling of all units and some side crack and circumference cracking. Very poor condition Proposed: CIPP lining if hydro allows. Final: CIPP Drawing: Risk: High Reason: Severe cracking in ceiling will only worsen and cannot be repaired. High risk of collapse. Lining with CIPP will save track closure and provide 50 years more life.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086016&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086016 | B52 -ST-GA-Balook-075.780km | CU200621 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 175646 | Goonyella | BALOOK | WANDOO | 0 | KM | GA01ML75 | 0.78 | GA01ML75 | 0.78 | KM |  |  |  |  | 75.78 |  | 2025-06-30 |  |  | CIPP | CIPP | 3.5 | 4.8 | 3 | 4.5 | 1 | 15.8 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate corrosion throughout, localised severe corrosion on RHS Proposed: CIPP Lining Final CIPP Drawing: Risk: Mod-High Reason: Invert severely corroded in locations which can cause movement of the pipe making it harder to line the longer it is left. also if left a remove and replace will be require causing impacts to customer with closure requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086010&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086010 | B52 -ST-MA-Belldeen-147.200km | CU400321 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 160371 | Moura | BELLDEEN | EARLSFIELD | 0 | KM | MA01ML147 | 0.2 | MA01ML147 | 0.2 | KM |  |  |  |  | 147.2 |  | 2025-06-30 |  |  | CIPP | CIPP | 4 | 1.3 | 3 | 3.2 | 1 | 12.8 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate corrosion throughout. Proposed: CIPP Lining Final CIPP Drawing: Risk: High Reason: High risk due to if more corrosion in invert there is a risk culvert shape and integroty will be compromised and llining solution may not be able to be applied. This would mean remove and replace with large cover willbe very impactful to customers and more than twice the cost.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086011&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086011 | B52 -ST-GA-Carborough Downs-000.290km | CU200617 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 551347 | Goonyella | CARBOROUGH DOWNS |  | 0 | KM | GA09ML0 | 0.2899 | GA09ML0 | 0.2899 | KM |  |  |  |  | 0.29 |  | 2025-06-30 |  |  | CIPP | CIPP | 4 | 1 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: FLOOR INVERT CORROSION. Moderate corrosions from 5-7 o'clock Proposed: CIPP Lining Final: CIPP LIning Drawing: Risk: Mod-High Reason: CIPP lining now is important as left longer a closure will be required and remove and replace will be needed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115479&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115479 | B52 -ST-BW-Memooloo-050.890km | CU100939 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 33466 | Blackwater | BW-RM |  | 0 | KM | BW06ML50 | 0.89 | BW06ML50 | 0.89 | KM |  |  |  |  | 50.89 |  | 2027-06-30 |  |  | CONCRETE LINE |  | 3.5 | 2.3 | 3 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Corrosion in top halg of culvert suggesting corrosion from outside in. High risk of sectional loss. Proposed: "Concrete Line in Stage 1, Cells 3,4,5,6,7,10,11,12,13,17,22" Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114804&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114804 | B52 -ST-GA-German Creek-147.880km | CU200381 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 33466 | Goonyella | GA-OC |  | 0.02 | KM | GA03ML147 | 0.9 | GA03ML147 | 0.88 | KM |  |  |  |  | 147.88 |  | 2027-06-30 |  |  | CONCRETE LINE |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate corrosion in spots in ceiling of the CMP. Localised sever corrosion with holes in steel. Not possible to fix from inside. Thereforece renewal required. Proposed: Concrete Line pending Hydro Design Risk: Mod-High Reason: Corrosion in Ceiling is an issue because the corrodion visible on the inside is likely to be much larger on the outside surface which is not visible, therefore the entire structural integroty may be compromised.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092310&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000092310 | B52 -ST-GA-Oaky Creek-151.880km | CU200559 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 33466 | Goonyella | GA-OC |  | 0 | KM | GA03ML151 | 0.88 | GA03ML151 | 0.88 | KM |  |  |  |  | 151.88 |  | 2026-06-30 |  |  |  |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to severe corrosion above invert concrete lining in Span 4, corrosion present in other spans in walls suggesting corrosion could also be coming from outside. Higher risk due to size and impact to track Tree above culverts to be removed <(>&<)> poisoned. Proposed: Line with Concrete if hydro suitable, span 4 first priority. Mobilisation for 1 cell may not be efficient, to be confirmed with construction team. Corrosion in walls may warrant concrete line all cells. to be confirmed in design. Tree above culverts to be removed <(>&<)> poisoned. Drawing: Risk: Mod-High Reason: Corrosion up from invert may be coming from outside in which is much higher risk of collapse as section thickness may be far less than appears on inside of cell.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100154&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100154 | B52 -ST-GA-Jilalan-021.700km | CU201273 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 1049075 | Goonyella | JILALAN |  | 0 | KM | GA01ML21 | 0.6999 | GA01ML21 | 0.6999 | KM |  |  |  |  | 21.7 |  | 2025-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 4.7 | 3 | 3.3 | 1 | 15.4 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect - Localised severe corrosion. Holed through armco steel allowing water to flow from outside to in. Proposed - Concrete Lining pending hydro study Final - Concrete lining. Drawings: AUR-Q-0740-4310 Risk - Mod-High Reason: Due to size of CMP, there is a high risk of loaclasied collapse in CMP above the concrete invert lining due to crushing at corroded holes in the CMP. Critical asset
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086017&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086017 | B52 -ST-GA-Norwich Park-110.950km | CU200432 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 983675 | Goonyella | NORWICH PARK | STEPHENS | 0.0509 | KM | GA03ML111 | 0 | GA03ML110 | 0.9499 | KM |  |  |  |  | 110.95 |  | 2025-06-30 |  |  | LINE | CONCRETE LINE | 3.5 | 1.5 | 3 | 3.3 | 1 | 11.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: approx 20% section loss above invert, moderate corrosion above invert lining throughout. risk to push this out that sleeving will no longer be an options. Could also consider GRP for this site now. Proposed: Sleeve with 2 / 1350 RCP <(>&<)> grout arount void. GRP may be an option for this which would give larger waterway and easier to work with. Less Hydro impact. Final: Concrete Line Drawing: AUR-Q-0575-4151 Risk: Mod-High Reason: Risk to push this out that sleeving will no longer be an option and remove and replace with large cover will be difficult and very time consuming and impactful to customers.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086015&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086015 | B52 -ST-GA-Bolingbroke-050.980km | CU200790 | CIVIL | STRUCTURES | ELIMINATE | RENEWAL | 1 | SITE | 122772 | Goonyella | BOLINGBROKE | HATFIELD | 0 | KM | GA01ML50 | 0.9799 | GA01ML50 | 0.9799 | KM |  |  |  |  | 50.98 |  | 2025-06-30 |  |  | CIPP | ELIMINATE | 4 | 5 | 3 | 4.5 | 1 | 18 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Defect: moderate Corrosion thoughout invert. Proposed: CIPP Lining Final Eliminate <(>&<)> Divert Drawing: Risk: Mod-High Reason: Hydrology has confirmed this culvert is not required without impacting significantly neighbouring properties, so elimination will reduce maintenance work required for this culvert.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085051&DY_MAB=X&~OKCODE=ONLI | FY25 | Non Coal Traffic | BASELOAD | NON-COAL | 002000085051 | B52 -ST-BW-Comet-237.020km | CU100059 | CIVIL | STRUCTURES | NON-MRSB RCP-CIPP LINE | RENEWAL | 1 | SITE | 110000 | Blackwater | COMET | YAMALA | 0 | KM | BW03ML237 | 0.02 | BW03ML237 | 0.02 | KM |  |  |  |  | 237.02 |  | 2026-06-30 |  |  |  | CIPP | 4 | 1.7 | 3 | 3.3 | 1 | 13.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20250630 | Defect - severe Cracks and spalling in units 2 and 6. also misalignment and gaps opening Proposed - RCP CIPP line Final: CIPP 1/510 Drawing - Risk: HIgh Reason: Units have cracked circumference and longitudinally and the longitudinal cracks are most concerning and risk of unexpected collapse. If we line with CIPP it will remove the need for a closure and provide a renewed life to the asset and reduce the risk to passenger services on this line. 16/2/22 EB RE-prioritised due to reduced use and loading as coal services no longer on this section of the line.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109563&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000109563 | B52 -ST-NL-Aberdeen-025.400km | CU300389 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Newlands | ARMUNA |  | 0 | KM | NL01ML25 | 0.4 | NL01ML25 | 0.4 | KM |  |  |  |  | 25.4 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Drain made up of 600mm long non reinforced units that are misaligned and appear to be breaking up and at risk of collapse. Proposed Remove <(>&<)> Replace Final: Drawing Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109416&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000109416 | B52 -ST-BW-Blackwater-187.111km | CU100081 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML187 | 0.08 | BW03ML187 | 0.08 | KM |  |  |  |  | 187.08 |  | 2028-06-30 |  |  | REPLACE |  | 4.5 | 3.2 | 3 | 3.9 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect - pumping in cell 6 units 2<(>&<)>3 approx 3-5mm. moderate cracking throughout cells. Proposed - Remove and Replace or concrete line, however pumping may not allow for lining. Final - Drawing - Risk - Mod-High Reason -
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100352&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100352 | B52 -ST-NL-Armuna-014.720km | CU300204 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Newlands | BUCKLEY | ARMUNA | 0 | KM | NL01ML14 | 0.7199 | NL01ML14 | 0.7199 | KM |  |  |  |  | 14.72 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 | 243 | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe crcaking in ceiling and sides of culvert Proposed: Remove <(>&<)> Replace, Consider elimination due to renewal of near by bridge site. Final: Drawing: Risk: High Reason: High risk of colapse, however as this is a 350 diamatere culvert the imapct to track may be limited. Important to get this asset renewed to prevent poetntial track impacts in teh future.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120873&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000120873 | B52 -ST-BW-Mount Larcom-567.000km | CU101461 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 41839 | Blackwater | BW |  | 0 | KM | BW01ML567 | 0 | BW01ML567 | 0 | KM |  |  |  |  | 567 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 | 241 | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Cell 3 grout filled with HDPE due to significant cracking in top half of the RCP. Waterway capacity reduced and increased risk of track washout. Proposed: REmove <(>&<)> REplace with RCBC Final: Drawing: Risk: HIgh Reason: Cell 3 has had to be grouted urgently to stop and severely crcaked RCP which has increased the risk of track washout and impacts to above rail services. Other 2 cells also cracked and being monitored on an increased frequency.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109357&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000109357 | B52 -ST-BW-Umolo-141.650km | CU100691 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-03CR |  | 0 | KM | BW36YR141 | 0.65 | BW36YR141 | 0.65 | KM |  |  |  |  | 141.65 |  | 2025-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Overall condition is poor, impact damage has caused the units to separate. Exposed reinforcement throughout. Able to see inlet now - could not see on 2020 Report. Location Dingo Siding - Track Machine use. Proposed: Remove and Replace
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115971&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115971 | B52 -ST-BW-0-066.580km | CU101958 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML66 | 0.5799 | BW03ML66 | 0.5799 | KM |  |  |  |  | 66.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Multiple types of culvert CMP, old RCBC. Major misalignment in middle with severe cracking in haunches and base slab. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115468&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115468 | B52 -ST-BW-Duaringa-106.590km | CU100198 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML106 | 0.5899 | BW03ML106 | 0.5899 | KM |  |  |  |  | 106.59 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: pumping severely, visible on track as well Proposed: remove and replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100359&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100359 | B52 -ST-BW-Wallaroo-117.620km | CU100338 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML117 | 0.6199 | BW03ML117 | 0.6199 | KM |  |  |  |  | 117.62 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.4 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Unit 7 both cells dropped and pumping approx 1-2mm under loaded traffic. Moderate cracking in ceiling Proposed: Remove and Replace Final: Drawing: Risk: High Reason: Pumping box culvert means well under strength, in this case 22TAL and operating 27TAL. The track will lose top of line and units are being pushed down by the constant pumping action.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115480&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115480 | B52 -ST-BW-Umolo-143.210km | CU100431 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML143 | 0.2099 | BW03ML143 | 0.2099 | KM |  |  |  |  | 143.21 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: bolts failed in bracing and main support steel beams. Units pumping under loaded trains. Proposed: Concrete Lining or Remove and replace. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115481&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115481 | B52 -ST-BW-Umolo-143.310km | CU100389 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML143 | 0.3099 | BW03ML143 | 0.3099 | KM |  |  |  |  | 143.31 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: strengthening struts failed evidence of pumping. Proposed: Concrete Lining or Remove and replace. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100354&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100354 | B52 -ST-BW-Parnabal-156.590km | CU100055 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML156 | 0.5899 | BW03ML156 | 0.5899 | KM |  |  |  |  | 156.59 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.5 | 3 | 4.4 | 1 | 15.3 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: C1-5 <(>&<)>6 severe exposed reinf in ceiling <(>&<)> walls <(>&<)> severe crack in low leg. Pumping under loaded trains. Insitu section also severe cracks Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Mod-High Reason: severe crack and spalling and pumping of reinforced cconcrete will lead to an unexpected failure which will likely cause a track alignment issue.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100355&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100355 | B52 -ST-BW-Bluff-175.450km | CU100151 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML175 | 0.45 | BW03ML175 | 0.45 | KM |  |  |  |  | 175.45 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.35 | 3 | 4 | 1 | 14 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe Spalling and exposed reinforcements, difficult to repair due to size. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Mod-High Reason: severe crack and spalling and pumping of reinforced cconcrete will lead to an unexpected failure which will likely cause a track alignment issue.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115466&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115466 | B52 -ST-BW-Boonal-180.490km | CU100179 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML180 | 0.4899 | BW03ML180 | 0.4899 | KM |  |  |  |  | 180.49 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe spalling and corroded reinf in ceiling of precast at grate drop chute. Severe cracks in insitu section and curved ceiling due to cracked section. severe cracks throughout insitu ceiling section and walls. Base slab also severely crack and heaving in middle. Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115938&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115938 | B52 -ST-BW-Blackwater-187.240km | CU100041 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML187 | 0.2399 | BW03ML187 | 0.2399 | KM |  |  |  |  | 187.24 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 3.2 | 3 | 3.9 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Exposed reinf in multiple units in the roof and some units appears to be breaking up and likely to collapse Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100353&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000100353 | B52 -ST-BW-Marmor-597.350km | CU101195 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-NCL |  | 0 | KM | BW01ML597 | 0.3499 | BW01ML597 | 0.3499 | KM |  |  |  |  | 597.35 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: failing leg of culvert Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Moderate Reason: failing leg of box will lead to pumping track and top of line misalignments.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100361&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000100361 | B52 -ST-BW-Bajool-605.130km | CU101367 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-NCL |  | 0 | KM | BW01ML605 | 0.13 | BW01ML605 | 0.13 | KM |  |  |  |  | 605.13 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.8 | 3 | 3.4 | 1 | 11.9 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Remote inspection shows cell pumping. Proposed: Remove and replace Final: Drawing: Risk: Mod-High Reason: Pumping in RCBC means it is under capacity and the base slab has normally failed and units are starting to fail or deteriorate quicker. Unable to repair a 300 high culvert, remove and replace only option. if left will collapse and this will impact drainage and increase risk of washout or lead to top of line issues in track.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115970&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115970 | B52 -ST-BW-Clinton-003.720km | CU101674 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-PG |  | 0 | KM | BW53CR3 | 0.7199 | BW53CR3 | 0.7199 | KM |  |  |  |  | 3.72 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: 300A on WL, but old culverts are badly deteriorated. Severe cracking in legs and CBS sinking and holding water. 3 units of the old section of RCBC are severely cracks and on verge of collapse. HDPE grouting will be required to hold asset. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123256&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000123256 | B52 -ST-BW-Curragh-012.060km | CU101721 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 44041 | Blackwater | CURRAGH |  | 0 | KM | BW12ML12 | 0.0599 | BW12ML12 | 0.0599 | KM |  |  |  |  | 12.06 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Severe spalling in ceiling of multiple units with corrosion visible of reinforcement Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: HIgh Reason: Conidtion is very poor with significant reinforcement apearing to be lost from ceiling which is the main span. High risk of further movement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100663&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100663 | B52 -ST-GA-Moranbah North-188.630km | CU200668 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Goonyella | GA |  | 0 | KM | GA01ML188 | 0.63 | GA01ML188 | 0.63 | KM |  |  |  |  | 188.63 |  | 2028-06-30 |  |  | REMOVE AND REPLACE |  | 3.5 | 1.1 | 3 | 4 | 1 | 10.7 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Minor to moderate spalling in all spans, worst around units 3-4 with cracks in base slab. Some spalling repaired. C1-U1-4 pumping. head wall are comig away and falling off. Old repairs failing again. Design strength est M160/220, could last to FY28 Proposed: Remove and replace with RCBC Risk: Mod-High Reason: Units are pumping under trains in unit 1-4 in all cells. This will deteriorate the culvert faster and creates higher risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091924&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000091924 | B52 -ST-GA-Waitara-104.580km | CU200715 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 44041 | Goonyella | GA-NG |  | 0 | KM | GA01ML104 | 0.5799 | GA01ML104 | 0.5799 | KM |  |  |  |  | 104.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON-MRSB | 20250630 | Defect: Pumping under loaded train. Spalling and concrete damage related to pumping. Previously patch repaired by failing again and more spalling. Proposed: Remove <(>&<)> Replace RCBC Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115465&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115465 | B52 -ST-GA-Saraji-081.440km | CU200492 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Goonyella | GA-OC |  | 0 | KM | GA03ML81 | 0.44 | GA03ML81 | 0.44 | KM |  |  |  |  | 81.44 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1.6 | 3 | 3.3 | 1 | 14.9 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: severe cracks in ceiling and walls in both units. Annual inspection required, Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114803&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114803 | B52 -ST-GA-German Creek-142.570km | CU200470 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Goonyella | GA-OC |  | 0.0299 | KM | GA03ML142 | 0.5999 | GA03ML142 | 0.5699 | KM |  |  |  |  | 142.57 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Regular spalling in ceilling in majority of cells difficult to maintain due to size. Proposed: Remove and replace Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115550&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115550 | B52 -ST-MA-Callide-009.580km | CU400514 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Moura | MA-CF |  | 0 | KM | MA07ML9 | 0.5799 | MA07ML9 | 0.5799 | KM |  |  |  |  | 9.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Sinking and circumference cracking. Joints opening and wing walls serevely damaged. Proposed: Remove <(>&<)> Replace Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091000&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000091000 | B52 -ST-BW-Epala-580.690km | CU101314 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Blackwater | NCL |  | 0 | KM | BW01ML580 | 0.6899 | BW01ML580 | 0.6899 | KM |  |  |  |  | 580.69 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Notif 2000076768 Unit dropped approx 40-75mm, suggesting failure. Observed under loaded train and no pumping was visible. Proposed: Remove and replace with RCBC Risk: Mod-High Reason: Units are sinking under track which will result in top of rail alignment issue and more resurfacing and increased risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124896&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000124896 | B52 -ST-NL-Armuna-016.430km | CU300435 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 44041 | Newlands | NL |  | 0 | KM | NL01ML16 | 0.4299 | NL01ML16 | 0.4299 | KM |  |  |  |  | 16.43 |  | 2027-06-30 |  |  | REMOVE AND REPLACE |  | 4.5 | 1.7 | 3 | 3.4 | 1 | 15.3 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Remote required but appears to be crushing under track. Asset is CP's Proposed: Remove and replace. Final: Drawing: Risk: High Reason: As unreinforced pipe, no slower ductile failure from steel reinforcement, more at risk of catastrophic brittle collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115469&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115469 | B52 -ST-NL-Almoola-065.350km | CU300150 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Newlands | NL |  | 0 | KM | NL01ML65 | 0.3499 | NL01ML65 | 0.3499 | KM |  |  |  |  | 65.35 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: unit 5 broken in half, also looks to being crushed, units 1-12 all with moderate to severe cracks. Possibly pumping. Proposed: remove and replace or cipp pending hydro. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115464&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115464 | B52 -ST-NL-Birralee-103.690km | CU300583 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Newlands | NL |  | 0 | KM | NL01ML103 | 0.6899 | NL01ML103 | 0.6899 | KM |  |  |  |  | 103.69 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Cell 3 pumping and significant movement and cracking present throughout cell. Minor movement and cracking in other cells. Cell 3 has been HDPE grouted in due to risk of collapse and low load capacity of M160. Placed on renewal as hydro been changed for the site by cell 3 grouting and other cells expected to go in similar fashion. Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109567&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000109567 | B52 -ST-GA-Balook-080.390km | CU200671 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 33466 | Goonyella | WANDOO |  | 0 | KM | GA01ML80 | 0.39 | GA01ML80 | 0.39 | KM |  |  |  |  | 80.39 |  | 2027-06-30 |  |  |  |  | 4 | 4.8 | 3 | 4.5 | 1 | 18 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severely Corroded throughout Proposed Renewal - CIPP if possible, otherwise remove and replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086033&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086033 | B52 -ST-MA-Annandale-004.180km | CU400500 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1711449 | Moura | ANNANDALE |  | 0 | KM | MA03ML2 | 0.7399 | MA03ML2 | 0.7399 | KM |  |  |  |  | 2.74 |  | 2025-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 1 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Spalling in ceiling throughout, worst in unit 2 which is under track. Proposed: Remove and replace 5/1500x600 RCBC Drawing: Risk: High Reason: Severe spalling under track with section loss to ceiling reinforcement. Risk of collapse is higher with reinforcement section loss as ductility of structure is reduced.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089490&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000089490 | B52 -ST-BW-Blackwater-189.290km | CU100645 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 912501 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML189 | 0.2899 | BW03ML189 | 0.2899 | KM |  |  |  |  | 189.29 |  | 2025-06-30 |  |  |  |  | 4.5 | 3.2 | 3 | 3.9 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | MEDIUM | Outstanding notification | SCPR INIF |  | 20250630 | Defect: Sinking approximately 100, severe cracking longitudanlly and partially failed in sections. Outlet may be into storm water drain on Cap Highway Proposed: Remove and Replace. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080947&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000080947 | B52 -ST-BW-Boonal-181.200km | CU100625 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 617901 | Blackwater | BOONAL |  | 0 | KM | BW03ML181 | 0.2 | BW03ML181 | 0.2 | KM |  |  |  |  | 181.2 |  | 2025-06-30 |  |  |  | 1/900X600RCBC 12M LONG | 4 | 3.4 | 3 | 3.4 | 1 | 16 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Pumping and severe cracks throughout ceiling and legs of insitu section. Proposed: Remove and replace with RCBC. Final "Remove and Replace 1/900x600RCBC WSP 12m long" Risk: Mod-High Reason: Severe cracking in ceiling increases risk of collapse and pumping will make the structure deteriorate faster. Original Insitu culverts were intended for 15TAL and we are running 26.5TAL so all factors increase risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085999&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085999 | B52 -ST-MA-Byellee-015.700km | CU400116 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 671019 | Moura | BYELLEE | STOWE | 0 | KM | MA01ML15 | 0.6999 | MA01ML15 | 0.6999 | KM |  |  |  |  | 15.7 |  | 2028-06-30 |  |  | REMOVE & REPLACE. | REMOVE & REPLACE | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Severe cracking insitu section near and far legs and base slab and RHS head and wing walls. Often under water due to poor free draining. Proposed: Remove and replace. Final: Remove <(>&<)> Replace 1/1200x900 RCBC 12.02m long. Drawing: AUR-Q-0881-4242 Risk: Mod-High Reason: The crack in the legs of the insitu section is likely creating pumping in the track above and this cannot be repaired and top track alignment will deteriorate until replaced.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086027&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086027 | B52 -ST-NL-Havilah-141.690km | CU300455 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 554729 | Newlands | HAVILAH | NEWLANDS | 0.01 | KM | NL01ML141 | 0.6999 | NL01ML141 | 0.6899 | KM |  |  |  |  | 141.69 |  | 2025-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 3.5 | 1.4 | 3 | 3.4 | 1 | 11.2 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Cracking in ceiling, legs and base slab. Haunch cracking highest risk of these. Materiall falling between joint. Units 3 <(>&<)> 4 pumping in both cells. M160 design loading Proposed: Remove and replace Final: 1/1800x900 RCBC 8.41m Long. Drawing: AUR-Q-0881-4272 Risk: Mod-High Reason: Design capacity for 15TAL, running 26.5TAL. Cracking through multiple cells and pumping under trains. All these factors increase the risk of collapse which will direct impact traffic on this line.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091001&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000091001 | B52 -ST-NL-McNaughton-083.280km | CU300611 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 809878 | Newlands | MCNAUGHTON |  | 0 | KM | NL04ML83 | 0.28 | NL04ML83 | 0.28 | KM |  |  |  |  | 83.28 |  | 2025-06-30 |  |  | CIPP | R&R 1/1200X900 | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20250630 | Defect: Severe cracking in ceiling of pipe under the track units 3, 4. Poly pipe in cell 1 and disconnected steel pipe in cell 2. concrete worn under poly pie and exposed reinf most units. Proposed: CIPP lining if hydro allows, otherwise remove and replace. Final: 1/1200x900 RCBC Drawing: Risk: High Reason: Severe cracking in ceiling will only worsen and cannot be repaired. High risk of collapse. Lining with CIPP will save track closure and provide 50 years more life.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086040&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000086040 | B52 -ST-BW-Midgee-626.390km | CU101607 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1130751 | Blackwater | MIDGEE | ROCKLANDS | 0 | KM | BW01ML626 | 0.39 | BW01ML626 | 0.39 | KM |  |  |  |  | 626.39 |  | 2025-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 4.5 | 3 | 4.4 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | HIGH | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: "Cell 1, unit 1 - crack in leg. Cell 1 unit 7 sunk 25mm base slab failing Cell 2 unit 7 sunk 25mm base slab failing Cell 3 unit 7 sunk 50mm base slab failing" Proposed: Remove and replace Final: Remove and replace 3/1200x900 RCBC Drawing: Risk: High Reason: Pumping under loaded trains cuasing top of line issues and resurfacing requirements. Severe cracks through base slab and units.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115939&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115939 | B52 -ST-BW-Rocklands-632.160km | CU101543 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1626619 | Blackwater | ROCKLANDS |  | 0 | KM | BW01ML629 | 0.16 | BW01ML629 | 0.16 | KM |  |  |  |  | 632.16 |  | 2025-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.5 | 3 | 4.4 | 1 | 17.6 | 5619 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: Culvert impacted <(>&<)> collapsed by Formation renewal machinery in April 2023. Grouted one cell and severe cracks in second cell. This is on the Central line fork section of the line. Severe impact to waterway. Severe cracks in haunches of C2-7, 1-7 and 30-40mm dropped units under track. Likely pumping under trains. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: High Reason: High risk of further collapse in second cell since impact in formation renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084074&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000084074 | B52 -ST-GA-Waitara-098.840km | CU201083 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 3706076 | Goonyella | WAITARA |  | 0 | KM | GA01ML98 | 0.8399 | GA01ML98 | 0.8399 | KM |  |  |  |  | 98.84 |  | 2025-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 4.7 | 3 | 4.4 | 1 | 17.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR | FY23 IN | 20250630 | Defect: Propeed all cells unit8-14. Poor patching is starting to spall again. Loaded trains now running on DN rd which is not propped. FY16 design for 20% reduction concrete lining, but this is only 125m thick, confirm 200-250 thickness will work. Proposed: Concrete lIning FY16 recommendation, but need to confirm constructability due to 1200 height or Remove <(>&<)> Replace RCBC Final Remove and Replce 9 / 2400x1200 RCBC 19m Long Risk: Mod-High Reason: Long term propped structures on units 8-14 and now all repairs are failing again and other section of culvert is spalling. Main section of goonyella line which is speed restriction or closure occured would impact many customer services.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085954&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085954 | B52 -ST-BW-Wallaroo-127.650km | CU100047 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2588959 | Blackwater | WALLAROO |  | 0 | KM | BW03ML127 | 0.65 | BW03ML127 | 0.65 | KM |  |  |  |  | 127.65 |  | 2025-06-30 |  |  |  | 7/1200X900 RCBC 13.2M LONG | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | ST BW-CL 127.65km RCBC Renewal - Wallaroo-Tryphinia - CU100047 Defect: Overall condition is poor. Displaced movement, cracking and spalling present in units 3/4 of every cell Proposed: Remove <(>&<)> Replace 7/1200x900 RCBC 13.2m long Drawing: AUR-Q-0740-4130 Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126415&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000126415 | B52 -ST-BW-Archer-613.070km | CU101579 | CIVIL | STRUCTURES | RCBC-BRIDGE-S1 | RENEWAL | 1 | SITE | 2965000 | Blackwater |  |  | 0 | KM | BW01ML613 | 0.07 | BW01ML613 | 0.07 | KM |  |  |  |  | 613.08 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 4.5 | 3 | 4 | 1 | 19.8 | 5543 | 2023-10-13 |  | Bridges Renewal | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20250630 | Stage 1 Construction Defect - Severe pumping on cells 1 <(>&<)> 28. Cell 1 severely cracked legs. Cell 24-28 appear to have dropped approx 50mm. This is second time dropped after being lifted almost 100mm previously with subgrade injections. Proposed Remove and Replace RCBC Risk: High Reason: High risk of collapse and track undermining due to severe pumping of the units, deferment would lead to speed restruction re quirements and delays to customer services. 15/2/22 EB Design was not completed by March 2022, therefore construction delivery pushed from FY24 to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110502&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000110502 | B52 -ST-BW-Archer-613.140km | CU101271 | CIVIL | STRUCTURES | RCBC-BRIDGE-S1 | RENEWAL | 1 | SITE | 1350000 | Blackwater |  |  | 0 | KM | BW01ML613 | 0.14 | BW01ML613 | 0.14 | KM |  |  |  |  | 613.14 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.5 | 3 | 4 | 1 | 17.6 | 5543 | 2023-10-13 |  | Bridges Renewal | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20250630 | Stage 1 Construction Defect - Joiner plates are broken in most cells. Most nibs are cracked and broken. required to be replaced at same time as 613.080 as part of same waterway. Proposed Remove and Replace RCBC with CU101579 Risk: Mod-High Reason: High risk of collapse and track undermining due to severe pumping of the units, deferment would lead to speed restruction re quirements and delays to customer services. 15/2/22 EB Advised by Design team that scope will not be finalised by March 2022, therefore construction must be pushed from FY24 to FY25 to allow adequate planning.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084878&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000084878 | B52 -ST-BW-Archer-613.070km | CU101579 | CIVIL | STRUCTURES | RCBC-BRIDGE-S2 | RENEWAL | 1 | SITE | 2950000 | Blackwater | ARCHER | BAJOOL | 0 | KM | BW01ML613 | 0.07 | BW01ML613 | 0.07 | KM |  |  |  |  | 613.08 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 4.5 | 3 | 4 | 1 | 19.8 | 5543 | 2023-10-13 |  | Bridges Renewal | BESPOKE DESIGN | HIGH | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Stage 2 Construction Defect - Severe pumping on cells 1 <(>&<)> 28. Cell 1 severely cracked legs. Cell 24-28 appear to have dropped approx 50mm. This is second time dropped after being lifted almost 100mm previously with subgrade injections. Proposed Remove and Replace RCBC Risk: High Reason: High risk of collapse and track undermining due to severe pumping of the units, deferment would lead to speed restruction re quirements and delays to customer services. 15/2/22 EB Design was not completed by March 2022, therefore construction delivery pushed from FY24 to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084879&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000084879 | B52 -ST-BW-Archer-613.140km | CU101271 | CIVIL | STRUCTURES | RCBC-BRIDGE-S2 | RENEWAL | 1 | SITE | 1050000 | Blackwater | ARCHER | BAJOOL | 0 | KM | BW01ML613 | 0.14 | BW01ML613 | 0.14 | KM |  |  |  |  | 613.14 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.5 | 3 | 4 | 1 | 17.6 | 5543 | 2023-10-13 |  | Bridges Renewal | BESPOKE DESIGN | HIGH | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Defect - Joiner plates are broken in most cells. Most nibs are cracked and broken. required to be replaced at same time as 613.080 as part of same waterway. Proposed Remove and Replace RCBC with CU101579 Risk: Mod-High Reason: High risk of collapse and track undermining due to severe pumping of the units, deferment would lead to speed restruction re quirements and delays to customer services. 15/2/22 EB Advised by Design team that scope will not be finalised by March 2022, therefore construction must be pushed from FY24 to FY25 to allow adequate planning.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115482&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115482 | B52 -ST-BW-Curragh-007.700km | CU101723 | CIVIL | STRUCTURES | RCBC-ELIMINATE | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CU |  | 0 | KM | BW12ML7 | 0.6999 | BW12ML7 | 0.6999 | KM |  |  |  |  | 7.7 |  | 2027-06-30 |  |  | ELIMINATE |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: "100% blocked to clean and does not appear to be impacting anything. Proposed: Eliminate pending hydro results. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086034&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086034 | B52 -ST-GA-Black Mountain-042.715km | CU200825 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 103712 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0 | KM | GA01ML42 | 0.7149 | GA01ML42 | 0.7149 | KM |  |  |  |  | 42.715 |  | 2025-06-30 |  |  | ELIMINATE | ELIMINATE & DIVERT | 3.5 | 5 | 3 | 4.5 | 1 | 15.8 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Defect: Regularly full of silt and appeasr to full to nearby culvert at 42.730. Proposed: Elimination Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000098642&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000098642 | B52 -ST-BW-Duaringa-103.870km | CU100331 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 100246 | Blackwater | DUARINGA |  | 0 | KM | BW03ML103 | 0.8699 | BW03ML103 | 0.8699 | KM |  |  |  |  | 103.87 |  | 2025-06-30 |  |  |  |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Defect - Sinking and badly misaligned. Last inspection had trouble finding this asset. Bit of confusion about km as 103.930 has been deleted in SAP, so need to check both km locations for this culvert and model both in hydro as both likely eliminated. M160 culvert as well. Proposed - Eliminate preferred as inlet has been blocked for a long time. Otherwise remove and replace. Risk - Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043882&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000043882 | B52 -ST-BW-Raglan-585.140km | CU101594 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 86385 | Blackwater | RAGLAN |  | 0 | KM | BW01ML585 | 0.1449 | BW01ML585 | 0.1449 | KM |  |  |  |  | 585.14 |  | 2026-06-30 |  |  |  | ELIMINATE & DIVERT | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | * 19.10.2020 09:35:16 AUSQLD Edward Brooks (R884255) * Defect Dropped in middle of tracks, suggesting base slab failure to be confirmed by remote inspectuon * * Proposed Grout and divert, pending hydro confirmation of raglan yard. Final: Eliminate <(>&<)> Divert
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086029&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086029 | B52 -ST-BW-Sagittarius-194.620km | CU100123 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 182232 | Blackwater | SAGITTARIUS |  | 0 | KM | BW03ML194 | 0.6199 | BW03ML194 | 0.6199 | KM |  |  |  |  | 194.62 |  | 2025-06-30 |  |  |  | ELIMINATE & DIVERT | 4 | 2.9 | 3 | 3.8 | 1 | 15.2 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Defect: RHS insitu section Pumping under loaded training. Cracking in haunches. Proposed: Remove and replace Final: Eliminate <(>&<)> Divert Drawing: Risk: Mod-High Reason: Updated costs of works to $150,000 based on advice from Project Manager.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085951&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085951 | B52 -ST-BW-Wallaroo-115.510km | CU100609 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 64206 | Blackwater | WALLAROO |  | 0 | KM | BW03ML115 | 0.51 | BW03ML115 | 0.51 | KM |  |  |  |  | 115.51 |  | 2025-06-30 |  |  | ELIMINATE | ELIMINATE & DIVERT | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Defect: Possible collapse as RHS completey blocked. Some misalignment visible from LHS Proposed: Possible eliminate and divert, hydro to confirm Final: Eliminate and Divert Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086020&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000086020 | B12 -ST-NL-Armuna-013.510km | BR300238 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 3536650 | Newlands | ARMUNA | BUCKLEY | 0.0109 | KM | NL01ML13 | 0.5 | NL01ML13 | 0.511 | KM |  |  |  |  | 13.51 |  | 2025-06-30 |  |  | UNIBOX | UNIBOX | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: 60 kph Speed restriction overloads 26.5-27.5tal, Under load capacity, only bridge component not culverts Proposed: Comparison of new vs repair in Freyssinet report, suggests Remove and replace with RCBC/Unicell, TBC with detailed design Drawing: Risk: Mod-High Reason: Remove long term speed restrictions to improve customer turn around time on Newlands system.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086021&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000086021 | B12 -ST-NL-Armuna-014.050km | BR300310 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 2774803 | Newlands | ARMUNA | BUCKLEY | 0.014 | KM | NL01ML14 | 0.048 | NL01ML14 | 0.0619 | KM |  |  |  |  | 14.05 |  | 2025-06-30 |  |  | UNIBOX | UNIBOX | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: 60 kph Speed restriction overloads 26.5-27.5tal, Under load capacity, only bridge component not culverts Proposed: Comparison of new vs repair in Freyssinet report, suggests Remove and replace with RCBC/Unicell, TBC with detailed design Drawing: Risk: Mod-High Reason: Remove long term speed restriction to improve customer turn around times.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115937&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115937 | B52 -ST-BW-Boorgoon-002.240km | CU100004 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 33466 | Blackwater | BW-BG |  | 0 | KM | BW23ML2 | 0.2399 | BW23ML2 | 0.2399 | KM |  |  |  |  | 2.24 |  | 2027-06-30 |  |  | RCP |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Mine pipes and runoff from mine operations has severely compromised the waterway. And head wall and wing walls have collapsed. Proposed: Additional RCP cells likely required. Replacement of headwall. Mine should be involved in funding. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100660&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100660 | B52 -ST-BW-Umolo-151.290km | CU100187 | CIVIL | STRUCTURES | RCP | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML151 | 0.2899 | BW03ML151 | 0.2899 | KM |  |  |  |  | 151.29 |  | 2027-06-30 |  |  | REMOVE & REPLACE RCP |  | 3.5 | 4.5 | 3 | 4.4 | 1 | 13.7 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Box culvert severely crack and spalling, head wall severe cracked and falling off. WR already upgraded with RCPs. Proposed: Remove and replac with RCP to match widening right and 8 cells. Final: Drawing: Risk: Mod-High Reason: Box culvert has sereve cracking and spalling which is being worsen by ongoing traffic over. It is under design capacity for the line and at risk of faster deterioration and possible collapse. Head wall collapse will lead to loss of ballast around the track sleepers compromising track condition.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092691&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000092691 | B52 -ST-GA-Balook-068.650km | CU200762 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 765585 | Goonyella | BALOOK | BOLINGBROKE | 0 | KM | GA01ML68 | 0.65 | GA01ML68 | 0.65 | KM |  |  |  |  | 68.65 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 5 | 3 | 4.5 | 1 | 18 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20250630 | Defect: Widening right severely corroded in invert and defomred in shape. Corrosion visible from outside face as well. Last inspection found the invert very brittle and starting to peak in the middle, suggesting crushing. Proposed: Replace failing windening Right CMP with RCP preferrably. Drawing: Risk: High Reason: Cannot be deferred as risk of collapse is quite high based on last inspection. Deteriorated in 2 years and therefore likley some temporary works required simply to get to FY25. If collapse waterway serevely compromised and risk to track as well.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043459&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000043459 | B52 -ST-BW-Archer-620.900km | CU101283 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33466 | Blackwater | ARCHER |  | 0 | KM | BW01ML620 | 0.9 | BW01ML620 | 0.9 | KM |  |  |  |  | 620.9 |  | 2027-06-30 |  |  | CIPP |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Moderate to severe cracks at 12 oclcok through every unit. Proposed: CIPP line or Remove and replace pedning hydro.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100360&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000100360 | B52 -ST-BW-Umolo-147.200km | CU100350 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML147 | 0.2 | BW03ML147 | 0.2 | KM |  |  |  |  | 147.2 |  | 2028-06-30 |  |  | CIPP OR GRP LINING |  | 4 | 2.3 | 3 | 3.6 | 1 | 14.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Minor to Severe cracking throughout. Designed slightly earlier in case reactive orks need to some of worst cells. Proposed: Consider for CIPP lining (max 1600 <(>&<)> grout annulus), otherwise consider for GRP, if not suitable remove and replace. Final: Drawing: Risk: Mod-High Reason: Moderate to severe horizontal cracking in RCP are difficult to repair and reinforcement tends to be corroded quite quickly and cracks tend to be full depth due to the relative thin wall tichkness meaning injection is not possible. To renew this asset without a closure lining is worth catching a little earlier.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115467&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115467 | B52 -ST-BW-Boonal-180.470km | CU100313 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33466 | Blackwater | BW-CL |  | 0 | KM | BW03ML180 | 0.4699 | BW03ML180 | 0.4699 | KM |  |  |  |  | 180.47 |  | 2027-06-30 |  |  | CIPP |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe cracks in RCPs, only 6 monthly remotes to hold. Can't see cracks from end, only on remote Proposed: CIPP lining pending hydro. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091925&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000091925 | B52 -ST-GA-South Walker-131.090km | CU201090 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 44041 | Goonyella | GA-NG |  | 0 | KM | GA01ML131 | 0.0899 | GA01ML131 | 0.0899 | KM |  |  |  |  | 131.09 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 4.7 | 3 | 4.4 | 1 | 15.5 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON-MRSB | 20250630 | Defect: Misalignment in units 1-3. Failed head wall on RHS. Proposed: CIPP Lining if possible with misalignment and potential associated ground issue. Otherwise remove and replace. Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114775&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000114775 | B52 -ST-MA-Parana-004.340km | CU400154 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33466 | Moura | MA |  | 0 | KM | MA01ML4 | 0.34 | MA01ML4 | 0.34 | KM |  |  |  |  | 4.34 |  | 2027-06-30 |  |  | CIPP |  | 4 | 1.3 | 3 | 3.2 | 1 | 12.8 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Severe corrosion in invert, holes regularly allow culvert. LHS under access rd upgraded with rcp but under track still an issue Proposed: CIPP lining preferred to be confirmed by hydro. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114829&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000114829 | B52 -ST-NL-Birralee-106.330km | CU300539 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 33466 | Newlands | NL |  | 0 | KM | NL01ML106 | 0.33 | NL01ML106 | 0.33 | KM |  |  |  |  | 106.33 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Culverts moving apart and letting material fall through approx moving apart up to 75mm. Reinf exposed at joint due to broken recessed joint Proposed: CIPP may be an options, however concerned about subgrade issues with opening of joints. Underbore new RCP may also be an option. Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085938&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085938 | B52 -ST-BW-Aroona-095.965km | CU100619 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 901482 | Blackwater | AROONA |  | 0 | KM | BW03ML95 | 0.9649 | BW03ML95 | 0.9649 | KM |  |  |  |  | 95.965 |  | 2025-06-30 |  |  |  | CIPP | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: one CMP cell is 100% blocked with material. Possible collapse. Other reasonable condition Proposed: CIPP or Remove and replace. Final: CIPP Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085885&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085885 | B52 -ST-BW-Edungalba-077.090km | CU100112 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 278748 | Blackwater | EDUNGALBA | TUNNEL | 0.01 | KM | BW03ML77 | 0.1 | BW03ML77 | 0.0899 | KM |  |  |  |  | 77.09 |  | 2025-06-30 |  |  | CIPP | CIPP | 4 | 3.8 | 3 | 4.1 | 1 | 16.4 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: LHS widening severe corrosion and need replacing. Proposed: remove and replace widening. As large cover consider CIPP lining entire culvert or widening only. Final CIPP Lining Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086028&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086028 | B52 -ST-BW-Edungalba-077.980km | CU100221 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 1144106 | Blackwater | EDUNGALBA | TUNNEL | 0.025 | KM | BW03ML78 | 0 | BW03ML77 | 0.9799 | KM |  |  |  |  | 77.98 |  | 2025-06-30 |  |  |  | R&R AND CIPP | 3.5 | 3.8 | 1 | 4.1 | 1 | 14.4 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: widening severe corrosion 6 m long Proposed: Remove and replace widening Final: Remove <(>&<)> Replace widening and CIPP entire. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114381&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000114381 | B52 -ST-BW-Callemondah-535.150km | CU101254 | CIVIL | STRUCTURES | RCP-PVC | DESIGN | 1 | SITE | 33466 | Blackwater | BW-NCL |  | 0 | KM | BW01ML535 | 0.1499 | BW01ML535 | 0.1499 | KM |  |  |  |  | 535.15 |  | 2027-06-30 |  |  | LINE |  | 3.5 | 2.4 | 3 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Defect: Majority of cells have severe wear in base of RCP exposing reinf and mod cracking at base. Cell 4 has mod to severe cracks in ceiling at 12 oclock in units 11, 14, 15 Proposed: Consider PVC lining, Concrete lining or GRP lining system for this. Low speed area, so PVC similar to QAL may be good option here. Risk: Mod Reason: Low speed area, but still part of north coast line and therefore subject to customer services. Difficult to get closures on NCL, so lining options would result in good option.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086025&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000086025 | B52 -ST-NL-McNaughton-085.350km | CU300621 | CIVIL | STRUCTURES | RCP-WL | RENEWAL | 1 | SITE | 1112739 | Newlands | MCNAUGHTON |  | 0 | KM | NL04ML85 | 0.3499 | NL04ML85 | 0.3499 | KM |  |  |  |  | 85.35 |  | 2025-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Defect: HDPE extension looks very poorly constructed. Need to be replaced with RCP. Confirm can it be replaced without impacting track? Hydro likely compromised. Also service pipes in cells 1 <(>&<)> 5. Proposed: Remove and replace extension. Design replace HDPE with 5/1500RCP's assumed 6m length approx for estimate Drawing: Risk: High Reason: HDPE pipe is failing by being crished which has been noticeably worse since last inspection If this collapses completed the water will not be able to drain and there is a high chance of track washout. This will impact the customer directly.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114493&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114493 | C21 NL ABERDEEN 43.576-44.450KM | NL-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.874 | TRACK KM | 1247965 | Newlands | ABERDEEN | BINBEE | 0.8739 | KM | NL01ML43 | 0.5759 | NL01ML44 | 0.45 | KM | 16 | 739 | 1.728 | 0.874 | 43.576 | 44.45 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 1.7 | 1 | 2.2 | 1 | 7.7 | 218 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Change cut in to 43.576RL nad 43.579LL as there is new rail installed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071139&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000071139 | C21 BW DUARINGA 102.800 - 103.738 | CV006246 | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.938 | TRACK KM | 1285181 | Blackwater | AROONA | DUARINGA | 0.879 | KM | BW03ML102 | 0.8 | BW03ML103 | 0.7379 | KM | 17 | 830 | 1.836 | 0.938 | 102.8 | 103.738 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 3.4 | 1 | 3.2 | 1 | 12.2 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Start re rail at back of Duaringa 11A/B Pts (102.800km) Cut out rail at 103.738km (removes 2016 re rail (103.249-103.733km)) Equality at 103km post. No plaques on monuments Chainage on Mast Stickers and Mast plaques do not align on some masts. Metre wheeled distance from 103km Post also does not align with some mast plaques / stickers (see attached)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070768&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000070768 | C21 GA BLACK MOUNTAIN 45.354 - 45.732 | CV002934 | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.378 | TRACK KM | 980137 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.378 | KM | GA02ML45 | 0.3539 | GA02ML45 | 0.7319 | KM | 7 | 552 | 0.756 | 0.378 | 45.354 | 45.732 | 2025-06-30 | UP | BOTH |  |  | 4 | 5 | 1 | 3.9 | 1 | 15.6 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | POST SITE WALKOUT: Changed cut out frpm 45.732 to 45.652 - it is at curve end - due to allowing us to cut into better rail - in next cycle will replace into the tangent - sleeper spacing reduced to 610m spacing for better track stability on Mountain
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109211&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000109211 | C21 GA DALRYMPLE BAY -0.443 - -0.103 | GA-03BA | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.34 | TRACK KM | 1085348 | Goonyella | DALRYMPLE BAY ARRIVAL ROAD | DALRYMPLE BAY ARRIVAL ROAD | 0.34 | KM | GA03BA0 | 0.1029 | GA03BA0 | 0.443 | KM | 7 | 500 | 0.702 | 0.34 | 0.103 | 0.443 | 2025-06-30 | TRACK 3 ARRIVAL ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121630&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000121630 | C21 GA DALRYMPLE BAY 0.456 - 0.729 | GA-04BA | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.273 | TRACK KM | 874224 | Goonyella | DALRYMPLE BAY ARRV. 1 | DALYRMPLE BAY ARRV. 1 | 0.273 | KM | GA04BA0 | 0.456 | GA04BA0 | 0.7289 | KM | 5 | 360 | 0.54 | 0.273 | 0.456 | 0.729 | 2025-06-30 | ARRIVAL ROAD 1 | BOTH |  |  | 3.7 | 2.6 | 1 | 2.8 | 1 | 10.36 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | NWSC |  | 20250630 | Scope will be put forward to change board to be bought into FY24 Taken to change board in August 2023. It was determined that this scope would be moved into FY25. Fix on Fail notification in system - 2000113890
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109220&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000109220 | C21 GA DAL BAY NO.2 DEP 0.018-0.379KM | GA-05BD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.361 | TRACK KM | 798723 | Goonyella | DALRYMPLE BAY DEPARTURE ROAD | DALRYMPLE BAY DEPARTURE ROAD | 0.3609 | KM | GA05BD0 | 0.0179 | GA05BD0 | 0.379 | KM | 7 | 528 | 0.756 | 0.359 | 0.018 | 0.379 | 2025-06-30 | TRACK 2 DEPARTURE ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20250630 | Post site walkout - changed Rail start from 0.016 to 0.020 to allow for better renewal (off the slab) - no change to rail qty but slight change to track km (reduction by 2m)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109218&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000109218 | C21 GA DALRYMPLE BAY 0.037-0.361KM | GA-04BD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.324 | TRACK KM | 716859 | Goonyella | DALRYMPLE BAY DEPARTURE ROAD | DALRYMPLE BAY DEPARTURE ROAD | 0.324 | KM | GA04BD0 | 0.0369 | GA04BD0 | 0.3609 | KM | 6 | 473 | 0.648 | 0.324 | 0.037 | 0.361 | 2025-06-30 | TRACK 1 DEPARTURE ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109217&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000109217 | C21 GA DAL BAY NO.3 DEP 0.039-0.367KM | GA-03BD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.328 | TRACK KM | 725709 | Goonyella | DALRYMPLE BAY DEPARTURE ROAD | DALRYMPLE BAY DEPARTURE ROAD | 0.328 | KM | GA03BD0 | 0.0389 | GA03BD0 | 0.3669 | KM | 6 | 480 | 0.648 | 0.328 | 0.039 | 0.367 | 2025-06-30 | TRACK 3 DEPARTURE ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20250630 | C21 GA DAL BAY NO.3 DEP 0.039-0.367KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109219&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000109219 | C21 GA DALRYMPLE BAY 1.532 - 1.927 | GA-04BD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.395 | TRACK KM | 934601 | Goonyella | DALRYMPLE BAY DEPARTURE ROAD | DALRYMPLE BAY DEPARTURE ROAD | 0.395 | KM | GA04BD1 | 0.532 | GA04BD1 | 0.927 | KM | 8 | 580 | 0.864 | 0.395 | 1.532 | 1.927 | 2025-06-30 | TRACK 1 DEPARTURE ROAD | BOTH |  |  | 4 | 2.6 | 1 | 2.8 | 1 | 10 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061297&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000061297 | C21 BW DUARINGA 109.487 - 109.914 | CV006262 | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.427 | TRACK KM | 1082600 | Blackwater | DUARINGA | WALLAROO | 0.4269 | KM | BW03ML109 | 0.4869 | BW03ML109 | 0.914 | KM | 8 | 625 | 0.864 | 0.427 | 109.487 | 109.914 | 2025-06-30 | DOWN | BOTH |  |  | 3.8 | 3.4 | 1 | 3.2 | 1 | 12.16 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111690&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111690 | C21 BW GORDONSTONE 6.650 - 7.481 | BW-10ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.831 | TRACK KM | 1361680 | Blackwater | GORDONSTONE | GORDONSTONE | 0.8309 | KM | BW10ML6 | 0.65 | BW10ML7 | 0.4809 | KM | 16 | 1235 | 1.728 | 0.831 | 6.65 | 7.481 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Rail is 107lb from 1970s History of internal defects in "A" rails Transposed rail in some sections 4 Bolt GIJ on both legs @ 6.685km Axle Counter @ 6.743km Complete in conjunction with adjoining scopes Steel sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111694&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111694 | C21 BW GORDONSTONE 8.100 8.788 | BW-10ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.688 | TRACK KM | 1127360 | Blackwater | GORDONSTONE | GORDONSTONE | 0.6879 | KM | BW10ML8 | 0.1 | BW10ML8 | 0.788 | KM | 13 | 995 | 1.404 | 0.688 | 8.1 | 8.788 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Removing 1970s 107lb cascaded rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114495&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114495 | C21 NL HAVILAH YARD 129.738 - 130.649 | NL-09PL | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.911 | TRACK KM | 1110264 | Newlands | HAVILAH PASSING LOOP | HAVILAH PASSING LOOP | 0.911 | KM | NL09PL129 | 0.7379 | NL09PL130 | 0.649 | KM | 17 | 690 | 1.836 | 0.911 | 129.738 | 130.649 | 2025-06-30 | LOOP | BOTH |  |  | 3.8 | 1.4 | 1 | 1.9 | 1 | 7.22 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut in at back of 7A/B Pts. Cut out at T.o.S of 1Pts PART OF 3 SCOPES BACK TO BACK
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114496&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114496 | C21 NL HAVILAH YARD 130.676 - 131.042 | NL-09PL | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.366 | TRACK KM | 446055 | Newlands | HAVILAH PASSING LOOP | HAVILAH PASSING LOOP | 0.3659 | KM | NL09PL130 | 0.676 | NL09PL131 | 0.042 | KM | 7 | 130 | 0.756 | 0.366 | 130.676 | 131.042 | 2025-06-30 | LOOP | BOTH |  |  | 3.8 | 1.4 | 1 | 1.9 | 1 | 7.22 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut in at LLB of 1Pts. Turnout on Timbers Cut out at Back of 2Pts. Turnout on Timbers Part of three scopes back to back
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114497&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114497 | C21 NL HAVILAH YARD 131.071 - 131.272 | NL-09PL | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.201 | TRACK KM | 244964 | Newlands | HAVILAH PASSING LOOP | HAVILAH PASSING LOOP | 0.201 | KM | NL09PL131 | 0.0709 | NL09PL131 | 0.272 | KM | 4 | 145 | 0.432 | 0.201 | 131.071 | 131.272 | 2025-06-30 | LOOP | BOTH |  |  | 3.8 | 1.4 | 1 | 1.9 | 1 | 7.22 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | PART OF THREE SCOPES BACK TO BACK WITH T/O IN BETWEEN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120145&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000120145 | C21 GA HAY POINT -0.017 - 0.145 | GA-02BD | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.162 | TRACK KM | 202481 | Goonyella | HAY POINT DEPARTURE ROAD | HAY POINT DEPARTURE ROAD | 0.162 | KM | GA02BD0 | -0.017 | GA02BD0 | 0.1449 | KM | 3 | 208 | 0.324 | 0.162 | 0.017 | 0.145 | 2026-06-30 | DEPARTURE ROAD | BOTH |  |  | 4 | 2.3 | 1 | 2.6 | 1 | 10.4 | 242 |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | THIS ONE WILL BE TAKEN TO CHANGE BOARD FOR FY25 APPROVAL TO BE COMPELTED WITH THE MINE CLOSURE - W.I.P cut from angle grinder in both rail heads at entry side of unloader corroded / pitted rail through unloader Start at unloader side of LX6470. Run out 1.5 lengths per leg. 68 sleepers required between LX6470 and Unloader Shed (include transition set) 140 sleepers required between exit side of shed and cut out point (include transition set) DED within renewal extents on exit side Require new plates on beam through unloader (32m). Also require new plates on concrete beam between edge of shed and pit (total length of 11m) Hay Point has a 45 Day shut in August 2024 on Unloader Number 1.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118429&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000118429 | C21 NL KAILI 1159.631 - 1159.887 | NC-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.256 | TRACK KM | 369555 | Newlands | KAILI | DURROBURRA | 0.256 | KM | NC03ML1159 | 0.631 | NC03ML1159 | 0.887 | KM | 5 | 374 | 0.54 | 0.256 | 1159.631 | 1159.887 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 217 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | Post Site Walkout - Scope is split into two part to avoid level crossing as it will get renewed in FY26 PT2 1159.631- 1159.887km 5 rails <(>&<)> 374 sleepers - all new - Captured SCR 217
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114439&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000114439 | C21 NL KAILI 1160.234-1160.506KM | NC-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.272 | TRACK KM | 776644 | Newlands | KAILI | DURROBURRA | 0.272 | KM | NC03ML1160 | 0.234 | NC03ML1160 | 0.506 | KM | 5 | 398 | 0.54 | 0.272 | 1160.234 | 1160.506 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 5833 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | RAIL: 1160.239 - 1160.777 - 10 RAILS SLEEPERS: 1160.239 - 1161.777 - 3104 SLEEPERS Scope was reduced post site walkouts due to completion of Euri Creek section prior to execution. New Scope 1160.234 - 1160.506 - 5 rails <(>&<)> 506 sleepers PCR 5833
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114490&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000114490 | C21 NL KAILI 1160.689 - 1160.777 | NC-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.088 | TRACK KM | 127034 | Newlands | KAILI | DURROBURRA | 0.0879 | KM | NC03ML1160 | 0.6889 | NC03ML1160 | 0.777 | KM | 2 | 129 | 0.216 | 0.088 | 1160.689 | 1160.777 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 233 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | RAIL: 1161.228 - 1162.183 - 18 RAILS SLEEPERS: 1161.219 - 1162.187 " PT2 1160.689 - 1160.777 - 2 rails <(>&<)> 129 sleepers Was 18 rails and 1407 sleepers +16 rails <(>&<)> +1021 sleepers"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118465&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000118465 | C21 NL KAILI 1162.225 - 1163.183 | NC-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.957 | TRACK KM | 1391609 | Newlands | KAILI | DURROBURRA | 0.9569 | KM | NC03ML1162 | -0.774 | NC03ML1163 | -0.8159 | KM | 18 | 1409 | 1.944 | 0.964 | 1162.225 | 1163.183 | 2025-06-30 | SINGLE | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 219 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | NWSC |  | 20250630 | New Notification as scope end was better clarified during site walkouts this addition removes all fatigue rail and fist sleepers within this section - SCR219 18 rails and 1409 sleepers
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114409&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114409 | C21 GA MCARTHUR 137.162 - 138.600 | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.438 | TRACK KM | 1806489 | Goonyella | MCARTHUR | COPPABELLA | 1.443 | KM | GA02ML137 | 0.162 | GA02ML138 | 0.5999 | KM | 27 | 2070 | 2.916 | 1.423 | 137.162 | 138.6 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C21 GA MCARTHUR UP 137.162-138.600KM back to back scopes 137.180 - 138.600 - TU 27 rails + 2070 sleepers 138.600 - 139.296 - RR ONLY 13 rails 139.296 - 141.523 - TU 42 rails + 3251 sleepers Scope increased on right rail @ Lower chainage due to GIJ @ 137.162 needs to be replaced. GIJ needs to move towards Lower chainage one bay - slight changes of 20m to scope - no SCR submitted
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114431&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114431 | C21 GA MCARTHUR 139.296 - 141.526 | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.229 | TRACK KM | 2800184 | Goonyella | MCARTHUR | COPPABELLA | 2.229 | KM | GA02ML139 | 0.2959 | GA02ML141 | 0.526 | KM | 42 | 3251 | 4.536 | 2.229 | 139.296 | 141.526 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C21 GA MCARTHUR UP 139.296-141.526KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115592&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000115592 | C21 BW MIDGEE 626.245 - 627.595 | BW-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.352 | TRACK KM | 1828036 | Blackwater | MIDGEE | ROCKLANDS | 1.352 | KM | BW01ML626 | 0.2449 | BW01ML627 | 0.5949 | KM | 25 | 2019 | 2.7 | 1.352 | 626.245 | 627.595 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 4.5 | 1 | 3.7 | 1 | 14.06 | 5834 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Changing location of works but not reducing scope - starting at 626.245km and finishing at 627.595km - this brings us 20m past curve transition at higher chaingage - sleepers have no change - in FY26 we will start at higher chainage end and work towards Rocky Changes to cut in point due to wanting to get 20m past the spring, this reduced rail qty by 1 - now only need 25 rails total. PCR 5834
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070803&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000070803 | C21 BW ROCKLANDS 631.739 - 631.880 | CV007524 | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.141 | TRACK KM | 549619 | Blackwater | MIDGEE | ROCKLANDS | 1.143 | KM | BW02ML631 | 0.7389 | BW02ML632 | 0.88 | KM | 3 | 141 | 0.324 | 0.141 | 631.739 | 631.88 | 2025-06-30 | DOWN | BOTH |  |  | 4 | 4.5 | 1 | 3.5 | 1 | 18 | 211 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Greaser located at approx 632.165km Axle Counter at 632.200 and 631.941 (Signal RD18) Bonds at 631.832, Bonds / Exit ATP Territory at 632.074 Tie into 12A/B Pts Scope extents may be increased to use all of the 9 lengths Scope driver is to remove worn S.C rail. Isolation Diagram: Change from NCL to CWL @ NCL 631.730km = CWL 1.230km Scope decreased for rail due to tieing into formation renewal works completed FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114619&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114619 | C21 MA MOURA MINE 0.089 - 0.575 | MA-04ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.486 | TRACK KM | 1089624 | Moura | MOURA MINE | MOURA MINE | 0.4859 | KM | MA04ML0 | 0.0889 | MA04ML0 | 0.5749 | KM | 9 | 700 | 0.972 | 0.486 | 0.089 | 0.575 | 2025-06-30 | ENTRY | BOTH |  |  | 3.8 | 1 | 1 | 1.5 | 1 | 5.7 | 206 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | Cut in at LLB of 10A/B Points - remove 50kg junction rail and tie into T/O O Signal MM18 @ 0.158km 4 Bolt GIJ LR @ 0.158km 4 Bolt GIJ RR @ 0.159kmm Survey and monumenting required here Cannot be pushed out of FY25 due to already exceeding limits and on TANC Removing existing 47kg rail Post Site walkout: Changed cut out point to 0.575 - increase on 0.5 rails per leg = 1 rail total due to coming out past the curve and utilising all rail - change capture SCR 206
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114670&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114670 | C21 MA MOURA MINE 1.478 - 1.860 | MA-04ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.382 | TRACK KM | 856453 | Moura | MOURA MINE | MOURA MINE | 0.382 | KM | MA04ML1 | 0.4779 | MA04ML1 | 0.8599 | KM | 8 | 558 | 0.864 | 0.382 | 1.478 | 1.86 | 2025-06-30 | ENTRY | BOTH |  |  | 3.8 | 1 | 1 | 1.5 | 1 | 5.7 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | LX6397 @ 1.801kmLX6397 @ 1.801km Signal MM14 @ 1.891km Cannot be psuhed out of FY25 - already exceeding limits and on TANC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114389&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114389 | C21 GA SOUTHWALKER DN 127.548-128.095KM | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.54 | TRACK KM | 799485 | Goonyella | SOUTHWALKER | TOOTOOLAH | 0.535 | KM | GA01ML127 | 0.548 | GA01ML128 | 0.095 | KM | 10 | 787 | 1.08 | 0.54 | 127.548 | 128.095 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 | 216 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C21 GA SOUTHWALKER DN 127.548-128.095KM Rail renewal scope increased at higher chainage to utilise rails <(>&<)> sleeper renewal scope increased remove fist sleepers accordingly Higher end changed to 128.095km for both rail legs and sleepers"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108735&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000108735 | C21 GA SOUTHWALKER UP 129.405-130.217KM. | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.817 | TRACK KM | 1209592 | Goonyella | SOUTHWALKER | TOOTOOLAH | 0.8169 | KM | GA02ML129 | 0.405 | GA02ML130 | 0.2169 | KM | 15 | 1044 | 1.62 | 0.817 | 129.405 | 130.217 | 2025-06-30 | UP | BOTH |  |  | 3.8 | 4.7 | 1 | 3.8 | 1 | 18 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C21 GA SOUTHWALKER UP 129.405-130.217KM Execute with RR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114441&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000114441 | C21 GA TOOTOOLAH DN 136.269-136.618KM | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.349 | TRACK KM | 600864 | Goonyella | TOOTOOLAH | MCARTHUR | 0.3489 | KM | GA01ML136 | 0.269 | GA01ML136 | 0.6179 | KM | 6 | 500 | 0.648 | 0.349 | 136.269 | 136.618 | 2025-06-30 | DOWN | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108738&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000108738 | C21 GA TOOTOOLAH UP 136.540-137.137KM | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.548 | TRACK KM | 943478 | Goonyella | TOOTOOLAH | MCARTHUR | 0.548 | KM | GA02ML136 | 0.54 | GA02ML137 | 0.137 | KM | 11 | 760 | 1.188 | 0.548 | 136.54 | 137.137 | 2025-06-30 | UP | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | C21 GA TOOTOOLAH UP 136.540-137.137KM Equality 136km 951m = 137km (-49m)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114494&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000114494 | C21 NL HAVILAH YARD 130.677 - 131.043 | NL-06SD | CIVIL | TRACK UPGRADE | SIDING | RENEWAL | 0.366 | TRACK KM | 446055 | Newlands | HAVILAH BOS | HAVILAH BOS | 0.3659 | KM | NL06SD130 | 0.677 | NL06SD131 | 0.0429 | KM | 7 | 535 | 0.756 | 0.366 | 130.677 | 131.043 | 2025-06-30 | SINGLE | BOTH |  |  | 4 | 1.4 | 1 | 1.9 | 1 | 7.6 |  | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | PART WORN RAIL CAN BE USED Post Site Walkout- extentes stays the same but not replacing cath points
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111578&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111578 | C21 BW WESTWOOD SIDING 46.379 - 46.685 | BW-07SD | CIVIL | TRACK UPGRADE | SIDING | RENEWAL | 0.306 | TRACK KM | 837244 | Blackwater | WESTWOOD SIDING | WESTWOOD SIDING | 0.3059 | KM | BW07SD46 | 0.379 | BW07SD46 | 0.685 | KM | 6 | 447 | 0.648 | 0.306 | 46.379 | 46.685 | 2025-06-30 | SIDING | BOTH |  |  | 4 | 3.35 | 1 | 3.2 | 1 | 12.8 | 237 | 2023-10-13 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20250630 | CV006114: 46.369 - 46.393 (200m Radius, Right) CV006115: 46.445 - 46.455 (400m Radius, Right) CV006116: 46.501 - 46.506 (200m Radius, Left) CV006117: 46.697 - 46.727 (250m Radius, Right) CP000165 <(>&<)> CP000164 Will need to be upgraded to 60kg Cutting out 1958 82lb rail CAN USE PART WORN RAIL POST SITE WALKOUT: only renewing between catch points as catchpoints will be upgraded later and tie into this scope - SCR 237
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115004&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115004 | BW SLAB TRACK RENEWALS | BW | CIVIL | TRACK UPGRADE | SLAB TRACK | REACTIVE WORKS | 0 | LUMPSUM | 300000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Slab Track reactive works funding
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115002&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115002 | GA SLAB TRACK RENEWALS | GA | CIVIL | TRACK UPGRADE | SLAB TRACK | REACTIVE WORKS | 0 | LUMPSUM | 300000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2023-10-13 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Slab Track Renewals Reactive Funding
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115962&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115962 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 0 | LUMPSUM | 3306726 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115963&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115963 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 0 | LUMPSUM | 3607337 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115964&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115964 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 0 | LUMPSUM | 661345 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115965&DY_MAB=X&~OKCODE=ONLI | FY25 |  | REACTIVE RENEWALS | COAL | 002000115965 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 0 | LUMPSUM | 601222 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  | 2023-10-13 |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043333&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000043333 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE293A | TO001150 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1069582 | Blackwater | CALLEMONDAH | GE293A | 0.0539 | KM | BW13YR536 | 0.234 | BW13YR536 | 0.234 | KM |  |  |  |  | 536.23 |  | 2024-06-30 |  |  |  |  | 0 | 3.5 |  | 0 |  | 100 | 2515 | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Notification in process | RRIG |  | 20250630 | * 11.03.2020 12:52:15 AUSQLD Lachlan Prescott (R881571) * [LP 11/03/2020] MOVED TO FY23 DUE TO OVERALLOCATION OF FY22. * 04.08.2020 17:52:40 AUSQLD Lachlan Prescott (R881571) * COST UPDATED TO BRING FORWARD 8% DESIGN COST TO FY22 25.10.2021 Alex Rohweder (R872340) FY23 overallocated - moved to FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094150&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000094150 | TURNOUTS ¦ DESIGN ¦ CONSTRUCT ¦ GE293BC | TO000865 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1069582 | Blackwater | CALLEMONDAH GE293B/C | GE293B/C | 0.05 | KM | BW01ML536 | 0.326 | BW01ML536 | 0.276 | KM |  |  |  |  | 536.326 |  | 2024-06-30 |  |  |  |  | 0 | 4.4 |  | 0 |  | 100 |  | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Notification in process | RRIG |  | 20250630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL GE293B/C ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043327&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal GAPE Traffic | BASELOAD | COAL | 002000043327 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ EC12A | TO000139 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 617339 | Newlands | EAGLEFIELD CREEK | EC12A | 0.069 | KM | NL01ML201 | 0.909 | NL01ML201 | 0.909 | KM |  |  |  |  | 201.91 |  | 2025-06-30 |  |  |  |  | 3.5 | 3 |  | 3 |  | 12.25 |  | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 04.08.2020 17:04:10 AUSQLD Lachlan Prescott (R881571) * COST UPDATED TO BRING FORWARD 8% DESIGN COST TO FY22 * 19.03.2021 12:05:04 AUSQLD Lachlan Prescott (R881571) * Deferred to FY24 due to over-allocated FY23 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy) * This is C11
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043306&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal GAPE Traffic | BASELOAD | COAL | 002000043306 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ EC7A | TO000141 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 617339 | Newlands | EAGLEFIELD CREEK | EC7A | 0.069 | KM | NL01ML204 | 0.111 | NL01ML204 | 0.111 | KM |  |  |  |  | 204.11 |  | 2025-06-30 |  |  |  |  | 4 | 2.5 |  | 2.5 |  | 12.25 |  | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 04.08.2020 16:58:38 AUSQLD Lachlan Prescott (R881571) * COST UPDATED TO BRING FORWARD 8% DESIGN COST TO FY22 * 19.03.2021 12:04:13 AUSQLD Lachlan Prescott (R881571) * Deferred to FY24 due to over-allocated FY23 Construction and As Built due by 30 June 2025 Alex Rohweder (R872340) POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH Replace the existing WHRBM (Welded Heel Rail Bound Manganese) crossing with a new Swing Nose Crossing (with plates). Install additional M23A motor at crossing. The project includes turnout renewal inableing works within the project extent. SAP asset data update post completion of the construction ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy) * This is C11
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115811&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115811 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ MM ER1.3 | TO000879 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1887727 | Blackwater | MOUNT MILLER | MM ER1.3A | 0.024 | KM | BW20ML0 | 0.451 | BW20ML0 | 0.4269 | KM |  |  |  |  | 0.451 | 0.427 | 2025-06-30 |  |  |  |  | 3.5 | 2 | 3.7 | 4 |  | 13 |  | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | Construction and As Built due by 30 June 2025 POINTS <(>&<)> X 60KG/M 12 CS SWC TGLASM EO LH FULL RENEWAL - Change angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ MM ER1.3A FY23 - Total Design Budget $35,880 (bundlled with MMER2.3B) (ITP-FY23, IFC-FY24) FY25 - CONSTRUCTION budget $1,000,000 Construction and As Built due by 30 June 2025 POINTS <(>&<)> X 60KG/M 12 CS SWC TGLASM EO LH FULL RENEWAL - Change angle <(>&<)> Additional Points motor. Including turnout renewal inableing works (i.e. formation works untder turnout, drainainge) within the project extent SAP asset data update post completion of the construction * This is C11
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115835&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000115835 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ MMER2.3B | TO000861 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 2004199 | Blackwater | MOUNT MILLER | MM ER2.3B | 0.035 | KM | BW01ML541 | 0.635 | BW01ML541 | 0.67 | KM |  |  |  |  | 541.285 | 541.32 | 2025-06-30 |  |  | POINTS & X 60KG/M 12 CS SNX EO |  | 3.5 | 3 | 4.1 | 4 |  | 16.4 |  | 2023-10-13 |  | Turnout Renewals | BESPOKE DESIGN | MEDIUM | HIGH | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | Construction and As Built due by 30 June 2025 POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. * This is C11
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094134&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000094134 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ DA 12A/B | TO000119 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 18740 | Newlands | DURROBURRA | 12A/B | 0.0709 | KM | NL02ML0 | -0.2099 | NL02ML0 | -0.139 | KM |  |  |  |  | 12.3 |  | 2025-02-25 |  |  |  |  | 5 | 3 | 4 | 4 | 1 | 21 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250225 | TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ DA 12A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $18,740 out of $187,400 30.03.2022 Alex Rohweder (R872349( Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094135&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000094135 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ DA 10A/B | TO000151 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 11900 | Newlands | DURROBURRA | DA 10A/B | 0.05 | KM | NC03ML1158 | 0.4979 | NC03ML1158 | 0.448 | KM |  |  |  |  | 1158.498 |  | 2025-02-25 |  |  |  |  | 5 | 3 | 4 | 4 | 1 | 21 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20250225 | TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ DA 10A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $11,900 out of $119,000 30.03.2022 Alex Rohweder (R872349) Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION Alex Rohweder (R872340) 22.03.2024 PCR 5880 request agreement between Am and PM Push out DD30 deliverable from FY24 to FY25 with no change the IFP, IFC <(>&<)> Construction dates. This allows the Design team time to develop the options etc required to progress the DD30 design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115802&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115802 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BK ER1.2A | TO000214 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 220925 | Goonyella | BALOOK | BK ER1.2A | 0.033 | KM | GA01ML74 | 0.799 | GA01ML74 | 0.8319 | KM |  |  |  |  | 74.68 | 74.713 | 2025-05-27 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | IFC due by 30 June 2025, FY26 Construction. Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM MO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123287&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000123287 | TURNOUTS ¦ DESIGN ¦ IFC ¦ PS 12A/B | TO000471 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 41403 | Goonyella | PRAGUELANDS | PS12A/B | 0.05 | KM | GA02ML14 | 0.4769 | GA02ML14 | 0.527 | KM |  |  |  |  | 14.472 | 14.426 | 2025-05-27 |  |  |  |  | 3 | 5 | 4 | 5 | 1 | 14.4 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123284&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000123284 | TURNOUTS ¦ DESIGN ¦ IFC ¦ PS 12C/D | TO000441 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 41403 | Goonyella | PRAGUELANDS | PS12C/D | 0.049 | KM | GA01ML14 | 0.5779 | GA01ML14 | 0.529 | KM |  |  |  |  | 14.472 | 14.426 | 2025-05-27 |  |  |  |  | 3 | 5 | 4 | 5 | 1 | 14.4 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115870&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115870 | TURNOUTS ¦ DESIGN ¦ IFC ¦ PS 8A/B | TO000442 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 41403 | Goonyella | PRAGUELANDS | PS8A/B | 0.05 | KM | GA01ML14 | 0.3589 | GA01ML14 | 0.4089 | KM |  |  |  |  | 14.377 | 14.427 | 2025-05-27 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 5 | 5 | 4 | 5 |  | 14.4 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115866&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115866 | TURNOUTS ¦ DESIGN ¦ IFC ¦ PS 8C/D | TO000470 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 41403 | Goonyella | PRAGUELANDS | PS8C/D | 0.0459 | KM | GA02ML14 | 0.455 | GA02ML14 | 0.4089 | KM |  |  |  |  | 14.472 | 14.426 | 2025-05-27 |  |  |  |  | 3 | 5 | 4 | 5 |  | 14.4 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with PS 8A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123499&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000123499 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AE 11A/B | TO000904 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 55001 | Blackwater | AMBROSE | AE 11A/B | 0.048 | KM | BW02ML570 | 0.2099 | BW02ML570 | 0.162 | KM | [6 empty] | 2025-02-27 |  |  |  |  | 4 | 4 |  | 4 |  | 16 | 5398 | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ AE 11A/B 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93 ,700 out of $187,400 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123742&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000123742 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AE 11C/D | TO000851 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 55001 | Blackwater | AMBROSE | AE 11C/D | 0.049 | KM | BW01ML570 | 0.111 | BW01ML570 | 0.16 | KM | [6 empty] | 2025-02-27 |  |  |  |  | 4 | 4 |  | 4 |  | 16 | 5398 | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ AE 11C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93 ,700 out of $187,400 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100872&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000100872 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AE 12A/B | TO000850 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 55001 | Blackwater | AMBROSE | AE 12A/B | 0.04 | KM | BW01ML570 | 0.334 | BW01ML570 | 0.2939 | KM | [6 empty] | 2025-02-27 |  |  |  |  | 4 | 4 |  | 4 |  | 16 | 5398 | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ AE 12A/B 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93 ,700 out of $187,400 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123496&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000123496 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AE 12C/D | TO000905 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 55001 | Blackwater | AMBROSE | AE 12C/D | 0.05 | KM | BW02ML570 | 0.232 | BW02ML570 | 0.2819 | KM | [6 empty] | 2025-02-27 |  |  |  |  | 4 | 4 |  | 4 |  | 16 | 5398 | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ AE 12C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93 ,700 out of $187,400 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094140&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000094140 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 273A | TO001151 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 104546 | Blackwater | CALLEMONDAH | CH 273A | 0.024 | KM | BW14YR534 | 0.317 | BW14YR534 | 0.341 | KM |  |  |  |  | 534.317 | 534.341 | 2025-02-27 |  |  | BESPOKE DESIGN |  | 4.5 | 4 |  | 4 |  | 19.8 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ CH 273A Design is to be completed in FY25 for FY28 construction. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094142&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000094142 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH ER275.2 | TO001152 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 104546 | Blackwater | CALLEMONDAH | CH ER275.2 | 0.025 | KM | BW14YR534 | 0.343 | BW14YR534 | 0.3679 | KM |  |  |  |  | 534.343 | 534.368 | 2025-02-27 |  |  |  |  | 4.5 | 3.5 |  | 5 |  | 19.8 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ CH ER275.2 Design is to be completed in FY25 for FY29 construction. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094139&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000094139 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HD 12A/B | TO000261 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | HATFIELD | 12A/B | 0.048 | KM | GA35XR49 | 0.775 | GA35XR49 | 0.8229 | KM |  |  |  |  | 49.775 | 49.823 | 2024-02-27 |  |  |  |  | 3 | 5 |  |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ HD 12A/B Alex Rohweder (R872340) 28.03.2024 PCR - 5877 Push out IFP deliverable from FY24 to FY25 and subsequently push out IFC <(>&<)> Construction dates. IFP to FY25, IFC to FY26 and Construct in FY27. Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with HD 12C/D and HD 11A/B FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094138&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000094138 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HD 11A/B | TO000328 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Goonyella | HATFIELD | HD 11A/B | 0.048 | KM | GA02ML49 | 0.8729 | GA02ML49 | 0.8249 | KM |  |  |  |  | 49.753 | 49.705 | 2025-02-27 |  |  |  |  | 3 | 5 |  |  |  | 16.8 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250227 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ HD 11A/B Alex Rohweder (R872340) 28.03.2024 PCR - 5877 Push out IFP deliverable from FY24 to FY25 and subsequently push out IFC <(>&<)> Construction dates. IFP to FY25, IFC to FY26 and Construct in FY27. Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. Bundle with HD 12A/B and HD 12C/D. FY24 Design budget adjusted to 50% off the total design budget = $59 ,500 out of $119,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 28.03.2024 PCR - 5877 Push out IFP deliverable from FY24 to FY25 and subsequently push out IFC <(>&<)> Construction dates. IFP to FY25, IFC to FY26 and Construct in FY27.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115863&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115863 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HD ER1.2A | TO000273 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 71399 | Goonyella | HATFIELD | HD ER1.2A | 0.0369 | KM | GA01ML49 | 0.334 | GA01ML49 | 0.3709 | KM |  |  |  |  | 49.334 | 49.334 | 2025-02-27 |  |  |  |  | 3.5 | 5 | 4.8 | 5 |  | 16.8 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250227 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115862&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115862 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HD ER2.2B | TO000329 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 71399 | Goonyella | HATFIELD | HD ER2.2B | 0.035 | KM | GA02ML49 | 0.331 | GA02ML49 | 0.3659 | KM |  |  |  |  | 127.264 | 127.193 | 2025-02-27 |  |  | POINTS & X 60KG/M 12 CS 400UHC |  | 3.5 | 5 | 4.8 | 5 |  | 16.8 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250227 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052820&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000052820 | TURNOUTS ¦ DESIGN ¦ IFP ¦ ML 10A | TO000910 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 18740 | Blackwater | MT LARCOM | ML 10A | 0.0359 | KM | BW02ML564 | 0.885 | BW02ML564 | 0.921 | KM |  |  |  |  | 562.963 | 562.999 | 2025-02-27 |  |  | POINTS & X 60KG/M 12 CS SNX TG |  | 3.5 | 4 | 4.1 | 3 |  | 13.2 | 4882 | 2022-03-31 | 2022-06-30 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250227 | * 28.02.2020 13:28:44 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is major refurbishment including upgrade from RBM to SNX. * 10.05.2021 11:03:13 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 28.02.2020 13:28:44 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is major refurbishment including upgrade from RBM to SNX. 10.05.2021 11:03:13 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 30.03.2022 Alex Rohweder (R872340) Design in FY24 to Construct in FY26. Asset renewal project collaboration with Level Crossing (Currently planned for 2027) and Culverts (FY24 design and FY26 Construction) TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ ML 10A 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $18,740 out of $187,400 Asset renewal project collaboration opportunity with Level Crossing (planned for 2027) and Culverts (FY24 design and FY26 Construction) ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000095945&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000095945 | BW MAINLINE PAN CAM | BW | CONTROL SYSTEMS | ASSET PROTECTION | MAINLINE PANCAM | DESIGN | 1 | SITE | 169231 | Blackwater | KALAPA |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 20 | 150 | 2023-10-13 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW | HIGH | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115343&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115343 | Graham RailBAM Design | ST009860-20 | CONTROL SYSTEMS | ASSET PROTECTION | RAILBAM | DESIGN | 1 | UNIT | 63710 | Moura | GRAHAM | GRAHAM | 0 | KM | MA01ML31 | 0.2999 | MA01ML31 | 0.2999 | KM |  |  |  |  | 31.3 | 31.3 | 2025-06-30 |  |  |  |  | 4 | 2 |  | 1 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  |  | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Graham RailBAM Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115357&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115357 | North Goonyella Weighbridge Design | ST004930-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | DESIGN | 1 | UNIT | 108617 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0 | KM | GA01ML217 | 0.3059 | GA01ML217 | 0.3059 | KM |  |  |  |  | 217.306 | 217.306 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 1 | 1 | 20 |  | 2023-10-13 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | North Goonyella Weighbridge Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115355&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000115355 | Wandoo Mainline Weighbridge Design | ST009410-25 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | DESIGN | 1 | UNIT | 108617 | Goonyella | WANDOO | WANDOO | 0 | KM | GA01ML92 | 0 | GA01ML92 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 5 |  | 1 | 1 | 20 |  | 2023-10-13 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Wandoo Mainline Weighbridge Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115470&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115470 | Kalapa Mainline Weigher Renewal | ST009570-29 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | RENEWAL | 1 | UNIT | 1474066 | Blackwater | KALAPA |  | 0 | KM | BW03ML30 | 0.4799 | BW03ML30 | 0.4799 | KM |  |  |  |  | 30.48 | 30.48 | 2025-06-30 |  |  |  |  | 4 | 4.8 |  | 4.8 | 1 | 19.2 |  | 2023-10-13 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Kalapa Mainline Weigher Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115371&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000115371 | Moura Weighbridge Renewal | ST003790-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | RENEWAL | 1 | UNIT | 1406976 | Moura | MOURA | MOURA | 0 | KM | MA04ML3 | 0.7079 | MA04ML3 | 0.7079 | KM |  |  |  |  | 3.708 | 3.708 | 2025-06-30 |  |  |  |  | 4 | 2 |  | 2 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | Moura Weighbridge Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102217&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000102217 | CSI CER Replacement | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | DESIGN | 1 | SITE | 57257 | Blackwater | CALLEMONDAH SER | CALLEMONDAH SER | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090666&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000090666 | CS CER Relocation | ST004050 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | DESIGN | 1 | SITE | 57257 | Goonyella | WANDOO CER | WANDOO CER | 0 | KM | GA01ML85 | 0.917 | GA01ML85 | 0.917 | KM |  |  |  |  | 85.92 | 85.92 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085370&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085370 | CSI Dehydrator Renewal | ST005730-55 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Newlands | COLLINSVILLE MW | COLLINSVILLE MW | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM |  |  |  |  | 76.66 | 76.66 | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078709&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000078709 | CSI Dehydrator Renewal | ST005930-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Goonyella | COLSTON PARK |  | 0 | KM | GA37CR0 | 0 | GA37CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR |  | 20250630 | * 10.06.2021 18:21:03 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085374&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085374 | CSI Dehydrator Renewal | ST005280-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Blackwater | CROCKER PEAK MW | CROCKER PEAK MW | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078711&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000078711 | CSI Dehydrator Renewal | ST003020-44 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Blackwater | EMERALD |  | 0 | KM | BW57CR0 | 0 | BW57CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR |  | 20250630 | * 10.06.2021 18:21:41 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085373&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085373 | CSI Dehydrator Renewal | ST005510-53 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Blackwater | GREGORY MW | GREGORY MW | 0 | KM | BW59CR0 | 0 | BW59CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085372&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085372 | CSI Dehydrator Renewal | ST005940-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Goonyella | PINE MOUNTAIN MW | PINE MOUNTAIN MW | 0 | KM | GA43CR0 | 0 | GA43CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085371&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085371 | CSI Dehydrator Renewal | ST005910-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 23337 | Goonyella | THREE SISTERS MW | THREE SISTERS MW | 0 | KM | GA47CR901 | 0 | GA47CR901 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085404&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085404 | CSI Generator Renewal | ST005950-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 161837 | Blackwater | CAPELLA | CAPELLA | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085405&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085405 | CSI Generator Renewal | ST005910-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 161837 | Goonyella | THREE SISTERS MW | THREE SISTERS MW | 0 | KM | GA47CR901 | 0 | GA47CR901 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120656&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000120656 | CSI OF Renewal AMBROSE CER - AMBROSE AT | ST006440-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3411 | METERS | 364079 | Blackwater | AMBROSE AT0 | AMBROSE CER | 3.3359 | KM | BW01ML574 | 0.01 | BW01ML570 | 0.659 | KM |  |  |  |  | 570.678 | 574.021 | 2025-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-10-13 |  | Telecommunication Asset | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046864&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000046864 | CSI OF Renewal BAJOOL JOINT - ARCHER CER | ST006290-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 8395 | METERS | 1300523 | Blackwater | ARCHER CER | BAJOOL JOINT | 9.6129 | KM | BW01ML614 | 0.9789 | BW01ML605 | 0.3719 | KM |  |  |  |  | 614.984 | 606.633 | 2025-06-30 | ALL |  |  |  | 4 | 4.5 |  | 4.5 |  | 18 |  | 2023-10-13 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079387&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000079387 | CSI OF Renewal EPAL CER - EPALA NTH MI | ST009070-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1551 | METERS | 166941 | Blackwater | EPALA MI NTH | EPALA CER | 1.502 | KM | BW01ML577 | 0.75 | BW01ML576 | 0.2399 | KM |  |  |  |  | 577.75 | 576.24 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079388&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000079388 | CSI OF Renewal AMBROSE AT - EPALA STH AT | ST009050-16 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1880 | METERS | 262598 | Blackwater | EPA-MIS TO AMB-AT0 O/FBR CABLE |  | 1.834 | KM | BW01ML575 | 0.8149 | BW01ML574 | 0.01 | KM |  |  |  |  | 575.815 | 574.01 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046862&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000046862 | CSI OF Renewal RAGLAN TO MARMOR AT | ST001880-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 10289 | METERS | 1643505 | Blackwater | RAGLAN CER | MARMOR AT | 10.198 | KM | BW01ML594 | 0.9 | BW01ML584 | 0.7189 | KM |  |  |  |  | 594.9 | 584.719 | 2025-06-30 | ALL |  |  |  | 4 | 4.1 |  | 4.1 |  | 16.4 |  | 2023-10-13 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046872&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | STRATEGIC | COAL | 002000046872 | CSI OF Ren ROCKLANDS MI - ROCKLANDS SER1 | ST004360-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1455 | METERS | 221637 | Blackwater | ROCKLANDS SR1 | ROCKLANDS MI | 0.5849 | KM | BW01ML631 | 631.25 | BW01ML631 | 631.835 | KM |  |  |  |  | 0.25 | 1.67 | 2025-06-30 |  |  |  |  | 4 | 4.5 |  | 4.5 |  | 18 |  | 2023-10-13 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | * 28.03.2021 16:41:44 AUSQLD Scott Andrews (R003573) * Renew OF at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085350&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085350 | CSI Radome Renewal FY25 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 64382 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085348&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085348 | CSI Radome Renewal FY25 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 64382 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085346&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085346 | CSI Radome Renewal FY25 | MA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 64382 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085347&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085347 | CSI Radome Renewal FY25 | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 64382 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR INIF |  | 20250630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085550&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000085550 | CSI Structure Renewal | ST002940-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | DESIGN | 1 | SITE | 36362 | Blackwater | CLERMONT |  | 0 | KM | BW03ML100 | 0.26 | BW03ML100 | 0.26 | KM |  |  |  |  | 100.26 | 100.26 | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085529&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000085529 | CSI Structure Renewal | ST005730-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | DESIGN | 1 | SITE | 36362 | Newlands | COLLINSVILLE |  | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM |  |  |  |  | 76.66 | 76.66 | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050844&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000050844 | Data Network Renewal BW | BW | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 0 | LUMPSUM | 1145156 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085608&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085608 | Data Network Renewal GA | GA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 0 | LUMPSUM | 858867 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085713&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085713 | Data Network Renewal MA | MA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 0 | LUMPSUM | 114515 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085688&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085688 | Data Network Renewal NL | NL | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 0 | LUMPSUM | 229031 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065501&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000065501 | SIG_Interlocking Renewal - CH Stg2A_Bld | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN | 1 | UNIT | 3229362 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | * 28.09.2020 10:39:11 AUSQLD Peter Rayner (R003851) * Scope of works IV.00694 Control Systems Renewal Callemondah Project (Stage 2) * 16.03.2021 17:59:00 AUSQLD Robert Love (R111379) * Completion of final phase of design and principal testing of the Callemondah Interlocking data, as per Callemondah Strategy Stage 2A.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104546&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000104546 | SIG_Interlocking Renewal - CH Stag1F_Bld | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | DESIGN & PROCURE | 1 | SITE | 1064233 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2026-06-30 |  |  |  |  | 5 | 4 | 5 | 5 | 1 | 25 |  | 2023-10-13 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Complete the site works for the Renewal/Commissioning phase of Callemondah Stage 1F - commissioning the new hut GE OC East.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074217&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000074217 | SIG_Interlocking Renewal - CH Stg1E_Com | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 2945157 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | HIGH | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630 | * 16.03.2021 17:37:55 AUSQLD Robert Love (R111379) * Complete the renewal/commissioning phase of Callemondah Stage 1E - commission the final cabling for GE OC West.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104497&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000104497 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | SITE | 40070 | Newlands | ABBOT POINT | EAGLEFIELD CREEK | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4.5 | 2 | 2 | 2 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20250630 | Replace existing Newlands System Maintenance PC with Aurizon IT PC. PC to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PC to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104498&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000104498 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | SITE | 103039 | Goonyella | HAY POINT | NORTH GOONYELLA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4.5 | 2 | 2 | 2 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20250630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100648&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100648 | SIG_Diagnostic Computer_MA_Com | MA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 41215 | Moura | GLADSTONE | MOURA MINE | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20250630 | Replace 2 existing Moura System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104571&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000104571 | SIG_Diagnostic Computer_GA_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 9 | UNIT | 206078 | Blackwater | MOUNT LARCOM | GREGORY | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4.5 | 2 | 2 | 2 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20250630 | Replace 9 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115503&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | FUTURE SCOPE | COAL | 002000115503 | SIG_Interlocking Renewal_BW_Archer_Bld | ST004090-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN | 1 | SITE | 319258 | Blackwater | ARCHER | ARCHER | 0 | KM | BW01ML614 | 0.9659 | BW01ML614 | 0.9659 | KM |  |  |  |  | 614.966 | 614.966 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630 | Start early works for renewing the interlocking at Archer in a following year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060294&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000060294 | SIG_Replace FOP signal_BW_BL18_Com | ST000600-D5 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 90335 | Blackwater | BAJOOL | BAJOOL | 0 | KM | BW02ML603 | 0.8 | BW02ML603 | 0.8 | KM |  |  |  |  | 603.8 | 603.8 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:56:20 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060299&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000060299 | SIG_Replace FOP signal_BW_MR27_Com | ST000610-C7 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 90335 | Blackwater | MARMOR | MARMOR | 0 | KM | BW02ML594 | 0.467 | BW02ML594 | 0.467 | KM |  |  |  |  | 594.467 | 594.467 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:57:04 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060300&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000060300 | SIG_Replace FOP signal_BW_MR28_Com | ST000610-D2 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 90335 | Blackwater | MARMOR | MARMOR | 0 | KM | BW01ML594 | 0.467 | BW01ML594 | 0.467 | KM |  |  |  |  | 594.467 | 594.467 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:57:12 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060297&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000060297 | SIG_Replace FOP signal_BW_MR16_Com | ST000610-B6 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 90335 | Blackwater | MARMOR | MARMOR | 0 | KM | BW01ML594 | 0.9499 | BW01ML594 | 0.9499 | KM |  |  |  |  | 594.95 | 594.95 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:56:46 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060298&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000060298 | SIG_Replace FOP signal_BW_MR18_Com | ST000610-B9 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 90335 | Blackwater | MARMOR | MARMOR | 0 | KM | BW02ML594 | 0.9499 | BW02ML594 | 0.9499 | KM |  |  |  |  | 594.95 | 594.95 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:56:55 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000096049&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000096049 | SIG_Interlocking Renewal_MA_Dumgree_Des | ST003600-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1199075 | Moura | DUMGREE | DUMGREE | 0 | KM | MA01ML108 | 0.545 | MA01ML108 | 0.545 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  | 2023-10-13 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20250630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares. The axle counter block between Dumgree and Annandale is to be completed as part of this scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125112&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000125112 | SIG_Interlocking Renewal - MA_AE_Bld | ST003290-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1166557 | Moura | ANNANDALE | EARLSFIELD | 0 | KM | MA01ML0 | 0.1 | MA01ML0 | 0.1 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 |  | 20 |  | 2023-10-13 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20250630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060279&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060279 | C58-LX-GA-BLACKRIDGE-80.68km | LX000663 | CONTROL SYSTEMS | LEVEL CROSSINGS | HOUSING REPLACEMENT | RENEWAL | 1 | SITE | 496983 | Goonyella | BLACKRIDGE | BLACKRIDGE | 0 | KM | GA05ML80 | 0.68 | GA05ML80 | 0.68 | KM |  |  |  |  | 80.68 | 80.68 | 2025-06-30 |  |  |  |  | 5 | 2 | 4 | 4 | 1 | 19.5 |  | 2023-10-13 |  | Other Control Sys Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | * 23.06.2020 12:54:06 AUSQLD Peter Rayner (R003851) * Replace 4 housing with hut and renew train detection equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125147&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000125147 | SIG_Points Impr_M23A Contact Rem_GA_Des | GA | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | DESIGN | 8 | UNIT | 387639 | Goonyella | OAKY CREEK | RED MOUNTAIN | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 4.5 | 3 |  |  |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Design for the removal ofthe contactor from the following (8) M23A machines: Bundoora BD11A Pts; German Creek GC12B Pts; Oaky Creek Oaky Creek OC9 Pts, OC10 Pts; Red Mountain RM12A Pts, RM12B Pts, RM7A Pts, RM7B Pts. This is to create spares of unsupported contactor relays and renew old machines in the field.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104573&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000104573 | SIG_Points Impr_M23A Contact Rem_GA_Pln | GA | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | PLANNING | 10 | UNIT | 56450 | Goonyella | HAY POINT | GREGORY | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | 3 | 5 | 4 | 1 | 20 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Planning for the removal of the contactor from the following (10) M23A machines: Red Mountain RM12A Pts, RM12B Pts, RM7A Pts, RM7B Pts, PD12A Pts, PD12B Pts, PD7A Pts, PD7B Pts, PD8A Pts, PD8B Pts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060093&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060093 | SIG_Replace M23A_GA_DT7A_Com | TO000468-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | DYSART | DYSART | 0 | KM | GA03ML88 | 0.315 | GA03ML88 | 0.315 | KM |  |  |  |  | 88.315 | 88.315 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:24:30 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060091&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060091 | SIG_Replace M23A_GA_DT12A_Com | TO000414-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | DYSART | DYSART | 0 | KM | GA03ML90 | 0.5829 | GA03ML90 | 0.5829 | KM |  |  |  |  | 90.583 | 90.583 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:24:12 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060092&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060092 | SIG_Replace M23A_GA_DT12B_Com | TO000414-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | DYSART | DYSART | 0 | KM | GA03ML90 | 0.5829 | GA03ML90 | 0.5829 | KM |  |  |  |  | 90.583 | 90.583 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:24:21 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060180&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060180 | SIG_Replace M23A_GA_NP8A_Com | TO000410-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | NORWICH PARK | NORWICH PARK | 0 | KM | GA03ML108 | 0.0149 | GA03ML108 | 0.0149 | KM |  |  |  |  | 108.015 | 108.015 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:39:02 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060208&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060208 | SIG_Replace M23A_GA_SI7A_Com | TO000397-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML64 | 0.796 | GA03ML64 | 0.796 | KM |  |  |  |  | 64.796 | 64.796 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:43:10 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060209&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060209 | SIG_Replace M23A_GA_SI7B_Com | TO000397-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML64 | 0.796 | GA03ML64 | 0.796 | KM |  |  |  |  | 64.796 | 64.796 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:43:19 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060210&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060210 | SIG_Replace M23A_GA_SI9A_Com | TO000395-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML65 | 0.193 | GA03ML65 | 0.193 | KM |  |  |  |  | 65.193 | 65.193 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:43:28 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060206&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060206 | SIG_Replace M23A_GA_SI12A_Com | TO000394-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML67 | 0.535 | GA03ML67 | 0.535 | KM |  |  |  |  | 67.535 | 67.535 | 2025-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:42:53 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available. M23A Mark 1 machine
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060207&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000060207 | SIG_Replace M23A_GA_SI12B_Com | TO000394-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 125187 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML67 | 0.535 | GA03ML67 | 0.535 | KM |  |  |  |  | 67.535 | 67.535 | 2025-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-10-13 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | MEDIUM | MEDIUM | Notification in process | SCPR INIF |  | 20250630 | * 23.06.2020 12:43:02 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043592&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000043592 | SIG_Power Res_GA_Batteries FY25_Ren | GA | CONTROL SYSTEMS | POWER RESILIENCE | SIGNALLING BATTERY BANK | RENEWAL | 4 | SITE | 194888 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 | 4 |  | 4 |  | 20 |  | 2023-10-13 | 2020-11-13 | Other Control Sys Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073952&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000073952 | SIG_Train Detection_BW_Wycarbah_CSEE_Pln | ST004480 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | PLANNING | 1 | STATION | 140765 | Blackwater | WYCARBAH | WYCARBAH | 0 | KM | BW03ML36 | 0.115 | BW03ML36 | 0.115 | KM |  |  |  |  | 36.115 | 36.115 | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 | 2021-10-05 | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR | FY23 IN | 20250630 | * 11.03.2021 11:42:19 AUSQLD Robert Love (R111379) * Plan for the replacement of all 36 logical tracks in interlocking with Thales axle counters. Determine if blocks in both directions are replaced or Westwood blocks are delayed until Thales is replaced at Westwood.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103866&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000103866 | SIG_Train Detection_GA_Millennium_ML_Des | ST007030 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 746499 | Goonyella | MILLENNIUM JUNCTION | MILLENNIUM JUNCTION | 0 | KM | GA03ML16 | 0.7229 | GA03ML16 | 0.7229 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20250630 | Replace all track circuits (primarily defunct 13 ML tracks and 1 AzS350U axlecounter track around part of the loop) with 16 new axlecounter tracks. New axlecounters are to be Frauschser. The axlecounter block to Ingsdon is to remain.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103982&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000103982 | SIG_Train Detection_GA_Saraji_ML_Des | ST000930 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 632723 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML64 | 0.755 | GA03ML64 | 0.755 | KM |  |  |  |  | 64.755 | 64.755 | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Replace 10 ML track circuits in the balloon loop (freq E,F,G,H) with 3 Frauscher. This interlocking is relay based and hence the resetting of the 3 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125249&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000125249 | SIG_Train Detection_GA_Ingsdon_ML_Pln | ST004770-09 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 155804 | Goonyella | INGSDON | INGSDON | 0 | KM | GA03ML11 | 0 | GA03ML11 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Replace all track circuits (primarily defunct ML tracks) with 23 axlecounter track sections. This is the planning phase.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104761&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000104761 | SIG_Train Detection_GA_Riverside_ML_Pln | ST005050 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 84675 | Goonyella | RIVERSIDE | RIVERSIDE | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Planning phase to replace 4 ML track circuits in the balloon loop (freq E,F plus 1xD) with 2 Frauscher tracks. Tracks with ML freq are 19BBT(1xF) and 19BAT(1xE,2xF,1xD). This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103860&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000103860 | SIG_Train Detection_GA_Mallawa_ML_Com | ST001210 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 5374139 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA01ML167 | 0.92 | GA01ML167 | 0.92 | KM |  |  |  |  | 167.92 | 167.92 | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Notification in process | SCPR |  | 20250630 | Replace all track circuits (primarily 26 defunct ML tracks) with 25 axlecounter tracks. Axlecounter is to be Frauschser.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103826&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000103826 | SIG_Train Detection_GA_PeakDowns_ML_Con | ST000940 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 1634340 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.9529 | GA03ML43 | 0.9529 | KM |  |  |  |  | 43.953 | 43.953 | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2023-10-13 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | Replace 7 ML track circuits in the balloon loop (freq E,F,G,H) with 2 Frauscher or Thales tracks. Preference is for Frauscher but there is a Thales axlecounter used for a semi-attached level crossing. This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110951&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000110951 | ACOM BW SYSTEM CONTRIBUTION | BW | CONTROL SYSTEMS | TRANSMISSION | ACOM | DESIGN | 1 | SYSTEM | 34544 | Blackwater | BLACKWATER | BLACKWATER | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-10-13 | 2022-11-30 | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | DESIGN FOR ACOM RENEWAL IN FY24 GA SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075234&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000075234 | ACOM GA SYSTEM CONTRIBUTION | GA | CONTROL SYSTEMS | TRANSMISSION | ACOM | DESIGN | 1 | SYSTEM | 34544 | Goonyella | GOONYELLA | GOONYELLA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-10-13 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20250630 | * 30.03.2021 07:19:38 AUSQLD Scott Andrews (R003573) * DESIGN FOR ACOM RENEWAL IN FY24 GA SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053514&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000053514 | ACOM MA SYSTEM CONTRIB | MA | CONTROL SYSTEMS | TRANSMISSION | ACOM | DESIGN | 1 | SYSTEM | 21817 | Moura | MOURA | MOURA | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 5 |  | 20 |  | 2023-10-13 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20250630 | * 29.03.2021 19:17:24 AUSQLD Scott Andrews (R003573) * DESIGN FOR ACCOM RENEWALINFY24MA SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075216&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000075216 | NL ACOM DESIGN SYSTEM CONTRIBUTION | NL | CONTROL SYSTEMS | TRANSMISSION | ACOM | DESIGN | 1 | SYSTEM | 10908 | Newlands | NEWLANDS | NEWLANDS | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-10-13 | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20250630 | * 29.03.2021 20:36:22 AUSQLD Scott Andrews (R003573) * NL ACOM DEISNG FOR RENEWAL IN FY24 SYSTEM CONTRIBUTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100900&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100900 | CS Transmission DMR Link | ST005600-19 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 402044 | Moura | BANANA RANGE | SPECIMEN HILL | 0 | KM | MA13CR0 | 0 | MA13CR0 | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085523&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085523 | CS Transmission DMR Renewal | ST006120-49 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 402044 | Blackwater | BLACKWATER | BLUFF | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM |  |  |  |  | 189.259 | 189.259 | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100290&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100290 | CS Power Supply Renewal | ST005130-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Newlands | ABBOT POINT SER | ABBOT POINT SER | 0 | KM | NL02CR16 | 0.44 | NL02CR16 | 0.44 | KM |  |  |  |  | 16.44 | 16.44 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100573&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100573 | CS Transmission Power Supply | ST003290-15 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Moura | ANNANDALE SER | ANNANDALE SER | 0 | KM | MA01ML0 | 0.1 | MA01ML0 | 0.1 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100292&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100292 | CS Transmission Power Supply Renewal | ST002650-11 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Newlands | ARMUNA SER | ARMUNA SER | 0 | KM | NL01ML24 | 0.1069 | NL01ML24 | 0.1069 | KM |  |  |  |  | 24.107 | 24.107 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100530&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000100530 | CS Transmission Power Supply | ST009080-02 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Blackwater | BAJOOL PSC | BAJOOL PSC | 0 | KM | BW01ML603 | 0.53 | BW01ML603 | 0.53 | KM |  |  |  |  | 603.53 | 603.53 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100534&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000100534 | CS Transmission Power Supply | ST007740-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Blackwater | BAJOOL TSC | BAJOOL TSC | 0 | KM | BW01ML604 | 0.2999 | BW01ML604 | 0.2999 | KM |  |  |  |  | 604.3 | 604.3 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100596&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100596 | CS Transmission Power Supply | ST002690-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Newlands | BINBEE SER | BINBEE SER | 0 | KM | NL01ML45 | 0.9549 | NL01ML45 | 0.9549 | KM |  |  |  |  | 45.955 | 45.955 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100594&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100594 | CS Transmission Power Supply | ST008610-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Newlands | COCKOOL SER | COCKOOL SER | 0 | KM | NL01ML112 | 0.76 | NL01ML112 | 0.76 | KM |  |  |  |  | 112.76 | 112.76 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100570&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100570 | CS Transmission Power Supply | ST001680-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Goonyella | COPPABELLA MI | COPPABELLA MI | 0 | KM | GA01ML142 | 0.7479 | GA01ML142 | 0.7479 | KM |  |  |  |  | 142.748 | 142.748 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100548&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100548 | CS Transmission Power Supply | ST004190-14 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Blackwater | DUARINGA SER | DUARINGA SER | 0 | KM | BW03ML104 | 0.78 | BW03ML104 | 0.78 | KM |  |  |  |  | 104.78 | 104.78 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100291&DY_MAB=X&~OKCODE=ONLI | FY25 | Dual Traffic | BASELOAD | COAL | 002000100291 | CS Transmission Power Supply Renewal | ST002790-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Newlands | DURROBURRA SER | DURROBURRA SER | 0 | KM | NC03ML1158 | 0.532 | NC03ML1158 | 0.532 | KM |  |  |  |  | 1158.532 | 1158.532 | 2025-06-30 |  |  |  |  | 5 |  |  |  |  | 12 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078650&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000078650 | CS Transmission Power Supply | ST007820-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Blackwater | GRACEMERE ATS 8.9KM |  | 0 | KM | BW03ML8 | 0.8499 | BW03ML8 | 0.8499 | KM |  |  |  |  | 8.85 | 8.85 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | * 10.06.2021 15:59:46 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078657&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000078657 | CS Transmission Power Supply | ST004770-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Goonyella | INGSDON SER |  | 0 | KM | GA03ML11 | 0.02 | GA03ML11 | 0.02 | KM |  |  |  |  | 11.02 | 11.02 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | * 10.06.2021 16:07:28 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100531&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100531 | CS Transmission Power Supply | ST007780-40 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Blackwater | KABRA TSC | KABRA TSC | 0 | KM | BW03ML15 | 0.46 | BW03ML15 | 0.46 | KM |  |  |  |  | 15.46 | 15.46 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078658&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000078658 | CS Transmission Power Supply | ST008040-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Goonyella | MIDDLEMOUNT JUNCTION SER |  | 0 | KM | GA03ML125 | 0.511 | GA03ML125 | 0.511 | KM |  |  |  |  | 125.511 | 125.511 | 2025-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | * 10.06.2021 16:08:35 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100572&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000100572 | CS Transmission Power Supply | ST008260-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 43337 | Goonyella | NORTH GOONYELLA SER2 | NORTH GOONYELLA SER2 | 0 | KM | GA01ML213 | 0.52 | GA01ML213 | 0.52 | KM |  |  |  |  | 213.52 | 213.52 | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085432&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000085432 | CS Transmission Renewal | ST005490-JP | CONTROL SYSTEMS | TRANSMISSION | REVELOC | RENEWAL | 1 | SITE | 54544 | Blackwater |  |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM |  |  |  |  | 638.8 | 638.8 | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093777&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000093777 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 0 | LUMPSUM | 107080 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093768&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000093768 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 0 | LUMPSUM | 99148 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085252&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085252 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 1 | BLACKWATER 1 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100650&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100650 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 2 | BLACKWATER 2 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100651&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100651 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 3 | BLACKWATER 3 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100652&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100652 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 4 | BLACKWATER 4 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100653&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100653 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 5 | BLACKWATER 5 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100654&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100654 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 6 | BLACKWATER 6 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100655&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100655 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 7 | BLACKWATER 7 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100656&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100656 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Blackwater | BLACKWATER 8 | BLACKWATER 8 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085253&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085253 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 1 | GOONYELLA 1 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100569&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100569 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 2 | GOONYELLA 2 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100658&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100658 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 3 | GOONYELLA 3 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100670&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100670 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 4 | GOONYELLA 4 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100671&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100671 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 5 | GOONYELLA 5 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100672&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100672 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 6 | GOONYELLA 6 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100673&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100673 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 7 | GOONYELLA 7 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100674&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100674 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Goonyella | GOONYELLA 8 | GOONYELLA 8 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085255&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085255 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Moura | MOURA 1 | MOURA 1 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100568&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100568 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Moura | MOURA 2 | MOURA 2 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085254&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000085254 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Newlands | NEWLANDS 1 | NEWLANDS 1 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100657&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000100657 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13829 | Newlands | NEWLANDS 2 | NEWLANDS 2 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114897&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000114897 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | PLANNING | 0 | LUMPSUM | 22726 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114896&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000114896 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | PLANNING | 0 | LUMPSUM | 22726 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102842&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000102842 | CS TETRA AP Site Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 0 | LUMPSUM | 115052 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102839&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000102839 | CS TETRA AP Site Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 0 | LUMPSUM | 115052 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 2.4 |  | 12 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085470&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000085470 | CS TETRA RADIO | ST006850 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 513158 | Blackwater | STANWELL | STANWELL | 0 | KM | BW04BL1 | 0.5 | BW04BL1 | 0.5 | KM |  |  |  |  | 1.5 | 1.5 | 2025-06-30 |  |  |  |  | 5 |  |  | 5 |  | 25 |  | 2023-10-13 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000064107&DY_MAB=X&~OKCODE=ONLI | FY25 |  | FUTURE SCOPE | COAL | 002000064107 | Dig Telem BR Renewal | BW | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | DESIGN | 9 | SITE | 906651 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-10-13 |  | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085036&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000085036 | UTC DTC Renewal BW | BW | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 0 | LUMPSUM | 947597 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | UTC DTC | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085080&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000085080 | UTC DTC Renewal GA | GA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 0 | LUMPSUM | 947597 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | UTC DTC | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085035&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000085035 | UTC DTC Renewal MA | MA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 0 | LUMPSUM | 118449 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | UTC DTC | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085083&DY_MAB=X&~OKCODE=ONLI | FY25 |  | STRATEGIC | COAL | 002000085083 | UTC DTC Renewal NL | NL | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 0 | LUMPSUM | 355349 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 10 | 10 |  | 0.1 |  | 100 |  | 2023-10-13 |  | UTC DTC | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085271&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000085271 | OVERHEAD¦FW CLEARANCE¦DESIGN¦BALOOK | GA-0212-00212B | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | DESIGN | 1 | SITE | 504211 | Goonyella | BALOOK | BALOOK | 11.458 | KM | GA/74/565/D | 0 | GA/86/023/D | 0 | KM |  |  |  |  | 74.565 | 86.023 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | FW and Clearance Improvement | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071616&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000071616 | OVERHEAD¦FW CLEARANCE¦DESIGN¦BLUFF | BW-0852 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | DESIGN | 1 | SITE | 127818 | Blackwater | BLUFF | BLUFF | 20.102 | KM | CW/153/1002/D | 0 | CW/173/202/D | 0 | KM |  |  |  |  | 153.1 | 173.202 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | FW and Clearance Improvement | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | 28/06/23: The scope for Bluff FW Clearance is to raise the feeder wires in Bluff yard to our current standard and relocate the feeder wire above the correct road (where applicable).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085192&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000085192 | OVERHEAD¦GOONYELLA PORTS OHL¦RENEWAL | GA-0912 | ELECTRICAL | OVERHEAD | GOONYELLA PORTS OHL RENEWAL | RENEWAL | 1 | SITE | 2448000 | Goonyella | DALRYMPLE BAY | HAY POINT | 9.6679 | KM | DL/-0/068/DR1 | 0 | GA/9/600/D | 0 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Goonyella Ports Overhead Line Renewal | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. 24/08/22: Estimate updated following development of Class 4 estimate. Refer to PCR 5347.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121340&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000121340 | T30-OH-HEADSPAN-Dysart-89.963km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 89.963 | 89.963 | 2025-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 03/07/2023 EK: Renewal (Headspans) @OC/89/963 will be in FY25. See attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121269&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000121269 | T30-OH-HEADSPAN-Dysart-90.009km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.009 | 90.009 | 2025-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | NWSC |  | 20250630 | 03/07/2023 EK: Renewal (Headspans) @ OC/90/009 will be in FY25. See attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121266&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000121266 | T30-OH-HEADSPAN-Dysart-90.073km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.073 | 90.073 | 2025-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 03/07/2023 EK: Renewal(Headspans) @ OC/90/073 will be in FY25. See attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094956&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094956 | T30-OH-HEADSPAN-Dysart-90.136km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.136 | 90.136 | 2025-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Notification in process | SCPR |  | 20250630 | 03/07/2023 EK: Updated the renewal year to FY25 as per latest requirement/instruction. See attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094957&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094957 | T30-OH-HEADSPAN-Dysart-90.198km | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM |  |  |  |  | 90.198 | 90.198 | 2025-06-30 |  |  |  |  | 3 | 1.4 | 4 | 3.7 | 1 | 11.1 |  | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Notification in process | SCPR |  | 20250630 | 03/07/2023 EK: Updated to FY 25 renewal as per latest requirement/instruction. See attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094950&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094950 | T30-OH-HEADSPAN-Peak DNs-44.156km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.156 | 44.156 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094951&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094951 | T30-OH-HEADSPAN-Peak DNs-44.216km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.216 | 44.216 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094952&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094952 | T30-OH-HEADSPAN-Peak DNs-44.276km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.276 | 44.276 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094953&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094953 | T30-OH-HEADSPAN-Peak DNs-44.336km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.336 | 44.336 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094954&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094954 | T30-OH-HEADSPAN-Peak DNs-44.396km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.396 | 44.396 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094955&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094955 | T30-OH-HEADSPAN-Peak DNs-44.460km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.46 | 44.46 | 2025-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 | 5554 | 2023-10-13 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS | HIGH | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20250630 | 12.01.23 PCR 5554. Due to resoure <(>&<)> possession availability the introduction of additional headspans is not achievable as FY23 scope will not be achieved. Current approved possessions will only complete FY22 scope. Alternate plans have been requested but not approved. Propose to Defer FY23 to FY24 Possession plans and place FY24 proposal to FY25 planning process.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084405&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000084405 | Small Component Renewals | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 0 | LUMPSUM | 1004709 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | 31.03.2023: decision to reduce from $1m to $800k in meeting of 31.03.23 to reduce FY25 spend.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084404&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000084404 | Small Component Renewals | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 0 | LUMPSUM | 1004709 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2023-10-13 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630 | 31.03.2023: decision to reduce from $1m to $800k in meeting of 31.03.23 to reduce FY25 spend.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068755&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068755 | OH - Termination Portal Renewal | SQ020483 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0.033 | KM | GA01ME0 | 103.1899 | GA01ME0 | 103.2229 | KM |  |  |  |  | 103.19 | 103.19 | 2025-06-30 |  |  |  |  | 4 | 1.2 | 3 | 3.1 | 1 | 12.4 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555. The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068749&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068749 | OH - Termination Portal Renewal | SQ020476 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | BURTON | BURTON | 0.035 | KM | GA01ME0 | 3.5819 | GA01ME0 | 3.6169 | KM |  |  |  |  | 3.582 | 3.582 | 2025-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068747&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068747 | OH - Termination Portal Renewal | SQ020473 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.07 | KM | GA01ME0 | 134.233 | GA01ME0 | 134.3029 | KM |  |  |  |  | 134.233 | 134.233 | 2025-06-30 |  |  |  |  | 4 | 1.2 | 3 | 3.1 | 1 | 12.4 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068751&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068751 | OH - Termination Portal Renewal | SQ020479 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | GOONYELLA | GOONYELLA | 0.033 | KM | GA01ME0 | 198.1959 | GA01ME0 | 198.229 | KM |  |  |  |  | 198.196 | 198.196 | 2025-06-30 |  |  |  |  | 4 | 2.1 | 3 | 3.5 | 1 | 14 |  | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068741&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068741 | OH - Termination Portal Renewal | SQ020466 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | MOORVALE | MOORVALE | 0.035 | KM | GA01ME0 | 5.4729 | GA01ME0 | 5.508 | KM |  |  |  |  | 5.473 | 5.473 | 2025-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068745&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068745 | OH - Termination Portal Renewal | SQ020471 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | NORWICH PARK | NORWICH PARK | 99.9659 | KM | GA01ME0 | 111.194 | GA01ME0 | 11.2279 | KM |  |  |  |  | 111.194 | 111.194 | 2025-06-30 |  |  |  |  | 4 | 1.4 | 3 | 3.2 | 1 | 12.8 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068752&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000068752 | OH - Termination Portal Renewal | SQ020480 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 106673 | Goonyella | RIVERSIDE | RIVERSIDE | 0.0299 | KM | GA01ME0 | 203.506 | GA01ME0 | 203.536 | KM |  |  |  |  | 203.506 | 203.506 | 2025-06-30 |  |  |  |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 | 5555 | 2023-10-13 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105127&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105127 | AT¦BLACK MTN HATFIELD AT2¦DESIGN | ST001300-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Goonyella | BLACK MTN | BLACK MTN | 0 | KM | GA01ML45 | 0.225 | GA01ML45 | 0.225 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105129&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105129 | AT¦BROADLEA ATS AT1¦DESIGN | ST001440-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML154 | 0.1739 | GA01ML154 | 0.1739 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105130&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105130 | AT¦ROCKLANDS TSC AT2¦DESIGN | ST000160-21 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105131&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105131 | AT¦ROCKLANDS TSC AT4¦DESIGN | ST000160-23 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105132&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105132 | AT¦ROCKLANDS TSC AT5¦DESIGN | ST000160-24 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050168&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic |  | COAL | 002000050168 | AT¦Balook-Wandoo ATS AT2¦RENEWAL | ST001350-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | BALOOK-WANDOO ATS - AT2 | BALOOK WANDOO ATS | 0 | KM | GA01ML76 | 0.783 | GA01ML76 | 0.783 | KM |  |  |  |  | 76.783 | 76.783 | 2025-06-30 | [7 empty] | 0.1 |  | 100 |  | 2021-03-31 | 2021-10-05 | Autotransformer Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | RRIG INIF | FY23 IN | 20250131 | * 01.06.2020 20:45:35 AUSQLD Emma-Kate Clyburn (R870828) * Site to be confirmed in Jan 2021 * 23.03.2021 14:29:17 AUSQLD Dhavalkumar Patel (R866429) * Site Confirmed. * 31.03.2021 19:17:27 AUSQLD Tracy Holmes (R870040) failures elsewhere in the system. * 12.04.2021 16:21:36 AUSQLD Jeremy Stevenson (R867415) * Current procurement contract will expire in FY23 - need to discuss this in FY23. (design implementat * ion for FY23 for reduction in cost with optimised design) - scope is low but as the design is being optimised in FY23 there may be change to scope on AT), duration is medium due to AT failures elsewhe * re in the system. 06/02/24 EK: This update based on the action required for PCR5847. See excerpt below: Balook Wandoo was FY23 scope which we have not been able to gain access to due to land owner imposed restrictions. This PCR is to scope substitute Balook Wandoo AT2 (2000050168) with Bollingbroke AT2 (2000098510). This will allow Bollingbroke AT1 and Bollingbroke AT2 to be completed at the same time in March FY24 and allow time to resolve access issued at Balook Wandoo before FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000076184&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000076184 | AT¦GREGORY FS AT2¦RENEWAL | ST000110-16 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | GREGORY FS - AT2 | GREGORY FS | 0 | KM | BW08ML66 | 0.066 | BW08ML66 | 0.066 | KM |  |  |  |  | 66.066 | 66.066 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Placeholder. FY25 AT renewals to be confirmed post condition assessment in December 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000098512&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000098512 | AT¦RANGAL FS AT3¦RENEWAL | ST000340-35 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Placeholder. FY25 AT renewals to be confirmed post condition assessment in December 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085290&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000085290 | AT¦RANGAL FS AT5¦RENEWAL | ST000340-37 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Placeholder. FY25 AT renewals to be confirmed post condition assessment in December 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000098511&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000098511 | AT¦SARAJI TSC AT2¦RENEWAL | ST000740-08 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM |  |  |  |  | 71.271 | 71.271 | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Placeholder. FY25 AT renewals to be confirmed post condition assessment in December 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112946&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | STRATEGIC | COAL | 002000112946 | AT¦VILLAFRANCA TSC AT1¦RENEWAL | ST000790-08 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | VILLAFRANCA TSC | VILLAFRANCA TSC | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2023-10-13 |  | Autotransformer Renewal | LIKE FOR LIKE | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20250630 | Swap into FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094384&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094384 | T32-PS-GA-DBCT-1.485km | ST007600-19 | ELECTRICAL | POWER SYSTEMS | EARTHING AND BONDING | RENEWAL | 1 | SITE | 63613 | Goonyella | DALRYMPLE BAY COAL TERMINAL | DALRYMPLE BAY COAL TERMINAL | 0 | KM | GA01BA1 | 0.6889 | GA01BA1 | 0.6889 | KM |  |  |  |  | 1.485 | 1.485 | 2025-06-30 |  |  |  |  | 3 | 2.6 | 0.5 | 2.5 | 1 | 7.5 |  | 2023-10-13 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR INIF |  | 20250630 | DBCT FS masts hollow channel
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044453&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000044453 | MI Renewal 211/2 Balook | SQ030295 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | BALOOK | BALOOK | 0 | KM | GA/74/494/U | 0 | GA/74/494/U | 0 | KM |  |  |  |  | 74.494 | 74.494 | 2025-06-30 |  |  |  |  | 4.1 | 4.8 | 2 | 4.2 | 1 | 17.22 | 3634 | 2023-10-13 | 2019-11-29 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | * 10.11.2020 14:39:48 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 19.03.2021 14:30:36 AUSQLD Rinaldo Licis (R851602) * Moved to FY23-24 21/2/2022 R.Licis: Attached FY24 scope and inspection form. Photo are in \\bneprdfps001\PD\5a. Nwk Projects\IV00505 - FY2021 - Power Systems Renewal Package No. 3\1000_Approval <(>&<)> Scope\1400_Project Plan\IV.00505.E.B - FY21 Motorised Isolators\Scope\Photos\Goonyella\211.2 Balook 13.01.2023 PCR 5557. Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support. This reduce the demand for overheads and allows for typical trends of deferred scope. Scope moved from FY24 to FY25. 5/3/2023 R.Licis: Scope type D1 Double. BOM attached. For FY25 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044452&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000044452 | MI Renewal 211/3 Balook | SQ030294 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | BALOOK | BALOOK | 0 | KM | GA/74/685/U | 0 | GA/74/685/U | 0 | KM |  |  |  |  | 74.685 | 74.685 | 2025-06-30 |  |  |  |  | 4.1 | 4.8 | 2 | 4.2 | 1 | 17.22 | 3634 | 2023-10-13 | 2019-11-29 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | * 10.11.2020 14:38:37 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 21/2/2022 Renewal and Site Inspection Form attached. Photos are in: \\bneprdfps001\PD\5a. Nwk Projects\IV00505 - FY2021 - Power Systems Renewal Package No. 3\1000_Approval <(>&<)> Scope\1400_Project P lan\IV.00505.E.B - FY21 Motorised Isolators\Scope\Photos\Goonyella\211.3 Balook 13.01.2023 PCR 5557. Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support. This reduce the demand for overheads and allows for typical trends of deferred scope. Scope moved from FY24 to FY25. 5/3/2023 R.Licis: Scope type is D2 double. BOM attached. 17/12/2023 R.Licis: Due to earth fault on cable and application of MI philosophy, MI will be renewed as a manual handle isolator. Scope form and BOM updated. New Scope Type is E2
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044456&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000044456 | MI Renewal 612/2 Bolingbroke | SQ030288 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA/60/486/D | 0 | GA/60/486/D | 0 | KM |  |  |  |  | 60.486 | 60.486 | 2025-06-30 |  |  |  |  | 4.1 | 5 | 2 | 4.2 | 1 | 17.22 | 3634 | 2023-10-13 | 2019-11-29 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | * 10.11.2020 14:40:53 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 19.03.2021 16:28:25 AUSQLD Rinaldo Licis (R851602) * Moved to FY24-25 by RL and HC 13/2/2022 Moved back to FY23-24 by RL 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 7/3/2023 R.Licis: BOM attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075908&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000075908 | MI Renewal 911A/912J Dalrymple | SQ030497 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0 | KM | DL/-0/833/AR2 | 0 | DL/-0/833/AR2 | 0 | KM |  |  |  |  | 0.833 | 0.833 | 2025-06-30 |  |  |  |  | 3.86 | 4.6 | 2 | 4.1 | 1 | 15.83 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | 5/3/2023 R.Licis: Scope attached. Scope is B1 Single. Confirm is PSC is at 0k620 still operational before finalising scope. 19/4/2023: John Bati and Trent confirm PSC @0k620 is decommissioned. Therefore scope of MI is turn it to manual isolator.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074293&DY_MAB=X&~OKCODE=ONLI | FY25 |  | BASELOAD | COAL | 002000074293 | MI Renewal at 232/9 Tootoolah | SQ030265 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0 | KM | GA/132/727/D | 0 | GA/132/727/D | 0 | KM |  |  |  |  | 3.933 |  | 2025-06-30 |  |  |  |  | 3.4 | 4.7 | 2 | 4.1 | 1 | 13.94 |  | 2023-10-13 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification completed | SCPR | FY23 IN | 20250630 | * 31.03.2021 19:19:57 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 7/2/2022 R.Licis: The functional location was originally allocated was GA. Therefore not pointing to anything. This notification has been counted as part of FY23 MI RIG submission. Therefore Functional Location replaced with Isolator 232/9 Tootoolah. 11/4/2022 R.Licis: Scope: B2 Double WBS: IV.00824.E.D.GA.07 13/4/2022 R.Licis: Updated the B2 double bill of material. See updated attachment in noti. Also updated the BOM in WO (Component tab): - Changed single pole 55013298 to double pole 55013785 - Increased isolator lug 65010651 from qty 2 to 4 30/01/2023 R.Christensen: B2 IFC Drawing attached 6/2/2023: 232/9 Tootoolah (FY23) has been swapped with isolator 622/2 Mallawa (FY25). Therefore 232/9 Tootoolah has been set to FY25. Scope is identical B2 Double. PM has been advised of change. PCR 5598 has been lodged 232/9 was replace on 18.08.2023
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074290&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000074290 | MI Renewal 902K/904H Jilalan | SQ030550 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/454/DY | 0 | GA/17/454/DY | 0 | KM |  |  |  |  | 17.454 | 17.454 | 2025-06-30 |  |  |  |  | 3.4 | 4.6 | 2 | 4.1 | 1 | 13.94 |  | 2023-10-13 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR | FY23 IN | 20250630 | * 31.03.2021 19:20:21 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 1/4/2022 R.Licis: Scope and inspection attached. Scope type is F3 11/4/2022 R.Licis: Scope:F3 SINGLE POLLUTED WBS:IV.00824.E.D.GA.04 29/6/2022 R.Licis: Zane Hooton has requested that this one is swapped out and replaced with Jilalan 901/4 at GA/17/634 from FY24. PCR number to be advised. Therefore 902K/904H to be done in FY24 5/8/2022 R.Licis: PCR number for this is 5432 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 5/3/2022 R.Licis: This was reviewed by RIG/Aurizon and it was decided to be moved to FY25. Scope type is F3 SINGLE POLLUTED
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094340&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000094340 | Hand Rail Installation Jilalan 902D/907C | SQ030558 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/480/PR1 | 0 | GA/22/480/PR1 | 0 | KM |  |  |  |  | 22.48 | 22.48 | 2025-06-30 |  |  |  |  | 3.9 | 4.6 | 2 | 4.1 | 1 | 15.99 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | 30/3/2022 R.Licis: This N4 is for installation of handrail ONLY behind MI 902D/907C at GA/22/480 (Jilalan TSC side). Hand rail to be installed in FY24 and renewal of MI to be done in FY25. Scope, photo, and hand rail drawing attached. K.Robinson (Net Ops Electrical)will organise external contractor to install handrail. Handrail to be ordered via IML (material ID 10061928) 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). This reduces the demand for overheads and allows for typical trends of deferred scope. Scope moved to FY25. 5/3/2023 R.Licis: Required end date changed to FY25 as per above reason.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044523&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000044523 | MI Renewal 901/6 Jilalan | SQ030559 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/531/UM | 0 | GA/22/531/UM | 0 | KM |  |  |  |  | 22.531 | 22.531 | 2025-06-30 |  |  |  |  | 3.29 | 4.8 | 2 | 4.2 | 1 | 13.82 |  | 2023-10-13 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR | FY24 OUT | 20250630 | * 06.03.2020 14:30:44 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 901/6 * 22.03.2021 14:46:46 AUSQLD Rinaldo Licis (R851602) * 901/6 MI at Jilalan swapped with 622/20 MI at Burton. Therefore 901/6 to be done in FY23 * 23.03.2021 10:15:56 AUSQLD Rinaldo Licis (R851602) * Incorrect 901/6 moved to FY24 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 5/3/2023 R.Licis: Scope F4 double. BOM attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075930&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000075930 | MI Renewal 902/14 Praguelands | SQ030225 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA/14/450/J4S | 0 | GA/14/450/J4S | 0 | KM |  |  |  |  | 14.412 | 14.412 | 2025-06-30 |  |  |  |  | 3.29 | 4.6 | 2 | 4.1 | 1 | 13.5 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR | FY24 OUT | 20250630 | 11/3/2022 R.Licis: Scope and inspection form attached Photos are located in \\bneprdfps001\PD\5a. Nwk Projects\IV00505 - FY2021 - Power Systems Renewal Package No. 3\1000_Approval <(>&<)> Scope\1400_Project Plan\IV.00505.E.B - FY21 Motorised Isolators\Scope\Photos\FY22 and 23 GA Inspection\Pragueland 902_14 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 5/3/2023 R.Licis: Scope type E2 Double. BOM attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075931&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000075931 | MI Renewal 901/3 Praguelands | SQ030235 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA/14/614/U | 0 | GA/14/614/U | 0 | KM |  |  |  |  | 14.614 | 14.614 | 2025-06-30 |  |  |  |  | 3.29 | 4.6 | 2 | 4.1 | 1 | 13.49 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR | FY24 OUT | 20250630 | 11/3/2022 R.Licis: Scope and Inspection form attached. All files and photos are located at: \\bneprdfps001\PD\5a. Nwk Projects\IV00505 - FY2021 - Power Systems Renewal Package No. 3\1000_Approval <(>&<)> Scope\1400_Project Plan\IV.00505.E.B - FY21 Motorised Isolat ors\Scope\Photos\FY22 and 23 GA Inspection\Pragueland 901_3 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). This reduces the demand for overheads and allows for typical trends of deferred scope. Scope moved to FY25. 5/3/2023 R.Licis: Scope type E2 double. BOM to be attached. Set to FY25
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075945&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000075945 | MI Renewal 301/2 Red Mountain | SQ030256 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | OC/21/890/D | 0 | OC/21/890/D | 0 | KM |  |  |  |  | 21.89 | 21.89 | 2025-06-30 |  |  |  |  | 4.59 | 2.5 | 2 | 3.3 | 1 | 15.15 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | 15/6/2022 R.Licis: Inspection and scope form attached. Scope is for FY25 Scope is B2 variation 5 (B2 Double).Bill of material attached. 20/7/2022 R.Licis: Propose to swap this with Jilalan 908/3 (B2 Single) currently in FY22. PCR to be submitted shortly. 5/3/2022 R.Licis: 301/2 to be done in FY25.Scope type B2 double. BOM attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075933&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000075933 | MI Renewal 231/4 Tootoolah | SQ030280 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 59764 | Goonyella | TOOTOOLAH | TOOTOOLAH | 0 | KM | GA/132/942/U | 0 | GA/132/942/U | 0 | KM |  |  |  |  | 132.942 | 132.942 | 2025-06-30 |  |  |  |  | 3.44 | 4.7 | 2 | 4.1 | 1 | 14.1 |  | 2023-10-13 |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20250630 | 11/3/2022 R.Licis: Scope and Inspection form attached. All files and photos are located here: \\bneprdfps001\PD\5a. Nwk Projects\IV00505 - FY2021 - Power Systems Renewal Package No. 3\1000_Approval <(>&<)> Scope\1400_Project Plan\IV.00505.E.B - FY21 Motorised Isol ators\Scope\Photos\FY22 and 23 GA Inspection\Tootoolah 231_4 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 5/3/2023 R.Licis: Scope type is B2 Double.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105406&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105406 | BRAESIDE 107.800 PSC SITE DESIGN | ST001650-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA01ML107 | 0.8 | GA01ML107 | 0.8 | KM |  |  |  |  | 107.8 | 107.8 | 2025-06-30 |  |  |  |  | 3.5 | 5 | 0.5 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105408&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105408 | COPPABELLA 142.748 PSC SITE DESIGN | ST001680-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML142 | 0.7479 | GA01ML142 | 0.7479 | KM |  |  |  |  | 142.748 | 142.748 | 2025-06-30 |  |  |  |  | 3.5 | 4.6 | 0.5 | 3.5 | 1 | 12.3 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105409&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105409 | COPPABELLA 145.381 PSC SITE DESIGN | ST001730-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML145 | 0.381 | GA01ML145 | 0.381 | KM |  |  |  |  | 145.381 | 145.381 | 2025-06-30 |  |  |  |  | 3.5 | 4.6 | 0.5 | 3.5 | 1 | 12.3 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110126&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000110126 | JILALAN YARD 19.404 PSC SITE DESIGN | ST001520-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Goonyella | JILALAN YARD | JILALAN YARD | 0 | KM | GA01ML19 | 0.404 | GA01ML19 | 0.404 | KM |  |  |  |  | 19.404 | 19.404 | 2025-06-30 |  |  |  |  | 3.5 | 4.8 | 0.5 | 3.6 | 1 | 12.6 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Design N4 for renewal of Jilalan Yard 19.404 km PSC. Initial site visit completed. Initial plan is to pour a new concrete slab adjacent to existing, and install new PSE, to minimise cutover time.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105460&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105460 | MIDGEE 623.280 PSC SITE DESIGN | ST002100-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Blackwater | MIDGEE | MIDGEE | 0 | KM | BW01ML623 | 0.28 | BW01ML623 | 0.28 | KM |  |  |  |  | 623.28 | 623.28 | 2025-06-30 |  |  |  |  | 3.5 | 4.5 | 0.5 | 3.5 | 1 | 12.3 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105407&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | FUTURE SCOPE | COAL | 002000105407 | WAITARA 98.160 PSC SITE DESIGN | ST001640-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | DESIGN | 1 | SITE | 12575 | Goonyella | WAITARA | WAITARA | 0 | KM | GA01ML98 | 0.16 | GA01ML98 | 0.16 | KM |  |  |  |  | 98.16 | 98.16 | 2025-06-30 |  |  |  |  | 3.5 | 5 | 0.5 | 3.7 | 1 | 13 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105461&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000105461 | PEAK DOWNS 43.789 PSC SITE RENEWAL | ST001740-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 190380 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA17ML43 | 0.789 | GA17ML43 | 0.789 | KM |  |  |  |  | 43.789 | 43.789 | 2025-06-30 |  |  |  |  | 3.5 | 2.1 | 0.5 | 2.1 | 1 | 7.4 |  | 2023-10-13 |  | Power Supply Cubicle (PSC) Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111544&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111544 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH BS1-2 | ST000210-31 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111541&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111541 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH C11 | ST000210-29 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111542&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111542 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH C12 | ST000210-30 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111543&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111543 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH GT/111 | ST000210-32 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111545&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111545 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH GT/112 | ST000210-33 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111546&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111546 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH GT/121 | ST000210-34 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111547&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111547 | PS¦RELAYS¦RENEWAL¦GRANTLEIGH GT/122 | ST000210-35 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2025-06-30 |  |  |  |  | 3.5 | 3.4 | 0.5 | 2.9 | 1 | 10.5 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111548&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111548 | PS¦RELAYS¦RENEWAL¦MT MCLAREN B42 | ST000800-21 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2025-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111549&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111549 | PS¦RELAYS¦RENEWAL¦MT MCLAREN B43 | ST000800-22 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2025-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111550&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111550 | PS¦RELAYS¦RENEWAL¦MT MCLAREN MM/421 | ST000800-25 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2025-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111551&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111551 | PS¦RELAYS¦RENEWAL¦MT MCLAREN MM/431 | ST000800-26 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2025-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111552&DY_MAB=X&~OKCODE=ONLI | FY25 | Coal Traffic | BASELOAD | COAL | 002000111552 | PS¦RELAYS¦RENEWAL¦MT MCLAREN MM/BS1-2 | ST000800-27 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Goonyella | MOUNT MCLAREN | MOUNT MCLAREN | 0 | KM | GA05ML76 | 0.4319 | GA05ML76 | 0.4319 | KM |  |  |  |  | 76.432 | 76.432 | 2025-06-30 |  |  |  |  | 3.5 | 1.2 | 0.5 | 1.2 | 1 | 4.2 |  | 2023-10-13 |  | Protection Relay Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103897&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000103897 | FY26 ACCESS POINT REACTIVE WORKS | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103900&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000103900 | FY26 ACCESS POINT REACTIVE WORKS | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | FY26 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103903&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000103903 | FY26 ACCESS POINT REACTIVE WORKS | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103906&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000103906 | FY26 ACCESS POINT REACTIVE WORKS | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093522&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000093522 | C60-ACP-BW-BLACKWATER-189.4km | AP100722 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | BLACKWATER | SAGITARIUS | 0 | KM | BW46YR189 | 0.4 | BW46YR189 | 0.4 | KM |  |  |  |  | 189.4 | 189.4 | 2026-06-30 |  |  |  |  | 10 | 3.15 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default the design for this renewal will flow to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed renewal out this renewal to FY26. 31 March- to be designed in FY23 for construction in FY25. Detail design and F5083 to be sent to TMR for approval before the slip lanes etc. can be constructed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093523&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000093523 | C60-ACP-BW-BLACKWATER-189.617km | AP100169 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | BLACKWATER | SAGITARIUS | 0 | KM | BW04ML189 | 0.6179 | BW04ML189 | 0.6179 | KM |  |  |  |  | 189.617 | 189.617 | 2026-06-30 |  |  |  |  | 10 | 3.15 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | AP100169 BW CWL 04ML (UP ROAD) 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default the design for this renewal will flow to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed this renewal out to FY26. 31 March- To be designed in FY23 for FY25 construction. Detail design to be completed, to be sent to TMR for approval with the form F5083. This has to be completed before the construction can be completed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093521&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000093521 | C60-ACP-BW-SAGITARIUS-187.563km | AP100089 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | SAGITARIUS | BLACKWTATER | 0 | KM | BW03ML187 | 0.5629 | BW03ML187 | 0.5629 | KM |  |  |  |  | 187.565 | 187.565 | 2026-06-30 |  |  |  | RENEWAL DESIGN | 10 | 3.15 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 04.09.2023 R888068 Ben Crozier Civil Assets Design was not completed in FY23 as intended. There is no update on status of TMR submission. By default this design flows to FY24 and impacts FY24 AP IFP programme (now sitting at 10x IFP's). PM has pushed renewal out to FY26. To be designed in FY23 for FY25 construction. detail/TMR approval to be sorted. F5083 form to be submitted for TMR approval with detail design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120587&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120587 | C60-ACP-NL-ARMUNA-27.1km | AP300018 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Newlands | ARMUNA | ABERDEEN | 0 | KM | NL01ML27 | 0.139 | NL01ML27 | 0.139 | KM |  |  |  |  | 27.1 | 27.1 | 2026-06-30 |  |  |  |  | 10 | 1.7 | 0.5 | 10 | 1 | 100 | 38 | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN. Scope of work may include: 1. Survey works 2. Installation of signage 3. Construction of adequate drainage features 4. Road manager's approval 5. Construction of turning lanes.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120588&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000120588 | C60-ACP-BW-GLADSTONE-546.571km | AP100686 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Blackwater | GLADSTONE | MT LARCOM | 0 | KM | BW01ML546 | 0.5709 | BW01ML546 | 0.5709 | KM |  |  |  |  | 546.571 | 546.571 | 2026-06-30 |  |  |  |  | 10 | 4.9 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of slip/turning lanes 2. Installation of signage 3. Construction of adequate drainage works 4. Achieve road managers approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120589&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120589 | C60-ACP-MA-STIRRAT-45.25km | AP400052 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Moura | STIRRAT | CLARKE | 0 | KM | MA01ML45 | 0.251 | MA01ML45 | 0.251 | KM |  |  |  |  | 45.25 | 45.25 | 2026-06-30 |  |  |  |  | 10 | 1.3 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN. Scope of renewal works may include: 1. Construction of turning lanes 2. Construction of drainage infrastructures as required 3. Installation of signage 4. Receive road manager's approval 4. Survey works
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120590&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120590 | C60-ACP-BW-WALLAROO-115.759km | AP100112 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Blackwater | WALLAROO | TRYPHINIA | 0 | KM | BW04ML115 | 0.761 | BW04ML115 | 0.761 | KM |  |  |  |  | 115.759 | 115.759 | 2026-06-30 |  |  |  |  | 10 | 3.35 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY25 ACCESS POINT DESIGN 1. Construction of slip and turning lanes 2. Construction of adequate drainage 3. Construction/installation of signage 4. Survey works 5. Achieve TMR/Council approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120591&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120591 | C60-ACP-GA-YUKAN-36.5km | AP200371 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML36 | 0.4799 | GA01ML36 | 0.4799 | KM |  |  |  |  | 36.5 | 36.5 | 2026-06-30 |  |  |  |  | 10 | 4 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN. Scope may include: 1. Construction of slip/turning lanes 2. Installation of signage 3. Construction of drainage works 4. Road managers's approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125415&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000125415 | C60-ACP-NL-BIRRALEE-95.621km | AP300091 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML95 | 0.6209 | NL01ML95 | 0.6209 | KM |  |  |  |  | 95.6 | 95.6 | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 10 | 1.4 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN- IFP Scope of work may include: 1. Construction of slip lanes. 2. Installation of signage. 3. Construction of adequate drainage 4. Achieve road Managers approval. 5. Relocation to a safer location.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114130&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | FUTURE SCOPE | COAL | 002000114130 | C60-ACP-BW-BURNGROVE-203.32km | AP100421 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater | BURNGROVE | TOLMIES | 0 | KM | BW03ML203 | 0.318 | BW03ML203 | 0.318 | KM |  |  |  |  | 203.32 | 203.32 | 2026-06-30 |  |  |  |  | 10 | 1.65 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Do not categorise this AP as "non-coal" - this AP is required to access the Gregory Branch 0.000-16.900km which is coal network. Moved to FY26 Design to meet the funding and design resource constraint. FY25 ACCESS POINT DESIGN as per TMR Road Access requirements: 1. Construction of slip and turning lanes 2. Installation of signage as per Aurizon standard 3. Drainage Improvements as per TMR Std.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114144&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000114144 | C60-ACP-GA-COPPABELLA-151.5km | AP200335 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | COPPABELLA | BROADLEA | 0 | KM | GA02ML151 | 0.276 | GA02ML151 | 0.276 | KM |  |  |  |  | 151.5 | 151.5 | 2026-06-30 |  |  |  |  | 10 | 4.6 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Moved to FY26 for funding and design resource constraint. FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of turning lanes 2. Construction of drainage works 3. Installation of signage 4. Survey works 5. Road Manager's approval
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125411&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000125411 | C60-ACP-MA-GRAHAM-37.613km | AP400042 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura | GRAHAM | STIRRAT | 0 | KM | MA01ML37 | 0.6129 | MA01ML37 | 0.6129 | KM |  |  |  |  | 37.613 | 37.613 | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 10 | 3.35 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 ACCESS POINT DESIGN- IFP ACCESS POINT DESIGN. Scope of work may include: 1. Construction of slip and turning lanes 2. Construction of adequate drainage 3. Achieve road managers approval 4. Installation of Aurizon signage. 5. Relocation to a safer location.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114138&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000114138 | C60-ACP-GA-HAY POINT-12.811km | AP200359 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01ML12 | 0.811 | GA01ML12 | 0.811 | KM |  |  |  |  | 12.9 | 12.9 | 2026-06-30 |  |  |  |  | 10 | 2.3 | 0.5 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | AP200359 was pushed out to FY26 to allow AP200121 Grasstree Beach in FY24. FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of slip and turning lanes 2. Construction of adequate drainage 3. Achieve road managers approval 4. Installation of Aurizon signage.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114142&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000114142 | C60-ACP-GA-MIDDLEMT-128.32km | AP200151 | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | MIDDLEMOUNT | BUNDOORA | 0 | KM | GA27SD128 | 0.328 | GA27SD128 | 0.328 | KM |  |  |  |  | 128.32 | 128.32 | 2026-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Moved to FY26 for funding and design resource constraint. FY25 ACCESS POINT DESIGN. Scope OF WORK MAY INCLUDE: 1. Construction of slip lanes. 2. Installation of signage. 3. Construction of adequate drainage 4. Achieve road Managers' approval. 5. Relocation to a safer location.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068910&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000068910 | Access Roads Reactive | BW | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 350000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068911&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000068911 | Access Roads Reactive | GA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 350000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068913&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000068913 | Access Roads Reactive | MA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068912&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000068912 | Access Roads Reactive | NL | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138554&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138554 | Non Coal Reactive Renewals - Ballast | BW | CIVIL | BALLAST UNDERCUTTING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138555&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138555 | Non Coal Reactive Renewals - Ballast | GA | CIVIL | BALLAST UNDERCUTTING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138556&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138556 | Non Coal Reactive Renewals - Ballast | MA | CIVIL | BALLAST UNDERCUTTING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138557&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138557 | Non Coal Reactive Renewals - Ballast | NL | CIVIL | BALLAST UNDERCUTTING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138070&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138070 | FY26 C01 Plant Depreciation - BW | BW | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -3123188 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138071&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138071 | FY26 C01 Plant Depreciation - GA | GA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -2325778 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138073&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138073 | FY26 C01 Plant Depreciation - MA | MA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -265803 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138072&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138072 | FY26 C01 Plant Depreciation - NL | NL | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | DEPRECIATION | 0 | LUMPSUM | -332254 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | FY24 C01 Plant Depreciation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115872&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000115872 | C01-BU-BW-Ambrose-570.420km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.549 | KM | 1581001 | Blackwater | AMBROSE | EPALA | 2.5489 | KM | BW01ML570 | 0.4199 | BW01ML572 | 0.9559 | KM |  |  |  |  | 570.42 | 572.956 | 2026-06-30 | UP |  |  |  | 4.4 | 4.1 | 2 | 3.9 | 1 | 17.2 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Condition Based Cut from 50m off Ambrose 12AB (no need to cut through LX640 next to turnout) to tie in 50m from BR101453 splay rails at high end cut out point. Deferred from FY25 to FY26 to make way for the Moura scope at the same time. NAM endorsed the change as Moura was deemed a higher priority. Scope: C01 - 570.420km to 572.956km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115873&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000115873 | C01-BU-BW-Ambrose-573.150km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.596 | KM | 1618406 | Blackwater | AMBROSE | EPALA | 2.596 | KM | BW01ML573 | 0.1499 | BW01ML575 | 0.6999 | KM |  |  |  |  | 573.15 | 575.7 | 2026-06-30 | UP |  |  |  | 3.7 | 4.1 | 2 | 3.9 | 1 | 14.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Condition Based Cut from 50m from BR101453 spaly rails at low km cut in and tie in with Epala 12C/D. Cut through AT site at the 574.030km. Deferred from FY26 to FY25 at Phase 2 to make way for the Moura scope at the same time. NAM endorsed the change as Moura was deemed a higher priority. Scope: C01 - 573.150km to 575.700km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138792&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138792 | C01-BU-BW-Archer-619.300km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.723 | KM | 2321004 | Blackwater | ARCHER | MIDGEE | 3.7229 | KM | BW01ML619 | 0.2999 | BW01ML623 | 0.0309 | KM |  |  |  |  | 619.3 | 623.031 | 2026-06-30 | UP |  |  |  | 3.6 | 4.1 | 2 | 3.9 | 1 | 14 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 619.3km to 623.031km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138790&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138790 | C01-BU-BW-Archer-623.187km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.215 | KM | 1380882 | Blackwater | ARCHER | MIDGEE | 2.2149 | KM | BW01ML623 | 0.1869 | BW01ML625 | 0.4 | KM |  |  |  |  | 623.187 | 625.4 | 2026-06-30 | UP |  |  |  | 3.9 | 4.1 | 2 | 3.9 | 1 | 15.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 623.187km to 625.4km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140693&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140693 | C01-BU-BW-BAJOOL-611.293km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.663 | KM | 1036753 | Blackwater | BAJOOL | ARCHER | 1.663 | KM | BW01ML611 | 0.2929 | BW01ML612 | 0.9599 | KM |  |  |  |  | 611.293 | 612.96 | 2026-06-30 | UP |  |  |  | 3 | 4.9 |  |  |  | 3.9 | 4748 | 2024-03-28 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | NWSC |  | 20250330 | FY22 Residual Scope Replan Comments: Moderately fouled. Geometry okay with the exception of a near D7 top at 611.420. Last time it rained preventing access to site / processing of material Email received from Reagan Case 24/08/2022 advising this scope is able to be moved to FY25. Mod ID Updated accordingly There is a single D7 defect at the 611.420km that should be on the districts radar to remove FY26 scoping - scope updated from starting 609.6 to 611.280 as it appears part of the scope was completed in FY22, not previously ca ptured. Scope: C01 - 609.600km to 612.960km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138812&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138812 | C01-BU-GA-Black Mountain-41.000km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.603 | KM | 999347 | Goonyella | BLACK MOUNTAIN | HATFIELD | 1.6029 | KM | GA02ML41 | 0 | GA02ML42 | 0.5999 | KM |  |  |  |  | 41 | 42.6 | 2026-06-30 | UP |  |  |  | 3.6 | 5 | 2 | 4.2 | 1 | 15.1 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 41km to 42.6km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052359&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000052359 | C01-BU-GA-Black Mountain-41.065km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.536 | KM | 1581001 | Goonyella | BLACK MOUNTAIN | HATFIELD | 2.536 | KM | GA01ML41 | 0.065 | GA01ML43 | 0.5999 | KM |  |  |  |  | 41.065 | 43.6 | 2026-06-30 | UP |  |  |  | 3.5 | 4.6 |  |  |  | 17.5 | 4748 | 2024-03-28 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | FY22 Residual Scope Scope: C01 - 41.065km to 43.600km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094863&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094863 | C01-BU-GA-Black Mountain-45.850km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.581 | KM | 985632 | Goonyella | BLACK MOUNTAIN | HATFIELD | 1.5809 | KM | GA01ML45 | 0.8499 | GA01ML47 | 0.4299 | KM |  |  |  |  | 45.85 | 47.43 | 2026-06-30 | DN |  |  |  | 3.3 | 5 | 2 | 4 | 1 | 13.7 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Moderately fouled with some high to severe patches Moderately rough track geometry Scope: C01 - 45.850km to 47.430km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138800&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138800 | C01-BU-BW-Bluff-178.230km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.889 | KM | 1801069 | Blackwater | BLUFF | BOONAL BALLOON POINTS | 2.8889 | KM | BW03ML178 | 0.23 | BW03ML181 | 0.14 | KM |  |  |  |  | 178.23 | 181.14 | 2026-06-30 | DN |  |  |  | 4.8 | 3.4 | 2 | 3.6 | 1 | 17.1 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 178.23km to 181.14km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138801&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138801 | C01-BU-BW-Boonal Balloon-187.780km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.705 | KM | 1062936 | Blackwater | BOONAL BALLOON POINTS | BLACKWATER | 1.705 | KM | BW03ML187 | 0.78 | BW03ML189 | 0.4899 | KM |  |  |  |  | 187.78 | 189.49 | 2026-06-30 | DN |  |  |  | 3.4 | 3.2 | 2 | 3.6 | 1 | 12.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 187.78km to 189.49km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138794&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138794 | C01-BU-BW-Byelle-537.000km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.63 | KM | 392757 | Blackwater | BYELLEE | STOWE | 0.63 | KM | BW02ML537 | 0 | BW02ML537 | 0.63 | KM |  |  |  |  | 537 | 537.63 | 2026-06-30 | DN |  |  |  | 4.7 | 1.3 | 2 | 2.6 | 1 | 12.1 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 537km to 537.63km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094874&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094874 | C01-BU-GA-Coppabella-145.630km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.167 | KM | 1350958 | Goonyella | COPPABELLA | BROADLEA | 2.1669 | KM | GA01ML145 | 0.63 | GA01ML147 | 0.8 | KM |  |  |  |  | 145.63 | 147.8 | 2026-06-30 | DN |  |  |  | 3.8 | 4.5 | 2 | 4 | 1 | 15.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Highly fouled ballast in general moderately rough track geometry Scope: C01 - 145.630km to 147.800km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094873&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094873 | C01-BU-GA-Coppabella-142.950km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.648 | KM | 1027401 | Goonyella | COPPABELLA | COPPABELLA | 1.6479 | KM | GA01ML142 | 0.9499 | GA01ML145 | -0.402 | KM |  |  |  |  | 142.95 | 144.6 | 2026-06-30 | DN |  |  |  | 3.8 | 4.6 | 2 | 4 | 1 | 15.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Sections of severely fouled ballast, other sections are moderately fouled moderately rough track geometry Scope: C01 - 142.950km to 144.600km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094894&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094894 | C01-BU-GA-Coppabella-3.900km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.399 | KM | 1495592 | Goonyella | COPPABELLA | INGSDON | 2.399 | KM | GA03ML3 | 0.9 | GA03ML6 | 0.2999 | KM |  |  |  |  | 3.9 | 6.3 | 2026-06-30 | MAIN |  |  |  | 3.3 | 2.4 | 2 | 3 | 1 | 10.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Highly fouled ballast on average, some severe fouling and some moderate Generally good track geometry Scope: C01 - 3.900km to 6.300km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138817&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138817 | C01-BU-GA-Coppabella-147.900km UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.102 | KM | 1310435 | Goonyella | COPPABELLA FORK (WEST JCT) | BROADLEA | 2.1019 | KM | GA02ML147 | 0.9 | GA02ML150 | 0 | KM |  |  |  |  | 147.9 | 150 | 2026-06-30 | DN |  |  |  | 3.1 | 2.5 | 2 | 3.3 | 1 | 10.2 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 147.9km to 150km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138806&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138806 | C01-BU-BW-Crew-17.230km-MN | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.524 | KM | 1573520 | Blackwater | CREW | MACKENZIE | 2.524 | KM | BW08ML17 | 0.23 | BW08ML19 | 0.75 | KM |  |  |  |  | 17.23 | 19.75 | 2026-06-30 | MAIN |  |  |  | 3.4 | 1.2 | 2 | 2.5 | 1 | 8.5 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 17.23km to 19.75km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138811&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138811 | C01-BU-GA-Daly Jct-11.450km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.009 | KM | 1252457 | Goonyella | DALRYMPLE XOVER POINTS | PRAGUELANDS | 2.0089 | KM | GA02ML12 | 0.2999 | GA02ML14 | 0.2999 | KM |  |  |  |  | 12.3 | 14.3 | 2026-06-30 | UP |  |  |  | 4.3 | 4.6 | 2 | 4.1 | 1 | 17.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 12.3km to 14.3km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094969&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094969 | C01-BU-GA-Daly Jct-4.050km-DN | GA-03BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.316 | KM | 1443848 | Goonyella | DALY JCT | DALY BAY | 2.3159 | KM | GA03BA4 | 0.05 | GA03BA7 | 0.75 | KM |  |  |  |  | 4.05 | 7.75 | 2026-06-30 | ARRIVAL |  |  |  | 4 | 2.6 | 2 | 3.3 | 1 | 13.2 | 258 | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | "Highly fouled ballast with severe patches Several at or near D7 twist" Outcome from the NLT session on 17.01.23 was to remove this from the FY24 Final Submission due to risk of delivery. Moved to FY25. Scope: C01 - 4.05km to 7.750km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094641&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094641 | C01-BU-GA-Daly Jct-8.350km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.129 | KM | 703845 | Goonyella | DALY JCT | PRAGUELANDS | 1.129 | KM | GA01ML8 | 0.3499 | GA01ML9 | 0.4699 | KM |  |  |  |  | 8.35 | 9.47 | 2026-06-30 | DN |  |  |  | 3.8 | 4.6 | 2 | 4 | 1 | 15.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | HIGH | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | "Highly to severely fouled ballast Near D7 top the whole section according to track geometry" Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 12/07/2022: Site Inspection Document Uploaded Scope: C01 - 8.350km to 9.470km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138803&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138803 | C01-BU-BW-Gracemere-9.230km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.887 | KM | 1176399 | Blackwater | GRACEMERE | KABRA | 1.887 | KM | BW04ML9 | 0.23 | BW04ML11 | 0.1 | KM |  |  |  |  | 9.23 | 11.1 | 2026-06-30 | UP |  |  |  | 3.5 | 3.4 | 2 | 3.6 | 1 | 12.6 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 9.23km to 11.1km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138797&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138797 | C01-BU-BW-Gracemere-13.750km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.548 | KM | 965059 | Blackwater | GRACEMERE | KABRA | 1.548 | KM | BW03ML13 | 0.75 | BW03ML15 | 0.2899 | KM |  |  |  |  | 13.75 | 15.29 | 2026-06-30 | DN |  |  |  | 2.9 | 3.4 | 2 | 3.6 | 1 | 10.5 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 13.75km to 15.29km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104043&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000104043 | C01-BU-BW-Grantleigh-69.104km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.606 | KM | 1001217 | Blackwater | GRANTLEIGH | TUNNEL | 1.606 | KM | BW03ML69 | 0.1039 | BW03ML70 | 0.6999 | KM |  |  |  |  | 69.104 | 70.7 | 2026-06-30 | DN |  |  |  | 3 | 3.75 |  |  |  | 11.25 | 4748 | 2024-03-28 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | FY22 Residual Scope Replan Comments: Geometry okay, some moderately rough sections. Mostly 30-40% with the last few hundred metres 40-60%. Email received from Reagan Case 24/08/2022 advising this scope is able to be moved to FY25. Mod ID Updated accordingly Refer to notification 2000052439, this notification has been created to split the residual FY22 scope as a work order and actuals are attached to the original notification and it is therefore unable to be carried across FY26 scoping - notification extended to tie into turnout back at the 68.280km. Scope: C01 - 69.104km to 70.700km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138798&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138798 | C01-BU-BW-Grantleigh-70.850km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.678 | KM | 1669527 | Blackwater | GRANTLEIGH | TUNNEL | 2.6779 | KM | BW03ML70 | 0.8499 | BW03ML73 | 0.55 | KM |  |  |  |  | 70.85 | 73.55 | 2026-06-30 | DN |  |  |  | 3.6 | 3.4 | 2 | 3.6 | 1 | 12.9 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 70.85km to 73.55km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138807&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138807 | C01-BU-GA-Hatfield-52.700km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.379 | KM | 1483124 | Goonyella | HATFIELD | BOLINGBROKE | 2.379 | KM | GA01ML52 | 0.6999 | GA01ML55 | 0.1 | KM |  |  |  |  | 52.7 | 55.1 | 2026-06-30 | DN |  |  |  | 4.1 | 5 | 2 | 4.2 | 1 | 17.2 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 52.7km to 55.1km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138808&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138808 | C01-BU-GA-Hatfield-56.925km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.003 | KM | 625293 | Goonyella | HATFIELD | BOLINGBROKE | 1.0029 | KM | GA01ML56 | 0.925 | GA01ML57 | 0.92 | KM |  |  |  |  | 56.925 | 57.92 | 2026-06-30 | DN |  |  |  | 3.8 | 5 | 2 | 4.2 | 1 | 15.8 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 56.925km to 57.92km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140694&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000140694 | C01-GA-Hay Point-0.050km-BALLOON | GA-02BD | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.999 | KM | 1869646 | Goonyella | HAY POINT | DALRYMPLE XOVER POINTS | 2.999 | KM | GA02BD0 | 0.05 | GA02BD3 | 0.033 | KM |  |  |  |  | 0.05 | 3.033 | 2026-06-30 | BLOOP1 |  |  |  | 4.4 | 2.3 | 2 | 3.2 | 1 | 14.1 | 5440 | 2024-03-28 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | HIGH | HIGH | Outstanding notification | NWSC | FY23 IN | 20250330 | 22.03.2021 10:43:10 AUSQLD Tracy Holmes (R870040) Fouled, top and twist at D7 at various points 31.03.2021 18:48:50 AUSQLD Tracy Holmes (R870040) to overall program low risk 12.04.2021 16:23:09 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor." 22.03.2021 10:43:10 AUSQLD Tracy Holmes (R870040) Fouled, top and twist at D7 at various points 31.03.2021 18:48:50 AUSQLD Tracy Holmes (R870040) to overall program low risk 12.04.2021 16:23:09 AUSQLD Jeremy Stevenson (R867415) Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per site cost? To ind notifications med risk but to ov erall program low risk
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138793&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138793 | C01-BU-BW-Midgee-625.400km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.178 | KM | 3228085 | Blackwater | MIDGEE | ROCKLANDS | 5.1779 | KM | BW01ML625 | 0.4 | BW01ML630 | 0.5699 | KM |  |  |  |  | 625.4 | 630.57 | 2026-06-30 | UP |  |  |  | 4.3 | 4.5 | 2 | 4.1 | 1 | 17.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 625.4km to 630.57km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138719&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138719 | C01-BU-BW-Mt Larcom-566.910km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.79 | KM | 1115927 | Blackwater | MT LARCOM | AMBROSE | 1.78 | KM | BW01ML566 | 0.91 | BW01ML568 | 0.8 | KM |  |  |  |  | 566.91 | 568.8 | 2026-06-30 | UP |  |  |  | 3.9 | 4.1 | 2 | 3.9 | 1 | 15.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | "Scope: C01 - 566.91km to 568.8km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094966&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094966 | C01-BU-BW-Mt Miller-540.480km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.671 | KM | 1041740 | Blackwater | MT MILLER | YARWUN | 1.671 | KM | BW02ML540 | 0.4799 | BW02ML542 | 0.1499 | KM |  |  |  |  | 540.48 | 542.15 | 2026-06-30 | DN |  |  |  | 3.5 | 3.8 | 2 | 4 | 1 | 13.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | "Highly fouled around 541km, otherwise moderately fouled ballast D7 top and moderately rough near 541km otherwise okay" Scope: C01 - 540.480km to 542.150km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138799&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138799 | C01-BU-BW-Parnabal-156.474km-DN | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.511 | KM | 3435685 | Blackwater | PARNABAL | WALTON | 5.511 | KM | BW03ML156 | 0.4739 | BW03ML162 | 0.2899 | KM |  |  |  |  | 156.474 | 162.29 | 2026-06-30 | DN |  |  |  | 4.3 | 3.4 | 2 | 3.6 | 1 | 15.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 156.474km to 162.29km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094897&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094897 | C01-BU-GA-Peak Downs-50.200km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.5 | KM | 1558558 | Goonyella | PEAK DNS | HARROW | 2.5 | KM | GA03ML50 | 0.2 | GA03ML52 | 0.6999 | KM |  |  |  |  | 50.2 | 52.7 | 2026-06-30 | MAIN |  |  |  | 3.5 | 1.8 | 2 | 3 | 1 | 10.2 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Moderately fouled ballast generally with some high and severe patches Generally good track geometry Scope: C01 - 50.200km to 52.700km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138795&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138795 | C01-BU-BW-Raglan-586.700km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.031 | KM | 1266172 | Blackwater | RAGLAN | MARMOR | 2.031 | KM | BW02ML586 | 0.6999 | BW02ML588 | 0.7239 | KM |  |  |  |  | 586.7 | 588.724 | 2026-06-30 | DN |  |  |  | 2.9 | 4.9 | 2 | 4.2 | 1 | 12.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 586.7km to 588.724km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115874&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000115874 | C01-BU-BW-Raglan-586.830km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.909 | KM | 1190115 | Blackwater | RAGLAN | MARMOR | 1.909 | KM | BW01ML586 | 0.8299 | BW01ML588 | 0.7279 | KM |  |  |  |  | 586.83 | 588.728 | 2026-06-30 | UP |  |  |  | 3.3 | 4.9 | 2 | 4.2 | 1 | 14 | 258 | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Condition Based Cut from Horrigan Ck Bridge and tie in with FY23 Undercut. Cut through crossing 1717 at 588.770 pending CE and diversion considerations. Scope: C01 - 586.830km to 588.728km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138796&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138796 | C01-BU-BW-Raglan-588.824km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.692 | KM | 3548524 | Blackwater | RAGLAN | MARMOR | 5.692 | KM | BW02ML588 | 0.8239 | BW02ML594 | 0.5 | KM |  |  |  |  | 588.824 | 594.5 | 2026-06-30 | DN |  |  |  | 2.9 | 4.9 | 2 | 4.2 | 1 | 12.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 588.824km to 594.5km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138791&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138791 | C01-BU-BW-Raglan-588.828km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.679 | KM | 1670150 | Blackwater | RAGLAN | MARMOR | 2.6789 | KM | BW01ML588 | 0.8279 | BW01ML591 | 0.5 | KM |  |  |  |  | 588.828 | 591.5 | 2026-06-30 | UP |  |  |  | 2.9 | 4.9 | 2 | 4.2 | 1 | 12.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 588.828km to 591.5km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138802&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138802 | C01-BU-BW-Rocklands-4.520km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.339 | KM | 2081610 | Blackwater | ROCKLANDS | GRACEMERE | 3.3389 | KM | BW04ML4 | 0.52 | BW04ML8 | 0.9 | KM |  |  |  |  | 4.52 | 8.9 | 2026-06-30 | UP |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14.1 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 4.52km to 8.9km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138818&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138818 | C01-BU-GA-Saraji Jct-70.800km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.628 | KM | 2261779 | Goonyella | SARAJI JCT | LAKE VERMONT FORK (NORTH JCT) | 3.628 | KM | GA03ML73 | 0.6199 | GA03ML77 | 0.25 | KM |  |  |  |  | 73.62 | 77.25 | 2026-06-30 | MAIN |  |  |  | 4.3 | 1.6 | 2 | 2.8 | 1 | 12.1 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 70.8km to 77.25km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor. M Durnsford: 70.800km to 73.620km completed on 05/03/2024. Start KM on notification updated to reflect this.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138816&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138816 | C01-BU-GA-South Walker Jct-127.500km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.108 | KM | 3184445 | Goonyella | SOUTH WALKER JCT | TOOTOOLAH | 5.1079 | KM | GA02ML127 | 0.5 | GA02ML132 | 0.5999 | KM |  |  |  |  | 127.5 | 132.6 | 2026-06-30 | UP |  |  |  | 4.3 | 4.7 | 2 | 4.1 | 1 | 17.4 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 127.5km to 132.6km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138813&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138813 | C01-BU-GA-Waitara-118.700km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.247 | KM | 777409 | Goonyella | WAITARA | SOUTH WALKER JCT | 1.247 | KM | GA02ML118 | 0.6999 | GA02ML119 | 0.9499 | KM |  |  |  |  | 118.7 | 119.95 | 2026-06-30 | UP |  |  |  | 4.9 | 4.4 | 2 | 4 | 1 | 19.7 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 118.7km to 119.95km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138814&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138814 | C01-BU-GA-Waitara-120.730km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.52 | KM | 947603 | Goonyella | WAITARA | SOUTH WALKER JCT | 1.52 | KM | GA02ML120 | 0.7299 | GA02ML122 | 0.25 | KM |  |  |  |  | 120.73 | 122.25 | 2026-06-30 | UP |  |  |  | 3.6 | 4.4 | 2 | 4 | 1 | 14.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 120.73km to 122.25km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138815&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138815 | C01-BU-GA-Waitara-122.950km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.763 | KM | 1099095 | Goonyella | WAITARA | SOUTH WALKER JCT | 1.7629 | KM | GA02ML122 | 0.9499 | GA02ML124 | 0.6999 | KM |  |  |  |  | 122.95 | 124.7 | 2026-06-30 | UP |  |  |  | 3.8 | 4.4 | 2 | 4 | 1 | 15 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 122.95km to 124.7km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138809&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138809 | C01-BU-GA-Waitara-124.650km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.993 | KM | 619059 | Goonyella | WAITARA | SOUTH WALKER JCT | 0.9929 | KM | GA01ML124 | 0.65 | GA01ML125 | 0.65 | KM |  |  |  |  | 124.65 | 125.65 | 2026-06-30 | DN |  |  |  | 3.6 | 4.4 | 2 | 4 | 1 | 14.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 124.65km to 125.65km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138804&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138804 | C01-BU-BW-Walton-163.830km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 5.153 | KM | 3212499 | Blackwater | WALTON | BLUFF | 5.1529 | KM | BW04ML163 | 0.8299 | BW04ML168 | 0.914 | KM |  |  |  |  | 163.83 | 168.914 | 2026-06-30 | UP |  |  |  | 4.4 | 3.4 | 2 | 3.6 | 1 | 15.9 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 163.83km to 168.914km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138810&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138810 | C01-BU-GA-Wotonga Jct-176.900km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.497 | KM | 933264 | Goonyella | WOTONGA | MORANBAH NORTH | 1.497 | KM | GA01ML176 | 0.9 | GA01ML178 | 0.4 | KM |  |  |  |  | 176.9 | 178.4 | 2026-06-30 | DN |  |  |  | 4.3 | 1.8 | 2 | 2.9 | 1 | 12.3 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C01 - 176.9km to 178.4km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094967&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094967 | C01-BU-BW-Yarwun-550.100km-DN | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.604 | KM | 2246817 | Blackwater | YARWUN | ALDOGA | 3.604 | KM | BW02ML550 | 0.1 | BW02ML553 | 0.7369 | KM |  |  |  |  | 550.1 | 553.737 | 2026-06-30 | DN |  |  |  | 3.5 | 4.1 | 2 | 4 | 1 | 13.7 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Moderate fouled ballast with high to severe patches Moderately rough track geometry Scope: C01 - 550.100km to 553.737km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074497&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000074497 | C01-BU-GA-Yukan-30.100km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.095 | KM | 1929494 | Goonyella | YUKAN | BLACK MOUNTAIN | 3.095 | KM | GA01ML30 | 0.1 | GA01ML33 | 0.2 | KM |  |  |  |  | 30.1 | 33.2 | 2026-06-30 | DN |  |  |  | 4 | 4.4 |  |  |  | 17.6 |  | 2024-03-28 | 2021-10-05 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | MEDIUM | HIGH | HIGH | Notification in process | SCPR | FY23 IN | 20260630 | * 22.03.2021 10:36:45 AUSQLD Tracy Holmes (R870040) * All severely fouled, top nearing D7 limits. Fouling improves closer to 31.6, ties in up to FY22 scope, geometry not too bad, could push to FY24 * 12.04.2021 16:22:57 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Was in FY23 but not completed. Moved to FY26 Cess drainage requires reinstating at the same time - budget and allow time for this! Scope: C01 - 30.1km to 33.200km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094884&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094884 | C01-BU-GA-Yukan-30.200km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.797 | KM | 496868 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.797 | KM | GA02ML30 | 0.2 | GA02ML31 | 0 | KM |  |  |  |  | 30.2 | 31 | 2026-06-30 | UP |  |  |  | 3.5 | 4.4 | 2 | 4 | 1 | 14 | 185 | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM | MEDIUM | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | Moderate to highly fouled ballast Moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Scope: C01 - 30.200km to 31.000km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094861&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094861 | C01-BU-GA-Black Mountain-39.035km-DN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 1.77 | KM | 1103459 | Goonyella | YUKAN | BLACK MOUNTAIN | 1.77 | KM | GA01ML39 | 0.035 | GA01ML40 | 0.8 | KM |  |  |  |  | 39.035 | 40.8 | 2026-06-30 | DN |  |  |  | 3.3 | 4.4 | 2 | 4 | 1 | 13 |  | 2024-03-28 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Moderately fouled ballast with some high to severe patches moderately rough track geometry Scope: C01 - 39.035km to 40.800km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138819&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138819 | C14 BW Reactive Works | BW | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.7 | KM | 1917000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | "Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138820&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138820 | C14 GA Reactive Works | GA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 2.7 | KM | 2160000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | "Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138821&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138821 | C14 MA Reactive Works | MA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | REACTIVE WORKS | 0.3 | KM | 225000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 2 | 4.2 | 1 | 21 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | "Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052466&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000052466 | C14-BU-BW-Epala-581.921km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.386 | KM | 308800 | Blackwater | EPALA | RAGLAN | 0.386 | KM | BW01ML581 | 0.921 | BW01ML582 | 0.2999 | KM |  |  |  |  | 581.921 | 582.3 | 2026-06-30 | UP |  |  |  | 3 | 1.3 |  |  |  | 3.9 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Appears to be residual FY22 scope moved to FY25, however partially picked up in an FY24 scope, so extents required revising. Revised kms to align with FY24 scopes either side. 21.02.23 R.Case. Scope: C01 - 581.400km to 582.300km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor." M Durnsford: Updated notification start km to 581.921km. 581.400km to 581.921km was completed on 17 – 19 February 2024
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000141821&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000141821 | C14-BU-BW-Walton-169.076km UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.13 | KM | 104000 | Blackwater | WALTON | BLUFF | 0.13 | KM | BW04ML169 | 0.0759 | BW04ML169 | 0.2059 | KM |  |  |  |  | 169.076 | 169.206 | 2026-06-30 | UP |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14.1 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: C14 - 169.076km to 169.206km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138805&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138805 | C14-BU-BW-Walton-169.835km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.035 | KM | 28000 | Blackwater | WALTON | BLUFF | 0.034 | KM | BW04ML169 | 0.8359 | BW04ML169 | 0.8699 | KM |  |  |  |  | 169.835 | 169.87 | 2026-06-30 | UP |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14.1 |  | 2024-03-28 |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: C14 - 169.835km to 169.87km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. •Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000141049&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000141049 | Blackwater Monumenting | BW | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 570000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000141060&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000141060 | Goonyella Monumenting | GA | CIVIL | BALLAST UNDERCUTTING | MONUMENTING | RENEWAL | 1 | SITE | 430000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2023-10-13 |  | Monumenting | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080280&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000080280 | C13 TURNOUT U/C BW REACTIVE | BW | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 4 | TURNOUT | 1066000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | BW | [10 empty] | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 0.6 km allowed for Fix on Fail Adjacent at $710,000 per km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080281&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000080281 | C13 Turnout U/C GA Reactive | GA | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 2 | TURNOUT | 600000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | GA | [10 empty] | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 0.3 km allowed for Fix on Fail Adjacent at $800,000 per km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080286&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000080286 | C13 TURNOUT U/C MA REACTIVE | MA | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 2 | TURNOUT | 373000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | MA | [10 empty] | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 0.3 km allowed for Fix on Fail Adjacent at $310,000 per km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080283&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000080283 | C13 TURNOUT U/C NL REACTIVE | NL | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | REACTIVE WORKS | 2 | TURNOUT | 704000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | NL | [10 empty] | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 0.3 km allowed for Fix on Fail Adjacent at $1,080,000 per km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138240&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138240 | C13 Turnout B/U Callemondah 212A Pts | TO001158 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 373560 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.024 | KM | BW17YR0 | 0.326 | BW17YR0 | 0.3499 | KM |  |  |  |  | 0.326 | 0.35 | 2026-06-30 | BW-17YR |  |  |  | 4.4 | 0.9 | 2 | 2.3 | 1 | 10.1 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO001158 Lead: 0.200km to TOS Trailing: back of TO to 0.510km Divergent (BW-05XR): 0.35km to 0.4km TO to be packaged with TO001155 (2000104181), TO001173 (2000138241) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138241&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138241 | C13 Turnout B/U Callemondah 212B Pts | TO001173 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 277000 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.032 | KM | BW20YR0 | 0.402 | BW20YR0 | 0.3699 | KM |  |  |  |  | 0.37 | 0.402 | 2026-06-30 | BW-20YR |  |  |  | 4.4 | 2.6 | 2 | 3.3 | 1 | 14.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO001173 Lead: 0.32km to TOS Trailing: back of TO to 0.502km Divergent (BW-05XR): 0.402km to 0.452km TO to be packaged with TO001158 (2000138240),TO001155 (2000104181) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104181&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104181 | C13 Turnout B/U Callemondah 205A Pts | TO001155 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 172630 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.028 | KM | BW17YR0 | 0.4829 | BW17YR0 | 0.511 | KM |  |  |  |  | 0.483 | 0.511 | 2026-06-30 | BW-17YR |  |  |  | 4.6 | 0.9 | 2 | 2.3 | 1 | 10.6 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO001155 Lead: 0.43km to TOS Trailing: back of TO to 0.6km TO to be packaged with TO001158 (2000138240), TO001173 (2000138241) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104199&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104199 | C13 Turnout B/U Clarke 12A Pts | TO000939 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 283750 | Moura | CLARKE | CLARKE | 0.0309 | KM | MA01ML61 | 0.9819 | MA01ML62 | 0.01 | KM |  |  |  |  | 61.982 | 62.01 | 2026-06-30 | MA-01ML |  |  |  | 4 | 1.3 | 2 | 2.6 | 1 | 10.4 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000939 Lead: 61.947km to TOS Trailing: back of TO to 62.09km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115716&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115716 | C13 Turnout B/U Coppabella 88A | TO000381 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 263300 | Goonyella | COPPABELLA | COPPABELLA | 0.035 | KM | GA42YR145 | 0.1789 | GA42YR145 | 0.1439 | KM |  |  |  |  | 145.144 | 145.179 | 2026-06-30 | GA-42YR |  |  |  | 4.1 | 2.2 | 2 | 3.1 | 1 | 12.7 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000381 Lead: 145.079km to TOS Trailing: back of TO to 145.235km Divergent (GA-41YR): 145.110km to 145.160km TO to be packaged with TO000370 (2000115715) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115715&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115715 | C13 Turnout B/U Coppabella 90A/B | TO000370 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 192500 | Goonyella | COPPABELLA | COPPABELLA | 0.0299 | KM | GA42YR145 | 0.315 | GA42YR145 | 0.2849 | KM |  |  |  |  | 145.285 | 145.315 | 2026-06-30 | GA-42YR |  |  |  | 3.7 | 2.2 | 2 | 3.1 | 1 | 11.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000370 Lead: 145.235km to TOS Trailing: back of TO to 145.335km TO to be packaged with TO000381 (2000115716) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080202&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080202 | C13 Turnout U/C Coppabella 10A/B | TO000229 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 257200 | Goonyella | COPPABELLA | COPPABELLA | 0.028 | KM | GA01ML145 | 0.3699 | GA01ML145 | 0.342 | KM |  |  |  |  | 145.342 | 145.37 | 2026-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 14.4 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000229 Lead: 145.292km to TOS Trailing: back of TO to 145.380km Divergent (GA-40YR): 145.290km to 145.340km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080235&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080235 | C13 Turnout B/U Daly Bay 49A/B | TO000103 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 266500 | Goonyella | DALY BAY | DALY BAY | 0.05 | KM | GA02BA8 | 0.33 | GA02BA8 | 0.28 | KM |  |  |  |  | 8.28 | 8.33 | 2026-06-30 | GA-02BA |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 11.6 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Near D7 top (Jan 21) Scope: C13 - TO000103 Lead: 8.2km to TOS Trailing: back of TO to 8.430km Divergent (GA-01BA): 8.260km to 8.310km TO to be packaged with TO000553 (2000104219) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104219&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104219 | C13 Turnout U/C Daly Bay 12C/D | TO000553 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 343200 | Goonyella | DALY BAY ARRIVAL RD 3 | DALY BAY ARRIVAL RD 3 | 0.0709 | KM | GA03BA8 | 0.2169 | GA03BA8 | 0.1459 | KM |  |  |  |  | 8.146 | 8.217 | 2026-06-30 | GA-03BA |  |  |  | 4.5 | 4.6 | 2 | 4.1 | 1 | 18.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000553 Lead: 8.1km to TOS Trailing: back of TO to 8.35km Divergent (GA-07XR): 8.120km to 8.170km TO to be packaged with TO000103 (2000080235) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104206&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104206 | C13 Turnout U/C Goonyella ER1.2A | TO000403 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 290000 | Goonyella | GOONYELLA BALLOON | GOONYELLA BALLOON | 0.034 | KM | GA13ML198 | 0.7299 | GA13ML198 | 0.6959 | KM |  |  |  |  | 198.696 | 198.78 | 2026-06-30 | GA-13ML |  |  |  | 3.9 | 0.9 | 2 | 2.3 | 1 | 9 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000403 Lead: 198.646km to TOS Trailing: back of TO to 198.780km Divergent (GA-06SD): 198.650km to 198.700km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074625&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000074625 | C13 Turnout U/C Hatfield 8A/B | TO000449 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 466000 | Goonyella | HATFIELD | HATFIELD | 0.049 | KM | GA01ML47 | 0.447 | GA01ML47 | 0.4959 | KM |  |  |  |  | 47.447 | 47.496 | 2026-06-30 | GA-01ML |  |  |  | 4 | 5 | 2 | 4.2 | 1 | 16.8 | 5677 | 2024-03-28 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | * 22.03.2021 11:08:38 AUSQLD Tracy Holmes (R870040) * Very near D7 top and twist, (Jan 21). Needs to Tie in with ML UC * 12.04.2021 16:23:37 AUSQLD Jeremy Stevenson (R867415) * Sites are subject to change due to condition of T/ O sites changing * * Trailing: back of TO to 584.881km Divergent (BW-01SD): 584.795km to 584.845km " 22.03.2021 11:08:38 AUSQLD Tracy Holmes (R870040) Very near D7 top and twist, (Jan 21). Needs to Tie in with ML UC 12.04.2021 16:23:37 AUSQLD Jeremy Stevenson (R867415) Sites are subject to change due to condition of T/ O sites changing Divergent: back of TO to xxx.xxxkm " 22.03.2021 11:08:38 AUSQLD Tracy Holmes (R870040) Very near D7 top and twist, (Jan 21). Needs to Tie in with ML UC 12.04.2021 16:23:37 AUSQLD Jeremy Stevenson (R867415) Sites are subject to change due to condition of T/ O sites changing Scope: C13 - TO000449 Lead: 47.397km to TOS Trailing: back of TO to 47.566km Divergent (GA-01PL): 47.490km to 47.740km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080224&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080224 | C13 Turnout U/C Hatfield ER1.2A | TO000273 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 277200 | Goonyella | HATFIELD | HATFIELD | 0.0369 | KM | GA01ML49 | 0.334 | GA01ML49 | 0.3709 | KM |  |  |  |  | 49.334 | 49.371 | 2026-06-30 | GA-01ML |  |  |  | 3.5 | 5 | 2 | 4.2 | 1 | 14.7 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000273 Lead: 49.280km to TOS Trailing: back of TO to 49.401km Divergent (GA-25YR): 0.02km to 0.07km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104255&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104255 | C13 Turnout U/C Jilalan 69A | TO000991 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 210000 | Goonyella | JILALAN YARD | JILALAN YARD | 0 | KM | GA22CT20 | 0.762 | GA22CT20 | 0.762 | KM |  |  |  |  | 20.762 | 20.815 | 2026-06-30 | GA-22CT |  |  |  | 3.4 | 4.8 | 2 | 4.2 | 1 | 14.3 | 257 | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Scope: C13 - TO000991 Trailing: back of TO to 20.865km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104256&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104256 | C13 Turnout U/C Jilalan 84A | TO000994 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 210000 | Goonyella | JILALAN YARD | JILALAN YARD | 0 | KM | GA25CT21 | 0.005 | GA25CT21 | 0.005 | KM |  |  |  |  | 21.005 | 21.058 | 2026-06-30 | GA-25CT |  |  |  | 3.4 | 4.8 | 2 | 4.2 | 1 | 14.3 | 257 | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Scope: C13 - TO000994 Trailing: back of TO to 21.108km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104226&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104226 | C13 Turnout B/U Kabra 11A/B | TO000676 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 211970 | Blackwater | KABRA | KABRA | 0.0729 | KM | BW03ML13 | 0.6199 | BW03ML13 | 0.6929 | KM |  |  |  |  | 13.62 | 13.693 | 2026-06-30 | BW03ML |  |  |  | 4.2 | 3.4 | 2 | 3.7 | 1 | 15.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000676 Trailing: back of TO to 13.750km Divergent (BW-54XR): 13.570km TO 13.620km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115693&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000115693 | C13 Turnout B/U Midgee 12C/D | TO000875 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 238750 | Blackwater | MIDGEE | MIDGEE | 0.0509 | KM | BW02ML622 | 0.9649 | BW02ML623 | 0.033 | KM |  |  |  |  | 622.965 | 623.033 | 2026-06-30 | BW-01ML |  |  |  | 4.2 | 4.1 | 2 | 3.9 | 1 | 16.4 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000875 Lead: 622.915km to TOS Trailing: back of TO to 623.083km Divergent (BW-44XR): 622km1010m to 622km1035m TO to be packaged with TO000841 (2000138245) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138245&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000138245 | C13 Turnout B/U Midgee 12A/B | TO000841 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 233250 | Blackwater | MIDGEE | MIDGEE | 0.0429 | KM | BW01ML623 | 0.081 | BW01ML623 | 0.0379 | KM |  |  |  |  | 623.038 | 623.081 | 2026-06-30 | BW-01ML |  |  |  | 4.2 | 4.1 | 2 | 3.9 | 1 | 16.4 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000841 Lead: 622.988km to TOS Divergent (BW-44XR): 622km1035m to 622km1060km TO to be packaged with TO000875 (2000115693) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094420&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094420 | C13 Turnout B/U Moura Mine 10A | TO000977 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 258000 | Moura | MOURA MINE | MOURA MINE | 0.025 | KM | MA04ML0 | 0.0529 | MA04ML0 | 0.0779 | KM |  |  |  |  | 0.053 | 0.078 | 2026-06-30 | MA-04ML |  |  |  | 4.2 | 1.1 | 2 | 2.5 | 1 | 10.5 | 5869 | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Scope: C13 - TO000977 Lead: 0km to TOS Trailing: back of TO to 0.119km TO to be packaged with TO000954 (2000094422) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094422&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000094422 | C13 Turnout B/U Moura Mine 9A | TO000954 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 262500 | Moura | MOURA MINE | MOURA MINE | 0 | KM | MA01ML179 | 0.921 | MA01ML179 | 0.921 | KM |  |  |  |  | 179.921 | 179.97 | 2026-06-30 | MA-01ML |  |  |  | 3.8 | 1.1 | 2 | 2.5 | 1 | 9.5 | 5869 | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Scope: C13 - TO000954 Lead: 179.871km to TOS Trailing: back of TO to 180.02km TO to be packaged with TO000977 (2000094420) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080111&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000080111 | C13 Turnout B/U Mt Miller 9A/B | TO000859 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 242500 | Blackwater | MT MILLER | MT MILLER | 0.05 | KM | BW01ML542 | 0.451 | BW01ML542 | 0.401 | KM |  |  |  |  | 542.401 | 542.451 | 2026-06-30 | BW-01ML |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000859 Lead: 542.351km to TOS Trailing: back of TO to 542.501km Divergent (BW-20ML): 0km to 0.5km TO to be packaged with TO000858 (2000080112) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080112&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000080112 | C13 Turnout B/U Mt Miller 8C/D | TO000858 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 235200 | Blackwater | MT MILLER | MT MILLER | 0.0729 | KM | BW01ML542 | 0.4709 | BW01ML542 | 0.544 | KM |  |  |  |  | 542.471 | 542.544 | 2026-06-30 | BW-01ML |  |  |  | 4.2 | 4.8 | 2 | 4.2 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000858 Lead: 542.451km to TOS Trailing: back of TO to 542.594km Divergent (BW-44XR): 542.52km to 542.57km TO to be packaged with TO000859 (2000080111) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080086&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080086 | C13 Turnout B/U Parnabal 11C/D | TO000578 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 194515 | Blackwater | PARNABAL | PARNABAL | 0.0449 | KM | BW03ML156 | 0.331 | BW03ML156 | 0.2859 | KM |  |  |  |  | 156.286 | 156.331 | 2026-06-30 | BW-03ML |  |  |  | 4.4 | 3.4 | 2 | 3.7 | 1 | 16.3 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000578 Trailing: back of TO to 156.378km Divergent (BW-86XR): 156.301km to 156.351km TO to be packaged with TO000579 (2000104220) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080120&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000080120 | C13 Turnout B/U Raglan 12C/D | TO000908 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 255790 | Blackwater | RAGLAN | RAGLAN | 0.049 | KM | BW02ML583 | 0.9809 | BW02ML584 | 0.028 | KM |  |  |  |  | 583.981 | 584.028 | 2026-06-30 | BW-02ML |  |  |  | 4.4 | 4.1 | 2 | 3.9 | 1 | 17.2 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000908 Lead: 583.931km to TOS Trailing: back of TO to 584.078km Divergent (BW-53XR): 583.981km to 583km1030km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080115&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000080115 | C13 Turnout B/U Raglan ER1.2B Pts | TO000846 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 252950 | Blackwater | RAGLAN | RAGLAN | 0.0359 | KM | BW01ML584 | 0.795 | BW01ML584 | 0.8309 | KM |  |  |  |  | 584.795 | 584.831 | 2026-06-30 | BW-01ML |  |  |  | 4 | 4.1 | 2 | 3.9 | 1 | 15.6 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000846 Lead: 584.75km to TOS Trailing: back of TO to 584.881km Divergent (BW-01SD): 584.795km to 584.845km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104191&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104191 | C13 Turnout U/C Riverside ER1.2A | TO000327 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 300000 | Goonyella | RIVERSIDE BALLOON | RIVERSIDE BALLOON | 0.034 | KM | GA14ML204 | 0.393 | GA14ML204 | 0.3589 | KM |  |  |  |  | 204.25 | 204.283 | 2026-06-30 | GA-14ML |  |  |  | 3.9 | 1.1 | 2 | 2.5 | 1 | 9.8 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000327 Lead: 204.2km to TOS Trailing: back of TO to 204.33km Divergent (GA-07SD): 204.210km to 204.26km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104251&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000104251 | C13 Turnout B/U Rocklands 50C/D | TO000759 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 217450 | Blackwater | ROCKLANDS | ROCKLANDS | 0.05 | KM | BW02ML631 | 0.507 | BW02ML631 | 0.557 | KM |  |  |  |  | 631.507 | 631.557 | 2026-06-30 | BW-02ML |  |  |  | 4.5 | 4.5 | 2 | 4.1 | 1 | 18.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000759 Lead: 631.477km to TOS Trailing: back of TO to 631.587km Divergent (BW-46XR): 631.54km to 631.575km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080147&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080147 | C13 Turnout B/U Rolleston 11 Pts | TO000824 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 231000 | Blackwater | ROLLESTON | ROLLESTON | 0.033 | KM | BW06ML103 | 5.5679 | BW06ML103 | 5.535 | KM |  |  |  |  | 103.721 | 103.754 | 2026-06-30 | BW-06ML |  |  |  | 4.5 | 2.3 | 2 | 3.2 | 1 | 14.4 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000824 Lead: 103.671km to TOS Trailing: back of TO to 103.804km Divergent (BW-06ML): 108.515km to 108.565km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104202&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | BASELOAD | NON-COAL | 002000104202 | C13 Turnout B/U Tolmies 12A Pts | TO000635 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 256500 | Blackwater | TOLMIES | TOLMIES | 0.032 | KM | NC09ML203 | 0.375 | NC09ML203 | 0.4069 | KM |  |  |  |  | 203.336 | 203.368 | 2026-06-30 | NC-09ML |  |  |  | 4 | 1.7 | 2 | 2.8 | 1 | 11.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: C13 - TO000635 Lead: 203.286km to TOS Trailing: back of TO to 203.418km Divergent (NC-06PL): 203.336km to 203.386km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104207&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | BASELOAD | NON-COAL | 002000104207 | C13 Turnout B/U Tolmies 7A Pts | TO000685 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 213960 | Blackwater | TOLMIES | TOLMIES | 0.032 | KM | NC09ML204 | 0.1719 | NC09ML204 | 0.14 | KM |  |  |  |  | 204.141 | 204.173 | 2026-06-30 | NC-09ML |  |  |  | 4.2 | 1.7 | 2 | 2.8 | 1 | 11.8 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: C13 - TO000685 Lead: 204.123km to TOS Trailing: back of TO to 204.191km Divergent (NC-06PL): 204.123km to 204.163km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080168&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080168 | C13 Turnout B/U Tunnel 8A/B | TO000637 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 270700 | Blackwater | TUNNEL | TUNNEL | 0.033 | KM | BW03ML75 | 0.447 | BW03ML75 | 0.4799 | KM |  |  |  |  | 75.447 | 75.48 | 2026-06-30 | BW-03ML |  |  |  | 4.5 | 3.35 | 2 | 3.6 | 1 | 16.2 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000637 Lead: 75.347km to TOS Trailing: back of TO to 75.53km Divergent (BW-69XR): 75.47km to 75.49km TO to be packaged with TO000714 (2000104230) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104230&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104230 | C13 Turnout B/U Tunnel 8C/D | TO000714 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 233070 | Blackwater | TUNNEL | TUNNEL | 0.033 | KM | BW04ML75 | 0.511 | BW04ML75 | 0.4779 | KM |  |  |  |  | 75.478 | 75.511 | 2026-06-30 | BW-04ML |  |  |  | 4.4 | 3.4 | 2 | 3.7 | 1 | 16.3 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000714 Lead: 75.411km to TOS Trailing: back of TO to 75.561km Divergent (BW-69XR): 75.461km to 75.511km TO to be packaged with TO000637 (2000080168) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104220&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104220 | C13 Turnout B/U Parnabal 12A/B | TO000579 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 259815 | Blackwater | UMOLO | PARNABAL | 0.0449 | KM | BW03ML156 | 0.4239 | BW03ML156 | 0.4689 | KM |  |  |  |  | 156.424 | 156.469 | 2026-06-30 | BW-03ML |  |  |  | 4 | 3.4 | 2 | 3.7 | 1 | 14.8 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000579 Lead: 156.378km to TOS Trailing: back of TO to 156.519km Divergent (BW-87XR): 156.454km to 156.484km TO to be packaged with TO000578 (2000080086) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115695&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115695 | C13 Turnout B/U Wallaroo ER.2B | TO000639 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 256500 | Blackwater | WALLAROO | WALLAROO | 0.035 | KM | BW03ML115 | 0.1849 | BW03ML115 | 0.22 | KM |  |  |  |  | 115.185 | 115.22 | 2026-06-30 | BW-03ML |  |  |  | 4.5 | 3.4 | 2 | 3.7 | 1 | 16.7 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000639 Lead: 115.135km to TOS Trailing: back of TO to 115.27km Divergent (BW-11SD): 115.2km to 115.25km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115696&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115696 | C13 Turnout B/U Warren 10A/B | TO000673 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 246500 | Blackwater | WARREN | WARREN | 0.0449 | KM | BW03ML25 | 0.134 | BW03ML25 | 0.1789 | KM |  |  |  |  | 25.134 | 25.179 | 2026-06-30 | BW-03ML |  |  |  | 4.2 | 3.4 | 2 | 3.7 | 1 | 15.5 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000673 Lead: 25.804km to TOS Trailing: back of TO to 25.229km Divergent (BW-57XR): 25.16km to 25.21km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138195&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138195 | C13 Turnout U/C Wotonga 10A/B | TO000295 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 290000 | Goonyella | WOTONGA | WOTONGA | 0.07 | KM | GA02ML176 | 0.5649 | GA02ML176 | 0.4949 | KM |  |  |  |  | 176.495 | 176.565 | 2026-06-30 | GA-02ML |  |  |  | 4.5 | 1.5 | 2 | 2.7 | 1 | 12.2 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000295 Lead: 176.445km to TOS Trailing: back of TO to 176.615km Divergent (GA-02FK): 2.630km to 2.680km TO to be packaged with TO000211 (2000115710) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115710&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115710 | C13 Turnout U/C Wotonga 12A/B | TO000211 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 318000 | Goonyella | WOTONGA | WOTONGA | 0.0719 | KM | GA01ML176 | 0.7459 | GA01ML176 | 0.8179 | KM |  |  |  |  | 176.746 | 176.818 | 2026-06-30 | GA-02ML |  |  |  | 4.5 | 1.5 | 2 | 2.7 | 1 | 12.2 |  | 2024-03-28 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope: C13 - TO000211 Lead: 176.696km to TOS Trailing: back of TO to 176.868km Divergent (GA-02ML): 176.695km to 176.780km TO to be packaged with TO000295 (2000138195) Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074637&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000074637 | C13 Turnout U/C YUKAN 8C/D | TO000341 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 424400 | Goonyella | YUKAN | YUKAN | 0.047 | KM | GA02ML27 | 0.783 | GA02ML27 | 0.7359 | KM |  |  |  |  | 27.736 | 27.783 | 2026-06-30 | GA-02ML |  |  |  | 4 | 4.8 | 2 | 4.2 | 1 | 16.8 | 5677 | 2024-03-28 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | * 31.03.2021 18:57:21 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing Scope: C13 - TO000341 Lead: 27.6km to TOS Trailing: back of TO to 27.9km Divergent (GA-16XR): 27.720km to 27.760km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor. 31.03.2021 18:57:21 AUSQLD Tracy Holmes (R870040) Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000055198&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000055198 | C13 Turnout U/C YUKAN 11C/D | TO000333 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 302800 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML30 | 0.14 | GA02ML30 | 0.14 | KM |  |  |  |  | 30.086 | 30.14 | 2026-06-30 |  |  |  |  | 3 | 4.4 |  |  |  | 13.2 | 5601 | 2024-03-28 | 2020-11-13 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Scope: C13 - TO000333 Lead: 30.036km to TOS Trailing: back of TO to 30.200km Divergent (GA-31XR): 30.05km to 30.1km Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138173&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138173 | C20-BR-MA-CLYDE CREEK-MAIN-20.880KM. | BR400291-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.058 | KM | 720000 | Moura | BYELLEE | STOWE | 0.058 | KM | MA01ML20 | 0.8389 | MA01ML20 | 0.897 | KM |  |  |  |  | 20.853 | 20.911 | 2026-06-30 | MAIN |  |  |  | 4.08 | 1.3 | 2 | 2.6 | 1 | 10.6 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | C20 - 20.853km to 20.911km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104159&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104159 | C20-BR-BW-MACKENZIE RIVER-MAIN-16.685KM. | BR101090-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.5 | KM | 1919467 | Blackwater | CREW | MACKENZIE | 0.445 | KM | BW08ML16 | 0.7119 | BW08ML17 | 0.158 | KM |  |  |  |  | 16.685 | 17.185 | 2026-06-30 | MAIN |  |  |  | 4.58 | 1.2 | 3 | 3.1 | 1 | 14.2 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | HIGH | Notification in process | SCPR |  | 20260630 | PLAN TO REPLACE 50% OF SLEEPERS DUE TO POTENTIAL ROUNDING FROM PUMPING Relieving slabs and permanent handrails (with walkway) on right / eastern side of bridge to be completed in the same year - structures notification - 2000094230 High priority bridge - pumping at both abutments and mud holes forming into bridge for approx 50m both ends C20 - 16.71km to 17.161km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104156&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104156 | C20-BR-BW-SPRINGTON CK-DOWN-143.264KM. | BR100295-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.123 | KM | 840000 | Blackwater | DINGO | UMOLO | 0.1229 | KM | BW03ML143 | 0.2929 | BW03ML143 | 0.4159 | KM |  |  |  |  | 143.293 | 143.416 | 2026-06-30 | DOWN |  |  |  | 3.75 | 3.4 | 2 | 3.6 | 1 | 13.5 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | C20 - 143.29km to 143.415km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065309&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000065309 | C20-BR-GA-WILLY CK-DN-21.560KM. | BR201202-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.036 | KM | 400000 | Goonyella | JILALAN | YUKAN | 0.0359 | KM | GA01ML21 | 0.527 | GA01ML21 | 0.5629 | KM |  |  |  |  | 21.527 | 21.563 | 2026-06-30 | DOWN |  |  |  | 3.75 | 4.8 | 2 | 4.2 | 1 | 15.8 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Notification in process | SCPR |  | 20260630 | C20 - 21.527km to 21.563km Bridge does not have splays - review delivery methodology - may be able to use excavators or other alternative delivery method In Jilalan yard - bridge has 4 tracks Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138180&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138180 | C20-BR-GA-NCL OPASS-UP-22.820KM. | BR201201-91-02 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.056 | KM | 570000 | Goonyella | JILALAN | YUKAN | 0.056 | KM | GA02ML22 | 0.81 | GA02ML22 | 0.8659 | KM |  |  |  |  | 22.81 | 22.866 | 2026-06-30 | UP |  |  |  | 3.75 | 4.8 | 2 | 4.2 | 1 | 15.8 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | C20 - 22.81km to 22.866km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138163&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138163 | C20-BR-BW-STEWARTS CK-UP-24.629KM. | BR100234-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.048 | KM | 560000 | Blackwater | KABRA | WARREN | 0.048 | KM | BW04ML24 | 0.629 | BW04ML24 | 0.677 | KM |  |  |  |  | 24.629 | 24.677 | 2026-06-30 | UP |  |  |  | 3.74 | 3.4 | 2 | 3.6 | 1 | 13.5 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | C20 - 24.629km to 24.677km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138109&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138109 | C20-BR-MA-BELL CREEK-MAIN-93.370KM. | BR400421-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.046 | KM | 620000 | Moura | MT RAINBOW | MT RAINBOW | 0.0459 | KM | MA01ML93 | 0.3539 | MA01ML93 | 0.4 | KM |  |  |  |  | 93.354 | 93.4 | 2026-06-30 | MAIN |  |  |  | 4.08 | 1.3 | 2 | 2.6 | 1 | 10.6 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | C20 - 93.354km to 93.4km Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094375&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094375 | C20-BR-BW-BOOTES CREEK-MAIN-102.887KM | BR100863-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.101 | KM | 502975 | Blackwater | STARLEE | ROLLESTON | 0.101 | KM | BW06ML102 | 0.887 | BW06ML102 | 0.9879 | KM |  |  |  |  | 102.887 | 102.988 | 2026-06-30 | MAIN |  |  |  | 4.42 | 2.3 | 2 | 3.2 | 1 | 14.1 |  | 2024-03-28 |  | Bridge Roll Out | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | Was FY23 bridge, didn't make it into MRSB so has been deferred to FY24. HIgh fouling, poor geometry both ends of brudge - D7 top defects. Undercutting needs to tie in with nearby undercutting works - check formation due to dropping top - district doesn't think there is an obvious formation issue. Shorter bridge and good access either end - lower priority for handrail, ideally we would have handrail both sides Previous FY23 noti # 2000074680 (for ref only) 11/01/2024 - Not completed as planned due to wet weather. To be deferred to FY26. PCR 5802 - deferred to FY26 Track components to be replaced and formation repairs to be completed as per tech scopes. Ballast Undercutting General Requirements: • Complete Ballast Undercutting in accordance with Civil Engineering Track Standard - Ballast Module 4 and Aurizon Specification AZN .NA.SPC.12.6135.002 – Railway Ballast. • Clean, clear and reinstate drainage as per the notification extents in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that water does not pond within the track formation. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access within the rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132865&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000132865 | FENCING & CORRIDOR SECURITY REACTIVE | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 555000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132866&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000132866 | FENCING & CORRIDOR SECURITY REACTIVE | GA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 476000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132868&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000132868 | FENCING & CORRIDOR SECURITY REACTIVE | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 558000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Reactive allocation of $146,000 as well as an additional $412,000 for the following existing N7 notifications (Total $558,000): 2000111687 2000125591 2000125595 Increase in reactive funding for Moura due to no planned fencing renewals (N4s) due to backlog of existing N7 fencing notifications unable to be funded in previous years.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132902&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000132902 | FENCING & CORRIDOR SECURITY REACTIVE | NL | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 146000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138538&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138538 | Non Coal Reactive Renewals - Fencing | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138539&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138539 | Non Coal Reactive Renewals - Fencing | GA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138540&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138540 | Non Coal Reactive Renewals - Fencing | MA | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138541&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138541 | Non Coal Reactive Renewals - Fencing | NL | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112785&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | NON-COAL | 002000112785 | Burngrove to Nogoa Fencing FY26 | BW | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 60000 | Blackwater | BURNGROVE | NOGOA | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 202.36 | 263.15 | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137417&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137417 | C61-CSF-BW-AROONA-97.597km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 3.792 | KM | 189600 | Blackwater | AROONA | DUARINGA | 3.814 | KM | BW03ML97 | 0.5969 | BW03ML101 | 0.389 | KM |  |  |  |  | 97.597 | 101.389 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137422&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137422 | C61-CSF-GA-BLACK MOUNTAIN-46.000km | GA-01CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 2.9 | KM | 145000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 2.906 | KM | GA01ML46 | 0 | GA01ML48 | 0.9 | KM |  |  |  |  | 46 | 48.9 | 2026-06-30 |  |  |  |  | 3.6 | 5 | 1 | 3.9 | 1 | 14.04 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137419&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137419 | C61-CSF-BW-DUARINGA-113.721km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 1.089 | KM | 54450 | Blackwater | DUARINGA | WALLAROO | 1.0889 | KM | BW03ML113 | 0.7209 | BW03ML114 | 0.81 | KM |  |  |  |  | 113.721 | 114.81 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137392&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137392 | C61-CSF-GA-HATFIELD-52.600km | GA-01CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 10.4 | KM | 520000 | Goonyella | HATFIELD | BOLINGBROKE | 10.387 | KM | GA01ML52 | 0.5999 | GA01ML63 | 0 | KM |  |  |  |  | 52.6 | 63 | 2026-06-30 |  |  |  |  | 3.6 | 5 | 1 | 3.9 | 1 | 14.04 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137420&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137420 | C61-CSF-GA-HATFIELD-52.600km | GA-01CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 10.4 | KM | 520000 | Goonyella | HATFIELD | BOLINGBROKE | 10.387 | KM | GA01ML52 | 0.5999 | GA01ML63 | 0 | KM |  |  |  |  | 52.6 | 63 | 2026-06-30 |  |  |  |  | 3.6 | 5 | 1 | 3.9 | 1 | 14.04 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137413&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000137413 | C61-CSF-NL-NEWLANDS-147.560km | NL-01CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 1.26 | KM | 63000 | Newlands | NEWLANDS | LEICHHARDT RANGE | 1.2239 | KM | NL01ML147 | 0.56 | NL01ML148 | 0.8199 | KM |  |  |  |  | 147.56 | 148.82 | 2026-06-30 |  |  |  |  | 3.6 | 1.2 | 1 | 1.7 | 1 | 6.12 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137415&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137415 | C61-CSF-BW-ROCKLANDS-1.950km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 1.42 | KM | 71000 | Blackwater | ROCKLANDS | GRACEMERE | 1.401 | KM | BW03ML1 | 0.9499 | BW03ML3 | 0.3699 | KM |  |  |  |  | 1.95 | 3.37 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137423&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137423 | C61-CSF-GA-WANDOO-92.500km | GA-01CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 6.6 | KM | 330000 | Goonyella | WANDOO | WAITARA | 6.602 | KM | GA01ML92 | 0.5 | GA01ML99 | 0.1 | KM |  |  |  |  | 92.5 | 99.1 | 2026-06-30 |  |  |  |  | 3.6 | 5 | 1 | 3.9 | 1 | 14.04 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137484&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137484 | C61-CSF-BW-WESTWOOD-48.050km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 7.288 | KM | 364400 | Blackwater | WESTWOOD | WINDAH | 7.293 | KM | BW03ML48 | 0.05 | BW03ML55 | 0.338 | KM |  |  |  |  | 48.05 | 55.338 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137450&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137450 | C61-CSF-BW-WYCARBAH-39.812km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 1.862 | KM | 93100 | Blackwater | WYCARBAH | WESTWOOD | 1.866 | KM | BW03ML39 | 0.812 | BW03ML41 | 0.674 | KM |  |  |  |  | 39.812 | 41.674 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137482&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137482 | C61-CSF-BW-WYCARBAH-40.470km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 2.006 | KM | 100300 | Blackwater | WYCARBAH | WESTWOOD | 2.0049 | KM | BW03ML40 | 0.4699 | BW03ML42 | 0.4759 | KM |  |  |  |  | 40.47 | 42.476 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137483&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137483 | C61-CSF-BW-WYCARBAH-39.812km | BW-03CR | CIVIL | CORRIDOR SECURITY & FENCING |  | RENEWAL | 4.052 | KM | 202600 | Blackwater | WYCARBAH | WESTWOOD | 4.0529 | KM | BW03ML43 | 0.456 | BW03ML47 | 0.508 | KM |  |  |  |  | 43.456 | 47.508 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3.2 | 1 | 16 |  | 2024-03-28 |  | Corridor Fencing and Security | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Complete fencing renewal in accordance with: • Aurizon Standard Drawings #2549 - Rural Fences (Steel Posts) <(>&<)> #2550 - Rural Fences (Miscellaneous Site Layout Details). • Aurizon Standard Drawings #AUR-S-9999-0600, AUR-S-9999-0601 <(>&<)> AUR-S-9999-0602 - Trespass Signage • Aurizon Civil Specification AZN.NA.SPC.12.6135.200 SUPPLY AND CONSTRUCTION MODULE 03 – FENCING (4 OR 6 WIRE) (QR-CTS-PART 03). Additional Requirements <(>&<)> Information: • Fencing to be Standard 4-Wire, low tensile barb wire fencing unless otherwise specified. • Where existing fence line/property boundary is unable to be established or where any ambiguity exists towards the location of Auri zon property boundaries, the Aurizon boundary shall be surveyed and pegged out prior to fencing construction by a registered Cadastral Surveyor. • Works to include removal and disposal of existing fencing components <(>&<)> any fencing construction waste from Aurizon property. • Works to include clearing and removal of vegetation along fence line as well as repairs to any localised erosion which may impact the fences ability to be stock proof. • Where the boundary line is intersected by a permanent waterway, the boundary fence is to be constructed as returned to the abutments of the bridge or culvert as a 'wing' fence. The location of the boundary fence across small variable flow waterways shall be designed to avoid flood damage to the fence. As detailed in Standard Drawing #2550 - Rural Fences (Miscellaneous Site Layout Details).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077885&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077885 | FORMATION GEOTECH DESIGN | BW | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 60000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Conduct Geotech Testing for Blackwater Formation Renewals: • BW-01ML 554.059 – 554.540km (FY26 2000115119) • BW-01ML 603.650 - 604.512km (FY26 2000115200) • BW-03ML 31.000 - 31.730km (FY26 2000077788) • BW-03ML 29.100 - 29.600km (FY29 Proposed) • BW-03ML 29.600 - 30.150km (FY28 Proposed) • BW-03ML 30.465 - 31.000km (FY27 Proposed) • BW-02ML 580.100 - 580.500km (TBC Proposed) • Adhoc Geotechnical design advice for BW system as required Note: • Forms part of proposed multi year renewals scope • FY27+ Proposed scope subject to change prior to final scope turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077887&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077887 | FORMATION GEOTECH DESIGN | GA | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 60000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Conduct Geotech Testing for Goonyella Formation Renewals: • GA-01ML 166.500 - 167.300km (FY26 2000136288) • GA-03ML 21.700 - 22.250km (FY26 2000052749) • GA-03ML 31.100 - 32.100km (FY26 2000136286) • GA-01ML 164.970 - 166.500km, 167.300 - 167.700km (TBC future renewals) • GA-03ML 18.900 - 20.500km (TBC future renewals) • GA-03ML 23.700 - 27.530km (TBC future renewals) • Adhoc Geotechnical design advice for GA system as required Note: • Forms part of proposed multi year renewals scope • FY27+ Proposed scope subject to change prior to final scope turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077888&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077888 | FORMATION GEOTECH DESIGN | MA | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 25000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Conduct Geotech Testing for Moura Formation Renewals: • MA-01ML 70.050 – 70.450km (FY26 2000133264) • MA-01ML 70.450 - 70.850km (FY27 Proposed) • MA-01ML 70.850 - 71.200km (FY28 Proposed) • Adhoc Geotechnical design advice for MA system as required Note: • Forms part of proposed multi year renewals scope 70.050 - 71.200km • FY24 Completed scope 71.200 – 71.500km (2000067365)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077889&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077889 | FORMATION GEOTECH DESIGN | NL | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 30000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation - Other | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Conduct Geotech Testing for Newlands Formation Renewals: • NL-01ML 114.000 – 114.600km (FY26 2000052758) • NL-01ML 116.300 - 116.800km (FY27 Proposed 2000134379) • NL-01ML 137.000 - 137.465km (FY28 Proposed 2000134433) • Adhoc Geotechnical design advice for NL system as required Note: • Forms part of proposed multi year renewals scope • FY27+ Proposed scope subject to change prior to final scope turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138542&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138542 | Non Coal Reactive Renewals - Formation | BW | CIVIL | FORMATION |  | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138550&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138550 | Non Coal Reactive Renewals - Formation | GA | CIVIL | FORMATION |  | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138552&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138552 | Non Coal Reactive Renewals - Formation | MA | CIVIL | FORMATION |  | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138553&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138553 | Non Coal Reactive Renewals - Formation | NL | CIVIL | FORMATION |  | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136288&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000136288 | C05-FR-GA-BROADLEA-166.500km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.8 | KM | 3500000 | Goonyella | BROADLEA | MALLAWA | 0.803 | KM | GA01ML166 | 0.5 | GA01ML167 | 0.2999 | KM |  |  |  |  | 166.5 | 167.3 | 2026-06-30 | DOWN |  |  |  | 4.2 | 2.5 | 3.5 | 3.9 | 1 | 16.5 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Existing sleeper type is fist, formation renewal to include sleeper renewal, refer to 2000140073 for sleeper notification for capture of sleeper material costs. Note: • Location experiencing formation failures following undercutting in November 2023 (FY24 166.400 - 167.750km, 002000094875), further reactive intervention may be required, see known list below. • Includes level crossing ID3206 - Ensure longitudinal drainage is effective. Lack of pipe under crossing suspected cause of formation failure at this location causing water ponding on low chainage (uphill) side of crossing. Formation Renewal Requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 166.400km to 167.400km Down Road side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • BMF Survey <(>&<)> Design should reinstate renewal location to design ballast depth and install Rail Level data plaques in reference to top of formation design level if not already present. Refer to AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Note - encompasses below reactive works: • 166.612 - 166.662km (FY20 2000039826 Reactive Renewal CM) • 166.760 - 166.920km (FY24 2000133371 Reactive Renewal TBA) • 166.780 - 166.796km (FY24 2000133270 Shear Key TBC) • 166.828 - 166.862km (FY24 2000133278 Shear Key TBC) • 166.990 - 167.004km (FY18 2000010061 Reactive Renewal)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052758&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000052758 | C05-FR-NL-COCKOOL-114.000km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 2700000 | Newlands | COCKOOL | HAVILAH | 0.5999 | KM | NL01ML114 | 0 | NL01ML114 | 0.5999 | KM |  |  |  |  | 114 | 114.6 | 2026-06-30 | MAIN |  |  |  | 4.6 | 1.4 | 3.5 | 3.5 | 1 | 16 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Existing sleeper type is fist, formation renewal to include sleeper renewal, refer to 2000140074 for sleeper notification for capture of sleeper material costs. Important Notes: • Site will require removal <(>&<)> reinstatement of flood rock. • Scope can be extended back to 113.900 to tie into adjacent culvert if cost estimates come in under SPM estimate (based on $4,500/m). Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 113.900km to 115.000km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115200&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000115200 | C05-FR-BW-MARMOR-603.650km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.848 | KM | 3879000 | Blackwater | MARMOR | BAJOOL | 0.8479 | KM | BW01ML603 | 0.65 | BW01ML604 | 0.512 | KM |  |  |  |  | 603.65 | 604.512 | 2026-06-30 | UP |  |  |  | 3.9 | 4.1 | 3.5 | 4.4 | 1 | 17.2 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | 21/02/2024 - Scope start amended from 604.350km to 603.650km (Increased scope by 700m for increased unit rate efficiencies) and put in scope for FY26 based on district feedback and priorities. 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 603.250km to 604.650km Up Rd field side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Joins FY24 formation Scope (002000092001 604.512 - 604.672km)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052749&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000052749 | C05-FR-GA-RED MOUNTAIN-21.700km | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.55 | KM | 2475000 | Goonyella | MILLENIUM JCT | RED MOUNTAIN | 0.548 | KM | GA03ML21 | 0.6999 | GA03ML22 | 0.25 | KM |  |  |  |  | 21.7 | 22.25 | 2026-06-30 | MAIN |  |  |  | 4.7 | 2.5 | 3.5 | 3.9 | 1 | 18.2 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | HIGH | Notification in process | SCPR |  | 20260630 | Note: • Requires removal <(>&<)> reinstatement of turnout Red Mountain 7A/B pts (TO000385) • Red Mountain 7A/B (TO000385). Was in for turnout undercut in FY24 however was removed from scope as DCP test results showed formation was weak and could be contributing to poor geometry (PCR5474, Undercut Noti 2000094427, DCP Test noti 2000087684) Tie in to adjacent strategic formation renewals: • GA-03ML 20.500 - 21.000km (FY22 2000043952) • GA-03ML 21.000 - 21.700km (FY21 2000043955) • GA-03ML 21.700 - 22.250km (FY26 This Notification) • GA-03ML 22.250 - 23.050km (FY24 2000052736) • GA-03ML 23.050 - 23.700km (FY23 2000052718) Formation Renewal Requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 21.600km to 22.350km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • BMF Survey <(>&<)> Design should reinstate renewal location to design ballast depth and install Rail Level data plaques in reference to top of formation design level if not already present. Refer to AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to construction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Note - covers previous reactive formation works: • 22.152 - 22.197km (FY15 80061682 Reactive Renewal)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077788&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000077788 | C05-FR-BW-WARREN-31.000km | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.73 | KM | 3045000 | Blackwater | WARREN | WYCARBAH | 0.7299 | KM | BW03ML31 | 0 | BW03ML31 | 0.7299 | KM |  |  |  |  | 31 | 31.73 | 2026-06-30 | DOWN |  |  |  | 3.6 | 3.4 | 3.5 | 4.2 | 1 | 15 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Formation Scope integrated with new installation of mainline weigher at Kalapa (~31.200km) in FY26, formation works to be completed in conjunction with or prior to weighbridge installation. Formation Renewal requirements: Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. Clean, clear and reinstate drainage from 31.000km to 31.760km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to construction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): - Reuse existing rail - Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) - Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) - Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017. Note - Forms part of proposed multi year scope: • 28.800 - 29.100km (FY24 2000133330) • 29.100 - 29.600km (FY29 Proposed) • 29.600 - 30.150km (FY28 Proposed) • 30.150 - 30.465km (FY24 2000077789) • 30.465 - 31.000km (FY27 Proposed) • 31.000 - 31.730km (FY26 2000077788 This noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136286&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136286 | C05-FR-GA-WINCHESTER-31.100km | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 1 | KM | 3500000 | Goonyella | WINCHESTER | WINCHESTER | 0.9989 | KM | GA03ML31 | 0.1 | GA03ML32 | 0.1 | KM |  |  |  |  | 31.1 | 32.1 | 2026-06-30 | MAIN |  |  |  | 4.8 | 2.1 | 4 | 3.9 | 1 | 18.8 |  | 2024-03-28 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Note: • Scope driven by reactive history (see below) Tie in to adjacent previous strategic formation renewals: • Nil known. Formation Renewal Requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 31.000km to 32.200km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • BMF Survey <(>&<)> Design should reinstate renewal location to design ballast depth and install Rail Level data plaques in reference to top of formation design level if not already present. Refer to AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Note - covers previous reactive formation works: • 31.176 - 31.206km (FY24 2000123019 Shear Key) • 31.176 - 31.206km (MONI 2000119309 Reactive Renewal) • 31.214 - 31.230km (FY23 2000107250 Reactive Renewal) • 31.595 - 31.631km (FY17 2000000749 Reactive Renewal) • 31.622 - 31.648km (FY24 2000109420 Shear Key) • 31.782 - 31.822km (FY23 2000114213 Reactive Renewal) • 31.802 - 31.836km (FY18 2000007429 Reactive Renewal) • 31.922 - 31.938km (FY23 2000107251 Shear Key) • 31.970 - 32.010km (FY24 2000114216 Reactive Renewal) • 32.127 - 32.146km (FY23 2000109365 Reactive Renewal) • 32.132 - 32.148km (FY23 2000109420 Shear Key)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077834&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000077834 | Formation C05 Reactive Works | BW | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 2400000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077836&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000077836 | Formation C05 Reactive Works | GA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 2400000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077835&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000077835 | Formation C05 Reactive Works | MA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 2000000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 27/03/2024: FY26 Reactive formation allocation increased from 1,200 ,000.00 AUD to 2,000,000.00 AUD to compensate for the cancellation of all planned Moura formation renewals (Previously $1.8M) in FY26 due to capital constraint as directed by NAM leadership.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077837&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000077837 | Formation C05 Reactive Works | NL | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Formation Reactive | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077869&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077869 | CIVIL GPR RUN BLACKWATER | BW | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 624000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 27.05.2021 12:03:23 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE. APPROX KM BASED ON FY21 SCOPE = 954.068KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077870&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077870 | CIVIL GPR RUN GOONYELLA | GA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 590000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 27.05.2021 12:03:24 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE FOR FUTURE YEARS SCOPE HANDOVER. SCOPE BASED ON FY21 SUBMISSION IS 796.421KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077872&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077872 | CIVIL GPR RUN MOURA | MA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 210000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 27.05.2021 12:03:40 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN SCOPE FOR GPR AS REQUIRED FOR BALLAST UNDERCUTTING SCOPE HANDOVER IN FUTURE YEARS. SCOPE FOR GPR FOR MOURA BASED ON GPR FY21 IS 246.07KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077871&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000077871 | CIVIL GPR RUN NEWLANDS | NL | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 240000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Ground Penetrating Radar | STRATEGIC |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 27.05.2021 12:03:39 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN SCOPE AS REQUIRED FOR SCOPING FUTURE YEARS. KILOMETRES FROM FY21 SCOPE WAS 282.556KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083399&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000083399 | C58-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 350000 | Blackwater | BW | BW | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 2 | 25 | 1 | 25 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Reduced the allocation from $600k to $300k due to funding limit. FY26 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083401&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000083401 | C58-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 350000 | Moura | MA | MA | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 2 | 25 | 1 | 25 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Reduced the allocation (from $600k to $350k) due to funding limit. FY26 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083402&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000083402 | C58-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Newlands | NL | NL | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 2 | 25 | 1 | 25 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120604&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120604 | C58-LX-MA-CALLE-16.416km | LX005753 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML16 | 0.4179 | MA01ML16 | 0.4179 | KM |  |  |  |  | 16.416 | 16.416 | 2026-06-30 | JEFFERIES ROAD |  |  |  | 3.2 | 1.3 | 2 | 3 | 1 | 9.6 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Originally kept in FY26 Design for FY27 Renewal as per the mtg with Geoff O'Connor. Dec. 2022 Changed to FY25 Design for FY27 Renewal due to increased maintenance activities and poor formation witnessed during recent undercut in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120605&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120605 | C58-LX-NL-COLLINSVILLE-77.186km | LX003301 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Newlands | COLLINSVILLE | MCNAUGHTON | 0 | KM | NL01ML77 | 0.1859 | NL01ML77 | 0.1859 | KM |  |  |  |  | 77.186 | 77.186 | 2026-06-30 | BOWEN DEVELOPMENT ROAD |  |  |  | 3.3 | 2.5 | 2 | 3 | 1 | 10.6 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY25 Design for FY27 Renewal. This crossing is being put forward for alternative surface (Bodan preferably).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135349&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000135349 | C58-LX-MA-FRY-MA-01ML-89.560km | LX006516 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.56 | MA01ML89 | 0.56 | KM | 2 |  | 0.22 | 0.22 | 89.56 | 89.56 | 2026-06-30 | MAINTENANCE ACCESS ROAD |  |  |  | 4.17 | 2.66 | 2 | 3.34 | 1 | 10.8 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | PCR 5859 for IFC design of LX6516 to deliver the renewal of CU400615.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137537&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000137537 | C40-LX-GA-HAY POINT-0.066 | LX006470 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28826 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA0 | 0.068 | GA01BA0 | 0.068 | KM | 6 |  |  |  | 0.066 |  | 2026-06-30 | BURTON MINE ACCESS RIAD |  |  |  | 2.16 | 2.3 | 2 | 3.58 | 1 | 7.73 | 5706 | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120608&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120608 | C58-LX-GA-JILALAN-28.84km | LX003500 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | JILALAN | YUKAN | 0 | KM | GA01ML28 | 0.8399 | GA01ML28 | 0.8399 | KM |  |  |  |  | 28.84 | 28.84 | 2026-06-30 | BORGS ACCESS RD |  |  |  | 3.2 | 4.2 | 2 | 4 | 1 | 12.8 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY25 Design for FY27 Renewal. QR to be informed by the project team about this upcoming works. The Borgs (the property owner) to be advised by Community Engagement about the work in due course. Although there are seven tracks, renewal works to be completed for Goonyella Up and Down tracks only.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120600&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000120600 | C58-LX-BW-MT LARCOM-570.366km | LX000640 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | MOUNT LARCOM | EPALA | 0 | KM | BW01ML570 | 0.3659 | BW01ML570 | 0.3659 | KM |  |  | 570.366 | 570.366 | 570.366 | 570.366 | 2026-06-30 | DARTS CREEK ROAD |  |  |  | 3.16 | 4.1 | 2 | 3.92 | 1 | 12.39 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | PCR 5858 for the integrated work with TOs. FY27 Renewal. FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120609&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000120609 | C58-LX-BW-MT LARCOM-576.77km | LX005586 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | MT LARCOM | EPALA | 0 | KM | BW01ML576 | 0.773 | BW01ML576 | 0.773 | KM |  |  |  |  | 576.77 | 576.77 | 2026-06-30 | EPALA LANE |  |  |  | 3.2 | 4.1 | 2 | 4 | 1 | 12.8 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Crossing km was reviewed and found to be 576.773km. ID640 and ID1717 took priority in FY24 over ID5586. Moved ID5586 to FY25 Design based on the discussion on 11 July 2022 with the Gracemere district.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137534&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000137534 | C58-LX-GA-NORWICH PARK-120.716 | LX003629 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM | 2 |  |  |  | 120.756 | 120.756 | 2026-06-30 | BOOROONDARRA ROAD |  |  |  | 10 | 1.5 | 2 | 10 | 1 | 100 | 5706 | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120611&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120611 | C58-LX-BW-WALTON-163.87km | LX005562 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML163 | 0.9579 | BW03ML163 | 0.9579 | KM |  |  |  |  | 163.87 | 163.87 | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 2 | 3.4 | 2 | 4 | 1 | 7.32 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY25 DESIGN FOR FY27 CONSTRUCTION.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103555&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000103555 | C58-LX-BW-BOORGOON-34.95km | LX006954 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML34 | 0.913 | BW06ML34 | 0.913 | KM |  |  |  |  | 34.95 | 34.95 | 2026-06-30 | HUMBOLDT ROAD |  |  |  | 4.6 | 2.3 | 2 | 3.16 | 1 | 14.7 | 5758 | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 22.09.2023 Civil Assets spoke with IM about the timing of renewal. IM advised this crossing could be delayed to FY28. This crossing was showing severe ballast and geometry defects and undercut in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051965&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000051965 | C58-LX-NL-BUCKLEY-15.516km | LX003279 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Newlands | BUCKLEY | ARMUNA | 0 | KM | NL01ML15 | 0.516 | NL01ML15 | 0.516 | KM |  |  |  |  | 15.516 | 15.516 | 2026-06-30 | 88A BOWEN DEVELOPMENT ROAD |  |  |  | 3.5 | 1.7 | 2 | 3 | 1 | 10.5 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | IV.00459 | 20260630 | * 20.02.2020 11:25:51 AUSQLD Sharbaree Biswas (R865006) * This crossing is having an undercut in 2020. The crossing will be monitored over the next several years and thus renewal if required is delayed till FY23. 20.02.2020 11:25:51 AUSQLD Sharbaree Biswas (R865006) This crossing is having an undercut in 2020. The crossing will be monitored over the next several years and thus renewal if required is delayed till FY23. delayed till FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123457&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000123457 | C40-LX-GA-168.375km | LX020259 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | BURTON DOWNS | MALLAWA | 0 | KM | GA01ML168 | 0.375 | GA01ML168 | 0.375 | KM |  |  |  |  | 168.375 | 168.375 | 2028-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CIVIL DESIGN -IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101684&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000101684 | C58-LX-MA-CALLE-22.165km | LX005755 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML22 | 0.164 | MA01ML22 | 0.164 | KM |  | 5758 |  |  | 22.165 | 22.165 | 2026-06-30 | JIM WHYTE WAY |  |  |  | 3.9 | 2.6 | 2 | 3 | 1 | 12.87 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Moved to FY26 IFP for fund limit. Kept in FY24 Design for FY27 Renewal as per the discussion with Geoff on 5 Sept <(>&<)> previous mtgs with other IM team and asset management team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104127&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | FUTURE SCOPE | NON-COAL | 002000104127 | C58-LX-BW-COMET-242.435km | LX001087 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | COMET | YAMALA | 0 | KM | BW03ML242 | 0.4359 | BW03ML242 | 0.4359 | KM |  |  |  |  | 242.435 | 242.435 | 2026-06-30 | BONNIE DOON ROAD |  |  |  | 4.4 | 1.7 | 2 | 3 | 1 | 13.2 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133823&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000133823 | C58-LX-GA-MINDI-127.043km | LX006644 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | MINDI | SOUTHWALKER | 0 | KM | GA01ML127 | 0.0429 | GA01ML127 | 0.0429 | KM |  |  |  |  | 127.043 | 127.043 | 2028-06-30 | MINE ACCESS ROAD |  |  |  | 3.5 | 4 | 2 | 3.9 | 1 | 13.65 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 DESIGN-IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127629&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000127629 | C58-LX-BW-WALTON-166.675km | LX005563 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML166 | 0.675 | BW03ML166 | 0.675 | KM |  |  |  |  | 166.675 | 166.675 | 2026-06-30 | ROCKVIEW ROAD |  |  |  | 3.9 | 3.64 | 2 | 3.8 | 1 | 13.68 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 DESIGN-IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044032&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044032 | C58-LX-MA-BILOELA-JAMBIN Rd-128.396km | LX006025 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1340000 | Moura | BILOELA - JAMBIN ROAD |  | 0 | KM | MA01ML128 | 0.399 | MA01ML128 | 0.399 | KM | 2 |  |  |  | 128.396 | 128.396 | 2026-06-30 |  |  |  |  | 3.4 | 1.1 | 2 | 3 | 1 | 10.2 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Civil renewal (this N4 2000044032) is to be aligned with FY26 signal upgrade (N4-2000123422).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044030&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044030 | C58-LX-BW-BLUFF-171.08km | LX005564 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1438067 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML171 | 0.08 | BW03ML171 | 0.08 | KM | 4 |  | 171.08 | 171.08 | 171.08 | 171.08 | 2026-06-30 | UNNAMED ROAD |  |  |  | 3.1 | 3.35 | 2 | 4 | 1 | 12.4 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 15.01.2020 12:59:14 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY24 due to low priority 15.01.2020 12:59:14 AUSQLD Sanjna Rajagopalan (R884639) Moved from FY22 to FY24 due to low priority.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104895&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000104895 | C58-LX-MA-CALLE-533.897km | LX000708 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1679000 | Moura | CALLEMONDAH | YARWUN | 0 | KM | NC02ML533 | 0.893 | NC02ML533 | 0.893 | KM | 2 |  |  |  | 533.897 | 533.897 | 2026-06-30 | CALLEMONDAH DRIVE NCL |  |  |  | 3.3 | 4.8 | 2 | 4 | 1 | 13.74 | 5471 | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | PCR 5471. LX000708 (NCL) to be renewed together with LX006090 (MA N4 2000101687). All docs for supporting the IFP have been added.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101060&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000101060 | C58-LX-NL-DURROBURRA-1159.574km | LX007195 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1325905 | Newlands | DURROBURRA | KAILI | 0 | KM | NC03ML1159 | 0.5729 | NC03ML1159 | 0.5729 | KM | 4 |  |  |  | 1159.574 | 1159.574 | 2026-06-30 | DRY CKEEK ROAD |  |  |  | 3.6 | 3.2 | 2 | 4 | 1 | 14.4 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | The precedence has been set that a Level Crossing which supports and enables a critical part of the coal industry forms part of CQCN Coal fundings. This has been updated now from Non-Coal to Coal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101989&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000101989 | C58-LX-GA-HAY POINT-5.518km | LX020011 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1438067 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA5 | 0.506 | GA01BA5 | 0.506 | KM | 4 |  |  |  | 5.518 | 5.518 | 2026-06-30 | ACCESS RD HAY PT ARRIVAL |  |  |  | 3.6 | 2.3 | 2 | 3 | 1 | 10.8 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101687&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000101687 | C58-LX-MA-PARANA-10.354km | LX006090 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 859655 | Moura | PARANA | CALLEMONDAH | 0 | KM | MA01ML10 | 0.3569 | MA01ML10 | 0.3569 | KM | 4 |  |  |  | 10.355 | 10.355 | 2026-06-30 | CALLEMONDAH DRIVE |  |  |  | 4.3 | 1.3 | 2 | 3 | 1 | 12.9 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | To be renewed in FY26 in conjunction with LX000708 (N4 2000104895)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101061&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000101061 | C58-LX-BW-RAGLAN-588.78km | LX001717 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1348965 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW01ML588 | 0.778 | BW01ML588 | 0.778 | KM | 4 |  |  |  | 588.78 | 588.78 | 2026-06-30 | TWELVE MILE ROAD |  |  |  | 3.4 | 4.9 | 2 | 4 | 1 | 14.28 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135364&DY_MAB=X&~OKCODE=ONLI | FY26 | RIM Infrastructure | BASELOAD | RIM | 002000135364 | C58-LX-QAL-NC-04ML-1.125km | LX000785 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1000000 | Moura | SOUTH GLADSTONE | QAL | 0 | KM | NC04ML1 | 0.127 | NC04ML1 | 0.127 | KM | 2 |  | 0.22 | 0.22 | 1.125 | 1.125 | 2027-06-30 | QAL ACCESS ROAD |  |  |  | 3.5 | 2.3 | 2 | 2.3 | 1 | 7.86 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Non-RIG renewal.To be designed in FY25 (IFP <(>&<)> IFP).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044062&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044062 | C58-LX-BW-WARREN-36.715km | LX001079 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1438067 | Blackwater | WARREN | WYCARBAH | 0 | KM | BW03ML36 | 0.7099 | BW03ML36 | 0.7099 | KM | 4 |  | 36.715 | 36.715 | 36.715 | 36.715 | 2026-06-30 | ROSEWOOD ROSE |  |  |  | 3.4 | 3.35 | 2 | 4 | 1 | 13.6 |  | 2024-03-28 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 11.11.2020 13:15:30 AUSQLD Sharbaree Biswas (R865006) * Renewed in FY16 and thus delayed till FY25. * 01.12.2020 10:05:13 AUSQLD Sharbaree Biswas (R865006) * Renewed in FY16 and thus delayed till FY25. TO BE DESIGNED IN FY24 FOR RENEWAL IN FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083400&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000083400 | C58-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 220000 | Goonyella | GA | GA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  | 2 | 25 | 1 | 25 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FY26 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123421&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000123421 | C58-LX-GA-NORWICH PARK-120.756km | LX003629 | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 228912 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM |  |  |  |  | 120.756 | 120.756 | 2026-06-30 |  |  |  | DESIGN SIGNAL | 10 | 1.5 | 2 | 10 | 1 | 100 |  | 2024-03-28 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123422&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000123422 | C58-LX-MA-EARLSFIELD-128.396km | LX006025 | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML128 | 0.396 | MA01ML128 | 0.396 | KM |  |  |  |  | 128.396 | 128.396 | 2026-06-30 |  |  |  | UPGRADE SIGNAL | 4.5 | 1.1 | 2 | 10 | 1 | 13.5 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123423&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000123423 | C58-LX-MA-EARLSFIELD-0.225km | LX006554 | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Moura | EARLSFIELD | CALLIDE | 0 | KM | MA02ML0 | 0.224 | MA02ML0 | 0.224 | KM | 0 |  |  |  | 0.225 | 0.225 | 2026-06-30 |  |  |  | UPGRADE SIGNAL | 4.5 | 1 | 2 | 10 | 1 | 11 |  | 2024-03-28 |  | Level Crossing Other | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138516&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138516 | Non Coal Reactive Renewals - Rail | BW | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138517&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138517 | Non Coal Reactive Renewals - Rail | GA | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138518&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138518 | Non Coal Reactive Renewals - Rail | MA | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138519&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138519 | Non Coal Reactive Renewals - Rail | NL | CIVIL | RAIL |  | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135555&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000135555 | TRACK RENEWALS FIX ON FAIL | MA | CIVIL | RAIL |  | REACTIVE WORKS | 0 | LUMPSUM | 35000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FoF/Reactive for Moura System - All rail/sleepers/ track upgrade reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135583&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000135583 | TRACK RENEWALS FIX ON FAIL | NL | CIVIL | RAIL |  | REACTIVE WORKS | 0 | LUMPSUM | 35000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FoF/Reactive for Newlands System - All rail/sleepers/ track upgrade
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130675&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130675 | C17 ALDOGA 551.428 - 552.319 | BW-01ML | CIVIL | RAIL |  | RENEWAL | 1.836 | RAIL KM | 828647 | Blackwater | ALDOGA | YARWUN | 0.892 | KM | BW01ML551 | 0.4279 | BW01ML552 | 0.319 | KM | 17 |  | 1.836 | 0.892 | 551.428 | 552.319 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 4.1 | 0.1 | 3.5 | 1 | 13.3 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138523&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138523 | C17 NL COLLINSVILLE 76.272 - 76.595 | NL-01ML | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 292464 | Newlands | ALMOOLA | COLLINSVILLE | 0.3099 | KM | NL01ML76 | 0.2849 | NL01ML76 | 0.5949 | KM | 6 |  | 0.648 | 0.323 | 76.272 | 76.595 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 2.5 | 1 | 2.7 | 1 | 9.45 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Removing 53kg SC Max wear measurements (%) : Low leg 40/55 <(>&<)> high leg 22/45 Overall wear rate (mm/yr): Low leg 1.5 <(>&<)> high leg 0.7 Weld (km) : GIJ @ 76.584 Defect : Worn Low leg, multiple TD's Required rail : 60 kg Post Site Walkouts Extended cut-in point to ensure the cut-out point is past the curve spring.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137310&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000137310 | C17 NL ARMUNA 31.570 - 32.400 | NL-01ML | CIVIL | RAIL |  | RENEWAL | 1.728 | RAIL KM | 799903 | Newlands | ARMUNA | ABERDEEN | 0.8289 | KM | NL01ML31 | 0.5699 | NL01ML32 | 0.4 | KM | 16 |  | 1.728 | 0.829 | 31.56 | 32.4 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 1.7 | 1 | 2.2 | 1 | 7.7 | 278 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | This is a desktop scope only, rail type and wear at cut in and cut out need to be determined during site walkouts, scope drive is to remove rail that has shelling in it and 53kg rail in tangent.will have to assess rail within level crossing to see what condition it is and if it can be skipped Post Site Walkout: 64m of rail already on site. Scope extended to tie into new rail at this location.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130702&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130702 | C17 AROONA 103.800 -104.86 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 2.16 | RAIL KM | 974879 | Blackwater | AROONA | DUARINGA | 1.068 | KM | BW03ML103 | 0.8 | BW03ML104 | 0.8599 | KM | 20 |  | 2.16 | 1.06 | 103.8 | 104.86 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133924&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133924 | C17 MA BELDEEN 155.440 - 156.750 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 2.7 | RAIL KM | 1218599 | Moura | BELLDEEN | MOURA MINE | 1.3129 | KM | MA01ML155 | 0.44 | MA01ML156 | 0.75 | KM | 25 |  | 2.7 | 1.313 | 155.44 | 156.75 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.1 | 1 | 1.6 | 1 | 6.08 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver for this scope is wear, high leg is at 14mm/19mm, wearing at 0.5mm/year There is some shelling between 156.656km to 156.684km, TDW 10mm 2019 Replacing 1997 SC rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133925&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133925 | C17 MA BELDEEN 156.750 - 157.420 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 633672 | Moura | BELLDEEN | MOURA MINE | 0.67 | KM | MA01ML156 | 0.75 | MA01ML157 | 0.4199 | KM | 13 |  | 1.404 | 0.67 | 156.75 | 157.42 | 2026-06-30 | SINGLE | BOTH |  |  | 3.6 | 1.1 | 1 | 1.6 | 1 | 5.76 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver for this scope is rail wear, High leg is at 16mm/19mm wearing at 0.5mm/year Defect : TDW 10mm 2019 replacing 60kg 1997 sc rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133928&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133928 | C17 MA BELDEEN 158.770 - 159.490 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 682415 | Moura | BELLDEEN | MOURA MINE | 0.7219 | KM | MA01ML158 | 0.77 | MA01ML159 | 0.4899 | KM | 14 |  | 1.512 | 0.722 | 158.77 | 159.49 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.1 | 1 | 1.6 | 1 | 6.08 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver of scope is rail wear High leg is 15mm/19mm, wearing at 0.4mm/year Side wear also present RCF in Both rails Replacing 60kg 1997 SC rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070778&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000070778 | C17 BLACK MT 40.970 - 43.628 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 5.4 | RAIL KM | 2437198 | Goonyella | BLACK MOUNTAIN | HATFIELD | 2.6619 | KM | GA02ML40 | 0.9699 | GA02ML43 | 0.628 | KM | 50 |  | 5.4 | 2.662 | 40.97 | 43.63 | 2026-06-30 | UP | BOTH |  |  | 4.5 | 5 | 1 | 3.9 | 1 | 17.55 | 281 | 2024-03-28 | 2021-10-05 | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | * 19.03.2021 15:36:10 AUSQLD Sanjna Rajagopalan (R884639) * Re Rail Only * 2 Curves = 2 notifications: * 2000070778 -this one has all qtys * * 41.391 - 41.900 - UP 5.5 rails * cut in and cut outs are different for both legs * * cant review required on both curves * tie left rail into FY22 RRP starting 41.900km * 19.03.2021 15:44:31 AUSQLD Sanjna Rajagopalan (R884639) * 2000071027 Post Site Walkout: Start Km changed to tie in with TOS 12A/B Pts
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131101&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131101 | C17 BLACK MOUNTAIN 43.765 - 44.520 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 682416 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.751 | KM | GA02ML43 | 0.765 | GA02ML44 | 0.52 | KM | 15 |  | 1.512 | 0.751 | 43.765 | 44.52 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Q1 Execution
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080695&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000080695 | C17 BOLINGBROKE 62.074 - 62.560 | CV002960 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 438696 | Goonyella | BOLINGBROKE | BALOOK | 0.4859 | KM | GA02ML62 | 0.0739 | GA02ML62 | 0.56 | KM | 9 |  | 0.972 | 0.486 | 62.074 | 62.56 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 | 292 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Site Walkouts: Start and end points reduced to tie into rail with minimal wear on a tangent. Reduced by 2 rails.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135585&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal GAPE Traffic | BASELOAD | COAL | 002000135585 | C17 NL BRIABA 57.899KM - 58.607KM | NL-03ML | CIVIL | RAIL |  | RENEWAL | 1.512 | RAIL KM | 682415 | Newlands | BRIABA DOWN ROAD | BRIABA DOWN ROAD | 0.7079 | KM | NL03ML57 | 0.899 | NL03ML58 | 0.6069 | KM | 14 |  | 1.512 | 0.708 | 57.899 | 58.607 | 2026-06-30 | DOWN | BOTH |  |  | 4 | 1.7 | 1 | 2.2 | 1 | 8.36 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver of this scope is multiple defects on rail head due to poor grinding/missed grinding cycles. Rail is breaking out and gauge face shelling throughout scope. Post site walkouts: Updated the linear data to reflect the full length of a rail.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135586&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal GAPE Traffic | BASELOAD | COAL | 002000135586 | C17 NL BRIABA 59.094 - 61.226 | NL-03ML | CIVIL | RAIL |  | RENEWAL | 4.32 | RAIL KM | 1949759 | Newlands | BRIABA DOWN ROAD | BRIABA DOWN ROAD | 3.394 | KM | NL03ML57 | 0.8319 | NL03ML61 | 0.226 | KM |  |  | 4.32 | 40 | 59.094 | 61.226 | 2026-12-31 | 2.132 | BOTH |  |  | 4 | 1.7 | 1 | 2.2 | 1 | 8.36 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver of this scope is multiple defects on rail head due to poor grinding/missed grinding cycles. Rail is breaking out and gauge face flow and head pitting throughout scope. Post site walkouts: Updated Kms to tie into FY23 Scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135587&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal GAPE Traffic | BASELOAD | COAL | 002000135587 | C17 NL BRIABA DN 62.707 - 64.530 | NL-03ML | CIVIL | RAIL |  | RENEWAL | 3.672 | RAIL KM | 1657295 | Newlands | BRIABA DOWN ROAD | BRIABA DOWN ROAD | 1.8229 | KM | NL03ML62 | 0.7069 | NL03ML64 | 0.53 | KM | 34 |  | 3.672 | 1.832 | 62.707 | 64.53 | 2026-12-31 | DOWN | BOTH |  |  | 4 | 1.7 | 1 | 2.2 | 1 | 8.36 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver of this scope is multiple defects starting to form due to poor grinding/missed grinding cycles. Rail is breaking out field side flow through out scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134009&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000134009 | C17 MA Callide 14.40 - 14.56 | MA-07ML | CIVIL | RAIL |  | RENEWAL | 0.324 | RAIL KM | 146232 | Moura | DAKENBA | CALLIDE | 0.16 | KM | MA07ML14 | 0.4 | MA07ML14 | 0.56 | KM | 3 |  | 0.324 | 0.16 | 14.4 | 14.56 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Scope driver is removing 47kg rail - need to finalize
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131088&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131088 | C17 PRAGUELANDS 10.790 - 11.214 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 389952 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0.4169 | KM | GA02ML10 | 0.79 | GA02ML11 | 0.2139 | KM | 8 | 0 | 0.864 | 0.424 | 10.79 | 11.214 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 4.6 | 1 | 3.7 | 1 | 14.06 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131104&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131104 | C17 DALY BAY 3.044 - 3.963 | GA-03BA | CIVIL | RAIL |  | RENEWAL | 1.838 | RAIL KM | 828647 | Goonyella | DALY BAY ARRIVAL | DALY BAY ARRIVAL | 0.919 | KM | GA03BA3 | 0.0439 | GA03BA3 | 0.9629 | KM | 17 |  | 1.838 | 0.919 | 3.044 | 3.963 | 2026-06-30 | ARRIVAL ROAD | BOTH |  |  | 3.5 | 2.3 | 1 | 2.6 | 1 | 9.1 | 278 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Rail in poor condition - squats, field side flow, RCF, wear 6 Bolt GIJ (right leg) @ 3.858km Signal DL39 Axle Counter @ 3.878km tie in to FY25 renewal @ 3.028km tie in to back of 45CD Pts @ 3.967km Post Site Walkouts: Reduced from 18 rails to 17 rails to tie into FY24 scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130704&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130704 | C17 DUARINGA 105.815 - 106.65 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.728 | RAIL KM | 779903 | Blackwater | DUARINGA | WALLAROO | 0.8679 | KM | BW03ML105 | 0.8149 | BW03ML106 | 0.65 | KM | 16 |  | 1.728 | 0.835 | 105.815 | 106.65 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058454&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000058454 | C17 DUARINGA 106.65 - 107.097 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 438696 | Blackwater | DUARINGA | WALLAROO | 0.448 | KM | BW03ML106 | 0.65 | BW03ML107 | 0.097 | KM | 9 |  | 0.972 | 0.447 | 106.65 | 107.097 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000061296&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000061296 | C17 DUARINGA 107.097 - 107.595 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Blackwater | DUARINGA | WALLAROO | 0.4979 | KM | BW03ML107 | 0.097 | BW03ML107 | 0.5949 | KM | 10 |  | 1.08 | 0.498 | 107.097 | 107.595 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063098&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000063098 | C17 DUARINGA 107.595 - 107.950 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 341208 | Blackwater | DUARINGA | WALLAROO | 0.3549 | KM | BW03ML107 | 0.5949 | BW03ML107 | 0.9499 | KM | 7 |  | 0.756 | 0.355 | 107.595 | 107.95 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130705&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130705 | C17 DUARINGA 107.950 - 108.382 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 389952 | Blackwater | DUARINGA | WALLAROO | 0.4329 | KM | BW03ML107 | 0.9499 | BW03ML108 | 0.382 | KM | 8 |  | 0.864 | 0.432 | 107.95 | 108.382 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063084&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000063084 | C17 DUARINGA 108.700 - 109.487 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.62 | RAIL KM | 731159 | Blackwater | DUARINGA | WALLAROO | 0.792 | KM | BW03ML108 | 0.6999 | BW03ML109 | 0.4869 | KM | 15 |  | 1.62 | 0.787 | 108.7 | 109.487 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131110&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131110 | C17 GERMAN CREEK 135.392 - 135.770 | GA-22ML | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 341208 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.378 | KM | GA22ML135 | 0.392 | GA22ML135 | 0.77 | KM | 7 |  | 0.756 | 0.378 | 135.392 | 135.77 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.2 | 1 | 1.7 | 1 | 6.46 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Scope Walkout: Start and end KMs changed to cut into the back of ER1 and run rail out towards the loadout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131111&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131111 | C17 GERMAN CREEK 135.792 - 136.437 | GA-22ML | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 584928 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0.656 | KM | GA22ML135 | 0.792 | GA22ML136 | 0.4369 | KM | 12 |  | 1.293 | 0.641 | 135.792 | 136.437 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.2 | 1 | 1.7 | 1 | 6.46 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Scope Walkouts: Start and end KMs changed to tie into back of turnout.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070856&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000070856 | C17 BW GRANTLEIGH 74.040 - 74.580 | CV006181 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Blackwater | GRANTLEIGH | TUNNEL | 0.54 | KM | BW03ML74 | 0.04 | BW03ML74 | 0.5799 | KM | 10 |  | 1.08 | 0.54 | 74.04 | 74.58 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063093&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000063093 | C17 GRANTLEIGH 74.647 - 75.140 | CV006183 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Blackwater | GRANTLEIGH | TUNNEL | 0.313 | KM | BW03ML74 | 0.811 | BW03ML75 | 0.1229 | KM | 10 |  | 1.08 | 0.493 | 74.647 | 75.14 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058446&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000058446 | C17 GRANTLEIGH 75.140 - 75.440 | CV006185 | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 292464 | Blackwater | GRANTLEIGH | TUNNEL | 0.2819 | KM | BW03ML75 | 0.158 | BW03ML75 | 0.44 | KM | 6 |  | 0.648 | 0.3 | 75.14 | 75.44 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | CRWO |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137555&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137555 | C17 BW TUNNEL 75.432 - 75.951 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Blackwater | GRANTLEIGH | TUNNEL | 0.519 | KM | BW03ML75 | 0.4319 | BW03ML75 | 0.9509 | KM |  |  | 1.08 | 0.519 | 75.433 | 75.951 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | This curve hsitoically had high war, removing rail as RC will require additonal grinding whcih will accelerate CETS limit being reached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131112&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131112 | C17 HATFIELD 54.081 - 56.166 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 4.212 | RAIL KM | 1901015 | Goonyella | HATFIELD | BOLINGBROKE | 2.0889 | KM | GA02ML54 | 0.081 | GA02ML56 | 0.166 | KM | 39 |  | 4.212 | 2.089 | 54.081 | 56.166 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 | 287 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Renewal driver is Fatigue Post Site Walkouts: Increase KMs to include some of Notification 2000131115, and close out other notifications. Good rail from 53.652-54.081km - no need to replace. Increase from 13 Rail to 39 Rails with combined scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131113&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131113 | C17 HATFIELD 56.916 - 58.305 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 2.808 | RAIL KM | 1267343 | Goonyella | HATFIELD | BOLINGBROKE | 1.3999 | KM | GA02ML56 | 0.915 | GA02ML58 | 0.3049 | KM | 26 |  | 2.808 | 1.39 | 56.916 | 58.306 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071014&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000071014 | C17 GA HATFIELD 58.36-59.068 | CV002954 | CIVIL | RAIL |  | RENEWAL | 1.404 | RAIL KM | 633672 | Goonyella | HATFIELD | BOLINGBROKE | 0.7009 | KM | GA01ML58 | 0.3599 | GA01ML59 | 0.068 | KM | 13 |  | 1.404 | 0.708 | 58.36 | 59.068 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Rail Wear based scope - RCA based wear limits on S.C rail. Zop's notes have this curve as HH rail. Wear limit is 21mm. 14mm in November 2022. Wearing at 0.9mm/yr Must be done first half FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131114&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131114 | C17 BOLINGBROKE 59.119 - 60.447 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 2.7 | RAIL KM | 1218599 | Goonyella | HATFIELD | BOLINGBROKE | 1.348 | KM | GA02ML59 | 0.1189 | GA02ML60 | 0.447 | KM | 25 |  | 2.7 | 1.348 | 59.119 | 60.447 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 | 288 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Scope Walkout: Start KM moved out to tie into good condition rail - reduced by 1 rail.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131117&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131117 | C17 HAY POINT 0.071 - 0.41 | GA-01BA | CIVIL | RAIL |  | RENEWAL | 0.756 | RAIL KM | 341208 | Goonyella | HAY POINT BALLOON ARRIVAL 1 | HAY POINT BALLOON ARRIVAL 1 | 0.339 | KM | GA01BA0 | 0.0709 | GA01BA0 | 0.4099 | KM | 7 |  | 0.41 | 0.071 | 0.071 | 0.41 | 2026-06-30 | ARRIVAL ROAD 1 | BOTH |  |  | 3.5 | 2.3 | 1 | 2.6 | 1 | 9.1 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | "Hay Point Arrival Road 2 Removing 2012 rail 60kg H One Steel both legs Corrossion driven - coastal location making the rail suceptible to corrossoion 28T Pandrol E Clip 2011 - no need to replace Condition is around 3.5 currently - can be completed any time in FY26 - do not push to FY27"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131116&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131116 | C17 HAY POINT 0.07 - 0.453 | GA-02BA | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 389952 | Goonyella | HAY POINT BALLOON ARRIVAL 2 | HAY POINT BALLOON ARRIVAL 2 | 0.383 | KM | GA02BA0 | 0.07 | GA02BA0 | 0.453 | KM | 8 |  | 0.864 | 0.383 | 0.07 | 0.453 | 2026-06-30 | ARRIVAL ROAD 2 | BOTH |  |  | 3.5 | 2.3 | 1 | 2.6 | 1 | 9.1 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | "Hay Point Arrival Road 1 Removing 2012 rail 60kg H One Steel both legs Corrossion driven - coastal location making the rail suceptible to corrossoion 28T Pandrol E Clip 2011 - no need to replace Gauge face flow Field side flow Re railing through the greaser @ 0.400km Condition is around 3.5 currently - can be completed any time in FY26 - do not push to FY27"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063283&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000063283 | C17 JILALAN 20.640 - 20.855 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.432 | RAIL KM | 194976 | Goonyella | JILALAN | YUKAN | 0.2149 | KM | GA02ML20 | 0.64 | GA02ML20 | 0.8549 | KM | 4 |  | 0.432 | 0.215 | 20.64 | 20.855 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 4.8 | 1 | 3.8 | 1 | 14.44 | 280 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | * 13.08.2020 14:46:03 AUSQLD Milton Saha (R884640) * 1. Rail Renewal FY22 Brought Forward * 2. 41.144-41.225 Q4 * 3. Black Mountain Up Road * 4. 11 Rails * 5. Tech Scope to be checked by AC * 16.10.2020 08:51:37 AUSQLD Milton Saha (R884640) * * RRP GA41.110km-41.272km Black Mountain UP [3 rails] * Change: Push back this job to FY25 and Start/end KMs have been refined (41.110-41.272km * oReason: Renewal not required due to condition * oAction: Construction date is 28th of September 2021 – Scope to therefore be cancelled (Within a 36 hr closure) – PM’s to confirm ca = ncellation and reallocate resources Post Site Walkouts: Scope reduced as rail on a tangent was in good condition with minimal wear - reduced by 1 rail.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107950&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000107950 | C17 GA MCARTHUR 142.316 - 142.583 | CV003052 | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 243720 | Goonyella | MCARTHUR | COPPABELLA | 0.267 | KM | GA02ML142 | 0.316 | GA02ML142 | 0.5829 | KM | 5 |  | 0.54 | 0.267 | 142.316 | 142.583 | 2026-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 | 291 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Site Walkout: Scope increased to 5 rails from 4 to tie into the back of 7A/B pts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138010&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000138010 | C17 MIDGEE 627.626 - 628.700 | BW-01ML | CIVIL | RAIL |  | RENEWAL | 2.052 | RAIL KM | 926135 | Blackwater | MIDGEE | ROCKLANDS | 0.9869 | KM | BW01ML627 | 0.626 | BW01ML628 | 0.6099 | KM | 19 |  | 2.052 | 0.987 | 627.626 | 628.61 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 4.5 | 1 | 3.7 | 1 | 14.06 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Max wear measurements (%) : Low Leg 35.5/55, High Leg 35.5/55 Maximum measurement (mm) : Low Leg 14.5/23, High Leg 14.5/23 Overall wear rate (mm/yr) : Low Leg 0.7, High Leg 0.6 Defect : Multiple UTI Defects Required rail : 60KG HH Near Abouts : LX988 @ 628.727, Culverts @ 628.580, 680.527, 628.295 ,627.900,627.810, 627.580. DED @ 628.513.Comments : Gladstone side tying into FY26 <(>&<)> Rockhampton side partially renewed with LX renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131119&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131119 | C17 MILLENIUM 18.92 - 20.855 | GA-03ML | CIVIL | RAIL |  | RENEWAL | 3.888 | RAIL KM | 1754783 | Goonyella | MILLENIUM | RED MOUNTAIN | 1.9299 | KM | GA03ML18 | 0.92 | GA03ML20 | 0.8549 | KM | 36 |  | 3.888 | 1.935 | 18.92 | 20.855 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 2.5 | 1 | 2.7 | 1 | 9.45 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058704&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000058704 | C17 MOUNT MILLER 544.740 - 545.278 | CV005685 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Blackwater | MOUNT MILLER | YARWUN | 0.44 | KM | BW01ML544 | 0.759 | BW01ML545 | 0.2 | KM | 10 |  | 1.08 | 0.54 | 544.738 | 545.278 | 2026-06-30 | UP |  |  |  | 3.8 | 3.8 | 0.1 | 3.4 | 1 | 12.92 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | MEDIUM | LOW | LOW | Outstanding notification | CRWO |  | 20260630 | Max wear measurements (%) : Low Leg 25/50, High Leg 17.5/46 Maximum measurement (mm) : Low Leg 10.5/21, High Leg 7/19 Overall wear rate (mm/yr) : Low Leg 1.8, High Leg 1.2 Defect : RCF Defect on Low leg rail, refer photos. Side wear on High Leg Required rail : 60KG HH Culverts @ 544.770, 545.040, 545.290. Housings @ 545.210, 544.947. Signals @ YN16, YN12P, YN28. DED @ 544.719, Axle Counter @ 544.850. Post Site Walkouts: Change to start KMs.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135480&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000135480 | C17 MA MOUNT RAINBOW 89.260 - 89.540 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 243720 | Moura | MOUNT RAINBOW | FRY | 0.27 | KM | MA01ML89 | 0.26 | MA01ML89 | 0.53 | KM | 5 |  | 0.54 | 0.27 | 89.26 | 89.53 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver of this scope is rail wear, paired with high critical section of the network and removing 1996 60kg sc rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138918&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138918 | C17 GA PEAK DOWNS LR 46.050-46.970 | GA-17ML | CIVIL | RAIL |  | RENEWAL | 0.92 | RAIL KM | 438695 | Goonyella | PEAK DOWNS BALLOON | PEAK DOWNS BALLOON | 0.92 | KM | GA17ML46 | 0.05 | GA17ML46 | 0.9699 | KM | 9 |  | 0.92 | 0.92 | 46.05 | 46.97 | 2026-06-30 | EXIT | BOTH |  |  | 4 | 1.1 | 1 | 1.6 | 1 | 6.4 | 284 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope is for re rail after exit side of loadout cut in point is end of FY23 track upgrade cut out point is end if CV3313 Post Scope Walkouts: Reducing the scope to only have the left rail being renewed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138970&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138970 | C17 GA PEAK DOWNS 47.292- 47.515 | GA-17ML | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 243720 | Goonyella | PEAK DOWNS BALLOON | PEAK DOWNS BALLOON | 0.2429 | KM | GA17ML47 | 0.272 | GA17ML47 | 0.515 | KM | 5 |  | 0.54 | 0.223 | 47.272 | 47.515 | 2026-06-30 | ENTRY | BOTH |  |  | 3.8 | 1.1 | 1 | 1.6 | 1 | 6.08 | 285 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Scope is for re rail only on entry side of load out Cut in - Tangent this after CV3314 Cut out - Tying into FY23 track upgrade job before loadout Start on low chainge end Post Scope Walkouts: Masts on site did not match tech scope kms. Scope reduced due to rail condition and is now ending after a greaser where pandrol e-clips end. Equality present 47.438km = 45.700km at the entry road overpass.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131089&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000131089 | C17 PRAGUELANDS 17.647 - 18.265 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 584928 | Goonyella | PRAGUELANDS | JILALAN | 0.6109 | KM | GA02ML17 | 0.647 | GA02ML18 | 0.265 | KM | 12 |  | 1.296 | 0.618 | 17.647 | 18.265 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 4.6 | 1 | 3.7 | 1 | 14.06 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110749&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000110749 | C17 BW WARREN 23.168 - 23.327 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.324 | RAIL KM | 146232 | Blackwater | STANWELL | WARREN | 0.159 | KM | BW03ML23 | 0.168 | BW03ML23 | 0.327 | KM | 3 |  | 0.342 | 0.159 | 23.168 | 23.326 | 2026-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 12 | 264 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | This one is between LX1735 and Warren 101A Pts
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110790&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000110790 | C17 BW WARREN 23.361 - 23.542 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.432 | RAIL KM | 194976 | Blackwater | STANWELL | WARREN | 0.1809 | KM | BW03ML23 | 0.3609 | BW03ML23 | 0.542 | KM | 4 |  | 0.432 | 0.181 | 23.361 | 23.542 | 2026-06-30 | DOWN | BOTH |  |  | 3.5 | 3.35 | 1 | 3.2 | 1 | 12 | 264 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | This one is between Warren 101A and 102B Pts
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134003&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000134003 | C17 MA STOWE 23.040 - 23.480 | MA-01ML | CIVIL | RAIL |  | RENEWAL | 0.864 | RAIL KM | 389952 | Moura | STOWE | GRAHAM | 0.44 | KM | MA01ML23 | 0.04 | MA01ML23 | 0.4799 | KM | 8 |  | 0.864 | 0.44 | 23.04 | 23.48 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.3 | 1 | 1.8 | 1 | 6.84 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Scope driver is wear and removing 60kg SC 1996 rail
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070851&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000070851 | C17 BW TUNNEL 77.725-78.707 | CV006194 | CIVIL | RAIL |  | RENEWAL | 2.052 | RAIL KM | 926135 | Blackwater | TUNNEL | EDUNGALBA | 0.9869 | KM | BW03ML77 | 0.7249 | BW03ML78 | 0.7069 | KM | 19 |  | 2.052 | 0.987 | 77.725 | 78.707 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.75 | 1 | 3.4 | 1 | 12.92 | 5656 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | High wear location. Previous re rails covering these extents: 77.687-78.661km (14/08/2018) 77.722-78.678km (10/11/2020) Lower chainage end to tie into FY23 Re Rail Scope 76.537-77.725km (2000070850). This may slightly change lower chainage cut-in point Equality 77km 1008.986m = 78km Post Lubricator at 78.660km Mud hole noted at 78.555-78.570km during site inspection SCOPE PUSHED FROM FY24 to FY26 due to condition deemed fit - PCR 5656 - Approved at MAY2023 Change Board
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137572&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137572 | C17 BW EDUNGALBA 82.191-82.826 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 1.296 | RAIL KM | 584928 | Blackwater | TUNNEL | EDUNGALBA | 0.635 | KM | BW03ML82 | 0.191 | BW03ML82 | 0.8259 | KM | 12 |  | 1.296 | 0.635 | 82.191 | 82.826 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.75 | 1 | 3.4 | 1 | 12.92 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Re rail scope, this curve historically has high wear rate, paired with RCF on rail this will require additonal grinds meaning artificial wear will impact when CETS limits are reached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137574&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137574 | C17 BW PARNABAL 158.2 - 159.172 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 2.052 | RAIL KM | 926135 | Blackwater | UMOLO | PARNABAL | 0.9759 | KM | BW03ML158 | 0.2 | BW03ML159 | 0.1719 | KM | 19 |  | 2.052 | 0.976 | 158.2 | 159.172 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070927&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000070927 | C17 GA WANDOO 88.500 - 88.982 | CV003009 | CIVIL | RAIL |  | RENEWAL | 0.972 | RAIL KM | 438696 | Goonyella | WANDOO | WAITARA | 0.4819 | KM | GA02ML88 | 0.5 | GA02ML88 | 0.9819 | KM | 9 |  | 0.972 | 0.482 | 88.5 | 88.982 | 2026-06-30 | UP | BOTH |  |  | 3 | 5 | 1 | 3.9 | 1 | 11.7 | 242 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Pushed for FY26 execution - needs to be completed in Q1 or Q2 Rail wear is driver, side wear location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130676&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130676 | C17 WYCARBAH 37.360 - 37.590 | BW-03ML | CIVIL | RAIL |  | RENEWAL | 0.54 | RAIL KM | 243720 | Blackwater | WYCARBAH | WESTWOOD | 0.23 | KM | BW03ML37 | 0.3599 | BW03ML37 | 0.5899 | KM | 5 |  | 0.54 | 0.23 | 37.36 | 37.59 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 0.1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136389&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000136389 | TRACK RENEWALS FIX ON FAIL | BW | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 315000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FoF/Reactive for Blackwater System - All rail/sleepers/ track upgrade reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138086&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138086 | TRACK RENEWALS FIX ON FAIL | GA | CIVIL | RAIL | FIX ON FAIL | REACTIVE WORKS | 0 | LUMPSUM | 315000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | FoF / Reactive Rail Renewal for Goonyella System - All rail/sleepers/ track upgrade reactive
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136410&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000136410 | BW GIJ RENEWALS | BW | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 320000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138087&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138087 | GA GIJ RENEWALS | GA | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 340000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135554&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000135554 | MA GIJ RENEWALS | MA | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 80000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Funding for GIJ renewals
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135584&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000135584 | NL GIJ RENEWALS | NL | CIVIL | RAIL | GIJ | REACTIVE WORKS | 0 | LUMPSUM | 80000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Lumpsum allocation for GIJ renewals for Newlands system
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138703&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138703 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ BW | BW | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS |  | LUMPSUM | 50000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138707&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138707 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ GA | GA | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS | 0 | LUMPSUM | 60000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138704&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138704 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ MA | MA | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS |  | LUMPSUM | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138706&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138706 | RAIL LUBRICATION ¦ CONST ¦ RENEWAL ¦ NL | NL | CIVIL | RAIL LUBRICATION |  | REACTIVE WORKS |  | LUMPSUM | 20000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140073&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140073 | C18 GA BROADLEA 166.500 - 167.300 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 1173 | SLEEPERS | 187680 | Goonyella | BRAODLEA | MALLAWA | 0.803 | KM | GA01ML166 | 0.5 | GA01ML167 | 0.2999 | KM |  | 1173 |  | 0.803 | 166.5 | 167.3 | 2026-06-30 | DOWN |  |  |  | 3.5 | 2.5 | 1 | 2.7 | 1 | 9.45 |  | 2024-03-28 |  | Sleeper Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Sleeper renewals as part of formation job - 2000136288, Material cost used
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140074&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000140074 | C18 NL COCKOOL 114.000 - 114.600 | NL-01ML | CIVIL | SLEEPERS |  | RENEWAL | 876 | SLEEPERS | 140160 | Newlands | COCKOOL | HAVILAH | 0.5999 | KM | NL01ML114 | 0 | NL01ML114 | 0.5999 | KM |  | 876 |  | 0.6 | 114 | 114.6 | 2026-06-30 | SINGLE |  |  |  | 3.5 | 1.4 | 1 | 1.9 | 1 | 6.65 |  | 2024-03-28 |  | Sleeper Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Sleeper renewals as part of formation job - 2000052758 only used material cost
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110840&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | BASELOAD | NON-COAL | 002000110840 | C18 BW ROCKLANDS 631.910 - 633.610 | NC-03PL | CIVIL | SLEEPERS |  | RENEWAL | 2482 | SLEEPERS | 2499374 | Blackwater | MIDGEE | ROCKLANDS | 1.6999 | KM | NC03PL631 | 0.91 | NC03PL633 | 0.6099 | KM |  | 2482 |  | 1.7 | 631.09 | 633.6 | 2026-06-30 | LOOP |  |  |  | 3.5 | 4.5 | 1 | 3.7 | 1 | 12.95 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108987&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | BASELOAD | NON-COAL | 002000108987 | C18 BW MIDGEE 631.820 - 633.680 | NC-05ML | CIVIL | SLEEPERS |  | RENEWAL | 2716 | SLEEPERS | 2735012 | Blackwater | MIDGEE | ROCKLANDS | 1.86 | KM | NC05ML631 | 0.8199 | NC05ML633 | 0.68 | KM |  | 2716 |  | 1.86 | 631.82 | 633.68 | 2026-06-30 | SINGLE |  |  |  | 3.5 | 4.5 | 1 | 2.59 | 2 | 16 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113670&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000113670 | C18 BW MAIN BURNGROVE 254.260 - 255.630 | BW-03ML | CIVIL | SLEEPERS |  | RENEWAL | 2000 | SLEEPERS | 1258000 | Blackwater | NOGOA | YAMALA | 1.3709 | KM | BW03ML254 | 0.26 | BW03ML255 | 0.63 | KM |  | 2000 |  | 1.371 | 254.26 | 255.63 | 2026-06-30 |  |  |  |  | 4 | 1.7 | 1 | 2.1 | 1 | 8.5 | 5828 |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Approved IAR Scope - 2000 Sleepers inserted every year original scope was 255.990 - 257.360 - approx. 2000 sleepers. Due to waterfall affects from incompleted sope in FY23 new scope is between 254.260 - 255.630 approx. 2000 sleepers. Tying into FY25 Job. Change Captured in PCR 5828
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115549&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115549 | C18 BW STANWELL BLOOP 4.565 - 5.093 | BW-04BL | CIVIL | SLEEPERS |  | RENEWAL | 771 | SLEEPERS | 776397 | Blackwater | STANWELL BALLOON LOOP EXIT | STANWELL BALLOON LOOP EXIT | 0.528 | KM | BW04BL4 | 0.5649 | BW04BL5 | 0.0929 | KM |  | 761 |  | 0.521 | 4.565 | 5.093 | 2026-06-30 | EXIT |  |  |  | 3.5 | 1.65 | 1 | 2.1 | 1 | 7.35 |  | 2024-03-28 |  | Sleeper Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110828&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000110828 | C18 BW YARWUN 558.037 - 558.889 | BW-02ML | CIVIL | SLEEPERS |  | RENEWAL | 1244 | SLEEPERS | 1252708 | Blackwater | YARWUN | ALDOGA | 0.8519 | KM | BW02ML558 | 0.0369 | BW02ML558 | 0.889 | KM |  | 1244 |  | 0.852 | 558.037 | 558.889 | 2026-06-30 | DOWN |  |  |  | 3.5 | 4.1 | 1 | 3.5 | 1 | 12.25 |  | 2024-03-28 |  | Sleeper Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092920&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000092920 | C38-SS-GA-BLACK MOUNTAIN-41.850KM | GA-01CR | CIVIL | SLOPE STABILITY | CUTTING | DESIGN | 1 | LUMPSUM | 125000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.139 | KM | GA01ML41 | 0.8499 | GA01ML41 | 0.9889 | KM |  |  |  |  | 41.85 | 41.989 | 2026-06-30 | DOWN |  |  |  | 5 | 5 | 3 | 4.5 | 1 | 22.5 |  | 2024-03-28 |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 21/02/2024: Agreed to proceed with Design in FY26. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). Design to complete: 1. Coordinate and conduct site inspection 2. Provide slope stability assessment including risk assessment <(>&<)> priority 3. Develop proposed renewal/stabilising options (Asset Manager to be consulted) 4. Develop site specific design and progress to IFC (or engage external if internal capacity not available). 03.08.22. Set to rejected. Requires site based inspection and consideration of other Black Mountain design scopes accomplishing the asset requirements. 04.03.2022 Tim Griffin (r8788533) Linked to FY23 Slope Stability Design N4 notification which requires design and costing to be completed by Q1FY23 (Sept 2022) so that construction delivery costs are accurate. See attached email to Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123347&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000123347 | C38-SS-GA-BLACK MOUNTAIN-36.350KM | GA-01CR | CIVIL | SLOPE STABILITY | CUTTING | DESIGN | 1 | LUMPSUM | 125000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0.0599 | KM | GA01ML36 | 0.32 | GA01ML36 | 0.38 | KM |  |  |  |  | 36.32 | 36.38 | 2026-06-30 | DOWN |  |  |  | 5 | 4.4 | 3 | 4.3 | 1 | 21.5 |  | 2024-03-28 |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 21/02/2024: Agreed to proceed with Design in FY26. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). Location has history of land slips and visible shear cracks within and at the top of the cutting. Design to complete: 1. Coordinate and conduct site inspection 2. Provide slope stability assessment including risk assessment <(>&<)> priority 3. Develop proposed renewal/stabilising options (Asset Manager to be consulted) 4. Develop site specific design and progress to IFC (or engage external if internal capacity not available).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078183&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000078183 | C38-SS-BW-ROCKLANDS-0.440KM | BW-03CR | CIVIL | SLOPE STABILITY | CUTTING | RENEWAL | 1 | LUMPSUM | 2700000 | Blackwater | ROCKLANDS | GRACEMERE | 0.4899 | KM | BW03ML0 | 0.1799 | BW03ML0 | 0.67 | KM |  |  |  |  | 0.18 | 0.67 | 2026-06-30 | UP |  |  |  | 5 | 3.35 | 3 | 4 | 1 | 20 |  | 2024-03-28 |  | Slope Stability | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 21/02/2024: Agreed to proceed with construct in FY26. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). Design / PM team have commenced Design <(>&<)> Construct contract with Geovert. 27/03/2024: Cost estimate reduced from 3,200,000.00 AUD to 2,700,000.00 AUD as per direction from NAM leadership.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093003&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000093003 | C38-SS-GA-BROADLEA-150KM | GA-01CR | CIVIL | SLOPE STABILITY | ROCK CUTTING | DESIGN | 1 | LUMPSUM | 125000 | Goonyella | COPPABELLA | BROADLEA | 0.93 | KM | GA01ML149 | 0.8399 | GA01ML150 | 0.77 | KM |  |  |  |  | 149.84 | 150.77 | 2026-06-30 | DOWN |  |  |  | 4 | 3.5 | 3 | 4.1 | 1 | 16.4 |  | 2024-03-28 |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Comprises of 2 x Locations RHS Rock Cutting: 149.840 - 150.120km 150.610 - 150.770km Both locations to include drainage in design at bottom of cutting to ensure adequate track <(>&<)> formation drainage. 150.610 - 160.770km design to consider an access road from low chainage end at top or bottom of cutting to access and maintenance and inspection requirements. Design to complete: 1. Coordinate and conduct site inspection 2. Provide slope stability assessment including risk assessment <(>&<)> priority 3. Develop proposed renewal/stabilising options (Asset Manager to be consulted) 4. Develop site specific design and progress to IFC (or engage external if internal capacity not available). Updates: 21/02/2024: Agreed to proceed with Design in FY26. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). 03.08.2022 - W Schuh - Moved to FY26 to align with RIG presentation. Change name to Broadlea to align with chainage. 04.03.2022 Tim Griffin (r8788533) Several incidents of rock dislodgement in IR Incident Reports - Severity 1 from Train Operations. See photos attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138534&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138534 | Non Coal Reactive Renewals - Structures | BW | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Culvert Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138535&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138535 | Non Coal Reactive Renewals - Structures | GA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Culvert Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138536&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138536 | Non Coal Reactive Renewals - Structures | MA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Culvert Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138537&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138537 | Non Coal Reactive Renewals - Structures | NL | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Culvert Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132533&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000132533 | B12 -ST-BW-Bajool-605.690km | BR101279 | CIVIL | STRUCTURES | BRIDGE BEARING | DESIGN | 1 | SITE | 75000 | Blackwater | BAJOOL |  | 0.0539 | KM | BW01ML605 | 0.635 | BW01ML605 | 0.6889 | KM |  |  |  |  | 605.69 |  | 2028-06-30 |  |  | BEARING PADS & STRENGTHENING |  | 4 | 4.1 | 4 | 4.3 | 1 | 17.2 |  | 2024-03-28 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | BR101279 SIX MILE CREEK - B12 -ST-BW-Bajool-605.690km Defect: Bearing pad moveing out from girder at abutment 2 and at same location girder ends appear to have shear cracking. Proposed: Bearing pad replacement and end of girder crack improvements Final: Drawing: Risk: High Reason: Further deteration of bearing ad will lead to concrete concrete interface and girder being damaged requiring full replacement which will require long closure and significantly more cost.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132542&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000132542 | B12 -ST-GA-Bolingbroke-052.570km | BR200823 | CIVIL | STRUCTURES | BRIDGE BEARING | DESIGN | 1 | SITE | 75000 | Goonyella | BOLINGBROKE |  | 0.1089 | KM | GA02ML52 | 0.4979 | GA02ML52 | 0.6069 | KM |  |  |  |  | 52.57 |  | 2028-06-30 |  |  | BEARING PADS & STRENGTHENING |  | 3.5 | 5 | 4 | 4.5 | 1 | 15.8 |  | 2024-03-28 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | BR200823 BOLINGBROKE CREEK - B12 -ST-GA-Bolingbroke-052.570km Defect: Bearing pad pier 1 girder 4. cracks in girder 2 span 1. Proposed: Bearing Pad Replacement and remove escape platforms and patch. Consider strengthening options for cracks in girders Final: Drawing: Risk: High Reason: Further deteration of bearing ad will lead to concrete concrete interface and girder being damaged requiring full replacement which will require long closure and significantly more cost.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132537&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000132537 | B12 -ST-GA-Dalrymple-009.514km | BR200725 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | DESIGN | 1 | SITE | 75000 | Goonyella | DALRYMPLE |  | 0.0459 | KM | GA01ML9 | 0.508 | GA01ML9 | 0.554 | KM |  |  |  |  | 9.514 |  | 2028-06-30 |  |  | STRENGTHENING |  | 3.5 | 4.6 | 4 | 4.7 | 1 | 16.5 |  | 2024-03-28 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | BR200725 GRASSTREE BEACH ROAD - B12 -ST-GA-Dalrymple-009.514km Defect: Severe cracks forming on top flange of girders longitudinally. Design assessment required. ASR cracking longitudinally requires ASR identification testing and monitoring of crack width. Inspect bridge annually. Seal cracks after confirmed to be dead and ASR. NMP at present Proposed: Considering strengthening methods or whether remove and replace required. Final: Drawing: Risk: High Reason: Aim for this design phase is to ideally strengthen girder before full replacement required. If full replacement required then structures management plan to be developed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043710&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000043710 | B12 -ST-NL-Durroburra-000.945km | BR300431 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | DESIGN | 1 | SITE | 100000 | Newlands | DURROBURRA |  | 0 | KM | NL01ML0 | 0.9449 | NL01ML0 | 0.9449 | KM |  |  |  |  | 0.95 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  | 2024-03-28 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 10.03.2020 08:31:42 AUSQLD Peter Rayner (R003851) * Defect - Design assessment found structures to shear deficient and borderline Moment capacity. - Proposed Renewal - Level 3 Inspections, measurements, Strengthening for shear * 06.10.2020 09:55:52 AUSQLD Edward Brooks (R884255) Construct. * 06.10.2020 12:55:34 AUSQLD Edward Brooks (R884255) Construction required
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131107&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | FUTURE SCOPE | NON-COAL | 002000131107 | B12 -ST-NO-Parana-526.300km | BR101585 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | DESIGN | 1 | SITE | 100000 | Moura | PARANA |  | 0.048 | KM | NC02ML526 | 0.276 | NC02ML526 | 0.324 | KM |  |  |  |  | 526.3 |  | 2028-06-30 |  |  | STRENGTHEN |  | 3.5 | 1.8 | 4 | 3.4 | 1 | 11.9 |  |  |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | BR101585 NORTH COAST LINE - B12 -ST-NO-Parana-526.300km Defect: Severe Cracking on Piers, majority of piers impacted and many headstocks also severely cracked. Proposed: Strengthening design required Final: Drawing: Risk: HIgh Reason: Deterioation of the pier walls are the most concening defect on this bridge that needs to be rectified to ensure the structural adequacy of the bridge longer term.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131105&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000131105 | B12 -ST-BW-Rocklands-000.950km | BR100576 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | DESIGN | 1 | SITE | 100000 | Blackwater | ROCKLANDS |  | 0.0619 | KM | BW03ML0 | 0.9449 | BW03ML0 | 1.0069 | KM |  |  |  |  | 0.95 |  | 2027-06-30 |  |  | STRENGTHEN & RELIEV SLABS |  | 3.5 | 3.35 | 4 | 4 | 1 | 14 | 5832 | 2024-03-28 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | BR100576 BURNETT HIGHWAY - B12 -ST-BW-Rocklands-000.950km Defect: Significant cracking in piear walls. LHS Handrails required. Also severe crack visible in high chainage relieving slab. Proposed: Strengthening design required of pier walls. Handrails also required. and relieving slab replacement due to severe cracking. Final: Drawing: Risk: HIgh Reason: Deterioation of the pier walls are the most concening defect on this bridge that needs to be rectified to ensure the structural adequacy of the bridge longer term.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092319&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000092319 | Bridge 22.650km BYAA DEADMAN Creek #1 | BR300154 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS | RENEWAL | 1 | SITE | 33416 | Newlands | ARMUNA | BUCKLEY | 0.049 | KM | NL01ML22 | 0.6159 | NL01ML22 | 0.665 | KM |  |  |  |  | 22.65 |  | 2026-06-30 |  |  |  |  | 10 | 10 |  | 10 | 1 | 100 | 184 | 2024-03-28 |  | Bridges Renewal | STRATEGIC | MEDIUM | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Close inspections of cracks and detailed scope of repairs to pier cracks and bearing pad movement. Design install of handrai ls/platforms on LHS and RHS of bridge and removal of concrete platforms. Proposed: Install new handrails and platforms. Inspect bearing pads and pier cracks. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094230&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000094230 | B12 -ST-BW-Crew-016.950km | BR101090 | CIVIL | STRUCTURES | BRIDGE-RELIEVING SLAB & HAND | RENEWAL | 1 | SITE | 1714000 | Blackwater | CREW | MCKENZIE | 0.445 | KM | BW08ML16 | 0.7119 | BW08ML17 | 0.158 | KM |  |  |  |  | 16.95 |  | 2026-06-30 |  |  | REPLACE RELIEVING SLAB |  | 10 | 10 | 3 | 10 | 1 | 100 |  | 2024-03-28 |  | Bridges Renewal | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | Defect: Top of line issues suggesting possible relieving slab issue. Also strategic for Handrails. Proposed: Remove and Replace Relieving Slabs and install handrails with walkway on right/eastern side (one side only) Drawing: TBC Risk: Mod Reason: Moved to FY26 to align with bridge rollout which has been moved to FY26 as well due to budget reason in FY25. FY26 Final Scoping Review - scope reviewed and handrail and walkyway on one side only, budget reduced $500k accordingly - 23.03.24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136115&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136115 | B52 -ST-NL-Armuna-016.920km | CU300440 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Newlands | ARMUNA |  | 0 | KM | NL01ML16 | 0.92 | NL01ML16 | 0.92 | KM |  |  |  |  | 16.92 | 16.92 | 2028-06-30 |  |  | CIPP |  | 3.2 | 1.7 | 3 | 3 | 1 | 11 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Cracking in ceiling of unreinforced pipe sections. Proposed:CIPP line or remove and replace confirm in designFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136117&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136117 | B52 -ST-NL-Armuna-019.160km | CU300153 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Newlands | ARMUNA |  | 0 | KM | NL01ML19 | 0.16 | NL01ML19 | 0.16 | KM |  |  |  |  | 19.16 | 19.16 | 2028-06-30 |  |  | CIPP |  | 3.3 | 1.7 | 3 | 3 | 1 | 11.2 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Cracking in ceiling of unreinforced pipe sections. Proposed:CIPP line or remove and replace confirm in designFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136118&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136118 | B52 -ST-NL-Armuna-020.350km | CU300776 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Newlands | ARMUNA |  | 0 | KM | NL01ML20 | 0.3499 | NL01ML20 | 0.3499 | KM |  |  |  |  | 20.35 | 20.35 | 2028-06-30 |  |  | CIPP |  | 4.5 | 1.7 | 3 | 3 | 1 | 15.3 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Unreinforced Pipes severe cracks and needs remoteProposed:CIPP line or remove and replace confirm in designFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136102&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136102 | B52 -ST-GA-Balook-066.860km | CU201104 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | BALOOK |  | 0 | KM | GA01ML66 | 0.8599 | GA01ML66 | 0.8599 | KM |  |  |  |  | 66.86 | 66.86 | 2028-06-30 |  |  | CIPP |  | 4 | 5 | 3 | 5 | 1 | 18 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Severe corrosion in invert of culvert, particularly at joint of widening right. Proposed:CIPP pending hydroFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136105&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136105 | B52 -ST-GA-Balook-084.780km | CU200872 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | BALOOK |  | 0 | KM | GA01ML84 | 0.78 | GA01ML84 | 0.78 | KM |  |  |  |  | 84.78 | 84.78 | 2028-06-30 |  |  | CIPP |  | 3.6 | 4.8 | 3 | 5 | 1 | 16.4 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:corrosion mod on outlet side. Proposed:CIPP line before too bad. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136094&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136094 | B52 -ST-MA-Callemondah-012.750km | CU400119 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Moura | CALLEMO |  | 0 | KM | MA01ML12 | 0.75 | MA01ML12 | 0.75 | KM |  |  |  |  | 12.75 | 12.75 | 2028-06-30 |  |  | CIPP |  | 3.5 | 2.4 | 3 | 4 | 1 | 13 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:half culvert not concrete lined and showing signs of moderate to severe corrrosionProposed:CIPP Line pending hydro studyFinal :Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136078&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000136078 | B52 -ST-NO-Callemondah-529.070km | CU101491 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Moura | CALLEMO |  | 0 | KM | NC02ML529 | 0.07 | NC02ML529 | 0.07 | KM |  |  |  |  | 529.07 | 529.07 | 2028-06-30 |  |  | CIPP |  | 4.5 | 1.8 | 3 | 3 | 1 | 15.3 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Severe cracking in RCP ceiling and starting to collapse, passeneger services over and section looks lke collapse potentialPro posed:CIPP Lining Ideally, but shape will be biggest issue. Final:Risk:HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136107&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136107 | B52 -ST-GA-Dysart-092.820km | CU200460 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | DYSART |  | 0 | KM | GA03ML92 | 0.8199 | GA03ML92 | 0.8199 | KM |  |  |  |  | 92.82 | 92.82 | 2028-06-30 |  |  | CIPP |  | 4 | 1.4 | 3 | 3 | 1 | 12.8 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Severe corrosion in the bottom of the pipe between 4 <(>&<)> 8 oclock Proposed:CIPP pending hydroFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136073&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136073 | B52 -ST-BW-Fairhill-047.970km | CU101163 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | FAIRHIL |  | 0 | KM | BW08ML47 | 0.9699 | BW08ML47 | 0.9699 | KM |  |  |  |  | 47.97 | 47.97 | 2028-06-30 |  |  | CIPP |  | 4 | 1.1 | 3 | 3 | 1 | 12.4 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Large voids behind and above ceiling and walls. Joints failing and exposed reinf. Moving sideways and pumping. Proposed:NMP going to try and fill voids to stabilise and then for renewal consider CIPP liningFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136097&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136097 | B52 -ST-MA-Graham-039.300km | CU400435 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Moura | GRAHAM |  | 0 | KM | MA01ML39 | 0.2999 | MA01ML39 | 0.2999 | KM |  |  |  |  | 39.3 | 39.3 | 2028-06-30 |  |  | CIPP |  | 3.5 | 1.1 | 3 | 0 | 1 | 10.9 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Widening Left severe corrosion in extension. Proposed:CIPP or remove and replace pending hydro and invert concrete lining current present. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136101&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136101 | B52 -ST-GA-Lake Vermont-012.616km | CU200292 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | LAKE VERMONT |  | 0 | KM | GA19ML12 | 0.6159 | GA19ML12 | 0.6159 | KM |  |  |  |  | 12.616 | 12.616 | 2028-06-30 |  |  | CIPP |  | 4 | 1.1 | 3 | 3 | 1 | 12.4 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Severe corrosion at 3-9 oclock in multiple cells. Proposed:CIPP pending hydroFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136074&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136074 | B52 -ST-BW-Memooloo-049.500km | CU100904 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | MEMOOLO |  | 0 | KM | BW06ML49 | 0.5 | BW06ML49 | 0.5 | KM |  |  |  |  | 49.5 | 49.5 | 2028-06-30 |  |  | CIPP |  | 3.5 | 2.3 | 3 | 4 | 1 | 12.6 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Corrosion in upper half of CMP moderate to severe in some cells Proposed:CIPPFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136109&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136109 | B52 -ST-GA-Stephens-104.500km | CU200475 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | STEPHEN |  | 0 | KM | GA03ML104 | 0.5 | GA03ML104 | 0.5 | KM |  |  |  |  | 104.5 | 104.5 | 2028-06-30 |  |  | CIPP |  | 4 | 1.4 | 3 | 3 | 1 | 12.8 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Severe corrosion in the bottom of the pipe between 4 <(>&<)> 8 oclock Proposed:CIPP pending hydroFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086054&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086054 | B52 -ST-NL-Almoola-074.090km | CU300135 | CIVIL | STRUCTURES | CIPP | RENEWAL | 1 | SITE | 430000 | Newlands | NL |  | 0 | KM | NL01ML74 | 0.0899 | NL01ML74 | 0.0899 | KM |  |  |  |  | 74.09 |  | 2026-06-30 |  |  |  |  | 3.5 | 2.5 |  |  |  | 13 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: numerous circumference cracking severe greater than 1mm up to 20mm. Horizontal crack in roof also which is a concern Proposed: Remove and Replace Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085971&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000085971 | B52 -ST-BW-Kenmare-013.250km | CU100911 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | BW-RM |  | 0 | KM | BW06ML13 | 0.25 | BW06ML13 | 0.25 | KM |  |  |  |  | 13.25 |  | 2027-06-30 |  |  | CIPP |  | 4 | 2.6 | 3 | 3.7 | 1 | 15 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Mpderate to severe corosion from 2-10 oclock which means holds considerable water, difficult to maintain as smaller culvert. Proposed: CIPP Line pending Hydro Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133041&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000133041 | B52 -ST-BW-Kenmare-019.290km | CU100928 | CIVIL | STRUCTURES | CMP-CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | KENMARE |  | 0 | KM | BW06ML19 | 0.2899 | BW06ML19 | 0.2899 | KM |  |  |  |  | 19.29 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 2.6 | 3 | 3.7 | 1 | 13 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU100928 - B52 -ST-BW-Kenmare-019.290km Defect: painted FY21. Severe corrosion in invert. line bfore corrosion goes too far Proposed: CIPP Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109413&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000109413 | B52 -ST-MA-Belldeen-136.050km | CU400411 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 300000 | Moura | BELLDEEN | EARLSFIELD | 0 | KM | MA01ML136 | 0.05 | MA01ML136 | 0.05 | KM |  |  |  |  | 136.05 |  | 2026-06-30 |  |  |  |  | 4 | 1.3 | 3 | 3.2 | 1 | 12.7 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Severe corrosion on invert of CMP. Poorly constructed lining has failed and will be making corrosion worse. Proposed: CIPP line to be confirmed during Hydrology design. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086061&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086061 | B52 -ST-GA-Bolingbroke-058.820km | CU200939 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 430000 | Goonyella | GA-NG |  | 0 | KM | GA01ML58 | 0.8199 | GA01ML58 | 0.8199 | KM |  |  |  |  | 58.82 |  | 2026-06-30 |  |  |  |  | 3.5 | 5 |  |  |  | 15.8 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: severe corrosion on outlet side widening. Holes in Proposed: CIPP lined Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000099882&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000099882 | B52 -ST-GA-Moranbah North-187.940km | CU200807 | CIVIL | STRUCTURES | CMP-CIPP LINE | DESIGN | 1 | SITE | 40000 | Goonyella | GA-GA |  | 0 | KM | GA01ML187 | 0.9399 | GA01ML187 | 0.9399 | KM |  |  |  |  | 187.94 |  | 2028-06-30 |  |  | CIPP LINE |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Deflecting in shape in last inspection. Under annual inspection, tentative scope Proposed: CIPP lining to be considered pending hydro Drawing: Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085884&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085884 | B52 -ST-BW-Memooloo-061.590km | CU100905 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | BW-BA |  | 0 | KM | BW06ML61 | 0.5899 | BW06ML61 | 0.5899 | KM |  |  |  |  | 61.59 |  | 2026-06-30 |  |  |  |  | 3.5 | 2.3 |  |  |  | 12.7 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: moderate to severe corrosion in invert or walls in majority of cells. cells 3, 4-10 worst Proposed: Concrete line, Consultant to confirm whether concrete line appropriate and if not propose an alternative solution. Risk: Mod-High Reason: NOTE: FY26 FINAL SCOPE REVIEW - NOTIFICATION CHANGED FROM RENEWAL TO DESIGN AS NO DESIGN NOFITICATION EXISTS - RC 23.03.24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136103&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136103 | B52 -ST-GA-Balook-071.400km | CU201050 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Goonyella | BALOOK |  | 0 | KM | GA01ML71 | 0.4 | GA01ML71 | 0.4 | KM |  |  |  |  | 71.4 | 71.4 | 2028-06-30 |  |  | CONCRETE LINE |  | 4 | 5 | 3 | 5 | 1 | 18 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Material coming through widening joint. Moderate to localised severe corrosion on wall and ceiling. Proposed:Concrete line pending HydroFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136079&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000136079 | B52 -ST-BW-Callemondah-534.730km | CU101383 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | CALLEMO |  | 0 | KM | BW01ML534 | 0.7299 | BW01ML534 | 0.7299 | KM |  |  |  |  | 534.73 | 534.73 | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 2.4 | 3 | 4 | 1 | 13 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Multi type culvert. Seevere corrosion in section of CMP. And exposed reinf throughout RCP. Proposed:Concrete line , CIPP (grout annulus) or GRP line pending hydro. Final:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136111&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136111 | B52 -ST-GA-Coppabella-147.570km | CU200871 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Goonyella | COPPABE |  | 0 | KM | GA01ML147 | 0.5699 | GA01ML147 | 0.5699 | KM |  |  |  |  | 147.57 | 147.57 | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 4.6 | 3 | 4 | 1 | 15.4 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Widening right with no invert lining is severely corroed. May be too late for maintenanceProposed:Concrete line or consider GRP lining pending hydro. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136084&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000136084 | B52 -ST-BW-Marmor-594.140km | CU101245 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | MARMOR |  | 0 | KM | BW01ML594 | 0.14 | BW01ML594 | 0.14 | KM |  |  |  |  | 594.14 | 594.14 | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 4.9 | 3 | 5 | 1 | 15.8 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:594.050 in sap currently previously patched failing Proposed:Concrete Line or remove and replace pending hydro study. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136104&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136104 | B52 -ST-GA-Saraji-076.470km | CU200536 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Goonyella | SARAJI |  | 0 | KM | GA03ML76 | 0.4699 | GA03ML76 | 0.4699 | KM |  |  |  |  | 76.47 | 76.47 | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 |  | 3 |  | 1 |  |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Moderate corrosion along joint in top half of the CMP. Appears to be corroding from outside in. Proposed:Concrete Line. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136048&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136048 | B52 -ST-BW-Tikardi-007.370km | CU101033 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | TIKARDI |  | 0 | KM | BW05ML7 | 0.3699 | BW05ML7 | 0.3699 | KM |  |  |  |  | 7.37 | 7.37 | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.7 | 3 | 3 | 1 | 11.9 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Regular haunch cracks and moderate spalling in legs and ceiling. Proposed:Concrete line or remove and replace pending hydroF inal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136075&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136075 | B52 -ST-BW-Aroona-095.910km | CU100693 | CIVIL | STRUCTURES | ELIMINATE | DESIGN | 1 | SITE | 40000 | Blackwater | AROONA |  | 0 | KM | BW03ML95 | 0.91 | BW03ML95 | 0.91 | KM |  |  |  |  | 95.91 | 95.91 | 2028-06-30 |  |  | ELIMINATE |  | 4.5 | 3.4 | 3 | 4 | 1 | 18 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:collapsed currently based on remote, Two culverts to be modelled within 10m of each otherProposed:Grout @ divert or remove and replace. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136049&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136049 | B52 -ST-BW-Curragh-007.700km | CU101723 | CIVIL | STRUCTURES | ELIMINATE | DESIGN | 1 | SITE | 40000 | Blackwater | CURRAGH |  | 0 | KM | BW12ML7 | 0.6999 | BW12ML7 | 0.6999 | KM |  |  |  |  | 7.7 | 7.7 | 2028-06-30 |  |  | ELIMINATE |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:100% blocked to clean. Remote planned for FY24. Proposed:Eliminate?Final:Risk:ModReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090220&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000090220 | B52 -ST-BW-Wallaroo-115.630km | CU100495 | CIVIL | STRUCTURES | ELIMINATE & DIVERT | RENEWAL | 1 | SITE | 65000 | Blackwater |  |  | 0 | KM | BW03ML115 | 0.63 | BW03ML115 | 0.63 | KM |  |  |  | 115.63 | 115.63 | 115.63 | 2026-06-30 | BW-CL |  |  |  | 4 | 3.4 |  |  |  | 16.1 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Full of ballast and misalignment issues suggesting the culvert is sinking. Proposed: Remove <(>&<)> Replace, confirm if required in hydro. Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043456&DY_MAB=X&~OKCODE=ONLI | FY26 | Non Coal Traffic | BASELOAD | NON-COAL | 002000043456 | B52 -ST-BW-Comet-224.300km | CU100177 | CIVIL | STRUCTURES | NON-MRSB RCBC-ELIMINATE | RENEWAL | 1 | SITE | 100000 | Blackwater | BURNGROVE | NOGOA | 0 | KM | BW03ML224 | 0.2999 | BW03ML224 | 0.2999 | KM |  |  |  |  | 224.3 |  | 2026-06-30 |  |  | ELIIMINATE |  | 4 | 1.7 | 3 | 3.3 | 1 | 13.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20260630 | * 20.10.2020 15:44:31 AUSQLD Edward Brooks (R884255) * Defect - Widening under access road miss-shaped due to pooor construction. * Renewal - Drawing 0575-4132 Replace widening only 5m with class 4 2400 dia RCP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136081&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000136081 | B52 -ST-BW-Aldoga-559.840km | CU101479 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | ALDOGA |  | 0 | KM | BW01ML559 | 0.8399 | BW01ML559 | 0.8399 | KM |  |  |  |  | 559.84 | 559.84 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.5 | 3 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Mod-severe Haunch cracks in C3-7, 5-7, 5-9, 6-7, 9-6, 12-9. Regular moderate to severe spalling in legs and ceiling through all cells. Appears to be old timber bridge site. Pumping 2-3mm. Dropped 25mm typicallyProposed:Remove <(>&<)> Replace. Final:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136116&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136116 | B52 -ST-NL-Armuna-018.460km | CU300406 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Newlands | ARMUNA |  | 0 | KM | NL01ML18 | 0.46 | NL01ML18 | 0.46 | KM |  |  |  |  | 18.46 | 18.46 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.2 | 1.7 | 3 | 3 | 1 | 11 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Unreinforced pipe. Severe crcaking in ceiling and sides of culvert, collapsingProposed:Remove <(>&<)> ReplaceFinal:Risk:HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136119&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136119 | B52 -ST-NL-Birralee-104.120km | CU300563 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Newlands | BIRRALE |  | 0 | KM | NL01ML104 | 0.1199 | NL01ML104 | 0.1199 | KM |  |  |  |  | 104.12 | 104.12 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.4 | 3 | 3 | 1 | 11.2 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Unit 3-5 horizontal displaced leg or ceiling. Remote to confirm scope. Proposed:Remove and ReplaceFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136165&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136165 | B52 -ST-NL-Birralee-102.000km | CU300502 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Newlands | BIRRALEE |  | 0 | KM | NL01ML102 | 0 | NL01ML102 | 0 | KM |  |  |  |  | 102 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1.4 | 3 | 3.2 | 1 | 14.4 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU300502 WATER - B52 -ST-NL-Birralee-102.000km Defect: Severe cracks in pipe, with podering at cracks suggesting pumping and movement in cracks. Proposed: Remove <(>&<)> Replace due to condition Final: Drawing: Risk: High Reason: Severe cracking and movement suggest collapse is getting closer and therefore should not be delays. It made need additional maintenance just to get to FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136120&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136120 | B52 -ST-BW-Blackwater-186.610km | CU100496 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | BLACKWA |  | 0 | KM | BW03ML186 | 0.6099 | BW03ML186 | 0.6099 | KM |  |  |  |  | 186.61 | 186.61 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.2 | 3 | 4 | 1 | 13.7 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Down Road Loosing ballast of track. Some washout of ballast on west side. Strengthened with steel frame, but spalling and cracking in haunches. Most localised at this stage. Pumping approx 3mm. Sheared biolts. Severe spalling and exposed reinf. Proposed:Remove and ReplaceFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136095&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136095 | B52 -ST-MA-Byellee-014.210km | CU400190 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Moura | BYELLEE |  | 0 | KM | MA01ML14 | 0.2099 | MA01ML14 | 0.2099 | KM |  |  |  |  | 14.21 | 14.21 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.8 | 1.1 | 3 | 3 | 1 | 11.9 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Moderate to severe cracking in arch section. Proposed:Remove and Replace. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136096&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136096 | B52 -ST-MA-Byellee-021.350km | CU400222 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Moura | BYELLEE |  | 0 | KM | MA01ML21 | 0.3499 | MA01ML21 | 0.3499 | KM |  |  |  |  | 21.35 | 21.35 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 0 | 1 | 11.2 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:severe cracks through base slab. Inspection section circumference Proposed:Remove and ReplaceFinal:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136077&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000136077 | B52 -ST-NO-Callemondah-528.670km | CU101232 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Moura | CALLEMO |  | 0 | KM | NC02ML528 | 0.67 | NC02ML528 | 0.67 | KM |  |  |  |  | 528.67 | 528.67 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1.8 | 3 | 3 | 1 | 15.3 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Seevere cracks in ceiling of units. Exposed corroded rail in insitu section. Large gaps in ceiling forming, high risk of material falling throughProposed:Remove and ReplaceFinal:Risk:Reason:FY28 renewal as low traffic area, but concerned about passenger services in this area. Needs speed restriction if greater than 25kph
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130441&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000130441 | B52 -ST-BW-Clinton-003.360km | CU101652 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.3599 | BW11BL3 | 0.3599 | KM |  |  |  |  | 3.36 |  | 2028-06-30 |  |  | REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 | 5832 | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Unit 3 sunk severely, estimated 75mm, erosion through formation material above starting to occur. Proposed: Remove and Replace Drawing: Risk: High Reason: High risk to track impact from the gap between the sunken unit and neighbouring. top of line issue and loss of ballast around sleepers high risk.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136044&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136044 | B52 -ST-BW-Clinton-003.460km | CU101642 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.46 | BW11BL3 | 0.46 | KM |  |  |  |  | 3.46 | 3.46 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Units are sinking 50-100mm. Will start to impact water flow and causing culvert to get blocked quickly. Proposed:Remove <(>&<)> ReplaceFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136045&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136045 | B52 -ST-BW-Clinton-003.560km | CU101646 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.56 | BW11BL3 | 0.56 | KM |  |  |  |  | 3.56 | 3.56 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Units are sinking 50-100mm. Will start to impact water flow and causing culvert to get blocked quickly. Proposed:Remove <(>&<)> ReplaceFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136046&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136046 | B52 -ST-BW-Clinton-003.660km | CU101665 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.66 | BW11BL3 | 0.66 | KM |  |  |  |  | 3.66 | 3.66 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Units are sinking 50-100mm. Will start to impact water flow and causing culvert to get blocked quickly. Proposed:Remove <(>&<)> ReplaceFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136047&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136047 | B52 -ST-BW-Clinton-003.760km | CU101706 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.76 | BW11BL3 | 0.76 | KM |  |  |  |  | 3.76 | 3.76 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Waiting for remote video footage. But cracked sleeper over culvert and a lot of movement noted. Liekly same condition as other RCP's on this section. Proposed:Remove <(>&<)> ReplaceFinal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109423&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000109423 | B52 -ST-GA-Dalrymple-000.330km | CU200346 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | GA - DALRYMPLE BL |  | 0 | KM | GA05BD0 | 0.335 | GA05BD0 | 0.335 | KM |  |  |  |  | 0.335 |  | 2026-06-30 |  |  |  |  | 4.5 | 2.6 | 3 | 3.7 | 1 | 16.65 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 08.12.2022 Max Holzschuher (R887760) There are cracks in the hocks of most units. Threr is some minor rust stains in the legs of most units in widening 2 right. Minor - moderate spalling and cracks throughout culvert. Propose Remove and Replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105046&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000105046 | B52 -ST-GA-Red Mountain-027.720km | CU200453 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | GA-OC |  | 0 | KM | GA03ML27 | 0.7199 | GA03ML27 | 0.7199 | KM |  |  |  |  | 27.72 |  | 2028-06-30 |  |  | R&R RCBC OR RCP |  | 4 | 1.7 | 3 | 4.2 | 1 | 13.3 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Severe Cracking and sinking in unit 4. Look to be subgrade issues and pumping to be confirmed at site walkout. Proposed: Remove and Replace with RCBC or RCP Risk: Mod-High Reason: May be pumping causing increased deterioration of ballast and top alignment issues. The sinking under track may also cause the joint to open up and allow formation and ballast to fall through.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132846&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000132846 | B52 -ST-BW-Gracemere-005.610km | CU101061 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | GRACEMERE |  | 0 | KM | BW03ML5 | 0.6099 | BW03ML5 | 0.6099 | KM |  |  |  |  | 5.61 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU101061 - B52 -ST-BW-Gracemere-005.610km Defect: Units 3 and 4 (LHS) pumping and will be propped from units 2 to 5. Bolts missing in strengthening beam and previously beam fell down from loss of connection. Regularly holds water in culvert, look to raise invert slightly. RHS has 300A units, consider partial replacements. Proposed: Remove and Replace Drawing: Risk: Mod-High Reason: Pumping of units increases risk of track geometry defects and deteriorates units faster, increasing risk of more severe defects forming suddenly.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136100&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136100 | B52 -ST-GA-Hay Point-003.673km | CU200983 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | HAY POINT |  | 0 | KM | GA03BA3 | 0.673 | GA03BA3 | 0.673 | KM |  |  |  |  | 3.673 | 3.673 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 2.3 | 3 | 4 | 1 | 12.6 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Moderate to sever spalling in localised areas ceiling and legs. Proposed:Patch repairs to be completed to determine if life can be lengthened. Otherwise remove and replace required which will be very costly as very long. Final:Risk:Reason:Time constraint limited full inspection. Assume similar issues as 3.22. Patch repair and Monitor.prop as required. Bat present in this culvert as well. Therefore unsafe. Condition 3.5
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132516&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000132516 | B52 -ST-BW-Marmor-592.550km | CU101241 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | MARMOR |  | 0 | KM | BW01ML592 | 0.55 | BW01ML592 | 0.55 | KM |  |  |  |  | 592.55 |  | 2027-06-30 |  |  | REPLACE |  | 4 | 4.9 | 3 | 4.5 | 1 | 18 | 5832 | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU101241 - B52 -ST-BW-Marmor-592.550km Defect: Base slab severely failed. Spalling of some precast and large sections of insitu section. On 12 monthly inspections. Proposed: Remove and Replace Drawing: Risk: High Reason: High risk to track impact from movement of units and failed base slab.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130570&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000130570 | B52-ST-BW-Marmor-597.670km | CU101603 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | MARMOR |  | 0 | KM | BW01ML597 | 0.67 | BW01ML597 | 0.67 | KM |  |  |  |  | 597.67 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 | 5832 | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: 18 Units long 600RCP. Units 5-18 mod-severe cracking horizontally in ceiling. Proposed: Remove and Replace Drawing: Risk: High Reason: High rsik of collapse and found as reactive work through a remote inspection.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136113&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136113 | B52 -ST-GA-Moranbah North-187.600km | CU200669 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | MORANBA |  | 0 | KM | GA01ML187 | 0.5999 | GA01ML187 | 0.5999 | KM |  |  |  |  | 187.6 | 187.6 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 2.9 | 3 | 4 | 1 | 13.7 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:pumping and propping required. Enit unit moving out from head wasll. Proposed:Remove and ReplaceFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131129&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000131129 | B52 -ST-GA-Red Mountain-026.210km | CU200396 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | RED MOUNTAIN |  | 0 | KM | GA03ML26 | 0.2099 | GA03ML26 | 0.2099 | KM |  |  |  |  | 26.21 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 2.1 | 3 | 3.5 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU200396 UNKNOWN - B52 -ST-GA-Red Mountain-026.210km Defect: Minor to moderate cracking in haunches and legs. Water coming through some of the haunch cracks increasing risk of reinf corrosion. Spalling at joints of loaded units 2/3. more severe in unit 10-3, 13-3/4, 16-3. Inspectors call up units 2/3/4 pumping in all cells. Proposed: Remove and replace. Final: Drawing: Risk: Mod-High Reason: Propped currently to hold until renewal can be completed. Haunch cracks are worsening over time and moistire coming through them increasing risk of collapse and impacting track seriously as cover limited.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136108&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136108 | B52 -ST-GA-Stephens-098.230km | CU200512 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | STEPHEN |  | 0 | KM | GA03ML98 | 0.23 | GA03ML98 | 0.23 | KM |  |  |  |  | 98.23 | 98.23 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.4 | 3 | 3 | 1 | 11.2 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect:Pumping under loaded train and spalling and cracking in pumping units. Also M160 rated. Proposed:Remove and ReplaceFinal:Risk :Reason:2019 SC Units in original section of drain, left side are pumping and base of legs are breaking up. Units also have vertical cracks in legs. Legs of units are only 60mm thick and 2400 long units.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130443&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000130443 | B52 -ST-BW-Tryphinia-130.360km | CU100160 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML130 | 0.3599 | BW03ML130 | 0.3599 | KM |  |  |  |  | 130.36 |  | 2027-06-30 |  |  | REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 | 5832 | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Units severely cracked both in legs and ceiling. Proposed: Remove and Replace Drawing: Risk: High Reason: Severe cracking in legs could lead to unexpected collapse of units under loaded section of track. High risk of derailment should this occur. in current condition if this was delay the likelihood will be unmanageable.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132694&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000132694 | B52 -ST-BW-Tryphinia-131.680km | CU100166 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML131 | 0.68 | BW03ML131 | 0.68 | KM |  |  |  |  | 131.68 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 3.35 | 3 | 4 | 1 | 16 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU100166 DRAIN - B52 -ST-BW-Tryphinia-131.680km Defect: Severe cracks in ceiling of insitu section. Severe cracks in base slab. Proposed: Remove and Replace Drawing: Risk: mod-High Reason: High risk to track impact cracks in ceiling of culvert
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133027&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000133027 | B52 -ST-BW-Tryphinia-133.050km | CU100202 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML133 | 0.05 | BW03ML133 | 0.05 | KM |  |  |  |  | 133.05 |  | 2029-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU100202 - B52 -ST-BW-Tryphinia-133.050km Defect: Rollout found top of units sinking and in poor condition and concern about structural capacity Proposed: Remove and Replace with bridge or unibox on ground improvement system. Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129725&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000129725 | B52 -ST-BW-Umolo-141.630km | CU100560 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | UMOLO |  | 0 | KM | BW36YR141 | 0.63 | BW36YR141 | 0.63 | KM |  |  |  |  | 141.63 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.3 | 3 | 3 | 1 | 12 | 5832 | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect - Remote inspection found severe cracks 12 oclock in RCP units and sereve sinking of some units, most damage under siding rd. moderate large sections of ceiling spalling in insitu BC. WR RCP's has severe cracking longitudinally and circumference. very poor condition. RCP WL, insitu BC O, RCP WR. Proposed Remove and Replace RCBC Risk: High Reason: Severe cracks in ceiling of RCP under track, could deteriorate faster now they have opened up into structural cracks which will cause pumping in track and potentially need grouting to hold until renewed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135516&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000135516 | B52 -ST-BW-Warren-033.810km | CU100419 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | WARREN |  | 0 | KM | BW03ML33 | 0.81 | BW03ML33 | 0.81 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | NON MRSB | 20260630 | Defect - Pumping 2-3mm, some are 300A, but minor cracking and spalling from movement. With large gaps between cells, looks like old bridge replacement. Proposed - Remove and Replace Final - Risk - Mod-high Reason - Pumping will lead to top of line issues with the track and likely TSR's
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133627&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133627 | B52 -ST-NL-Almoola-065.350km | CU300150 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 560000 | Newlands | ALMOOLA |  | 0 | KM | NL01ML65 | 0.3499 | NL01ML65 | 0.3499 | KM |  |  |  |  | 65.35 |  | 2026-06-30 |  |  | CIPP |  | 4.5 | 1.7 | 3 | 3.4 | 1 | 15.3 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: unit 5 broken in half, also looks to being crushed, units 1-12 all with moderate to severe cracks. Possibly pumping. Proposed: remove and replace or cipp pending hydro. Final: Drawing: Risk: Mod-high Reason
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000128770&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000128770 | B52 -ST-GA-Black Mountain-046.360km | CU201071 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1400000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0 | KM | GA01ML46 | 0.3599 | GA01ML46 | 0.3599 | KM |  |  |  |  | 46.36 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 5 | 3 | 4.5 | 1 | 18.1 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Sinking Units 100mm in Cells 1 and 2. temporarily lined with HDPE Proposed: Remove <(>&<)> Replace RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125105&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000125105 | B52 -ST-BW-Boonal-179.610km | CU100348 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1192500 | Blackwater | BOONAL |  | 0 | KM | BW03ML179 | 0.6099 | BW03ML179 | 0.6099 | KM |  |  |  |  | 179.61 |  | 2026-06-30 |  |  |  |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 | 184 | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Very mixed types. But severe cracking and gaps in the RCP section. Pumping at one of the RCPs. Proposed: Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093867&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000093867 | B52 -ST-BW-Westwood-047.700km | CU100457 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 421000 | Blackwater | BW-CL |  | 0 | KM | BW03ML47 | 0.6999 | BW03ML47 | 0.6999 | KM |  |  |  |  | 47.7 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 |  | 1 | 16.1 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: insitu severe spalling and corroded reinforcement. In need of propping Proposed: Remove <(>&<)> Replace RCBC Final: Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081442&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000081442 | B52 -ST-BW-Duaringa-104.650km | CU100332 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1500000 | Blackwater | BW-CL |  | 0 | KM | BW03ML104 | 0.65 | BW03ML104 | 0.65 | KM |  |  |  |  | 104.65 |  | 2026-06-30 |  |  |  |  | 3 | 3.4 |  |  |  | 12 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: pumping under dn track. Proposed: Remove <(>&<)> Replace Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125107&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000125107 | B52 -ST-BW-Boonal-180.490km | CU100179 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1113000 | Blackwater | BW-CL |  | 0 | KM | BW03ML180 | 0.4899 | BW03ML180 | 0.4899 | KM |  |  |  |  | 180.49 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Severe spalling and corroded reinf in ceiling of precast at grate drop chute. Severe cracks in insitu section and curved ceiling due to cracked section. severe cracks throughout insitu ceiling section and walls. Base slab also severely crack and heaving in middle. Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086060&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000086060 | B52 -ST-BW-Ambrose-573.340km | CU101231 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 900000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML573 | 0.34 | BW01ML573 | 0.34 | KM |  |  |  |  | 573.34 |  | 2026-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 17 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: pumping under loaded, possibly hdpe grouted. Sunk in middle of length, causing water to sit in middle worsening pumping. Proposed: Remove and Replace RCBC Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086035&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000086035 | B52 -ST-BW-Midgee-625.730km | CU101500 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1373760 | Blackwater | BW-NCL |  | 0 | KM | BW01ML625 | 0.7299 | BW01ML625 | 0.7299 | KM |  |  |  |  | 625.73 |  | 2035-06-30 |  |  |  |  | 3.5 | 4.5 |  |  |  | 15.3 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: head wall too small for ballast and failing. Units 5 to end dropped 50mm in unit 6 all spans. Proposed: Remove and replace with 4 cells 1200x900. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000116137&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000116137 | B52 -ST-BW-Clinton-003.720km | CU101674 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1520000 | Blackwater | BW-PG |  | 0 | KM | BW53CR3 | 0.7199 | BW53CR3 | 0.7199 | KM |  |  |  |  | 3.72 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: 300A on WL, but old culverts are badly deteriorated. Severe cracking in legs and CBS sinking and holding water. 3 units of the old section of RCBC are severely cracks and on verge of collapse. Had to grout up as unable to fit HDPE through collapsing culvert. High risk of track washout with largest structure. on balloon blocked. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Very High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083452&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000083452 | B52 -ST-MA-Fry-080.400km | CU400614 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML80 | 0.4 | MA01ML80 | 0.4 | KM |  |  |  | 80.3 | 80.3 | 80.3 | 2026-06-30 | MA-01ML | [6 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Overtpping of Rail and track washout at MA-80.300km, multiple washouts at this location historically. Proposed: Additional new Culverts at 80.300km - 2/1200x900mm RCBC Risk: Mod-High Reason: Significant flood risk at this locatio of 80.300 due to insufficient drainage through the track. Multiple washouts have occured at this location historically.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104576&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104576 | B52 -ST-GA-Goonyella-196.040km | CU200720 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1123000 | Goonyella | GA |  | 0 | KM | GA01ML196 | 0.04 | GA01ML196 | 0.04 | KM |  |  |  |  | 196.04 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.4 | 3 | 3.2 | 1 | 12.9 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect - Severe spalling in most legs, with exposed corroded reinf. Proposed - Remove and Replace or Concrete line. Risk - High Reason - Severe corrosion in walls and requires propping to hold until Fy26. Reactive scope for poor condition structure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086036&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086036 | B52 -ST-GA-Stephens-098.230km | CU200512 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 450000 | Goonyella | GA-OC |  | 0 | KM | GA03ML98 | 0.23 | GA03ML98 | 0.23 | KM |  |  |  |  | 98.23 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.4 |  |  |  | 11.3 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Pumping under loaded train and spalling and cracking in pumping units. Also M160 rated. Proposed: Remove and replace Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086062&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086062 | B52 -ST-GA-Bundoora-130.700km | CU200544 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 525000 | Goonyella | GA-OC |  | 0 | KM | GA03ML130 | 0.6999 | GA03ML130 | 0.6999 | KM |  |  |  |  | 130.7 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.4 |  |  |  | 11.3 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: severe spalling in units 2 <(>&<)> 3. Proposed: Remove and Replace RCBC Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086055&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086055 | B52 -ST-NL-Havilah-141.770km | CU300512 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Newlands | HAVILAH | NEWLANDS | 0.0299 | KM | NL01ML141 | 0.8 | NL01ML141 | 0.77 | KM |  |  |  |  | 141.77 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 11.8 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: 15mm crack in base slab under unit 2. 5-20mm laterally displace unit 1-6. Appears to be M160 load rating based on ceiling thickness Proposed: Remove and Replace Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086058&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086058 | B52 -ST-MA-Fry-086.100km | CU400186 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Moura | MA |  | 0 | KM | MA01ML86 | 0.1 | MA01ML86 | 0.1 | KM |  |  |  |  | 86.1 |  | 2026-06-30 |  |  |  |  | 3.5 | 1 |  |  |  | 10.5 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Outlet scouring and high risk of track washout and formation and rail not flood immune. Inadequate cover for CMP will also increase risk of washout. CMP itself in reasonable condition. Proposed: "Remove and replace - IInsufficient cover, if Aurizon wishes to remove and replace then 1200x900 RCBC unit required to achieve both formation and top of rail immunity. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122331&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000122331 | B52 -ST-BW-Midgee-625.190km | CU101415 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1373760 | Blackwater | MIDGEE | ROCKLANDS | 0 | KM | BW01ML625 | 0.19 | BW01ML625 | 0.19 | KM |  |  |  |  | 625.19 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.5 | 3 | 4.4 | 1 | 17.5 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Moderate to sever spalling in ceiling of units in Cells 2,3 and units sunk approx 40mm and minor pumping under loaded train. Proposed: Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092313&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000092313 | B52 -ST-NL-Buckley-007.760km | CU300303 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 502000 | Newlands | NL |  | 0 | KM | NL01ML7 | 0.76 | NL01ML7 | 0.76 | KM |  |  |  |  | 7.7 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 11.8 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Moderate to severe spalling in legs of units under track all cells. Proposed: Remove and Replace with 3/1200x900 RCBC, must be completed same year as 7.700km Drawing: AUR-Q-0740-4540 Risk: Mod-High Reason: Pumping under loaded trains, therefore detoration will be increased due to pumping action from loaded trains.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109378&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000109378 | B52 -ST-GA-Waitara-098.990km | CU201138 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 4000000 | Goonyella | WAITARA |  | 0 | KM | GA01ML98 | 0.9899 | GA01ML98 | 0.9899 | KM |  |  |  |  | 98.99 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.7 | 3 | 4.4 | 1 | 17.7 | 184 | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Unit 5 Pumping under loaded traffic. Regular severe spalling and exposed corroded reinf. Proposed: Remove <(>&<)> Replace RCBC Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000099417&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000099417 | B52 -ST-BW-Gracemere-009.500km | CU100107 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | BW-CL |  | 0 | KM | BW03ML9 | 0.5 | BW03ML9 | 0.5 | KM |  |  |  |  | 9.5 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.8 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Defect: Unit 4-7 pumping 2-4mm. and movement in legs 25mm similar movement in surrounding units. This unit propped due to crushing of legs. Proposed: Concrete lining to be considered pending hydro and pumping issue in cell 4. Otherwise Remove and replace Drawing: Risk: Moderate - High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044211&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000044211 | B52 -ST-BW-Rangal-001.160km | CU101044 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | BW-KA |  | 0 | KM | BW05ML1 | 0.085 | BW05ML1 | 0.085 | KM |  |  |  |  | 1.16 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.8 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.09.2020 10:43:19 AUSQLD Edward Brooks (R884255) * Defect: "Spalling in legs and roof. * Poor concrete material with limited fines in areas. Concerned throughout. " * Propose: Consider tunnel line for design"
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086064&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086064 | B52 -ST-NL-Buckley-007.700km | CU300262 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 125000 | Newlands | NL |  | 0 | KM | NL01ML7 | 0.6999 | NL01ML7 | 0.6999 | KM |  |  |  |  | 7.7 |  | 2026-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 11.8 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Defect: Moderate spalling in legs.must be completed with 7.760km Proposed: Grout and divert to 7.760km Drawing: AUR-Q-0740-4530/4531 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135513&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000135513 | B52 -ST-BW-Tryphinia-132.972km | CU100322 | CIVIL | STRUCTURES | RCBC-UNIBOX | DESIGN | 1 | SITE | 40000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML132 | 0.9719 | BW03ML132 | 0.9719 | KM |  |  |  |  | 132.972 |  | 2029-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | NON MRSB | 20260630 | Defect - Rollout found top of units sinking and in poor condition and concern about structural capacity. Cell 10 25mm drop . Pumping under loaded. Proposed - Remove and Replace with bridge or unibox. Consider ground improvement system if required. Final - Risk - Mod-high Reason - Pumping will lead to top of line issues with the track and likely TSR's
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086051&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086051 | B12 -ST-NL-Armuna-014.600km | BR300424 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 1500000 | Newlands | NL |  | 0.0379 | KM | NL01ML14 | 0.5899 | NL01ML14 | 0.628 | KM |  |  |  |  | 14.6 |  | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Propped 60 kph Speed restriction overload 26.5-27.5TAL, Under load capacity Proposed: Strengthening in accordance with Fryessinet Recommendation in 4/8/20 report. Based on freyssinet report 1.4M to Structural Strengthening and approx 4M to replace Drawing: Risk: Reason: Strategic
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086052&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000086052 | B12 -ST-NL-Armuna-015.700km | BR300147 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 1500000 | Newlands | NL |  | 0.014 | KM | NL01ML15 | 0.683 | NL01ML15 | 0.6969 | KM |  |  |  |  | 15.7 |  | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Propped 60 kph Speed restriction overload 26.5-27.5TAL, Under load capacity Proposed: Remove and replace with RCBC/Unicell based on comparison of cost to repair and strengthen in Freyssinet report. Drawing: Risk: Reason: Strategic
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094595&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094595 | B52 -ST-MA-Fry-080.090km | CU400194 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 400000 | Moura | MA |  | 0 | KM | MA01ML80 | 0.0899 | MA01ML80 | 0.0899 | KM |  |  |  |  | 80.09 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 3 | 1 | 11.1 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Defect: Invert of CMP completely corroded and miss-shapped on the ends. Unsure due to shape of CMP whether CIPP will be option on this, so selected replace above to be conservative. Proposed: CIPP line or remove and replace confirm in design Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135518&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000135518 | B52 -ST-BW-Aroona-091.900km | CU100456 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | AROONA |  | 0 | KM | BW03ML91 | 0.9 | BW03ML91 | 0.9 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | CIPP OR R&R |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | NON MRSB | 20260630 | Defect - Regular minor to severe cracking and differential settlement in majority of units. Proposed - CIPP or Remove and Replace pending hydro Final - Risk - Mod-high Reason - May lead to top of line issue with additional settlement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132476&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000132476 | B52 -ST-BW-Aroona-092.350km | CU100091 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | AROONA |  | 0 | KM | BW03ML92 | 0.3499 | BW03ML92 | 0.3499 | KM |  |  |  |  | 92.35 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 3.35 | 3 | 4 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU100091 - B52 -ST-BW-Aroona-092.350km Defect: Failing headwall. Butress wall have no pile and appear to be rotating. First 2 units and some third units all cells with cracks horizontal (minor to moderate) Proposed: CIPP RCP, confirm 1530 Ok to line. Remove and replace head wall, may benfit from 1-2 more units to get headwall away from track. Risk: Mod Reason: Including this now with CIPP may prevent more costing remove and replace of 22 cell system in the future.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133337&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000133337 | B52 -ST-NO-Callemondah-529.000km | CU101580 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 40000 | Moura | CALLEMONDAH |  | 0 | KM | NC02ML529 | 0 | NC02ML529 | 0 | KM |  |  |  |  | 529 |  | 2028-06-30 |  |  | CIPP |  | 4 | 1.8 | 3 | 3.4 | 1 | 13.6 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | CU101580 - B52 -ST-NO-Callemondah-529.000km Defect: Small section partially collapsed. Seevere cracking in other units and spalling. Proposed: CIPP line or Remove and replace pending hydro and shape considerations. Final: Drawings: Risk: Mod-High Reason: Passenger services use this section of the line and small section already broken out, high water flow through this culvert is likely to undermine the track from the broken section and lead to top of line defects and risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135580&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000135580 | B52 -ST-BW-Westwood-036.540km | CU100488 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 40000 | Blackwater | WESTWOOD |  | 0 | KM | BW03ML36 | 0.54 | BW03ML36 | 0.54 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  | 2024-03-28 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | NON MRSB | 20260630 | Defect - units U4 horizontal severe cracks, high risk of increased deterioration. Proposed - CIPP pending hydro Final - Risk - Mod-high Reason - If not complete in FY28 risk will be lining may not be an option and a track closure will be required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125106&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000125106 | B52 -ST-BW-Boonal-180.470km | CU100313 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 327540 | Blackwater | BW-CL |  | 0 | KM | BW03ML180 | 0.4699 | BW03ML180 | 0.4699 | KM |  |  |  |  | 180.47 |  | 2027-06-30 |  |  | CIPP |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Defect: Severe cracks in RCPs, only 6 monthly remotes to hold. Can't see cracks from end, only on remote Proposed: CIPP lining pending hydro. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103323&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000103323 | B52 -ST-BW-Curragh-008.430km | CU101728 | CIVIL | STRUCTURES | RCP-CONCRETE LINE | RENEWAL | 1 | SITE | 1056000 | Blackwater | CURRAGH |  | 0 | KM | BW12ML8 | 0.4299 | BW12ML8 | 0.4299 | KM |  |  |  |  | 8.43 |  | 2026-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 4 | 1.3 | 3 | 3.2 | 1 | 12 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Deferred scope as approved by Ryan Bell see attached email. Defect: moderate Spalling at joints <(>&<)> some horz cracking in unit 3-3. Likely slow speed as balloon, so pumping less likely. 2022 inspection has found increased speed of deterioration and voids behind unit 3 joints under track. Proposed: Line Final: 200mm thick Concrete line, hydro found 1% AEP for TOR <(>&<)> Formation. Drawing: AUR-Q-0772-4073 Risk: High Reason: Voids between the track and RCP provide high risk of movement in track alignment. This increases the risk of derailments. Also from 2020 to 2022 inspection, deterioration rate of this joint has increased, increasing risk of more movement if delayed from FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052615&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000052615 | B52 -ST-BW-Westwood-045.480km | CU100509 | CIVIL | STRUCTURES | REMOVE & REPLACE | RENEWAL | 1 | SITE | 1400000 | Blackwater | BW-CL |  | 0 | KM | BW03ML45 | 0.4799 | BW03ML45 | 0.4799 | KM |  |  |  |  | 45.48 |  | 2026-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  | 2024-03-28 |  | Culvert Renewals | BESPOKE DESIGN |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 26.02.2020 15:51:19 AUSQLD Peter Rayner (R003851) * Defect - upgrade with 602.600 for afflux issues on TMR rd and for construction timeframes. - Proposed Renewal - remove and replace 2/3000x3750 unibox * 12.05.2020 16:19:41 AUSQLD Edward Brooks (R884255) * Scope deferred to FY23 from FY22 due to budget limitations. This work can only happen in the same year as NC-602.600, as hydro dependent.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137947&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137947 | C21 GA BOLINGBROKE 67.239 - 68.905 | GA-02ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.666 | TRACK KM | 2747522 | Goonyella | BOLINGBROKE | BALOOK | 1.6659 | KM | GA02ML67 | 0.2389 | GA02ML68 | 0.905 | KM | 31 | 2433 | 3.348 | 1.666 | 67.239 | 68.905 | 2026-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Cutting in western side of LX5765 - Gravel Xing Removing 1999 BHP 60lg SC both legs Wear LR - 11, 0mm RR - 10, 0mm Sleepers are 28T Pandrol E clip 1993 - sleepers are derailment damaged Cut out: VAS 60kg 2022 H
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000139062&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000139062 | C21 BW BOONAL LOADOUT 180.561 - 180.694 | BW-17ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.133 | TRACK KM | 1500000 | Blackwater | BOONAL LOADOUT | BOONAL LOADOUT | 0.133 | KM | BW17ML180 | 0.561 | BW17ML180 | 0.6939 | KM | 3 | 195 | 324 | 0.133 | 180.561 | 180.694 | 2026-06-30 | SINGLE | BOTH |  |  | 4.5 | 1.1 | 1 | 1.6 | 1 | 7.2 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | This is re railing through the loadout Rail is sitting ontop of concrete not encased Rail fastenings need to be assessed Rail break occurred here due to servere corrossion - 21/03/2024
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115024&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115024 | C21 BW CURRAGH EXIT 12.758 - 13.833 | BW-12ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.126 | TRACK KM | 1856969 | Blackwater | CURRAGH BALLOON EXIT | CURRAGH BALLOON EXIT | 1.1259 | KM | BW12ML12 | 0.758 | BW12ML13 | 0.8329 | KM | 21 | 1603 | 2.268 | 1.126 | 12.758 | 13.833 | 2026-06-30 | EXIT | BOTH |  |  | 3.5 | 1.2 | 1 | 1.7 | 1 | 5.95 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Notification in process | SCPR |  | 20260630 | Cutting in after 1.2B Points Cutting out before 12A points Equality 12km 1051m = 13km (51m)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115023&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115023 | C21 BW CURRAGH BALLOON EXIT 12.178-12.72 | BW-12ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.555 | TRACK KM | 915291 | Blackwater | CURRAGH BALLOON LOOP EXIT | CURRAGH BALLOON LOOP EXIT | 0.555 | KM | BW12ML12 | 0.1779 | BW12ML12 | 0.7329 | KM | 11 | 800 | 1188 | 0.558 | 12.178 | 12.733 | 2026-06-30 | EXIT | BOTH |  |  | 3.5 | 1.2 | 1 | 1.7 | 1 | 5.95 | 248 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Cutting in after load out slab Cutting out before 1.2B Points Scope pushed to FY26 to be completed with 002000115024 - allows for better efficiencies and asset condtion allows for scope to be postponed for one year. SCR - 248
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134008&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000134008 | C21 MA Callide 12.980 - 13.290 | MA-07ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.31 | TRACK KM | 511244 | Moura | DAKENBA | CALLIDE MINE | 0.3079 | KM | MA07ML12 | 0.9799 | MA07ML13 | 0.2899 | KM | 6 | 453 | 0.648 | 0.308 | 12.98 | 13.29 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 1 | 1 | 1.5 | 1 | 5.25 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Driver here is to remove worn 47kg rail approaching limits - need to finalize Sleepers 12.980-13.290km - Replace. Broken due to derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130703&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130703 | C21 DUARINGA 105.46 - 105.815 | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.355 | TRACK KM | 585456 | Blackwater | DUARINGA | WALLAROO | 0.3549 | KM | BW03ML105 | 0.46 | BW03ML105 | 0.8149 | KM | 7 | 346 | 0.756 | 0.355 | 105.46 | 105.815 | 2026-06-30 |  | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130706&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000130706 | C21 DUARINGA 108.382 - 108.624 | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.242 | TRACK KM | 399100 | Blackwater | DUARINGA | WALLAROO | 0.2419 | KM | BW03ML108 | 0.382 | BW03ML108 | 0.6239 | KM | 5 | 354 | 0.23 | 0.242 | 108.382 | 108.624 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131069&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000131069 | C21 GERMAN CREEK 129.729 - 131.779 | GA-22ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 2.049 | TRACK KM | 3380805 | Goonyella | GERMAN CREEK | GERMAN CREEK | 2.0489 | KM | GA22ML129 | 0.7289 | GA22ML131 | 0.779 | KM | 38 | 730 | 4.104 | 2.049 | 129.729 | 131.779 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.2 | 1 | 1.7 | 1 | 6.46 | 290 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Post Scope Walkouts: End point changed to tie into the back of a turnout and clear the spring.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138830&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138830 | C21 GA GOONYELLA TLO 198.170 - 198.245 | GA-13ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.075 | TRACK KM | 500000 | Goonyella | GOONYELLA LOADOUT | GOONYELLA LOADOUT | 0.0749 | KM | GA13ML198 | 0.17 | GA13ML198 | 0.2449 | KM |  |  |  |  | 198.17 | 198.245 | 2026-06-30 |  |  |  |  | 3.8 | 2.1 | 1 | 2.5 | 2 | 9.5 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114438&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000114438 | C21 NL KAILI 1158.698 - 1159.517 | NC-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.819 | TRACK KM | 1349024 | Newlands | KAILI | DURROBURRA | 0.8179 | KM | NC03ML1158 | 0.6979 | NC03ML1159 | 0.517 | KM | 17 | 1196 | 1.836 | 0.819 | 1158.698 | 1159.517 | 2026-06-30 | SINGLE | BOTH |  |  | 3.5 | 3.2 | 1 | 3.1 | 1 | 10.85 | 247 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | RAIL: 1158.698 - 1158.886 - 4 RAILS SLEEPERS: 1158.698 - 1158.939 - 352 SLEEPERS Scope increased at the higher chainage due to wrong tech scope. Existing 53kg rail extends past tech scope finishing point. LX7195 is also 53kg <(>&<)> fist Sleepers however there is a proposed upgrade in FY26. We will unload rail for LX Upgrade. However, we will stop 27m before level crossing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102561&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000102561 | C21 TU NL MCNAUGHTON 84.200 - 84.421 | NL-04ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.221 | TRACK KM | 364467 | Newlands | MCNAUGHTON BALLOON | MCNAUGHTON BALLOON | 0.221 | KM | NL04ML84 | 0.2 | NL04ML84 | 0.4209 | KM | 4 | 324 | 0.432 | 0.221 | 84.2 | 84.421 | 2026-06-30 | SINGLE | BOTH |  |  | 3.8 | 1.7 | 1 | 2.2 | 1 | 8.36 | 250 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | McNaughton Loadout Track Upgrade - to be completed with weighbridge renewal Heavy coal fouling through extents making inspection difficult. Some corroded lugs. Slab extents 84.352-84.401km (approx) LX3299 - rail encased in concrete Rail encased in concrete on arrival and exit side of load out Condition of clips / rail through load out to be assessed during walkouts Corrosion and size of rail is driving renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137490&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137490 | C21 WALLAROO 115.213 - 115.657 | BW-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.444 | TRACK KM | 732233 | Blackwater | WALLAROO | TRYPHINIA | 0.444 | KM | BW03ML115 | 0.2129 | BW03ML115 | 0.657 | KM | 9 | 649 | 0.972 | 0.444 | 115.213 | 115.657 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136387&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136387 | C21 BINBEE SIDING 45.548 - 45.901 | NL-02SD | CIVIL | TRACK UPGRADE | SIDING | RENEWAL | 0.353 | TRACK KM | 582158 | Newlands | BINBEE SIDING | BINBEE SIDING | 0.3529 | KM | NL02SD45 | 0.548 | NL02SD45 | 0.901 | KM | 7 | 516 | 0.756 | 0.353 | 45.548 | 45.901 | 2026-06-30 | BAD ORDER SIDING | BOTH |  |  | 3.7 | 1.7 | 1 | 2.2 | 1 | 8.14 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Removing existing 82lb rail and timber and steel sleepers Can use part worn rail here
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137546&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000137546 | C21 BW EDUNGALBA SIDING 84.823 - 85.138 | BW-09SD | CIVIL | TRACK UPGRADE | SIDING | RENEWAL | 0.611 | TRACK KM | 1007645 | Blackwater | EDUNGALBA SIDING | EDUNGALBA SIDING | 0.6109 | KM | BW09SD84 | 0.8229 | BW09SD85 | 0.138 | KM | 23 | 892 | 1.296 | 0.611 | 84.823 | 85.138 | 2026-06-30 | SIDING | BOTH |  |  | 3.8 | 3.35 | 1 | 3.2 | 1 | 12.16 |  | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | This is siding scope, there are three parts to it, please see tech scope for breakdown Part worn rail can be used here Km's are taking from mainline, actual length is 611m
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111599&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000111599 | C21 BW WARREN SIDING 23.402 - 23.500 | BW-05SD | CIVIL | TRACK UPGRADE | SIDING | RENEWAL | 0.098 | TRACK KM | 161619 | Blackwater | WARREN SIDING | WARREN SIDING | 0.098 | KM | BW05SD23 | 0.402 | BW05SD23 | 0.5 | KM | 2 | 144 | 0.216 | 0.098 | 23.402 | 23.5 | 2026-06-30 | SIDING | BOTH |  |  | 4 | 3.35 | 1 | 3.2 | 1 | 12.8 | 264 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Part worn rail can be used here Post Site Walkout: Chnages to ony replace between catch points as the catch points cannot be renewed at this time. SCR 236
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136412&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000136412 | BW SLAB TRACK RENEWALS | BW | CIVIL | TRACK UPGRADE | SLAB TRACK | REACTIVE WORKS | 0 | LUMPSUM | 300000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Slab Track reactive works funding
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138088&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000138088 | GA SLAB TRACK RENEWALS | GA | CIVIL | TRACK UPGRADE | SLAB TRACK | REACTIVE WORKS | 0 | LUMPSUM | 300000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 | 1 | 5 | 1 | 25 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Slab Track Renewals Reactive Funding
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138983&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138983 | C21 BW CALLEMONDAH PROV SHED 0-0.078 | BW-22YR | CIVIL | TRACK UPGRADE | SLAB TRACK | RENEWAL | 0.078 | TRACK KM | 1560000 | Blackwater | CALLEMONDAH PROVISIONING SHED | CALLEMONDAH PROVISIONING SHED | 0.0779 | KM | BW22YR0 | 0 | BW22YR0 | 0.0779 | KM | 2 |  | 0.216 | 0.78 | 0 | 0.078 | 2026-06-30 | CLINTON SPUR3/ARRV 5 | BOTH |  |  | 4 | 4.8 | 1 | 3.8 | 1 | 15.2 |  | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Rail is encased in concrete requires new rails new pandrol plates
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121468&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000121468 | C21 BW KINROLA TLO 18.527 - 18.595 | BW-05ML | CIVIL | TRACK UPGRADE | SLAB TRACK | RENEWAL | 0.068 | TRACK KM | 84991 | Blackwater | KINROLA TLO | KINROLA TLO | 0.068 | KM | BW05ML18 | 0.527 | BW05ML18 | 0.5949 | KM | 2 | 49 | 0.216 | 0.068 | 18.527 | 18.595 | 2026-06-30 | SINGLE | BOTH |  |  | 4 | 1.2 | 1 | 1.7 | 1 | 6.8 | 244256 | 2024-03-28 |  | Permanent Way -Other | LIKE FOR LIKE |  | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Track Upgade required as rail is severely corroded through loadout - sleepers need to be replaced as lugs are corroded also as well as plates. Rail is not encased in concrete.SCR 244 Updated tech scope attached. Original tech scope incorrectly listed left leg at cut out as 60kg. Both legs at higher chainage end are actually 50kg. Moved to FY26 to allow for successful planning - SCR 256
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124078&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000124078 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4444240 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Turnout Components | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R87234) 28.03.2024 All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). $1.177,435 (12%) of the total BW budget is explicitly allocated for post-installation follow-up manual hand grinding via FSCL and planning. The manual hand grinding must be completed, and the QA form must be returned to Asset Management via Safety Culture. If support is required, it must be raised to namtrackassets@aurizon.com.au 20% increase from FY25 + 12% to enable follow-up grinding works (post-installation).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124077&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000124077 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4848261 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Turnout Components | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R87234) 28.03.2024 All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). $1.177,435 (12%) of the total GA budget is explicitly allocated for post-installation follow-up manual hand grinding via FSCL and planning. The manual hand grinding must be completed, and the QA form must be returned to Asset Management via Safety Culture. If support is required, it must be raised to namtrackassets@aurizon.com.au 20% increase from FY25 + 12% to enable follow-up grinding works (post-installation).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124079&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000124079 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 888848 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Turnout Components | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R87234) 28.03.2024 All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). $1.177,435 (12%) of the total MA budget is explicitly allocated for post-installation follow-up manual hand grinding via FSCL and planning. The manual hand grinding must be completed, and the QA form must be returned to Asset Management via Safety Culture. If support is required, it must be raised to namtrackassets@aurizon.com.au 20% increase from FY25 + 12% to enable follow-up grinding works (post-installation).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124100&DY_MAB=X&~OKCODE=ONLI | FY26 |  | REACTIVE RENEWALS | COAL | 002000124100 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 808042 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | Turnout Components | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R87234) 28.03.2024 All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). $1.177,435 (12%) of the total NL budget is explicitly allocated for post-installation follow-up manual hand grinding via FSCL and planning. The manual hand grinding must be completed, and the QA form must be returned to Asset Management via Safety Culture. If support is required, it must be raised to namtrackassets@aurizon.com.au 20% increase from FY25 + 12% to enable follow-up grinding works (post-installation).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073350&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073350 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 174A | TO001053 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | 174A | 0.0229 | KM | NC04YR528 | 0.627 | NC04YR528 | 0.6039 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:11:58 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:19:38 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura turnout asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073358&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073358 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 174B | TO001054 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | 174B | 0.0229 | KM | NC03YR528 | 0.5689 | NC03YR528 | 0.5919 | KM |  |  |  |  | 528.569 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:13 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:15:33 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073353&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073353 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 10 | TO001101 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 10 | 0 | KM | NC11YR527 | 0.7039 | NC11YR527 | 0.7039 | KM |  |  |  |  | 527.704 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:03 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:19:15 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073355&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073355 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 170A | TO001052 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 170A | 0.032 | KM | NC08YR527 | 0.762 | NC08YR527 | 0.7299 | KM |  |  |  |  | 527.762 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:08 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:16:53 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura turnout asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043315&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000043315 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 170B | TO001102 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 170B | 0.0269 | KM | NC02ML527 | 0.761 | NC02ML527 | 0.788 | KM |  |  |  |  | 527.761 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 04.08.2020 16:57:01 AUSQLD Lachlan Prescott (R881571) * MOVED TO FY23 UNDER PCR2515 * 05.11.2020 15:03:00 AUSQLD Lachlan Prescott (R881571) * Reduced by $16,440 to $189060 to strip design cost into FY22.PCR4728 * 09.03.2021 14:19:46 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura turnout asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073359&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073359 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 178A | TO001059 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 178A | 0.028 | KM | NC03YR529 | 0.0749 | NC03YR529 | 0.047 | KM |  |  |  |  | 529.075 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:14 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:15:56 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073360&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073360 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 178B | TO001060 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 178B | 0.029 | KM | NC04YR529 | 0.005 | NC04YR529 | 0.034 | KM |  |  |  |  | 529.005 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:14 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:16:31 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073354&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000073354 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 181A | TO001063 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 181A | 0.0379 | KM | NC01PL528 | 0.252 | NC01PL528 | 0.2899 | KM |  |  |  |  | 528.252 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:03 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:17:21 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073356&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073356 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE 193A | TO001079 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE 193A | 0.017 | KM | NC07CT529 | 0.268 | NC07CT529 | 0.2849 | KM |  |  |  |  | 529.268 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:08 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:17:45 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073357&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073357 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE A2 | TO001082 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE A2 | 0 | KM | NC07YR529 | 0.0539 | NC07YR529 | 0.0539 | KM |  |  |  |  | 529.054 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:08 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:18:06 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. PCR number is to be added.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044656&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044656 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE A3 | TO001083 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE A3 | 0 | KM | NC07YR529 | 0.07 | NC07YR529 | 0.07 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 |  | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF |  | 20260630 | * 09.03.2021 14:00:46 AUSQLD Lachlan Prescott (R881571) * Cost updated to 20k per PCR4825. Bulk of costs in original estimate were incurred through removal of overheads, which will now be spread over a series of renewals under Gladstone Yard Turnout Rationalisation Plan * 07.04.2021 14:52:18 AUSQLD Lachlan Prescott (R881571) * To be removed in FY21 - awaiting approval of PCR 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073352&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000073352 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ GE A6 | TO001086 | CIVIL | TURNOUTS | COMPONENT | RENEWAL | 1 | TURNOUT | 33333 | Moura | GLADSTONE | GE A6 | 0.025 | KM | NC04YR528 | 0.888 | NC04YR528 | 0.913 | KM |  |  |  |  | 528.888 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 3 | 4 | 1 | 19.5 |  | 2024-03-28 | 2021-10-05 | Turnout Components | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF | FY23 IN NON MRSB | 20260630 | * 01.03.2021 10:12:03 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 09.03.2021 14:18:33 AUSQLD Lachlan Prescott (R881571) * Cost reduced to 50k due to scale efficiencies 27/10/2021 Alex Rohweder (R872340) Defer the project to FY26, util non-coal (non-QAL) funding and business case is final approved. 22/03/2024 Alex Rohweder (R872340) This asset is Coal asset. "Renew compoenent to extend asset life fit for purpose" - Moura Turnout Asset Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138530&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138530 | Non Coal Reactive Renewals - Turnout Com | BW | CIVIL | TURNOUTS | COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM |  | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138531&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138531 | Non Coal Reactive Renewals - Turnout Com | GA | CIVIL | TURNOUTS | COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138533&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138533 | Non Coal Reactive Renewals - Turnout Com | MA | CIVIL | TURNOUTS | COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM |  | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Turnout Components | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138532&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | NON-COAL | 002000138532 | Non Coal Reactive Renewals - Turnout Com | NL | CIVIL | TURNOUTS | COMPONENTS | REACTIVE WORKS | 1 | LUMPSUM |  | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044005&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044005 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ BKER1.2A | TO000214 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1515000 | Goonyella | BALOOK | BK ER1.2A | 0.0539 | KM | GA01ML74 | 0.802 | GA01ML74 | 0.802 | KM |  |  |  |  | 74.8 |  | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094152&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094152 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH259A | TO001127 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1515000 | Blackwater | CALLEMONDAH | CH259A | 0.0359 | KM | BW07YR536 | 0.0519 | BW07YR536 | 0.016 | KM |  |  |  |  | 536.052 |  | 2026-06-30 |  |  | POINTS & X 60KG/M 12 CS SNX TG |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL CH259A Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). Alex Rohweder (R872340) FY22/FY23 DESIGN for FY25 CONSTRUCTION ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kat and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094151&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094151 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ CH260A | TO001136 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1515000 | Blackwater | CALLEMONDAH | CH260A | 0.035 | KM | BW10YR536 | 0.0919 | BW10YR536 | 0.057 | KM |  |  |  |  | 536.092 |  | 2026-06-30 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL CH260A Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). Alex Rohweder (R872340) FY22/FY23 DESIGN for FY25 CONSTRUCTION ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123288&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000123288 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ PS 12A/B | TO000471 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1215000 | Goonyella | PRAGUELANDS | PS12A/B | 0.05 | KM | GA02ML14 | 0.4769 | GA02ML14 | 0.527 | KM |  |  |  |  | 14.472 | 14.426 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123285&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000123285 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ PS 12C/D | TO000441 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1215000 | Goonyella | PRAGUELANDS | PS12C/D | 0.049 | KM | GA01ML14 | 0.5779 | GA01ML14 | 0.529 | KM |  |  |  |  | 14.472 | 14.426 | 2026-06-30 |  |  |  |  | 5 | 4 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) PCR 5705 https://k2workflow.aurizon.com.au/Runtime/Runtime/Form/Project__centralS tation__PCR__Form/?<(>&<)>id=5705
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115860&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115860 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ PS 8A/B | TO000442 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1215000 | Goonyella | PRAGUELANDS | PS8A/B | 0.05 | KM | GA01ML14 | 0.3589 | GA01ML14 | 0.4089 | KM |  |  |  |  | 14.377 | 14.427 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115861&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115861 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ PS 8C/D | TO000470 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1215000 | Goonyella | PRAGUELANDS | PS8C/D | 0.0459 | KM | GA02ML14 | 0.455 | GA02ML14 | 0.4089 | KM |  |  |  |  | 14.472 | 14.426 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Alex Rohweder (R872340) 28.03.2024 Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077234&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000077234 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WO12AB | TO000319 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 2015000 | Goonyella | WANDOO | WO12AB | 0.048 | KM | GA02ML86 | 0.058 | GA02ML86 | 0.1059 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Renewals | BESPOKE DESIGN |  | MEDIUM | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | * 13.05.2021 11:19:43 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Post rail grinding and follow up resurfacing within 3 months post installation. All CAPEX invested turnout rail steelworks require - post installation follow-up manual hand grinding must be planned, completed, and QA documented via Safety Culture. GRINDING REQUIREMENTS: The first grinding must occur within two (2) weeks from the installation date. Follow up at four weekly intervals post first grind until the 16th week (including the 16th week). 13.05.2021 11:19:43 AUSQLD Tracy Holmes (R870040) Allocated to FY25, to be confirmed later. Costs TBC (Alex Rohweder) Readjust the requried end date to 30.06.2025 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124052&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000124052 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 217A/B | TO001183 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 14200 | Blackwater | CALLEMONDAH | 217 A/B | 0.032 | KM | BW21YR2 | 0.3119 | BW21YR2 | 0.28 | KM |  |  |  |  | 534.698 |  | 2026-06-30 |  |  |  |  | 4 | 5 | 5 | 5 | 1 | 20 | 5773 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 217A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 235A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over to CH217 turnout (from CH 274). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts. PCR 5349 20/11/2023 Alex Rohweder (R972340) Move to FY26 to align with FY29 Construction project sequence. PCR 5773
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094143&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000094143 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 235A/B | TO001182 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 14200 | Blackwater | CALLEMONDAH | 235A/B | 0.0309 | KM | BW21YR2 | 0.199 | BW21YR2 | 0.168 | KM |  |  |  |  | 2.178 | 2.147 | 2026-06-30 |  |  |  |  | 4 | 5 | 5 | 5 | 1 | 20 | 5773 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 235A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over with CH 235A/B turnout (from CH 276A). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts PCR 5349 20/11/2023 Alex Rohweder (R972340) Move to FY26 to align with FY29 Construction project sequence. PCR 5773
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094145&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000094145 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 281A/B | TO001139 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 14200 | Blackwater | CALLEMONDAH | 281A/B | 0.033 | KM | BW11BL2 | 0.4949 | BW11BL2 | 0.528 | KM |  |  |  |  | 2.495 | 2.528 | 2026-06-30 |  |  |  |  | 4 | 5 | 5 | 5 | 1 | 20 | 5773 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ EARLY D ¦ CH 281A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 20/11/2023 Alex Rohweder (R972340) Move to FY26 to align with FY29 Construction project sequence. PCR 5773
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052807&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000052807 | TURNOUTS¦ DESIGN¦ EARLY DESIGN ¦WDER1.2A | TO000705 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 18740 | Blackwater | WESTWOOD | WD ER1.2A | 0.0539 | KM | BW04ML46 | 0.765 | BW04ML46 | 0.765 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 3 | 4 | 1 | 16.8 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.02.2020 11:43:52 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is major refurbishment including upgrade from RBM to SNX. * 10.05.2021 11:03:12 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 28.02.2020 11:43:52 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is major refurbishment including upgrade from RBM to SNX. 10.05.2021 11:03:12 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 28.02.2020 11:43:52 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is major refurbishment including upgrade from RBM to SNX. 10.05.2021 11:03:12 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882 30.03.2022 Alex Rohweder (R872340) Design in FY24 to construct in FY26. Budget adjusted. The original was quite insufficent($33K). TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ WD ER1.2A 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with WD7B/C. FY24 Design budget adjusted to 10% off the total desig nbudget = $18,740 out of $187,400
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100758&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000100758 | TURNOUTS ¦DESIGN ¦EARLY DESIGN¦ WD 7B/C | TO000670 | CIVIL | TURNOUTS | DESIGN - EARLY D | DESIGN | 1 | TURNOUT | 18740 | Blackwater | WESTWOOD | WD7B/C | 0.0369 | KM | BW03ML47 | 0.505 | BW03ML47 | 0.468 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 3 | 4 | 1 | 16.8 | 5398 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ WD 7B/C 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with WD ER1.2A. FY24 Design budget adjusted to 10% off the total desig nbudget = $18,740 out of $187,400
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123740&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000123740 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AE 11A/B | TO000904 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 49500 | Blackwater | AMBROSE | AE 11A/B | 0.048 | KM | BW02ML570 | 0.2099 | BW02ML570 | 0.162 | KM |  |  |  |  | 568.002 | 567.962 | 2026-06-30 |  |  |  |  | 4.5 | 4 | 3 | 4 | 1 | 19.8 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123743&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000123743 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AE 11C/D | TO000851 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 49500 | Blackwater | AMBROSE | AE 11C/D | 0.049 | KM | BW01ML570 | 0.111 | BW01ML570 | 0.16 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 4 | 3 | 4 | 1 | 19.8 | 5398 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ AE 11C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93 ,700 out of $187,400 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115853&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000115853 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AE 12A/B | TO000850 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 49500 | Blackwater | AMBROSE | AE 12A/B | 0.04 | KM | BW01ML570 | 0.334 | BW01ML570 | 0.2939 | KM |  |  |  |  | 568.002 | 567.962 | 2026-06-30 |  |  |  |  | 4.5 | 4 | 3 | 4 | 1 | 19.8 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123497&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000123497 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AE 12C/D | TO000905 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 49500 | Blackwater | AMBROSE | AE12C/D | 0.05 | KM | BW02ML570 | 0.232 | BW02ML570 | 0.2819 | KM |  |  |  |  | 568.002 | 567.962 | 2026-06-30 |  |  |  |  | 4.5 | 4 | 3 | 4 | 1 | 18.9 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118538&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118538 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 273A | TO001151 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 118000 | Blackwater | CALLEMONDAH | CH 273A | 0.024 | KM | BW14YR534 | 0.317 | BW14YR534 | 0.341 | KM |  |  |  |  | 534.317 | 534.341 | 2026-06-30 |  |  | BESPOKE DESIGN |  | 4.5 | 3.5 | 3 | 5 | 1 | 22.5 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ CH 273A Design is to be completed in FY25 for FY28 construction. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118539&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118539 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH ER275.2 | TO001152 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 54000 | Blackwater | CALLEMONDAH | CH ER275.2 | 0.025 | KM | BW14YR534 | 0.343 | BW14YR534 | 0.3679 | KM |  |  |  |  | 534.343 | 534.368 | 2026-06-30 |  |  |  |  | 4.5 | 3.5 | 3 | 5 | 1 | 22.5 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ CH ER275.2 Design is to be completed in FY25 for FY29 construction. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118659&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118659 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HD ER1.2A | TO000273 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 41500 | Goonyella | HATFIELD | HD ER1.2A | 0.0369 | KM | GA01ML49 | 0.334 | GA01ML49 | 0.3709 | KM |  |  |  |  | 127.108 | 127.18 | 2026-06-30 |  |  |  |  | 4 | 4 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118612&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118612 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HD ER2.2B | TO000329 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 47250 | Goonyella | HATFIELD | HD ER2.2B | 0.035 | KM | GA02ML49 | 0.331 | GA02ML49 | 0.3659 | KM |  |  |  |  | 127.264 | 127.193 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal enables supporting renewal within the project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. THE INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manager - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115869&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000115869 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HD 11A/B | TO000328 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 54197 | Goonyella | HATFIELD | HD11A/B | 0.048 | KM | GA02ML49 | 0.8729 | GA02ML49 | 0.8249 | KM |  |  |  |  | 49.753 | 49.705 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFC due by 30 June 2025, FY26 Construction. Three TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115868&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000115868 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HD 12A/B | TO000261 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 54197 | Goonyella | HATFIELD | HD12A/B | 0.048 | KM | GA35XR49 | 0.775 | GA35XR49 | 0.8229 | KM |  |  |  |  | 49.775 | 49.823 | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFC due by 30 June 2025, FY26 Construction. Three TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115867&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000115867 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HD 12C/D | TO000207 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 54197 | Goonyella | HATFIELD | HD12C/D | 0.049 | KM | GA01ML49 | 0.922 | GA01ML49 | 0.8729 | KM |  |  |  |  | 49.8 | 49.751 | 2026-06-30 |  |  | POINTS & X 60KG/M 16 CS SNX EO |  | 4 | 5 | 4 | 5 | 1 | 19.2 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFC due by 30 June 2025, FY26 ConstructionThree TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115838&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000115838 | TURNOUTS ¦ DESIGN ¦ IFC ¦ ML 10A | TO000910 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 100260 | Blackwater | MT LARCOM | ML10A | 0.0359 | KM | BW02ML564 | 0.885 | BW02ML564 | 0.921 | KM |  |  |  |  | 562.963 | 562.999 | 2026-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. Asset renewal project collaboration opportunity with Level Crossing (planned for 2027) and Culverts (FY24 design and FY26 Construction) ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118571&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000118571 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BL 9A | TO000572 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 93700 | Blackwater | BAJOOL | BL 9A | 0.0299 | KM | BW01ML605 | 0.5649 | BW01ML605 | 0.535 | KM |  |  |  |  | 603.078 | 603.048 | 2026-06-30 |  |  |  |  | 4 | 4 | 3 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118572&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118572 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BL 9B | TO000918 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 41850 | Blackwater | BAJOOL | BL 9B | 0.021 | KM | BW02PL605 | 0.4929 | BW02PL605 | 0.514 | KM |  |  |  |  | 605.493 | 605.514 | 2026-06-30 |  |  |  |  | 4 | 4 | 3.9 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM MO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (R872340) TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ BL9B FY25 IFP - $41,850 FY26 IFC - $41,850 FY27 CONST
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118569&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000118569 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BL 46A | TO000919 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 62775 | Blackwater | BAJOOL | BL46A | 0.0219 | KM | BW02PL605 | 0.4779 | BW02PL605 | 0.456 | KM |  |  |  |  | 605.478 | 605.456 | 2026-06-30 |  |  | POINTS & X 60KG/M 12 CS |  | 4 | 4 | 3.9 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124126&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000124126 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH210A | TO001157 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 210A | 0.028 | KM | BW17YR0 | 0.378 | BW17YR0 | 0.406 | KM |  |  |  |  | 0.378 |  | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052829&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000052829 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 211A | TO001159 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 211A | 0.0439 | KM | BW17YR0 | 0.2999 | BW17YR0 | 0.2999 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.02.2020 13:39:51 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution * 19.03.2021 16:16:18 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 per PCR4851. Will be updated once confirmed * 10.05.2021 11:01:27 AUSQLD Lachlan Prescott (R881571) * To be moved to FY24 pending PCR4882
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123850&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000123850 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 212A | TO001158 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Blackwater | CALLEMONDAH | CH 212A | 0.024 | KM | BW17YR0 | 0.326 | BW17YR0 | 0.3499 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 212A 28.02.2020 13:39:11 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade turnout rail size 16.10.2020 12:49:33 AUSQLD Lachlan Prescott (R881571) Correction: FY22 execution (subject to design and possessions) 10.05.2021 11:03:08 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052827&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000052827 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 212B | TO001173 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Blackwater | CALLEMONDAH | CH 212B | 0 | KM | BW20YR0 | 0.4069 | BW20YR0 | 0.4069 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.02.2020 13:39:24 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution * 16.10.2020 12:53:10 AUSQLD Lachlan Prescott (R881571) * Correction: FY22 execution (subject to design and possessions) * 10.05.2021 11:03:09 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124083&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000124083 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 213A | TO001174 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 213A | 0.028 | KM | BW20YR0 | 0.4099 | BW20YR0 | 0.438 | KM |  |  |  |  | 0.41 |  | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124123&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000124123 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH213B | TO001156 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 213B | 0.0269 | KM | BW17YR0 | 0.466 | BW17YR0 | 0.439 | KM |  |  |  |  | 0.466 |  | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065620&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065620 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 233A | TO001175 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 233A | 0 | KM | BW20YR0 | 0.501 | BW20YR0 | 0.501 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 30.09.2020 07:09:28 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044002
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065621&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065621 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 233B | TO001181 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 65450 | Blackwater | CALLEMONDAH | CH 233B | 0 | KM | BW21YR0 | 0.6179 | BW21YR0 | 0.6179 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3.5 | 4 | 4 | 1 | 17.6 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 30.09.2020 07:09:51 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044003 Alex Rohweder (R872340) Design IFP 26, IFC - FY27, CONSTRUCT - FY30
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123826&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000123826 | TURNOUTS ¦ DESIGN ¦ IFP ¦ DA 12A/B | TO000119 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 53550 | Newlands | DURROBURRA | 12A/B | 0.0709 | KM | NL02ML0 | -0.2099 | NL02ML0 | -0.139 | KM |  |  |  |  | 12.3 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 4 | 4 | 1 | 21 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DESIGN ¦ IFP ¦ DA 12A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $18,740 out of $187,400 30.03.2022 Alex Rohweder (R872349( Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123824&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000123824 | TURNOUTS ¦ DESIGN ¦ IFP ¦ DA 10A/B | TO000151 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 59500 | Newlands | DURROBURRA | DA 10A/B | 0.05 | KM | NC03ML1158 | 0.4979 | NC03ML1158 | 0.448 | KM |  |  |  |  | 1158.498 |  | 2026-06-30 |  |  |  |  | 5 | 3 | 4 | 4 | 1 | 21 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ EARLY DESIGN ¦ IFP ¦ DA 10A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $11,900 out of $119,000 30.03.2022 Alex Rohweder (R872349) Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052845&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal GAPE Traffic | FUTURE SCOPE | COAL | 002000052845 | TURNOUTS ¦ DESIGN ¦ IFP ¦ LR12A | TO000135 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 25000 | Newlands | LEICHARDT RANGE | LR12A | 0.069 | KM | NL01ML153 | 0.5769 | NL01ML153 | 0.5769 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 3.5 | 2 | 3 | 4 | 1 | 12.25 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.02.2020 13:41:28 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX * 10.05.2021 11:05:36 AUSQLD Lachlan Prescott (R881571) * To be moved to FY25 pending PCR4882 FY24 Design budget adjusted to 10% off the total design budget = $25,000 out of $50,000 28.02.2020 13:41:28 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:05:36 AUSQLD Lachlan Prescott (R881571) To be moved to FY25 pending PCR4882 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY25 construction. TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦LR12A 11/01/2023 Alex Rohweder (R972340) FY24 IFC, FY26 Construction. CROSSING REPLACEMENT ONLY RBM to SNX, Bundle with LR7A, very simular configuration. FY24 Design budget adjusted to 10% off the total design budget = $25,000 out of $50,000
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052844&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal GAPE Traffic | FUTURE SCOPE | COAL | 002000052844 | TURNOUTS ¦ DESIGN ¦ IFP ¦ LR7A | TO000136 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 25000 | Newlands | LEICHARDT RANGE | LR7A | 0.069 | KM | NL01ML155 | 0.4789 | NL01ML155 | 0.4789 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 3.5 | 2 | 3 | 4 | 1 | 12.3 | 4882 | 2024-03-28 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.02.2020 13:41:15 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX * 10.05.2021 11:05:37 AUSQLD Lachlan Prescott (R881571) * To be moved to FY25 pending PCR4882 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY25 construction. TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦LR7A 11/01/2023 Alex Rohweder (R972340) FY24 IFC, FY26 Construction. CROSSING REPLACEMENT ONLY RBM to SNX, Bundle with LR12A, very simular configuration. FY24 Design budget adjusted to 10% off the total design budget = $25,000 out of $50,000 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115511&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000115511 | TURNOUTS ¦ DESIGN ¦ IFP ¦ ME11A/B | TO000876 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 19800 | Blackwater | MIDGEE | ME 11A/B | 0.047 | KM | BW02ML623 | 0.2349 | BW02ML623 | 0.188 | KM |  |  |  |  | 621.092 | 621.045 | 2026-06-30 |  |  |  |  | 3.5 | 4 | 4 | 4 | 1 | 15.4 |  | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100871&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000100871 | TURNOUTS ¦ DESIGN ¦ IFP ¦ ME 11C/D | TO000840 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 47600 | Blackwater | MIDGEE | ME 11C/D | 0.0439 | KM | BW01ML623 | 0.137 | BW01ML623 | 0.1809 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 17.6 | 5398 | 2024-03-28 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦ ME 11C/D 11/01/2023 Alex Rohweder (R972340) FY24 IFP. FY26 Construction - K point matching. SNX to SNX. FY24 Design budget adjusted to 50% off the total design budget = $93,700 out of $187,400
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065622&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065622 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WA 10C | TO000369 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 192114 | Goonyella | WAITARA | WA 10C | 0 | KM | GA02PL100 | 0.452 | GA02PL100 | 0.452 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 3.5 | 5 | 4 | 5 | 1 | 16.8 | 5669 | 2024-03-28 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | SCPR | FY23 IN | 20260630 | * 30.09.2020 07:10:13 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044004 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 27/07/2023 Alex Rohweder (R872340) Extend the IFP and IFC due date as per the planned construction dates. PCR - 5669 Recommended change from PM - IFP due 28th Feb 2025 (FY26); - IFC due 1st May 2026 (FY27) Why: Construction is cited in the SPM as FY28. Asset Mgr confirmed FY28 construction <(>&<)> and FY27 required for preconstruction etc. activities. Note: WA 10C <(>&<)> WA12A construction remains unchanged being FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065609&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065609 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WA 12A | TO001028 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 158187 | Goonyella | WAITARA | WA 12A | 0 | KM | GA02PL100 | 0.4849 | GA02PL100 | 0.4849 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 3.5 | 5 | 4 | 5 | 1 | 16.8 | 5669 | 2024-03-28 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | SCPR | FY23 IN | 20260630 | * 30.09.2020 06:59:51 AUSQLD Peter Rayner (R003851) * Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043322 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 27/07/2023 Alex Rohweder (R872340) Extend the IFP and IFC due date as per the planned construction dates. PCR - 5669 Recommended change from PM - IFP due 28th Feb 2025 (FY26); - IFC due 1st May 2026 (FY27) Why: Construction is cited in the SPM as FY28. Asset Mgr confirmed FY28 construction <(>&<)> and FY27 required for preconstruction etc. activities. Note: WA 10C <(>&<)> WA12A construction remains unchanged being FY28 WA 10C <(>&<)> WA12A construction remains unchanged being FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137027&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137027 | CS BW CCTV Design 3 sites | BW | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | DESIGN | 3 | SITE | 60000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 4 | 4 | 1 | 16 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | 3 sites are Callemondah Drive, Blain Drive, Morga Street.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137029&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137029 | CS GA CCTV Design 2 Sites | GA | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | DESIGN | 2 | SITE | 40000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 5 | 5 | 1 | 20 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | 2 Sites Dysart Rd, Braeside Rd.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137026&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000137026 | CS Normanby St CCTV Renewal | LX000746-08 | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | RENEWAL | 1 | SITE | 50000 | Blackwater |  |  | 0 | KM | BW03ML141 | 0.26 | BW03ML141 | 0.26 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 4 | 5 | 1 | 20 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136914&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136914 | CS Ardurad Rd CCTV Renewal | LX000661-13 | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | RENEWAL | 1 | SITE | 50000 | Blackwater | ARDURAD RD | ARDURAD RD | 0 | KM | BW03ML189 | 0.6179 | BW03ML189 | 0.6179 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 2 |  | 1 | 1 | 8 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137025&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000137025 | NL DED Standard Design | NL | CONTROL SYSTEMS | ASSET PROTECTION | DED | DESIGN | 1 | SYSTEM | 50000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 4 | 2 | 1 | 8 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115472&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115472 | Dumgree MA112 HBD Renewal | ST005260-01 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | UNIT | 880000 | Moura | DUMGREE |  | 0 | KM | MA01ML112 | 0 | MA01ML112 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 2 |  | 1 | 1 | 10 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | Dumgree MA112 HBD Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136803&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000136803 | AP Mainline Pan Cam Renewal | BW | CONTROL SYSTEMS | ASSET PROTECTION | PAN CAM | RENEWAL | 1 | SITE | 1400000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 5 |  | 5 | 1 | 25 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Install Mainline Pan Cam in BW System.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115372&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000115372 | McNaughton Weighbridge Renewal | ST002865-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | RENEWAL | 1 | UNIT | 939800 | Newlands | MCNAUGHTON | MCNAUGHTON | 0 | KM | NL04ML84 | 0.28 | NL04ML84 | 0.28 | KM |  |  |  |  | 84.28 | 84.28 | 2026-06-30 |  |  |  |  | 4 | 4 |  | 4 | 1 | 16 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | McNaughton Weighbridge Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115359&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000115359 | Kalapa WILD Design | ST009570-31 | CONTROL SYSTEMS | ASSET PROTECTION | WHEEL IMPACT LD | DESIGN | 1 | UNIT | 50000 | Blackwater | WANDOO | WANDOO | 0 | KM | BW03ML30 | 0.4799 | BW03ML30 | 0.4799 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4.8 |  | 1 | 1 | 10 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | SCPR |  | 20260630 | Kalapa WILD Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115358&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000115358 | Wandoo WILD Design | ST009410-22 | CONTROL SYSTEMS | ASSET PROTECTION | WHEEL IMPACT LD | DESIGN | 1 | UNIT | 50000 | Goonyella | WANDOO | WANDOO | 0 | KM | GA01ML92 | 0 | GA01ML92 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 5 |  | 1 | 1 | 10 |  | 2024-03-28 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | SCPR |  | 20260630 | Wandoo WILD Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137060&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000137060 | CS Aberdeen WILD Design | ST009090-01 | CONTROL SYSTEMS | ASSET PROTECTION | WILD | DESIGN | 1 | SITE | 20000 | Newlands |  |  | 0 | KM | NL01ML38 | 0.2 | NL01ML38 | 0.2 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 4 | 4 | 1 | 16 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Design for the renewal of Aberdeen WILD
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105943&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000105943 | CSI CER Replacement | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | DESIGN & PROCURE | 1 | SITE | 200000 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2026-06-30 |  |  |  |  | 5 |  | 1 |  | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102218&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000102218 | CSI CER Replacement | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | DESIGN & PROCURE | 1 | SITE | 800000 | Blackwater | CALLEMONDAH SER | CALLEMONDAH SER | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM |  |  |  |  | 533.99 | 533.99 | 2026-06-30 |  |  |  |  | 5 |  | 1 |  | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085377&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085377 | CSI Dehydrator Renewal | ST006120-55 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Blackwater | BLACKWATER MWR | BLACKWATER MWR | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM |  |  |  |  | 189.18 | 189.18 | 2026-06-30 |  |  |  |  | 5 | 4.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085375&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085375 | CSI Dehydrator Renewal | ST005880-35 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Goonyella | KERLONG MWR | KERLONG MWR | 0 | KM | GA40CR0 | 0 | GA40CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085378&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085378 | CSI Dehydrator Renewal | ST005750-22 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Newlands | REDCLIFFE TABLELAND | REDCLIFFE TABLELAND | 0 | KM | NL10CR0 | 0 | NL10CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 3.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085376&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085376 | CSI Dehydrator Renewal | ST005740-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Newlands | SUMMER HILL | SUMMER HILL | 0 | KM | NL11CR0 | 0 | NL11CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 3.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101392&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000101392 | CSI Dehydrator Renewal | ST005530-20 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085408&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085408 | CSI Generator Renewal | ST005820-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 170000 | Goonyella | JILALAN MW | JILALAN MW | 0 | KM | GA39CR0 | 0 | GA39CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085407&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085407 | CSI Generator Renewal | ST009550-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 170000 | Goonyella | MORANBAH MWR | MORANBAH MW | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM |  |  |  |  | 19.994 | 19.994 | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085427&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085427 | CSI NMS Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 0.1 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086522&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000086522 | CSI OF Renewal | ST001840-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1500 | METERS | 180000 | Blackwater | BLUFF MI | BLUFF FSS | 2.2109 | KM | BW03ML171 | 0.01 | BW03ML173 | 0.2049 | KM |  |  |  |  | 170.955 | 173.166 | 2026-06-30 |  |  |  |  | 10 | 5 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086519&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000086519 | CSI OF Renewal | ST002410-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 120000 | Blackwater | BLUFF SER | BLUFF MI | 0.8299 | KM | BW03ML170 | 0.203 | BW03ML171 | 0.01 | KM |  |  |  |  | 170.125 | 170.955 | 2026-06-30 |  |  |  |  | 10 | 5 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086913&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000086913 | CSI OF Renewal | ST006140-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6000 | METERS | 720000 | Blackwater | BOORGOON CER | KINROLA CER | 6.0899 | KM | BW05ML9 | 0.56 | BW05ML15 | 0.655 | KM |  |  |  |  | 9.557 | 15.647 | 2026-06-30 |  |  |  |  | 10 | 2.6 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086915&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000086915 | CSI OF Renewal | ST006550-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 11700 | METERS | 1053000 | Goonyella | HAIL CREEK AT0 | HAIL CREEK AS SOUTH | 11.8279 | KM | GA07ML6 | 0.28 | GA07ML18 | 0.1059 | KM |  |  |  |  | 6.287 | 18.107 | 2026-06-30 |  |  |  |  | 10 | 1.2 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086910&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000086910 | CSI Optical Fibre | ST002590-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5500 | METERS | 660000 | Blackwater | RANGAL SER | TIKARDI CER | 5.5 | KM | BW03ML195 | 0.5869 | BW03ML190 | 0.131 | KM |  |  |  |  | 195.549 | 5.504 | 2026-06-30 |  |  |  |  | 10 | 2.6 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085520&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000085520 | CSI OF Renewal | ST006670-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6600 | METERS | 594000 | Goonyella | SOUTH WALKER JUNCTION CER | BIDGERLEY M10 | 120.8859 | KM |  | 0 |  | 0 | [5 empty] | 127.48 | 6.594 | 2026-06-30 |  |  |  |  | 10 | 1.2 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085354&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085354 | CSI Radome Renewal FY26 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 58000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085353&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085353 | CSI Radome Renewal FY26 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 58000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  | HIGH | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085552&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085552 | CSI Structure Renewal | ST005930-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 180000 | Goonyella | COLSTON PARK | COLSTON PARK | 0 | KM | GA37CR0 | 0 | GA37CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN |  | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085551&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085551 | CSI Structure Renewal | ST005750-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 300000 | Newlands | REDCLIFFE TABLELANDS | REDCLIFFE TABLELANDS | 0 | KM | NL10CR0 | 0 | NL10CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137346&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000137346 | Cyber Security Strengthening FY26 | BW | CONTROL SYSTEMS | CYBER SECURITY STRENGTHENING |  | RENEWAL | 1 | SYSTEM | 70000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Transmission & Data Renewals | STRATEGIC |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137347&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000137347 | Cyber Security Strengthening FY26 | GA | CONTROL SYSTEMS | CYBER SECURITY STRENGTHENING |  | RENEWAL | 1 | SYSTEM | 70000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Transmission & Data Renewals | STRATEGIC |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137370&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000137370 | Cyber Security Strengthening FY26 | NL | CONTROL SYSTEMS | CYBER SECURITY STRENGTHENING |  | RENEWAL | 1 | SYSTEM | 40000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [11 empty] | 2024-03-28 |  | Transmission & Data Renewals | STRATEGIC |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085639&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085639 | Data Network Renewal BW | BW | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 700000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085609&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085609 | Data Network Renewal GA | GA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 700000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085714&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085714 | Data Network Renewal MA | MA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085689&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085689 | Data Network Renewal NL | NL | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 200000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074218&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000074218 | SIG_Interlocking Renewal - CH Stg1F_Com | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 1800000 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 5 | 4 | 1 | 16 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 16.03.2021 17:41:57 AUSQLD Robert Love (R111379) * Complete the Renewal/Commissioning phase of Callemondah Stage 1F - commissioning the new hut GE OC East.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125246&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000125246 | SIG_Interlocking Renewal - CH Stg2C_Bld | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 1000000 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Commence the Testing/Renewal/Commissioning phase of Callemondah Stage 2C - Install and commission the data in the SER. Completion will be achievable in later years.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124046&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000124046 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 7 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123946&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000123946 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124045&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000124045 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065478&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065478 | SIG_Interlocking Renewal_GA_Balook_Des | ST003880-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 1358441 | Goonyella | BALOOK |  | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 | 5710 | 2024-03-28 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Notification in process | SCPR | FY23 IN | 20260630 | * 28.09.2020 10:22:29 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044655&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | FUTURE SCOPE | COAL | 002000044655 | SIG_Interlocking Renewal_BW_Midgee_Des | ST004310-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | UNIT | 690000 | Blackwater | MIDGEE | MIDGEE | 0 | KM | BW01ML624 | 0.5899 | BW01ML624 | 0.5899 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | 30.08.2022: Rob Love - Midgee delayed due to resources.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065491&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000065491 | SIG_Interlocking Renewal_GA_Yukan_Pln | ST004060-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 150000 | Goonyella | YUKAN |  | 0 | KM | GA01ML28 | 0.806 | GA01ML28 | 0.806 | KM |  |  |  |  | 28.806 | 28.806 | 2026-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2024-03-28 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | * 28.09.2020 10:32:06 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000064093&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000064093 | Archer Interlocking Renewal | ST004090-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | SITE | 1100000 | Blackwater | ARCHER | ARCHER | 0 | KM | BW01ML614 | 0.9659 | BW01ML614 | 0.9659 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2024-03-28 | 2021-10-05 | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 16:16:10 AUSQLD Scott Andrews (R003573) * RENEW ARCHER INTERLOCKING * 12.04.2021 16:21:13 AUSQLD Jeremy Stevenson (R867415) * Risk is missing closure date due to missing design dates? See additional scope to be packaeg into cl * osures that may impact time and cost. * 30.08.2022: Rob Love - Commissioning delayed to FY25 due to lack of resources. 09.01.2024: Rob Love - Commissioning delayed to FY27 due to lack of funding.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125148&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000125148 | SIG_Interlocking Renewal_GA_WO_Bld | ST003940-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | SITE | 1500000 | Goonyella | WANDOO |  | 0 | KM | GA01ML60 | 0.6199 | GA01ML60 | 0.6199 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 10 |  |  |  | 100 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Replace Relays with PBI, Digital Telem, Add VDRs, Split detection on crossovers, Replace offset signal posts with JRIs, Replace SER. Moved to FY27 as removed from scope in FY26 Corporate Budget review. Rob Love 23/01/2024.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060291&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060291 | SIG_Replace FOP signal_BW_AE23_Com | ST000570-76 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | AMBROSE | AMBROSE | 0 | KM | BW01ML570 | 0.01 | BW01ML570 | 0.01 | KM |  |  |  |  | 570.01 | 570.01 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:55:52 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060292&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060292 | SIG_Replace FOP signal_BW_AE25_Com | ST000570-79 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | AMBROSE | AMBROSE | 0 | KM | BW02ML570 | 0.01 | BW02ML570 | 0.01 | KM |  |  |  |  | 570.01 | 570.01 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:56:02 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060295&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060295 | SIG_Replace FOP signal_BW_DA13_Com | ST000030-59 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | DUARINGA | DUARINGA | 0 | KM | BW04ML105 | 0.1189 | BW04ML105 | 0.1189 | KM |  |  |  |  | 105.119 | 105.119 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:56:29 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060296&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060296 | SIG_Replace FOP signal_BW_DA14_Com | ST000030-65 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | DUARINGA | DUARINGA | 0 | KM | BW03ML105 | 0.1189 | BW03ML105 | 0.1189 | KM |  |  |  |  | 105.119 | 105.119 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:56:37 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060304&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060304 | SIG_Replace FOP signal_BW_RA22_Com | ST000620-B3 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01PL585 | 0.8569 | BW01PL585 | 0.8569 | KM |  |  |  |  | 585.857 | 585.857 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:57:48 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060303&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060303 | SIG_Replace FOP signal_BW_RA23_Com | ST000620-B5 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01ML585 | 0.8569 | BW01ML585 | 0.8569 | KM |  |  |  |  | 585.857 | 585.857 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:57:39 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060301&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060301 | SIG_Replace FOP signal_BW_RA13_Com | ST000620-93 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW02ML586 | 0.203 | BW02ML586 | 0.203 | KM |  |  |  |  | 586.203 | 586.203 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:57:21 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060302&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000060302 | SIG_Replace FOP signal_BW_RA14_Com | ST000620-99 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | RAGLAN | RAGLAN | 0 | KM | BW01ML586 | 0.203 | BW01ML586 | 0.203 | KM |  |  |  |  | 586.203 | 586.203 | 2026-06-30 |  |  |  |  | 4.5 | 3 |  | 3 |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:57:30 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060305&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060305 | SIG_Replace FOP signal_BW_WO16_Com | ST000260-55 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | WALLEROO | WALLEROO | 0 | KM | BW03ML115 | 0.1779 | BW03ML115 | 0.1779 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 23.06.2020 12:57:56 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060306&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060306 | SIG_Replace FOP signal_BW_WO18_Com | ST000260-58 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | WALLEROO | WALLEROO | 0 | KM | BW04ML115 | 0.1779 | BW04ML115 | 0.1779 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 23.06.2020 12:58:05 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060307&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060307 | SIG_Replace FOP signal_BW_WD13_Com | ST000190-67 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW04ML47 | 0.554 | BW04ML47 | 0.554 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 23.06.2020 12:58:14 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060308&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060308 | SIG_Replace FOP signal_BW_WH13_Com | ST000220-44 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW04ML38 | 0.7009 | BW04ML38 | 0.7009 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 23.06.2020 12:58:23 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060309&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060309 | SIG_Replace FOP signal_BW_WH14_Com | ST000220-26 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | SIGNAL FOP REPLACEMENT | RENEWAL | 1 | UNIT | 80000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW03ML38 | 0.7009 | BW03ML38 | 0.7009 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | LIKE FOR LIKE |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 23.06.2020 12:58:32 AUSQLD Peter Rayner (R003851) * Replace FOP mounted signal with drop-down type * This is a safety and operational focus
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125114&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000125114 | SIG_Interlocking Renewal - MA_DE_Bld | ST003600-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1028000 | Moura | DUMGREE | ANNANDALE | 0 | KM | MA01ML108 | 0.545 | MA01ML108 | 0.545 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Construction phase for the replacement of the VPI at Dumgree AND the replacement of the Annandale-Dumgree axle counter AzS600. PBI expected to be an eSmIO. Axle counter expected to be Frauscher. Working components from the removed VPI are to be placed into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000069556&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000069556 | SIG_Interlocking Renewal_MA_Stowe_Pln | ST003860-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | STATION | 114259 | Moura | STOWE | STIRRAT | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM | [6 empty] | 2027-06-20 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  | 2024-03-28 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | * 15.12.2020 15:06:42 AUSQLD Robert Love (R111379) * Plan and design the replacement of VPI Graham and replacement of Graham Interlocking with Object Controller if required. Replacement of Graham to Stirrat AzS600 axlecounter with Frauscher axlecounter.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100645&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100645 | SIG_Interlocking Renewal - MA_AE_Com | ST003290-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1567334 | Moura | ANNANDALE | ANNANDALE | 0 | KM | MA01ML0 | 0.1 | MA01ML0 | 0.1 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 |  | 20 |  | 2024-03-28 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125284&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000125284 | SIG_Points Impr_M23A Contact Rem_GA_Des | GA | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | DESIGN | 6 | UNIT | 60000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Design for the removal ofthe contactor from the following (6) M23A machines: Peak Downs PD12A(SNX), PD12B, PD7A, PD7B(SNX), PD8A, PD9. This is to create spares of unsupported contactor relays and renew old machines in the field.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060051&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060051 | SIG_Replace M23A_GA_BD11A_Com | TO000407-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BUNDOORA | BUNDOORA | 0 | KM | GA03ML129 | 0.6919 | GA03ML129 | 0.6919 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:17:19 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060102&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060102 | SIG_Replace M23A_GA_GC12B_Com | TO000401-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML132 | 0.0129 | GA03ML132 | 0.0129 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:25:53 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060202&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060202 | SIG_Replace M23A_GA_RM12A_Com | TO000384-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | GA03ML24 | 0.0589 | GA03ML24 | 0.0589 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | [6 empty] | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:42:17 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060203&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060203 | SIG_Replace M23A_GA_RM12B_Com | TO000384-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | GA03ML24 | 0.0589 | GA03ML24 | 0.0589 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | [6 empty] | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:42:26 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060204&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060204 | SIG_Replace M23A_GA_RM7A_Com | TO000385-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | GA03ML21 | 0.774 | GA03ML21 | 0.774 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | [6 empty] | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:42:35 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060205&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000060205 | SIG_Replace M23A_GA_RM7B_Com | TO000385-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | GA03ML21 | 0.774 | GA03ML21 | 0.774 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | [6 empty] | 2024-03-28 |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 23.06.2020 12:42:44 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085129&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000085129 | SIG_Train Detection_NL_Almoola_Pln | ST008620 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | PLANNING | 2 | UNIT | 50000 | Newlands | ALMOOLA | BRIABA | 0 | KM | NL01ML71 | 0.921 | NL01ML71 | 0.921 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 4 | 4 | 1 | 16 |  | 2024-03-28 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Planning phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The blocks are 2 blocks btn Almoola and Briaba and a block between Briaba and Binbee. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065526&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000065526 | SIG_Train Detection_BW_Warren_CSEE_Bld | ST005190 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 38 | UNIT | 3000000 | Blackwater | WARREN | WARREN | 0 | KM | BW03ML25 | 0.4749 | BW03ML25 | 0.4749 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 4 | 4 | 4 | 1 | 18 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | * 28.09.2020 10:59:15 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC 30.08.2022: Rob Love - Rescheduled due to resources and re-estimated based on improved unit rating. Change forecast from $5.5M to $3.0M to match FY26 Corporate Budget. Rob Love 23/01/2024. Change title to build to reflect commissioning in FY27. Rob Love 27/03/2024.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066593&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000066593 | SIG_Train Detection_BW_Westwood_CSEE_Pln | ST000190 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | PLANNING | 41 | UNIT | 246000 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW03ML44 | 0.44 | BW03ML44 | 0.44 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Plan for the replacement of the CSEE tracks at Westwood to an axle counter system. The axle counter system is to be Thales. The axle counter system is not to be electronically connected to the adjacent axle counter systems. The block to Wycarbah is to be implemented. The block to Windah to be done when Windah is converted to axle counters. Any level crossings and DEDs in the block to be identified during the planning. 30.08.2022: Rob Love - Re-estimated by project team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125262&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000125262 | SIG_Train Detection_GA_Ingsdon_ML_Des | ST004770-09 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 665000 | Goonyella | INGSDON | INGSDON | 0 | KM | GA03ML11 | 0 | GA03ML11 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Replace all track circuits (primarily defunct ML tracks) with 23 axlecounter blocks. This is the Design Phase. Changed forecast from $1,265,000 to match forecasting in FY26 Corporate Budget. Rob Love 20240123.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104765&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000104765 | SIG_Train Detection_GA_Riverside_ML_Des | ST005050 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 220000 | Goonyella | RIVERSIDE | RIVERSIDE | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Planning phase to replace 4 ML track circuits in the balloon loop (freq E,F plus 1xD) with 2 Frauscher tracks. Tracks with ML freq are 19BBT(1xF) and 19BAT(1xE,2xF,1xD). This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays. Change forecast from $110,000 to $220,000 to match FY26 Corporate budget. Rob Love 23/01/2024.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125264&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000125264 | SIG_Train Detection_GA_Goonyella_ML_Pln | ST004740-04 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 44000 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA13ML195 | 0.4199 | GA13ML195 | 0.4199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2024-03-28 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Planning phase to replace 5 ML track circuits in the balloon loop (freq E,F) with 2 Frauscher tracks. Tracks with ML freq are 17BBT(1xF) and 17B5AT-17BA2AT(2xE,2xF). This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103823&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000103823 | SIG_Train Detection_GA_Millennium_ML_Con | ST007030 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 2483000 | Goonyella | MILLENNIUM JUNCTION | MILLENNIUM JUNCTION | 0 | KM | GA03ML16 | 0.7229 | GA03ML16 | 0.7229 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 16.8 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Replace all track circuits (primarily defunct 13 ML tracks and 1 AzS350U axlecounter track around part of the loop) with 16 new axlecounter tracks. New axlecounters are to be Frauschser. The axlecounter block to Ingsdon is to remain.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103983&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000103983 | SIG_Train Detection_GA_Saraji_ML_Com | ST000930 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 573000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML64 | 0.755 | GA03ML64 | 0.755 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2024-03-28 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Replace 10 ML track circuits in the balloon loop (freq E,F,G,H) with 3 Frauscher. This interlocking is relay based and hence the resetting of the 3 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085264&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085264 | BW CS ACOM Renewal FY26 | BW | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM | 230000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 5 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085266&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085266 | GA CS ACOM Renewal FY26 | GA | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM | 230000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 5 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085283&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085283 | MA CS ACOM Renewal FY26 | MA | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 5 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085282&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085282 | NL CS ACOM Renewal FY26 | NL | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 5 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113360&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000113360 | CS Transmission DMR Planning | BW | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | PLANNING | 1 | LUMPSUM | 20000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 1 | 3 | 1 | 12 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113361&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000113361 | CS Transmission DMR Planning | GA | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | PLANNING | 1 | LUMPSUM | 20000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 1 | 3 | 1 | 12 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100879&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100879 | CS Transmission DMR Link | ST006250-05 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 350000 | Newlands | BOVEY'S LOOKOUT | REDCLIFFE TABLELAND | 0 | KM | NL08CR0 | 0 | NL08CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085525&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085525 | CS Transmission DMR Renewal | ST005280-25 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 120000 | Blackwater | CROCKER PEAK | BLUFF | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100901&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100901 | CS Transmission DMR Link | ST005750-08 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 140000 | Newlands | REDCLIFFE TABLELAND | COLLINSVILLE | 0 | KM | NL10CR0 | 0 | NL10CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085526&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085526 | CS Transmission DMR Renewal | ST005900-26 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 120000 | Goonyella | SARINA | MACKAY | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100902&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100902 | CS Transmission DMR Link | ST005610-16 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 120000 | Moura | SPECIMEN HILL | MAURICE HILL | 0 | KM | MA15CR0 | 0 | MA15CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115137&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000115137 | CS Transmission GPS Clock Design not req | BW | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | DESIGN | 1 | LUMPSUM | 30000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 1 | 20 |  |  | 2024-03-28 |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115138&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000115138 | CS Transmission GPS Clock Design not req | GA | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | DESIGN | 1 | LUMPSUM | 30000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 1 | 20 |  |  | 2024-03-28 |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100956&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100956 | CS Transmission IOT | GA | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella | GOONYELLA STATIONS | GOONYELLA STATIONS | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100518&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100518 | CS Transmission Power Supply | ST008090-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | ABBOT POINT MW | ABBOT POINT MW | 0 | KM | NL02CR18 | 0.3499 | NL02CR18 | 0.3499 | KM |  |  |  |  | 18.35 | 18.35 | 2026-06-30 |  |  |  |  | 5 | 3.2 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100592&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100592 | CS Transmission Power Supply | ST008470-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | BLACKWATER TSC | BLACKWATER TSC | 0 | KM | BW03ML186 | 0.3709 | BW03ML186 | 0.3709 | KM |  |  |  |  | 186.297 | 186.297 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085225&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085225 | CS Transmission Power Supply | ST008920-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Goonyella | BRAESIDE PSC | BRAESIDE PSC | 0 | KM | GA01ML104 | 0.2999 | GA01ML104 | 0.2999 | KM |  |  |  |  | 104.165 | 104.165 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100199&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100199 | CS Transmission Power Supply | ST007850-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | BUCKLEY SER | BUCKLEY SER | 0 | KM | NL01ML10 | 0.032 | NL01ML10 | 0.032 | KM |  |  |  |  | 10.051 | 10.051 | 2026-06-30 |  |  |  |  | 5 | 3.2 | 1 | 3 | 1 | 15 |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078655&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000078655 | CS Transmission Power Supply | ST005730-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | COLLINSVILLE MW | COLLINSVILLE MW | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM |  |  |  |  | 76.658 | 76.658 | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 3 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | * 10.06.2021 16:05:16 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100546&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100546 | CS Transmission Power Supply | ST005140-37 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 33000 | Blackwater | PARNABAL SER | PARNABAL SER | 0 | KM | BW03ML157 | 0.158 | BW03ML157 | 0.158 | KM |  |  |  |  | 157.32 | 157.32 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085224&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085224 | CS Transmission Power Supply | ST008790-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Goonyella | PN NEBO ADMIN CER | PN NEBO ADMIN CER | 0 | KM | GA16ML6 | 0.5 | GA16ML6 | 0.5 | KM |  |  |  |  | 6.502 | 6.502 | 2026-06-30 |  |  |  |  | 5 | 2.4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100532&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000100532 | CS Transmission Power Supply | ST008450-39 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 33000 | Blackwater | RAGLAN CS | RAGLAN CS | 0 | KM | BW01ML581 | 0.4099 | BW01ML581 | 0.4099 | KM |  |  |  |  | 579.096 | 579.096 | 2026-06-30 |  |  |  |  | 5 | 4.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100536&DY_MAB=X&~OKCODE=ONLI | FY26 | Dual Traffic | BASELOAD | COAL | 002000100536 | CS Transmission Power Supply | ST000150-20 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | RAGLAN FS | RAGLAN FS | 0 | KM | BW01ML582 | 0.506 | BW01ML582 | 0.506 | KM |  |  |  |  | 580.199 | 580.199 | 2026-06-30 |  |  |  |  | 5 | 4.5 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100590&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100590 | CS Transmission Power Supply | ST006270-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | TABLE MOUNTAIN MW | TABE MOUNTAIN MW | 0 | KM | BW63CR0 | 0 | BW63CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100535&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100535 | CS Transmission Power Supply | ST008020-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 33000 | Blackwater | WALLAROO TSC | WALLAROO TSC | 0 | KM | BW03ML118 | 0 | BW03ML118 | 0 | KM |  |  |  |  | 118.053 | 118.053 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100547&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000100547 | CS Transmission Power Supply | ST002630-36 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 33000 | Blackwater | WALTON SER | WALTON SER | 0 | KM | BW03ML163 | 0.375 | BW03ML163 | 0.375 | KM |  |  |  |  | 162.234 | 162.234 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078654&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000078654 | CS Transmission Power Supply | ST007750-42 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | WESTWOOD TSC | WESTWOOD TSC | 0 | KM | BW03ML48 | 0.069 | BW03ML48 | 0.069 | KM |  |  |  |  | 48.199 | 48.199 | 2026-06-30 |  |  |  |  | 4 | 5 | 1 | 3 | 1 | 20 |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | * 10.06.2021 16:04:09 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133032&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133032 | CS Power Supply - UPS Replacement | ST005860-C6 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 2 | UNIT | 160000 | Goonyella | MACKAY MWR | MACKAY MWR | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM |  |  |  |  | 959.4 | 959.4 | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133030&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133030 | CS Power Supply - UPS Replacement | ST005490-H9 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 2 | UNIT | 150000 | Blackwater | ROCKHAMPTON FLOOR 6 | ROCKHAMPTON FLOOR 6 | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM |  |  |  |  | 638.8 | 638.8 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133031&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000133031 | CS Power Supply - UPS Replacement | ST009410-28 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 50000 | Goonyella | WANDOO WSS | WANDOO WSS | 0 | KM | GA01ML92 | 0 | GA01ML92 | 0 | KM |  |  |  |  | 91.876 | 91.876 | 2026-06-30 |  |  |  |  | 5 | 2.4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140784&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140784 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 1 | BLACKWATER 1 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140793&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140793 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 10 | BLACKWATER 10 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140785&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140785 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 2 | BLACKWATER 2 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140787&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140787 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 3 | BLACKWATER 3 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140786&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140786 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 4 | BLACKWATER 4 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140788&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140788 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 5 | BLACKWATER 5 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140789&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140789 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 6 | BLACKWATER 6 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140790&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140790 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 7 | BLACKWATER 7 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140791&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140791 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 8 | BLACKWATER 8 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140792&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140792 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 14000 | Blackwater | BLACKWATER 9 | BLACKWATER 9 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140794&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140794 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 1 | GOONYELLA 1 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140803&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140803 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 10 | GOONYELLA 10 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140795&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140795 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 2 | GOONYELLA 2 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140796&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140796 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 3 | GOONYELLA 3 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140797&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140797 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 4 | GOONYELLA 4 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140798&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140798 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 5 | GOONYELLA 5 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140799&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140799 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 6 | GOONYELLA 6 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140800&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140800 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 7 | GOONYELLA 7 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140801&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140801 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 8 | GOONYELLA 8 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000140802&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000140802 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | SITE | 10000 | Goonyella | GOONYELLA 9 | GOONYELLA 9 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093781&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000093781 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 110000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093780&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000093780 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 110000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093765&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000093765 | CS Transmission Supervisory Card | NL | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 110000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101299&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000101299 | CS Transmission TDM Replacement Planning | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | PLANNING | 1 | LUMPSUM | 150000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 2.4 | 1 | 12 |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101320&DY_MAB=X&~OKCODE=ONLI | FY26 |  | FUTURE SCOPE | COAL | 002000101320 | CS Transmission TDM Replacement Planning | GA | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | PLANNING | 1 | LUMPSUM | 150000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101323&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000101323 | CS Transmission TDM Replacement | GA | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101324&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000101324 | CS Transmission TDM Replacement | NL | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085256&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085256 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 1 | BLACKWATER 1 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE |  | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100679&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100679 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 2 | BLACKWATER 2 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100682&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100682 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 3 | BLACKWATER 3 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100683&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100683 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 4 | BLACKWATER 4 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100684&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100684 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 5 | BLACKWATER 5 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100685&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100685 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 6 | BLACKWATER 6 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100686&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100686 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 7 | BLACKWATER 7 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100687&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100687 | CS Transmission Tele Battery | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Blackwater | BLACKWATER 8 | BLACKWATER 8 | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100689&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100689 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 3 | GOONYELLA 3 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100690&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100690 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 4 | GOONYELLA 4 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100691&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100691 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 5 | GOONYELLA 5 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100693&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100693 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 6 | GOONYELLA 6 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100694&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100694 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 7 | GOONYELLA 7 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100695&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100695 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 8 | GOONYELLA 8 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100681&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000100681 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Newlands | NEWLANDS 2 | NEWLANDS 2 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | MEDIUM | LOW | Outstanding notification | SCPR |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102844&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000102844 | CS TETRA AP Site Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | LUMPSUM | 100000 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102843&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000102843 | CS TETRA AP Site Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132799&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000132799 | CS TETRA RADIO | ST005520-28 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 200000 | Blackwater | BLUFF MWR | BLUFF MWR | 0 | KM | BW54CR0 | 0 | BW54CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132798&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000132798 | CS TETRA RADIO | ST007130-18 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 200000 | Blackwater | CALLEMONDAH MWR | CALLEMONDAH MWR | 0 | KM | BW50CR534 | 0.6999 | BW50CR534 | 0.6999 | KM |  |  |  |  | 534.7 | 534.7 | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085474&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000085474 | CS TETRA RADIO | ST007540 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 400000 | Goonyella | LAKE VERMONT | LAKE VERMONT | 0 | KM | GA19ML14 | 0.08 | GA19ML14 | 0.08 | KM |  |  |  |  | 14.059 | 14.059 | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127476&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000127476 | CS TETRA RADIO | ST008330 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Newlands | LR-BW HBD CER | LR-BW HBD CER | 0 | KM | NL01ML158 | 0.5999 | NL01ML158 | 0.5999 | KM |  |  |  |  | 158.6 | 158.6 | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085465&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000085465 | CS TETRA RADIO | ST005050 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 100000 | Goonyella | RIVERSIDE | RIVERSIDE | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM |  |  |  |  | 199.9 | 199.9 | 2026-06-30 |  |  |  |  | 10 | 10 | 1 | 10 | 1 | 100 |  | 2024-03-28 |  | Transmission & Data Renewals | STRATEGIC | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085052&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085052 | Dig Telem GA Renewal | GA | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 7 | SITE | 500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043410&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000043410 | Dig Telem BW Renewal | ST006470 | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 3 | UNIT | 240000 | Blackwater | ROCKHAMPTON ADMIN 5TH FLR |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2024-03-28 |  | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085037&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085037 | UTC DTC Renewal BW | BW | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 840000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | UTC DTC | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085081&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085081 | UTC DTC Renewal GA | GA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 840000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | UTC DTC | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085086&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085086 | UTC DTC Renewal MA | MA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 105000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | UTC DTC | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085084&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000085084 | UTC DTC Renewal NL | NL | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 315000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [7 empty] | 0.1 |  | 100 |  | 2024-03-28 |  | UTC DTC | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120194&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000120194 | OVERHEAD¦FW CLEARANCE¦DESIGN¦YUKAN | GA-0201-00201C | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | DESIGN | 1 | SITE | 15000 | Goonyella | YUKAN | YUKAN | 1.165 | KM | GA/28/788/TFR2 | 0 | GA/29/953/SR | 0 | KM |  |  |  |  | 28239 | 29937 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Notification for design to combine electrical subsections 201A, 201B and 201C to remove the FW hazard associated with electrical subsection 201A. This scope was justified for safety reasons. See attached report, estimate and risk assessment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085274&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000085274 | OVERHEAD¦FW CLEARANCE¦RENEWAL¦ROCKLANDS | BW-0553 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 1499575 | Blackwater | ROCKLANDS | ROCKLANDS | 11.0289 | KM | N/624/658/F1 | 0 | N/635/687/F1 | 0 | KM |  |  |  |  | 631.65 | 2.24 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | FW and Clearance Improvement | BESPOKE DESIGN | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | See attached email on why N4 was deffered to FY26 and risks associated with this. Scope: 1. Increase clearances of mainline feeder wire from lattice portal booms 2. Relocate feeder wire from back of masts to allow safe single line isolations. 23.02.2022: Scope moved from FY26 into FY25 to align with 2 year design/construct timeframe. Rocklands FW clearance is being designed in FY23. Construction team to review capability to deliver this scope in FY25 along with all other works. 6/10/23: Moved from FY25 to FY26 as part of MRSB budget reduction (LS)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085193&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000085193 | OVERHEAD¦GOONYELLA PORTS OHL¦RENEWAL | GA-0912 | ELECTRICAL | OVERHEAD | GOONYELLA PORTS OHL RENEWAL | RENEWAL | 1 | SITE | 4616000 | Goonyella | DALRYMPLE BAY | HAY POINT | 9.6679 | KM | DL/-0/068/DR1 | 0 | GA/9/600/D | 0 | KM |  |  |  |  | 0.068 | 9.6 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Goonyella Ports Overhead Line Renewal | BESPOKE DESIGN |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. 24/08/22: Estimate updated following development of Class 4 estimate. Refer to PCR 5347.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138330&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138330 | T30-OH-HEADSPAN-Peak DNs-44.654km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 |  | 2024-03-28 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | 18-03-24 EK: As per planned FY26 Headspans Renewal at Peaksdown with justification and confirmation based on site proposal. See attached email. 03/04/2024 MS: Uploaded IFC drawings from 2020 for IFP turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138288&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138288 | T30-OH-HEADSPAN-Peak DNs-44.525km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.525 | 44.525 | 2026-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 |  | 2024-03-28 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | 18-03-24 EK: As per planned FY26 Headspan Renewal at Peaksdown with justification and confirmation based on Site proposal. See attached email. 03/04/2024 MS: Uploaded IFC documents that were issued in July 2020 for IFP turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138289&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138289 | T30-OH-HEADSPAN-Peak DNs-44.588km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.588 | 44.588 | 2026-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 |  | 2024-03-28 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | 18-03-24 EK: As per planned FY26 Headspans Renewal at Peaksdown with justification and confirmation based on site proposal. See attached email. 03/04/2024 MS: Uploaded IFC drawings that were issued in 2020 for IFP turnover
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138331&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000138331 | T30-OH-HEADSPAN-Peak DNs-44.719km | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 1 | UNIT | 114951 | Goonyella | PEAK DNS | PEAK DNS | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM |  |  |  |  | 44.719 | 44.719 | 2026-06-30 |  |  |  |  | 3 | 2.1 | 4 | 3.9 | 1 | 11.7 |  | 2024-03-28 |  | Headspans | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | 18-03-24 EK: As per planned FY26 Headspans Renewal at Peaksdown with justifcation and confirmation based on site proposal. See attached email.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134889&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000134889 | SECTION INSULATOR - JILALAN | SQ020360 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | DESIGN | 1 | UNIT | 10000 | Goonyella | JILALAN | JILALAN | 0 | KM | JD/20/338/J12 | 0 | JD/20/338/J12 | 0 | KM |  |  |  |  | 20338 | 20388 | 2026-06-30 |  |  |  |  | 3.5 | 4.6 | 2 | 4.1 | 1 | 14.35 |  | 2024-03-28 |  | Section Insulator and Neutral Section Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 06/02/24 EK: This Section Insulator Design N4 (FY26) notification to align with the Renewal (FY28) notification of 2000074788. For details, refer to the attached documents.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103012&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000103012 | SECTION INSULATOR-BROADLEA | SQ020262 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 250000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA/156/001/D | 0 | GA/156/001/D | 0 | KM |  |  |  |  | 156.001 | 156.001 | 2026-06-30 |  |  |  |  | 3.5 | 2.5 | 2 | 2 | 1 | 11.55 |  | 2024-03-28 |  | Section Insulator and Neutral Section Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | HI25 SI Replaced with insulated overlap
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104485&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104485 | SECTION INSULATOR - BROADLEA | SQ020268 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 250000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA/155/987/U | 0 | GA/155/987/U | 0 | KM |  |  |  |  | 631581 | 631581 | 2026-06-30 |  |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 11.55 |  | 2024-03-28 |  | Section Insulator and Neutral Section Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20260630 | 02/04/2024 Michael Simmers: DD50 drawings, SID risk register, fdn schedule, reverse brief, photos, attached for IFP Turnover.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104481&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104481 | SECTION INSULATOR - ROCKLANDS | SQ020177 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 75000 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/581/U | 0 | N/631/581/U | 0 | KM |  |  |  |  | 631.581 | 631.581 | 2026-06-30 |  |  |  |  | 3.5 | 2.5 | 2 | 3.3 | 1 | 11.55 |  | 2024-03-28 |  | Section Insulator and Neutral Section Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084406&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000084406 | Small Component Renewals | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | LUMPSUM | 1000000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  | 2024-03-28 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084460&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000084460 | Small Component Renewals | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | LUMPSUM | 1000000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 0 |  | 5 | 1 | 25 |  | 2024-03-28 |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068739&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068739 | OH - Termination Portal Renewal | SQ020464 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | BIDGERLEY | BIDGERLEY | 0.035 | KM | GA01ME0 | 10.3399 | GA01ME0 | 10.375 | KM |  |  |  |  | 10.34 | 10.375 | 2026-06-30 |  |  |  |  | 4 | 1.2 | 3 | 3.1 | 1 | 12.4 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:15:36 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068736&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068736 | OH - Termination Portal Renewal | SQ020329 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 1 | STRUCTURES | 56000 | Blackwater | BOONAL | BOONAL | 0.0179 | KM | BO/180/625/BL | 0 | BO/180/643/BL | 0 | KM |  |  |  |  | 180.625 | 180.643 | 2026-06-30 |  |  |  |  | 4 | 3.35 | 3 | 4 | 1 | 16 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:15:44 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068731&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068731 | OH - Termination Portal Renewal | SQ020323 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Blackwater | BOORGOON | BOORGOON | 0.0379 | KM | BG/2/187/BL | 0 | BG/2/225/BL | 0 | KM |  |  |  |  | 2.187 | 2.225 | 2026-06-30 |  |  |  |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:15:49 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H - Completed IFC Pack attached to notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068732&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068732 | OH - Termination Portal Renewal | SQ020324 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 1 | STRUCTURES | 56000 | Blackwater | CURRAGH | CURRAGH | 0.0769 | KM | CU/12/075/BL | 0 | CU/12/152/BL | 0 | KM |  |  |  |  | 12.075 | 12.152 | 2026-06-30 |  |  |  |  | 4 | 1.2 | 3 | 3.1 | 1 | 12.4 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:15:57 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H - Completed IFC Pack attached to notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068733&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068733 | OH-AR-BW-TP-Const-EN | SQ020325 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 3 | STRUCTURES | 115000 | Blackwater | ENSHAM | ENSHAM | 0.0359 | KM | EM/13/030/L | 0 | EM/13/066/L | 0 | KM |  |  |  |  | 13.03 | 13.066 | 2026-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:00 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068735&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068735 | OH - Termination Portal Renewal | SQ020327 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Blackwater | GORDONSTONE | GORDONSTONE | 0.0379 | KM | GS/13/796/L | 0 | GS/13/834/L | 0 | KM |  |  |  |  | 13.796 | 13.834 | 2026-06-30 |  |  |  |  | 4 | 1 | 3 | 3 | 1 | 12 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:09 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068734&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068734 | OH - Termination Portal Renewal | SQ020326 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Blackwater | GREGORY | GREGORY | 0.193 | KM | GG/65/654/L | 0 | GG/65/847/L | 0 | KM |  |  |  |  | 65.654 | 65.847 | 2026-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:12 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H - Completed IFC Pack attached to notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068738&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068738 | OH - Termination Portal Renewal | SQ020463 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | HAIL CREEK | HAIL CREEK | 0.068 | KM | GA01ME0 | 44.444 | GA01ME0 | 44.512 | KM |  |  |  |  | 44.444 | 44.512 | 2026-06-30 |  |  |  |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:21 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068144&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068144 | OH - Termination Portal Renewal | SQ020321 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Blackwater | KOORILGAH | KOORILGAH | 0.0379 | KM | KH/4/587/BL | 0 | KH/4/625/BL | 0 | KM |  |  |  |  | 47.042 | 47.106 | 2026-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:25 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H - Completed IFC Pack attached to notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068744&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068744 | OH - Termination Portal Renewal | SQ020470 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | LAKE VERMONT | LAKE VERMONT | 0.04 | KM | GA01ME0 | 15.9979 | GA01ME0 | 16.038 | KM |  |  |  |  | 15.998 | 16.038 | 2026-06-30 |  |  |  |  | 4 | 1.6 | 3 | 3.3 | 1 | 13.2 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:33 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068740&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068740 | OH - Termination Portal Renewal | SQ020465 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | MACARTHUR | MACARTHUR | 0.0389 | KM | GA01ME0 | 4.322 | GA01ME0 | 4.3609 | KM |  |  |  |  | 4.322 | 4.361 | 2026-06-30 |  |  |  |  | 4 | 4.6 | 3 | 4.4 | 1 | 18.8 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:37 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068737&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068737 | OH - Termination Portal Renewal | SQ020401 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | MILLENIUN MINE | MILLENIUN MINE | 0.035 | KM | MM/4/288/L | 0 | MM/4/323/L | 0 | KM |  |  |  |  | 4.288 | 4.323 | 2026-06-30 |  |  |  |  | 4 | 2.5 | 3 | 3.7 | 1 | 14.8 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:45 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068750&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068750 | OH - Termination Portal Renewal | SQ020478 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | MORANBAH NORTH | MORANBAH NORTH | 0.0359 | KM | GA01ME0 | 5.025 | GA01ME0 | 5.0609 | KM |  |  |  |  | 5.025 | 5.061 | 2026-06-30 |  |  |  |  | 4 | 2.9 | 3 | 3.9 | 1 | 15.6 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:49 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068753&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000068753 | OH - Termination Portal Renewal | SQ020481 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 120000 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0.0379 | KM | GA01ME0 | 217.2069 | GA01ME0 | 217.245 | KM |  |  |  |  | 217.207 | 217.245 | 2026-06-30 |  |  |  |  | 4 | 0.9 | 3 | 3 | 1 | 12 | 5555 | 2024-03-28 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25. 31.03.2023: decision to defer made in meeting of 31.03.23 to reduce FY25 spend.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068748&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000068748 | OH - Termination Portal Renewal | SQ020474 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 120000 | Goonyella | OAKY CREEK | OAKY CREEK | 0.0359 | KM | GA01ME0 | 152.847 | GA01ME0 | 152.883 | KM |  |  |  |  | 152.847 | 152.847 | 2026-06-30 |  |  |  |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 | 5555 | 2024-03-28 |  | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | 12.01.2023 PCR 5555: The termination portals concept is to have a design that allows for installation in a 4hr window aligned with routine maintenace. Advice received this is not achievable and as such more detailed assessment and planning is required. Currently it is certain that a high proportion (potentially all) of the FY23 scope will defer into FY24. FY24 scope moved to FY25. 31.03.2023: decision to defer made in meeting of 31.03.23 to reduce FY25 spend
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068742&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068742 | OH - Termination Portal Renewal | SQ020468 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0.0859 | KM | GA01ME0 | 47.0009 | GA01ME0 | 47.087 | KM |  |  |  |  | 47.001 |  | 2026-06-30 |  |  |  |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:16:57 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068743&DY_MAB=X&~OKCODE=ONLI | FY26 |  | BASELOAD | COAL | 002000068743 | OH - Termination Portal Renewal | SQ020469 | ELECTRICAL | OVERHEAD | TERMINATION PORTAL | RENEWAL | 2 | STRUCTURES | 93000 | Goonyella | SARAJI | SARAJI | 0.0359 | KM | GA01ME0 | 68.134 | GA01ME0 | 68.17 | KM |  |  |  |  | 68.134 | 68.17 | 2026-06-30 |  |  |  |  | 4 | 1.8 | 3 | 3.4 | 1 | 13.6 | 5639 | 2024-03-28 | 2021-10-05 | Termination Portals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF | FY23 IN | 20260630 | * 31.03.2021 19:17:01 AUSQLD Tracy Holmes (R870040) * No Design completed yet (Q1 FY23) (should be able to do 3 generic designs for termination portals), new product category for MRSB document - needs new RIG category <(>&<)> settlement rule (in SAP). - final end state design exists on where they want to get this to (need to know the now state to get to end state) 11.01.2024 K.H. - Completed IFC Pack attached to the notification 23.01.2024 K.H - POST-IFC Pack attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136218&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136218 | AT - BLAIR ATHOL ATS - AT1 | ST001390-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | GA05ML103 | 0.5849 | GA05ML103 | 0.5849 | KM |  |  |  |  | 103.585 | 103.585 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23/02/2024 EK: Design Notification for FY26 AT Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136301&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136301 | AT - BOONAL ATS - AT1 | ST001980-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | BOONAL ATS | BOONAL ATS | 0 | KM | BW03ML179 | 0.448 | BW03ML179 | 0.448 | KM |  |  |  |  | 179.448 | 179.448 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23-02-24 EK: Design Notification for FY26 AT Renewal. Refer to the attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136302&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136302 | AT - BOONAL ATS - AT2 | ST001980-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | BOONAL ATS | BOONAL ATS | 0 | KM | BW03ML179 | 0.448 | BW03ML179 | 0.448 | KM |  |  |  |  | 179.448 | 179.448 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23-02-24 EK: Design Notification for FY26 AT Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136251&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136251 | AT - MORANBAH - VILLAFRANCA ATS - AT1 | ST001290-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Goonyella | MORANBAH - VILLAFRANCA ATS | MORANBAH - VILLAFRANCA ATS | 0 | KM | GA05ML37 | 0.4319 | GA05ML37 | 0.4319 | KM |  |  |  |  | 37.432 | 37.432 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23-02-24 EK: Design Notification for FY26 AT Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136219&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136219 | AT - VILLAFRANCA-MOUNT MCLAREN ATS - AT1 | ST001310-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Goonyella | VILLAFRANCA-MOUNT MCLAREN | VILLAFRANCA-MOUNT MCLAREN | 0 | KM | GA05ML55 | 0.4969 | GA05ML55 | 0.4969 | KM |  |  |  |  | 55.501 | 55.501 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23-02-24 EK: Design Notification for FY26 AT Renewal. Refer to attached documentation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136300&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136300 | AT - WALTON ATS - AT2 | ST001970-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | DESIGN | 1 | UNIT | 12589 | Blackwater | WALTON ATS | WALTON ATS | 0 | KM | BW03ML162 | 0.202 | BW03ML162 | 0.202 | KM |  |  |  |  | 162.202 | 162.202 | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 23-02-24 EK: Design Notification for FY26 AT Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105112&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000105112 | AT¦BURNGROVE AT2¦RENEWAL | ST000070-16 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | BURNGROVE | BURNGROVE | 0 | KM | BW03ML202 | 0.5 | BW03ML202 | 0.5 | KM |  |  |  |  | 202.5 | 202.5 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105110&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000105110 | AT¦GERMAN CREEK AT1¦RENEWAL | ST000760-08 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105111&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000105111 | AT¦GERMAN CREEK AT2¦RENEWAL | ST000760-09 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM |  |  |  |  | 136.433 | 136.433 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105114&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000105114 | AT¦GRANTLEIGH AT2¦RENEWAL | ST000210-21 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105113&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000105113 | AT¦GRANTLEIGH AT3¦RENEWAL | ST000210-22 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 | KM | BW03ML63 | 0.803 | BW03ML63 | 0.803 | KM |  |  |  |  | 63.803 | 63.803 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC |  | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000076109&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | STRATEGIC | COAL | 002000076109 | AT¦VILLAFRACA TSC - AT2¦RENEWAL | ST000790-13 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | VILLAFRANCA TSC - AT2 | VILLAFRANCA TSC | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM |  |  |  |  | 44.967 | 44.967 | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | 5595 | 2024-03-28 |  | Autotransformer Renewal | STRATEGIC | LOW | MEDIUM | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20260630 | 9/6/23: AT renewal moved from FY24 to FY26. Refer PCR 5595.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125195&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000125195 | WINDAH AT PSC DC-DC CONVERTER | ST002140-03 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | SITE | 26000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW03ML55 | 0.0929 | BW03ML55 | 0.0929 | KM |  |  |  |  | 54.1 | 54.1 | 2026-06-30 |  |  |  |  | 5 | 3.35 | 1 |  | 1 |  | 5614 | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STRATEGIC | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | REPLACE ELTEK WALLPACK WITH BENBRO DC-DC CONVERTER, SUPPLIED FROM EXISTING TELECOMMS DC SYSTEM. 28.03.24 EK: Typical applicable standard design, photos <(>&<)> forms with internal/external access information attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085297&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085297 | AROONA¦PSC DC SYSTEM¦RENEWAL | ST001930-05 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | UNIT | 25000 | Blackwater | AROONA | AROONA | 0 | KM | BW03ML94 | 0.8549 | BW03ML94 | 0.8549 | KM |  |  |  |  | 0.855 | 0.855 | 2026-06-30 |  |  |  |  | 3 | 3.35 |  | 2.9 | 1 | 8.7 |  | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Renewal of Amtex Charger. Renewal year may change. 28/03/24 EK: Typical applicable Std design for Aroona and site renewal checklist (includes internal/external access) attached. Post turnover, the information from checklist will be transferred to the PSC DC Renewal Scope/Site Walkout Form (AZN.NA.FRM.06.6191.148/149).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085298&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085298 | CLINTON¦PSC DC SYSTEM¦RENEWAL | ST009140-01 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | UNIT | 25000 | Blackwater | CLINTON | CLINTON | 0 | KM | BW53CR2 | 0.097 | BW53CR2 | 0.097 | KM |  |  |  |  | 0.097 | 0.097 | 2026-06-30 |  |  |  |  | 3 | 0.9 |  | 0.7 | 1 | 2.1 |  | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Renewal year may change. 28.03.24 EK: Only existing form for Clinton and applicable std design attached. Information incomplete and may need to be updated to include internal/external access and site photos.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085296&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000085296 | TUNNEL¦PSC DC SYSTEM¦RENEWAL | ST001920-05 | ELECTRICAL | POWER SYSTEMS | DC SUPPLY | RENEWAL | 1 | UNIT | 25000 | Blackwater | TUNNEL | TUNNEL | 0 | KM | BW03ML74 | 0.9749 | BW03ML74 | 0.9749 | KM |  |  |  |  | 0.975 | 0.975 | 2026-06-30 |  |  |  |  | 3 | 3.75 |  | 3.1 | 1 | 9.3 |  | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | Renewal of Amtex Charger. Renewal year may change. 28/03/24 EK: Typical applicable Std design and site renewal checklist (includes internal/external access) attached. Post turnover, the information from checklist will be transfered to the PSC DC Renewal Scope/Site Walkout Form (AZN.NA.FRM.06.6191.148/149).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094386&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094386 | T32-PS-GA-German Ck-1.485km | ST000760-04 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | GERMAN CREEK | GERMAN CREEK | 0 | KM | GA03ML136 | 0.4329 | GA03ML136 | 0.4329 | KM |  |  |  |  | 1.485 | 1.485 | 2026-06-30 |  |  |  |  | 3 | 1.4 | 0.5 | 1.4 | 1 | 4.2 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | German Ck TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094389&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094389 | T32-PS-GA-Moranbah Sth-20.02km | ST000780-09 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | MORANBAH SOUTH | MORANBAH SOUTH | 0 | KM | GA05ML19 | 0.9759 | GA05ML19 | 0.9759 | KM |  |  |  |  | 20.02 | 20.02 | 2026-06-30 |  |  |  |  | 3 | 1.5 | 0.5 | 1.5 | 1 | 4.5 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Moranbah Sth TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094392&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094392 | T32-PS-GA-Red Mountain-19.397km | ST000720-04 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | RED MOUNTAIN | RED MOUNTAIN | 0 | KM | GA03ML19 | 0.438 | GA03ML19 | 0.438 | KM |  |  |  |  | 19.397 | 19.397 | 2026-06-30 |  |  |  |  | 3 | 2.5 | 0.5 | 2.4 | 1 | 7.2 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Red Mtn TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094385&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094385 | T32-PS-BW-Red Rock-42.288km | ST000090-04 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Blackwater | RED ROCK | RED ROCK | 0 | KM | BW08ML42 | 0.14 | BW08ML42 | 0.14 | KM |  |  |  |  | 42.288 | 42.288 | 2026-06-30 |  |  |  |  | 3 | 1.1 | 0.5 | 1 | 1 | 3 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Red Rock TSC LV earth system isolation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094390&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094390 | T32-PS-GA-Saraji-61.216km | ST000740-03 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | SARAJI | SARAJI | 0 | KM | GA03ML71 | 0.271 | GA03ML71 | 0.271 | KM |  |  |  |  | 71.216 | 71.216 | 2026-06-30 |  |  |  |  | 3 | 1.8 | 0.5 | 1.8 | 1 | 5.4 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Saraji TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094391&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094391 | T32-PS-GA-South Walker-126.964km | ST006540-28 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | SOUTH WALKER | SOUTH WALKER | 0 | KM | GA01ML127 | 0.1 | GA01ML127 | 0.1 | KM |  |  |  |  | 126.964 | 126.964 | 2026-06-30 |  |  |  |  | 3 | 4.7 | 0.5 | 3.6 | 1 | 10.8 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Sth Walker TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094388&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094388 | T32-PS-GA-Villafranca-45.001km | ST000790-04 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Goonyella | VILLAFRANCA | VILLAFRANCA | 0 | KM | GA05ML44 | 0.9669 | GA05ML44 | 0.9669 | KM |  |  |  |  | 45.001 | 45.001 | 2026-06-30 |  |  |  |  | 3 | 1.2 | 0.5 | 1.2 | 1 | 3.6 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Villafranca TSC LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094387&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000094387 | T32-PS-BW-Yan Yan-0.118km | ST000460-06 | ELECTRICAL | POWER SYSTEMS | LV SYSTEM EARTHING | RENEWAL | 1 | SITE | 40000 | Blackwater | YAN YAN | YAN YAN | 0 | KM | BW10ML0 | 0.1179 | BW10ML0 | 0.1179 | KM |  |  |  |  | 0.118 | 0.118 | 2026-06-30 |  |  |  |  | 3 | 1.1 | 0.5 | 1 | 1 | 3 |  | 2024-03-28 |  | Earthing and Bonding | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Yan Yan TCU LV earth system isolation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136413&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136413 | MI Renewal 242/2 Coppabella | SQ030611 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | OC/3/932/D | 0 | OC/3/932/D | 0 | KM |  |  |  |  | 3.93 | 3.93 | 2026-06-30 |  |  |  |  | 3.94 | 2.4 | 2 | 3 | 1 | 12.61 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY24 MI Renewal. 28/2/24 R.Licis: This is a renewal noti fo FY26. The scope is a B1. Change to manual TRACTION CONSTRUCTION $32,290 MATERIAL: $10,000 SCADA UPDATE $1,100 TRACTION DESIGN ASBUILT $2,420 TOTAL: $45,810 (estimate only)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136414&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136414 | MI Design 902J/906E Jilalan | SQ030552 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/634/PR2 | 0 | GA/17/634/PR2 | 0 | KM |  |  |  |  | 17.63 | 17.63 | 2028-05-31 |  |  |  |  | 3.9 | 4.6 | 2 | 4 | 1 | 15.99 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28/02/24 R.Licis: Requires optioneering first due to access issue
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136417&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136417 | MI Design 905/4 Jilalan | SQ030563 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/804/UY | 0 | GA/22/804/UY | 0 | KM |  |  |  |  | 22.8 | 22.8 | 2026-06-30 |  |  |  |  | 2.9 | 4.6 | 2 | 4 | 1 | 11.89 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28/2/24 R.Licis: Requires optioneering first due to access issue 05-03-24 EK: Optioneering work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136419&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136419 | MI Design 622/4 Mallawa | SQ030262 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA/167/747/D | 0 | GA/167/747/D | 0 | KM |  |  |  |  | 167.75 | 167.75 | 2026-06-30 |  |  |  |  | 3.44 | 2.4 | 2 | 3 | 1 | 11.01 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28-02-24 RL: General scope is a B2 however check if this access issue to maintain isolator.Need to understand scope first. This may become a bespoke design.Optioneering to be done first 05-03-24 EK: Optioneering work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136444&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136444 | MI Design 282/2 Mindi | SQ030275 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Goonyella | MINDI | MINDI | 0 | KM | GA/120/720/D | 0 | GA/120/720/D | 0 | KM |  |  |  |  | 120.72 | 120.72 | 2026-06-30 |  |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification in FY26 MI Renewal 28/02/24 R.Licis: Requires optioneering first before design. 05-03-24 EK: Optionionaring work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136448&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136448 | MI Design 542/2 Raglan | SQ030183 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Blackwater | RAGLAN | RAGLAN | 0 | KM | N/584/102/D | 0 | N/584/102/D | 0 | KM |  |  |  |  | 584.1 | 584.1 | 2026-06-30 |  |  |  |  | 4.1 | 4.9 | 2 | 4 | 1 | 17.22 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design notification for FY26 MI Renewal 28/02/24 R.Licis: This noti to be scoped first with civil to see if access from the highway is possible or not.Need optioneering first! 05-03-24 EK: Optioneering work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136449&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136449 | MI Design 121/6 Tunnel West | SQ030595 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Blackwater | TUNNEL WEST | TUNNEL WEST | 0 | KM | CW/75/964/U | 0 | CW/75/964/U | 0 | KM |  |  |  |  | 75.96 | 75.96 | 2026-06-30 |  |  |  |  | 3.44 | 3.75 | 2 | 4 | 1 | 13.07 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28/2/24 R.Licis: Optioneering required first due to access issue 05-03-24 EK: Optioneering work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136450&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136450 | MI Design 811/4 Warren | SQ030536 | ELECTRICAL | POWER SYSTEMS | MI | DESIGN | 1 | UNIT | 20000 | Blackwater | WARREN | WARREN | 0 | KM | CW/25/152/U | 0 | CW/25/152/U | 0 | KM |  |  |  |  | 25.15 | 25.15 | 2026-06-30 |  |  |  |  | 3.4 | 3.35 | 2 | 4.2 | 1 | 12.24 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28/2/24 R.Licis: Requires optioneering first due to poor access 05-03-24 EK: Optioneering work as part of preliminary design is required before start of design. Estimates will be finalised at the end of this optioneering activity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044495&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044495 | MI Renewal 601/2 Black Mountain | SQ030213 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 84810 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA/40/770/U | 0 | GA/40/770/U | 0 | KM |  |  |  |  | 40.77 | 40.77 | 2026-06-30 |  |  |  |  | 3.4 | 5 | 2 | 4.2 | 1 | 14.28 | 5072 | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | * 06.03.2020 14:26:44 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 601/2 23/11/2021: Swap 601/2 Blackmountain with 621/3 Mallawa (From FY25) due to access issue. TO be a bespoke design. Refer to approved PCR 5072. Isolator 601/2 Blackmountain will be transferred to FY24. Mod ID updated from F22 to FY24. 13/2/2022 R.Licis: This renewal noti to be relocated to FY25. A separate noti for design to be done in FY24. 27/9/2022 R.Licis: PM has requested renewal to be done 2 years after design. Mod ID changed to FY26 22/8/2022 R.Licis: Design to be completed in FY24, Procurement in FY25, Renewal (this noti) will be done in FY26 2/10/2022 R.Licis: OHW cost breakdown TRACTION CONSTRUCTION $61,010 MATERIAL: $20,000 SCADA COMMISSIONING $1,100 TRACTION DESIGN ASBUILT $2,700 TOTAL: $84,810 (Estimate only) 22/3/2024 R.Licis: DD30 design attached.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136411&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136411 | MI Renewal 241/2 Coppabella | SQ030264 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 52330 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | OC/3/776/U | 0 | OC/3/776/U | 0 | KM |  |  |  |  | 3.78 | 3.78 | 2026-06-30 |  |  |  |  | 3.94 | 2.4 | 2 | 3.2 | 1 | 12.61 |  | 2024-03-28 |  | Motorised Isolator Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | 24-02-24 EK: Design Notification for FY26 MI Renewal 28-02-24 RL: Scope type for this is B2 double MATERIAL COST: $10,000 CONSTRUCTION COST: $38,530 SCADA: $1,100 ASBUILT $2,700 TOTAL: $52,330
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044500&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044500 | MI Renewal 241B/242C Coppabella | SQ030613 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 52330 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | OC/3/820/U | 0 | OC/3/820/U | 0 | KM |  |  |  |  | 3.85 | 3.85 | 2026-06-30 |  |  |  |  | 3.94 | 2.4 | 2 | 3.2 | 1 | 12.61 | 5073 | 2024-03-28 |  | Motorised Isolator Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | * 19.03.2021 22:22:00 AUSQLD Rinaldo Licis (R851602) * Reinstated from deletion since work has not been completed. Assigned to FY23-24 by RL and HC * 19.03.2021 22:24:22 AUSQLD Rinaldo Licis (R851602) * Assigned to FY23. Entered incorrectly previously. * 22.03.2021 14:42:11 AUSQLD Rinaldo Licis (R851602) * Replaces 602/4 at Blackmountain which has been completed already 13/2/2022 R.Licis: Relocate this Renewal noti for construction in FY25. To be done together with 242/2 once the PSC5 have connection with adjacent SER for communication. This communication will be designed in FY24. A separate noti for FY24 telecom design to be created. 6/3/2023 R.Licis: Moved to FY28 18/8/2023 R.Licis: Applied MI philosophy. Now the MI is manual. Now can be slotted to FY26 renewal.Telecom design noti 2000091899 deleted. 28-02-24 RL: Scope type for this is B2 double MATERIAL COST: $10,000 CONSTRUCTION COST: $38,530 SCADA: $1,100 ASBUILT $2,700 TOTAL: $52,330 (estimate only)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044465&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044465 | MI Renewal 321/3 Dysart | SQ030251 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 40745 | Goonyella | DYSART | DYSART | 0 | KM | OC/88/384/U | 0 | OC/88/384/U | 0 | KM |  |  |  |  | 88.384 | 88.384 | 2026-06-30 |  |  |  |  | 4.1 | 1.4 | 2 | 2.7 | 1 | 11.07 |  | 2024-03-28 | 2019-11-29 | Motorised Isolator Renewal | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 10.11.2020 15:29:51 AUSQLD Zane Hooton (R875021) * This MI was swapped out of FY21 for Tootoolah 231/3. Refer WOs 57040180 and 57039975 which appear like normal NMP wo's. * 19.03.2021 16:26:18 AUSQLD Rinaldo Licis (R851602) * Moved to FY24-525 by RL and HC 6/3/23 R.Licis: Renewal moved to FY26 22/8/2023 R.Licis: Scope type is E2. 2/10/2023 R.Licis: OHW cost breakdown: TRACTION CONSTRUCTION $27,225 MATERIAL: $10,000 SCADA COMMISSIONING $1,100 TRACTION DESIGN ASBUILT $2,420 TOTAL: $40,745
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104149&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104149 | MI Renewal 901A/902L Grasstree | ST007640-08 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | GRASS TREE | GRASS TREE | 0 | KM | GA/9/605/U | 0 | GA/9/605/U | 0 | KM |  |  |  |  | 9.605 | 9.605 | 2026-06-30 |  |  |  |  | 3.2 | 4.6 | 2 | 4.1 | 1 | 13.12 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | 9/9/2022 R.Licis: MI Renewal with bespoke design. Design to be completed in FY23 and Construction in FY25. PM to update unit cost in SPM. BOM to be attached once design has been completed - Dec 2022. 16/1/2022 R.Licis: BOM attached 6/3/2023 R.Licis: Moved renewal to FY26. Bespoke design completed. 26/6/2023 R.Licis: Bill of Material and Design attached. Planner and Site Engineer to order material in FY25 for delivery in FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104280&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000104280 | MI Renewal 911H/912A Grasstree | ST007640-07 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | GRASSTREE | GRASSTREE | 0 | KM | GA/9/595/D | 0 | GA/9/595/D | 0 | KM |  |  |  |  | 9.605 | 9.605 | 2026-06-30 |  |  |  |  | 3.2 | 4.6 | 2 | 4.1 | 1 | 13.12 |  | 2024-03-28 | 2021-10-05 | Motorised Isolator Renewal | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20260630 | 9/9/2022 R.Licis: MI Renewal with bespoke design. Design to be completed in FY23 and Construction in FY25. PM to update unit cost in SPM. BOM to be attached once design has been completed - Dec 2022. 16/1/2023 R.Licis: BOM attached. 6/3/2023 R.Licis: Renewal moved to FY26 26/6/2023 R.Licis: Bill of Material and Design attached. Planner and Site Engineer to order material in FY25 for delivery in FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075926&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000075926 | MI Renewal 902/9 Jilalan | SQ030547 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 45810 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/549/UJY | 0 | GA/17/549/UJY | 0 | KM |  |  |  |  | 17.549 | 17.549 | 2026-06-30 |  |  |  |  | 3.4 | 4.6 | 2 | 4.1 | 1 | 13.94 |  | 2024-03-28 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | 11/3/2021 R.Licis: Scope and inspection form attached. 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 6/3/2023 R.Licis: Move to FY26 2/10/2023 R.Licis: New Scope type is B2 Double. BOM attached 2/10/2023 R.Licis: OHW Cost breakdown TRACTION CONSTRUCTION $32,290 MATERIAL: $10,000 SCADA UPDATE $1,100 TRACTION DESIGN ASBUILT $2,420 TOTAL: $45,810
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075925&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000075925 | MI Renewal 902/8 Jilalan | SQ030546 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 45810 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/676/PR1 | 0 | GA/17/676/PR1 | 0 | KM |  |  |  |  | 17.676 | 17.676 | 2026-06-30 |  |  |  |  | 3.4 | 4.6 | 2 | 4.1 | 1 | 13.94 |  | 2024-03-28 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20260630 | 11/3/2022 R.Licis: Scope and inspection form attached. 12.01.2023 PCR 5557: Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support to FY25. This reduces the demand for overheads and allows for typical trends of deferred scope. 6/3/2023 R.Licis: Moved to FY26. 22/8/2023 R.Licis: Applied new MI philosophy now Scope type is B2 Double. Preiously F4. New Scope doc and BOM attached. N4 unit cost updated. 2/10/2023 R.Licis: OHW Cost breakdown: TRACTION CONSTRUCTION $32,290 MATERIAL: $10,000 SCADA UPDATE $1,100 TRACTION DESIGN ASBUILT $2,420 TOTAL: $45,810
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044520&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044520 | MI Renewal 902/3 Jilalan | SQ030556 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 78900 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/23/150/DM | 0 | GA/23/150/DM | 0 | KM |  |  |  |  | 23.15 | 23.15 | 2026-06-30 |  |  |  |  | 3.4 | 4.6 | 2 | 4.1 | 1 | 13.94 |  | 2024-03-28 | 2021-10-05 | Motorised Isolator Renewal | BESPOKE DESIGN |  | LOW | LOW | LOW | Notification in process | SCPR | FY23 IN | 20260630 | * 06.03.2020 14:33:13 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 902/3 * 22.03.2021 15:02:00 AUSQLD Rinaldo Licis (R851602) * MI 902/3 at Jilalan to be swapped with MI 232/35 at Macarthur. MI 902/3 to be done in FY23 now. * 12.04.2021 16:21:44 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 1. OHW design to relocate MI 902/3 to portal GA/26/96 on the up GA by pass road side, next to Access road. 2. New Control/Power cable design to be installed and tapped into existing run. Execution scope (cable schedule and estimate) Renewal Scope FY25 (this noti): 1. Relocate and renew MI portal GA/26/96 2. Connect new motor/control cable to existing or directly to new SER 27/9/2022:PM has requested the renewal to be done in FY26 to allow two years gap from design work of FY24. 2/10/2023 R.Licis: Scope is a bespoke design.Design and BOM to be provided in FY24. NOTE: change to manual 2/10/2023 R.Licis:OHW cost breakdown TRACTION CONSTRUCTION $55,200 MATERIAL: $22,000 (estimate without design) SCADA COMMISSIONING $1,100 TRACTION DESIGN ASBUILT $600 TOTAL: $78,900 (estimate) 22/3/2024 R.Licis: DD50 bespoke design attached to notification
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074338&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000074338 | MI Renewal Rockland TSC 551A/552E | ST000160-06 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 56100 | Blackwater | ROCKLAND | ROCKLAND | 0 | KM | BW03ML1 | 0.553 | BW03ML1 | 0.553 | KM |  |  |  |  | 1.56 | 1.56 | 2026-06-30 |  |  |  |  | 4.1 | 3.35 | 2 | 3.5 | 1 | 14.76 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | * 22.03.2021 15:42:03 AUSQLD Rinaldo Licis (R851602) * MI 551A/552E swapped with MI 551E/552D. MI 551A/552E to be renewed in FY22 Planned for 16-17 May 21 closure Waiting on Rocklands Confirmation of renewal options - Rinaldo 27.1.22 4/3/2022 R.Licis: Tentatively transfered to FY25 because funding and design for walkway access to isolator not available. Replaced by 522/6 Aldoga to be done in May 2022 closure. Identical scope. Subject to approval by Stakeholder in 8 March 2022. PCR to follow. 11/7/2022 R.Licis: Transfer to FY25 - PCR 5324. 27/9/2022 R.Licis: PM has requested renewal to be done 2 years after design. Mod ID changed to FY26 29/02/24 R.Licis: Bespoke design and BOM available at end of FY24 Traction Design Support: $1,200 Traction Construction: $43,000 Material based C type: $11,300 Traction Design: $600 Total: $56,100 (estimate only) 22/3/2024 R.Licis: DD30 OH Design attached. Note the embankment is higher than what is shown. Civil design not available at the time of writing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136906&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136906 | MI TWIN ACCESS WALKWAY ROCKLAND TSC | ST000160-03 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 55266 | Blackwater | ROCKLAND | ROCKLAND | 0 | KM | BW03ML1 | 0.558 | BW03ML1 | 0.558 | KM |  |  |  |  | 1.56 | 1.56 | 2026-06-30 |  |  |  |  | 4.8 | 3.35 | 2 | 3.6 | 1 | 17.28 |  | 2024-03-28 |  | Motorised Isolator Renewal | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | This is for construction for the twin walkway to access the two MI in front of Rockland TSC. Estimate provided by Brian Kinnear ESTIMATE: MATERIAL: $29,476 CONSTRUCTION: 25,750 TOTAL:$55,226 22/3/2024 R.Licis: At the time of writing civil design is not available. Refer to attachment, Option 2 has been selected. It will consist of two walkway ramp from top of embankment of Rockland TSC to each isolator mast. Refer to photo from Crew. Note two chainlink fence door to be installed as well. The attachment provided will be provide some info for planning purposes. 25/3/2024 R.Licis: Civil has provided prelim design sketch received 25/3/2024. Attached to notification.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044416&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044416 | MI Renewal Rockland TSC 101A/102G | ST000160-03 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 56100 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.558 | BW03ML1 | 0.558 | KM |  |  |  |  | 1.56 | 1.56 | 2026-06-30 |  |  |  |  | 4.8 | 3.35 | 2 | 3.6 | 1 | 17.28 | 4896 | 2024-03-28 | 2019-11-29 | Motorised Isolator Renewal | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Notification in process | SCPR |  | 20260630 | * 19.03.2021 16:56:02 AUSQLD Rinaldo Licis (R851602) * To be moved to FY23 temporarily due to access issue but most likely end up in FY22. PCR to be issued. * 22.03.2021 15:36:33 AUSQLD Rinaldo Licis (R851602) * MI 101A/102G to be renewed in FY22. * 12.05.2021 13:40:38 AUSQLD Zane Hooton (R875021) * Scoping forms attached. * 03.06.2021 16:44:55 AUSQLD Rinaldo Licis (R851602) * PCR 4896 lodged. Access issue to be design and construction prior to renewal 15/12/2021 R.Licis: This MI location has not been renewed yet. To be done May 2022 closure. For some reason this N4 was TECO'd.This MI is planned for May 2022 BW closure. Waiting on Rocklands Confirmation of renewal options - Rinaldo 27.1.22 4/3/2022 Tentatively swapped to FY25 as the walkway funding and design is not available yet. 27/9/2022 R.Licis: Noti was put back in process. Not sure why it was PCOM'd as the work has not been done yet. PM has requested renewal to be done 2 years after design. Mod ID changed to FY26 29/02/24 R.Licis: Bespoke design and BOM available at end of FY24 Traction Design Support: $1,200 Traction Construction: $43,000 Material based C type: $11,300 Traction Design: $600 Total: $56,100 (estimate only) 22/3/2024 R.Licis: DD30 OH Design attached. Note the embankment is higher than what is shown. Civil design not available at the time of writing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136894&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000136894 | MI AccessStairway Renewal 551/5 Rockland | SQ030172 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 30000 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | N/631/792/U | 0 | N/631/792/U | 0 | KM |  |  |  |  | 631.792 | 631.792 | 2026-06-30 |  |  |  |  | 4.1 | 3.35 | 2 | 3.6 | 1 | 14.76 |  | 2024-03-28 |  | Motorised Isolator Renewal | LIKE FOR LIKE |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | 29/2/24 R.Licis: This is the Civil renewal of an existing stairway to access isolator 551/5 at Rockland @NCL 631k792 Down Road. Design is currently being designed by Civil Engineering. Design to be completed by end of FY24.Renewal estimate provided by Simon Larsen 28/3/23.Renewal cost estimate is $30,000 25/3/2024 R.Licis: Civil Sketch Design received 25/3/2024 and attached to noti. Final design in progresss.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044441&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000044441 | MI Renewal 551/5 Rockland | SQ030172 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42420 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | CW/631/792/D | 0 | CW/631/792/D | 0 | KM |  |  |  |  | 631.792 | 631.792 | 2026-06-30 |  |  |  |  | 4.1 | 3.35 | 2 | 3.6 | 1 | 14.76 |  | 2024-03-28 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW | HIGH | HIGH | HIGH | Notification in process | SCPR | FY23 IN | 20260630 | * 06.03.2020 14:41:03 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 551/5 * 22.03.2021 15:23:33 AUSQLD Rinaldo Licis (R851602) * MI 551/5 at Rockland to be swapped with MI 161/9 McKenzie. MI 551/5 to be done in FY23. * 12.04.2021 16:21:45 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 2/3/2022 R.Licis: Inspection done. Stairway to MI to be renewed. To engage for Civil to do design in FY24 and renew stair and renew MI to manual isolator and new blade in FY25. This noti changed to FY25. Where the operator stand will need to be cleaned up as it is full of ballast. SCOPE TYPE is H2 11/7/2022 R.Licis: PCR 5409 submitted to renew MI in FY25. 27/9/2022 R.Licis: PM has requested renewal to be done 2 years after design. Mod ID changed to FY26 2/10/2023 R.Licis: Scope type is H2 2/10/2023 R.Licis: OHW Cost breakdown TRACTION CONSTRUCTION $40,000 TRACTION DESIGN ASBUILT $2,420 28/2/24 R.Licis: Stair design is being done in FY24. Therefore construction of stairway access (separate Electrical N4) to be done in first and then MI renewal(this N4). Both will be planned together to be done in FY26. There may be risk with ground level where is MI is that may be not level.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105466&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000105466 | ALDOGA AT 555.876 PSC SITE RENEWAL | ST001860-03 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Blackwater | ALDOGA | ALDOGA | 0 | KM | BW01ML555 | 0.876 | BW01ML555 | 0.876 | KM |  |  |  |  | 555.876 | 555.876 | 2026-06-30 |  |  |  |  | 3.5 | 4.5 | 0.5 | 3.5 | 1 | 12.3 |  | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | HIGH | LOW | Outstanding notification | SCPR |  | 20260630 | 28.03.24 EK: Optimisation led to the preliminary selection of the Aldoga PSC site. Further assessment post-turnover is required for final confirmation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105469&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | BASELOAD | COAL | 002000105469 | DYSART 88.400 PSC SITE RENEWAL | ST001750-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Goonyella | DYSART | DYSART | 0 | KM | GA03ML88 | 0.4 | GA03ML88 | 0.4 | KM |  |  |  |  | 88.4 | 88.4 | 2026-06-30 |  |  |  |  | 3.5 | 1.1 | 0.5 | 1 | 1 | 3.5 |  | 2024-03-28 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | LOW | HIGH | LOW | Outstanding notification | SCPR |  | 20260630 | 28.03.24 EK: Optimisation led to the preliminary selection of the Dysart PSC site. Further assessment post turn-over is required for final confirmation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136634&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136634 | PROTECTION RELAY - RANGAL - RL/C15 | ST000340-51 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2026-06-30 |  |  |  |  | 5 | 2.85 | 2 | 3.4 | 1 | 17 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26/02/24 EK: Design Notification for FY26 Relay. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136655&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136655 | PROTECTION RELAY - RANGAL- RL/BS1-2 | ST000340-52 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2026-06-30 |  |  |  |  | 5 | 2.85 | 2 | 3.4 | 1 | 17 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26-02-24 EK: Design Notification for FY26 Relay Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136656&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136656 | PROTECTION RELAY - RANGAL- RL/BS2-3 | ST000340-55 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2026-06-30 |  |  |  |  | 5 | 2.85 | 2 | 3.4 | 1 | 17 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26-02-24 EK: Design Notification for FY26 Relay Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136654&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136654 | PROTECTION RELAY - RANGAL- RL/C17 | ST000340-57 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2026-06-30 |  |  |  |  | 5 | 2.85 | 2 | 3.4 | 1 | 17 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26-02-24 EK: Design Notification for FY26 Relay Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136652&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136652 | PROTECTION RELAY - RANGAL- RL/O16 | ST000340-54 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM |  |  |  |  | 194.974 | 194.974 | 2026-06-30 |  |  |  |  | 5 | 2.85 | 2 | 3.4 | 1 | 17 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26/02/24 EK: Design Notification as part of FY26 Relay Renewal. Refer to attached documentation
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136657&DY_MAB=X&~OKCODE=ONLI | FY26 | Coal Traffic | FUTURE SCOPE | COAL | 002000136657 | PROTECTION RELAY - ROCKLAND - RD/BS1-2 | ST000160-29 | ELECTRICAL | POWER SYSTEMS | RELAYS | DESIGN | 1 | UNIT | 12000 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM |  |  |  |  | 1.56 | 1.56 | 2026-06-30 |  |  |  |  | 5 | 4.5 | 2 | 4.1 | 1 | 21 |  | 2024-03-28 |  | Protection Relay Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | 26-02-24 EK: Design Notification for FY26 Relay Renewal. Refer to attached documentation.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085330&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000085330 | Traction Substation Renewals | BW | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 8 | SITE | 2822190 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Traction Substation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. See cashflow spreadsheet attached to N4 for details. Estimate updated based on revised cashflow 7/9/22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085317&DY_MAB=X&~OKCODE=ONLI | FY26 |  | STRATEGIC | COAL | 002000085317 | Traction Substation Renewals | GA | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 14 | SITE | 4766916 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  | 2024-03-28 |  | Traction Substation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Will form part of FY24 rollover scope. Placeholder N4 to provide an indicative cashflow - CONCEPT level. See cashflow spreadsheet attached to N4 for details. Estimate updated based on revised cashflow 7/9/22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103909&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103909 | FY27 ACCESS POINT REACTIVE WORKS | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103912&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103912 | FY27 ACCESS POINT REACTIVE WORKS | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103915&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103915 | FY27 ACCESS POINT REACTIVE WORKS | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103918&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103918 | FY27 ACCESS POINT REACTIVE WORKS | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103905&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000103905 | C60-ACP-MA-BELLDEEN-156.087km | AP400037 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML156 | 0.0869 | MA01ML156 | 0.0869 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | C60-ACP-MA-BELLDEEN-156.087km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121200&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000121200 | C60-ACP-GA-DALY BAY-9.523km | AP200121 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA02ML9 | 0.523 | GA02ML9 | 0.523 | KM |  |  |  |  | 9.523 | 9.523 | 2026-06-30 |  |  |  |  | 10 | 10 | 2 | 0.1 | 1 | 100 |  |  |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY26 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103896&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000103896 | C60-ACP-BW-RAGLAN-591.798km | AP100303 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW02ML591 | 0.798 | BW02ML591 | 0.798 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY26 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103902&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000103902 | C60-ACP-NL 01ML-SONOMA-91.379km | AP300142 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Newlands | SONOMA | BIRRALEE | 0 | KM | NL01ML91 | 0.379 | NL01ML91 | 0.379 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | C60-ACP-NL 01ML-SONOMA-91.379km
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114616&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000114616 | FY27 ACCESS POINT RENEWAL | AP400052 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Moura | STIRRAT | CLARKE | 0 | KM | MA01ML45 | 0.251 | MA01ML45 | 0.251 | KM |  |  |  |  | 45.25 |  | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114131&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000114131 | FY27 ACCESS POINT RENEWAL | AP100112 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | WALLAROO | TRYPHINIA | 0 | KM | BW04ML115 | 0.761 | BW04ML115 | 0.761 | KM |  |  |  |  | 115.759 | 115.759 | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY25 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125416&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000125416 | C60-ACP-NL-BIRRALEE-95.6km | NL | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Newlands | BIRRALEE | COCKOOL | 214.038 | KM |  | 0 |  | 0 | [5 empty] | 95.6 |  | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY26 ACCESS POINT DESIGN- IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121188&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic | FUTURE SCOPE | NON-COAL | 002000121188 | C60-ACP-BW-BURNGROVE-203.32km | AP100421 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Blackwater | BURNGROVE | TOLMIES | 0 | KM | BW03ML203 | 0.318 | BW03ML203 | 0.318 | KM |  |  |  |  | 203.32 | 203.32 | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Moved to FY26 Design to meet the funding and design resource constraint. FY25 ACCESS POINT DESIGN as per TMR Road Access requirements: 1. Construction of slip and turning lanes 2. Installation of signage as per Aurizon standard 3. Drainage Improvements as per TMR Std.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121212&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000121212 | C60-ACP-GA-COPPABELLA-151.5km | AP200335 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella | COPPABELLA | BROADLEA | 0 | KM | GA02ML151 | 0.276 | GA02ML151 | 0.276 | KM |  |  |  |  | 151.5 | 151.5 | 2027-06-30 |  |  |  |  | 10 |  | 2 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Moved to FY26 for funding and design resource constraint. FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of turning lanes 2. Construction of drainage works 3. Installation of signage 4. Survey works 5. Road Manager's approval
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121210&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000121210 | C60-ACP-GA-HAY POINT-12.9km | AP200359 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01ML12 | 0.811 | GA01ML12 | 0.811 | KM |  |  |  |  | 12.9 | 12.9 | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 17.07.2023 Moved to FY27 IFC. Moved to FY26 for funding and design resource constraint. FY25 ACCESS POINT DESIGN. Scope of work may include: 1. Construction of slip and turning lanes 2. Construction of adequate drainage 3. Achieve road managers approval 4. Installaiton of Aurizon signage.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121211&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000121211 | C60-ACP-GA-MIDDLEMT-128.32km | AP200151 | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella | MIDDLEMOUNT | BUNDOORA | 0 | KM | GA27SD128 | 0.328 | GA27SD128 | 0.328 | KM |  |  |  |  | 128.32 | 128.32 | 2027-06-30 |  |  |  |  | 10 |  | 2 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Moved to FY26 for funding and design resource constraint. FY25 ACCESS POINT DESIGN. Scope OF WORK MAY INCLUDE: 1. CONSTRUCTION OF SLIP LANES 2. INSTALLATION OF SIGNAGE 3. Construction of adequate drainage 4. Achieve road Managers' approval.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103907&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103907 | FY27 ACCESS POINT DESIGN IFP | BW | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103910&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103910 | FY27 ACCESS POINT DESIGN IFP | GA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103913&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103913 | FY27 ACCESS POINT DESIGN IFP | MA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103916&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000103916 | FY27 ACCESS POINT DESIGN IFP | NL | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125412&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000125412 | C60-ACP-MA-MA-km | MA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 12000 | Moura | MA |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT DESIGN- IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103911&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000103911 | FY27 ACCESS POINT RENEWAL | AP200371 | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Goonyella |  |  | 0 | KM | GA01ML36 | 0.4799 | GA01ML36 | 0.4799 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114618&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000114618 | FY27 ACCESS POINT RENEWAL | AP300018 | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Newlands | ARMUNA | ABERDEEN | 0 | KM | NL01ML27 | 0.139 | NL01ML27 | 0.139 | KM |  |  |  |  | 27.1 |  | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114133&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000114133 | FY27 ACCESS POINT RENEWAL | AP100421 | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Blackwater | BURNGROVE | TOLMIES | 0 | KM | NC09ML203 | 0.318 | NC09ML203 | 0.318 | KM |  |  |  |  | 203.32 | 203.32 | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY25 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114137&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000114137 | FY27 ACCESS POINT RENEWAL | AP100686 | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Blackwater | GLADSTONE | MT LARCOM | 0 | KM | BW01ML546 | 0.5709 | BW01ML546 | 0.5709 | KM |  |  |  |  | 546.571 | 546.571 | 2027-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052258&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000052258 | C60-ACP-BW-RAGLAN-591.676km | AP100253 | CIVIL | ACCESS POINTS | UPGRADE | RENEWAL | 1 | SITE | 125000 | Blackwater | RAGLAN | MARMOR | 0 | KM | BW02ML591 | 0.676 | BW02ML591 | 0.676 | KM |  |  |  |  | 591.665 | 591.665 | 2023-06-30 | BRUCE HIGHWAY |  |  |  | 4 | 4.9 |  |  |  | 19.6 | 5660 | 2021-03-31 | 2021-10-05 | Access Points & Rds | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | HIGH | Outstanding notification | RRIG INIF | FY23 IN | 20270630 | * 24.02.2020 14:05:50 AUSQLD Allan Gough (R873345) * Check FLOC issues with Access Point AP007951 * 12.04.2021 16:20:56 AUSQLD Jeremy Stevenson (R867415) * No design complete * * Further analysis and consultation are required and revised Flocs to be provided by the OneSAP team- so delayed till FY26
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068914&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000068914 | Access Roads Reactive | BW | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 210000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4.5 | 2.5 |  |  |  | 11.25 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270730
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068915&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000068915 | Access Roads Reactive | GA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 195000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4.5 | 2.5 |  |  |  | 11.25 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270730
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068932&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000068932 | Access Roads Reactive | MA | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 165000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4.5 | 2.5 |  |  |  | 11.25 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270730
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068917&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000068917 | Access Roads Reactive | NL | CIVIL | ACCESS ROADS |  | REACTIVE WORKS | 1 | LUMPSUM | 175000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4.5 | 2.5 |  |  |  | 11.25 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270730
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074576&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000074576 | C14 GA DALRYMPLE BAY. | GA-04BA | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.25 | KM | 150806 | Goonyella | DALRYMPLE BAY | DALRYMPLE BAY | 0.25 | KM | GA04BA0 | 0.05 | GA04BA0 | 0.2999 | KM |  |  |  |  | 0.05 | 0.3 | 2026-06-30 | BLOOP4 |  |  |  | 4 | 2.6 |  |  |  | 10.4 | 5677 | 2021-03-31 | 2021-10-05 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW |  | HIGH | MEDIUM | Notification completed | RRIG INIF | FY23 IN | 20260630 | * 22.03.2021 10:55:08 AUSQLD Tracy Holmes (R870040) * severely fouling in 2018, no geometry, multiple D1 and D7 twists and top in Oct 20 report. * 12.04.2021 16:23:26 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Segmented notification due to point asset constraint during mainline high production RM902 u/c lined to notification 2000085868. 22.02.24 - Not delivered in FY23, put in FY26.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094906&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000094906 | C01-BU-BW-ALDOGA-556.190km-UP | BW-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 4.495 | KM | 2075386 | Blackwater | ALDOGA | MT LARCOM | 8.435 | KM | BW01ML556 | 0.19 | BW01ML564 | 0.65 | KM |  |  |  |  | 559 | 563.5 | 2026-06-30 | UP |  |  |  | 3.5 | 4.5 | 2 | 4 | 1 | 14.4 |  | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | HIGH | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Moderate to highly fouled ballast with severe patches Near D7 top and moderately rough Reviewed and updated during FY25 scoping to capture deleted FY22 scope FY26 scoping - extents increased to incorporate nearby scope. Deferred to FY27 due to condition score update reducing.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074512&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000074512 | CO1 GOONYELLA U/C | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.7 | KM | 328859 | Goonyella | BALOOK | WANDOO | 0.6999 | KM | GA01ML78 | 0.2 | GA01ML78 | 0.9 | KM |  |  |  |  | 78.2 | 78.9 | 2027-06-30 | DN |  |  |  | 4 | 4.8 |  |  |  | 19.2 |  | 2021-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20270630 | * 22.03.2021 10:39:07 AUSQLD Tracy Holmes (R870040) * Only 20m of section in Fy21, cut through crossing at 78.25. Track Upgrade starts at 78.161km - 79.290km in FY 22. Have not asked to do much except about 100m from 78.200 - 78.300km. 77.717km to 78.200km can be pushed to FY24 as it is not severely fouled and geometry is good. * 12.04.2021 16:23:02 AUSQLD Jeremy Stevenson (R867415) * Still to complete walkouts, need to identify bridg es, to etc. Need total escavation to confirm per * site cost? To ind notifications med risk but to ov erall program low risk * Luke Brownsey access planning advice and approved Tim Griffin 2 July 2021 with combining with N4 :2000074511 for FY22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074489&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000074489 | Ballast Undercut C01 ML Renew | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.227 | KM | 117932 | Goonyella | JILALAN | JILALAN | 0.227 | KM | GA01ML22 | 0.3029 | GA01ML22 | 0.53 | KM |  |  |  |  | 22.303 | 22.53 | 2027-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 22.03.2021 10:35:13 AUSQLD Tracy Holmes (R870040) * First section is from turnout through signals to start of km section. This was originally in FY23 and is now pushed out to FY25 to be completed with 81A/B and 11A/B.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074491&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000074491 | Ballast Undercut C01 ML Renew | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.45 | KM | 233786 | Goonyella | JILALAN | JILALAN | 0.45 | KM | GA01ML23 | 0 | GA01ML23 | 0.45 | KM |  |  |  |  | 23 | 23.45 | 2027-06-30 |  |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 22.03.2021 10:35:36 AUSQLD Tracy Holmes (R870040) * Third section is from bridge to one set of turnouts which will be completed in the same year - 83A/B. Over Bridge at 23.35km which will limit access. The scope includes the km for the turnout. Pushed out to FY25 with Turnout JB83A/B (TO000565)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094905&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000094905 | C01-BU-GA-NORWICH-PARK-118.200km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.22 | KM | 1023857 | Goonyella | NORWICH PARK | MIDDLEMOUNT JCT | 2.22 | KM | GA03ML118 | 0.2 | GA03ML120 | 0.4199 | KM |  |  |  |  | 118.2 | 120.42 | 2027-06-30 | MAINLINE |  |  |  | 3.5 | 1.5 | 2 | 3 | 1 | 9.5 |  | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20270630 | Highly fouled ballast with severe and moderate sections Near D7 defects according to track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094904&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000094904 | C01-BU-GA-NORWICH-PARK-108.260km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.206 | KM | 1019245 | Goonyella | NORWICH PARK | NORWICH PARK | 2.2059 | KM | GA03ML108 | 0.26 | GA03ML110 | 0.4699 | KM |  |  |  |  | 108.26 | 110.47 | 2027-06-30 | MAINLINE |  |  |  | 3.5 | 0.9 | 2 | 2 | 1 | 8.1 |  | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20270630 | Highly fouled ballast with severe and moderate sections Generally good track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052376&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000052376 | C01-BU-GA-SW-127.500km-DOWN | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.963 | KM | 0 | Goonyella | STH WLKR JCT-TOOTOOLAH | STH WLKR JCT-TOOTOOLAH | 1.2119 | KM | GA01ML127 | 0.75 | GA01ML128 | 0.9739 | KM |  |  |  |  | 127.5 | 128.475 | 2027-06-30 |  |  |  |  | 3 | 4.6 |  |  |  | 4.6 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | SCPR |  | 20270630 | FY22 Residual Scope Replan Comments: Not required to be replanned if not picked up in GPR. Some spots above 60%, with the majority falling in the 40-60% category, the remainder 30-40%. Geometry okay, but potential to deteriorate (note old geometry data) Email received from Reagan Case 24/08/2022 advising this scope is able to be moved to FY25. Mod ID Updated accordingly
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094896&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000094896 | C01-BU-GA-WINCHESTER-39.000km-MN | GA-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.95 | KM | 438137 | Goonyella | WINCHESTER | PEAK DNS | 0.9499 | KM | GA03ML39 | 0 | GA03ML39 | 0.9499 | KM |  |  |  |  | 39 | 39.95 | 2027-06-30 | MAINLINE |  |  |  | 3.5 | 2.1 | 2 | 3 | 1 | 10.9 |  | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20270630 | Highly to severely fouled ballast Generally good track geometry
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074495&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000074495 | Ballast Undercut C01 ML Renew | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.15 | KM | 77929 | Goonyella | YUKAN | BLACK MOUTAIN | 0.1499 | KM | GA01ML28 | 0.5999 | GA01ML28 | 0.75 | KM |  |  |  |  | 28.6 | 28.75 | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 22.03.2021 10:36:18 AUSQLD Tracy Holmes (R870040) * Leading into ER1.2A, Turnout 7CD is planned for FY22 an some of this will be picked up with it. The remainder is pushed out to be undertaken in FY25 with TO ER1.2A.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074499&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000074499 | Ballast Undercut C01 ML Renew | GA-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.601 | KM | 241579 | Goonyella | YUKAN | BLACK MOUTAIN | 0.6009 | KM | GA01ML40 | 0.55 | GA01ML41 | 0.1499 | KM |  |  |  |  | 40.55 | 41.15 | 2027-06-30 |  |  |  |  | 4 | 4.4 |  |  |  | 17.6 |  |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 22.03.2021 10:36:51 AUSQLD Tracy Holmes (R870040) * Ties scope before black mountain 8AB points through to FY22 scope together, could be pushed to FY24. Have pushed it to FY25
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103482&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000103482 | C14-BU-BW-BURNGROVE-0.050km-MAIN | BW-08ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.35 | KM | 218348 | Blackwater | BURNGROVE | CREW | 0.3499 | KM | BW08ML0 | 0.05 | BW08ML0 | 0.4 | KM |  |  |  |  | 0.05 | 0.4 | 2026-06-30 | MAIN |  |  |  | 3.5 | 1.2 | 2 | 2.5 | 1 | 8.75 | 189 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | NWSC |  | 20260630 | Split Notification from 2000094944
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085916&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085916 | C14-BU-GA-DALY BAY-0.330km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.47 | KM | 824424 | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 1.778 | KM | GA05BA0 | 0.6199 | GA05BA3 | 0.4 | KM |  |  |  |  | 0.33 | 0.8 | 2026-06-30 | LOOPS |  |  |  | 4 | 2.3 |  |  |  | 9.2 | 5428 |  |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC | FY23 IN | 20260630 | 19.10.2021 Tim Griffin (r878533) Mainline high production RM902 u/c segmented due to bridge and crew pad and linked to ntifications 2000074578 and 2000085915. 22.2.24 - Not delivered in FY23, moved to FY26.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103449&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103449 | C14-BU-GA-DALY BAY-0.650km-BALLOON | GA-04BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.937 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.937 | KM | GA04BA0 | 0.65 | GA04BA1 | 0.5869 | KM |  |  |  |  | 0.65 | 1.587 | 2023-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5862 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085868 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103500&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103500 | C14-BU-GA-DALY BAY-0.800km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 1.3 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.255 | KM | GA05BA0 | 0.8 | GA05BA2 | 0.1 | KM |  |  |  |  | 0.8 | 2.1 | 2023-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5861 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085916 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103501&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103501 | C14-BU-GA-DALY BAY-2.100km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.5 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.5 | KM | GA05BA2 | 0.1 | GA05BA2 | 0.5999 | KM |  |  |  |  | 2.1 | 2.6 | 2023-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5861 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085916 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103502&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103502 | C14-BU-GA-DALY BAY-2.600km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.25 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.25 | KM | GA05BA2 | 0.5999 | GA05BA2 | 0.8499 | KM |  |  |  |  | 2.6 | 2.85 | 2023-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5861 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085916 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103503&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103503 | C14-BU-GA-DALY BAY-2.850km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.25 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.2929 | KM | GA05BA2 | 0.8499 | GA05BA3 | 0.1 | KM |  |  |  |  | 2.85 | 3.1 | 2026-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5861 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085916 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103504&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000103504 | C14-BU-GA-DALY BAY-3.100km-BALLOON | GA-05BA | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.3 | KM |  | Goonyella | DALY BAY BLOOPS | DALY BAY BLOOPS | 0.2999 | KM | GA05BA3 | 0.1 | GA05BA3 | 0.4 | KM |  |  |  |  | 3.1 | 3.4 | 2023-06-30 | BALLOON |  |  |  | 3.75 | 2.6 | 2 | 3.3 | 1 | 12.38 | 5861 |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 2000085916 FY23 Split Scope
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104041&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000104041 | C14-BU-GA-BLACK MOUNTAIN-47.768km-UP | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C14 | RENEWAL | 0.442 | KM | 440528 | Goonyella | HATFIELD | HATFIELD | 0.442 | KM | GA02ML47 | 0.768 | GA02ML48 | 0.2099 | KM |  |  |  |  | 47.768 | 48.21 | 2022-06-30 |  |  |  |  | 4 | 5 | 2 | 4 | 1 | 16 | 5872 | 2020-03-06 | 2020-11-13 | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Notification in process | RRIG |  | 20270630 | FY22 Residual Scope Replan Comments: New notification created to split from 2000052405 as work order attached to FY22 notification and actuals recorded
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074604&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000074604 | C13 BLACKWATER T/O 226A CALLEMONDAH. | TO001161 | CIVIL | BALLAST UNDERCUTTING | TURNOUT | RENEWAL | 1 | TURNOUT | 141505 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.0309 | KM | BW02YR533 | 0.8709 | BW02YR533 | 0.902 | KM |  |  |  |  | 0.253 | 0.331 | 2027-06-30 |  |  |  |  | 4 | 4.8 |  |  |  | 19.2 | 5677 | 2021-03-31 | 2021-10-05 | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | RRIG INIF | FY23 IN | 20270630 | * 31.03.2021 18:55:16 AUSQLD Tracy Holmes (R870040) * Sites are subject to change due to condition of T/O sites changing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080284&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000080284 | BALLAST UNDERCUT TURNOUT REACTIVE | BW | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 138273 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [8 empty] | BW | [13 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080285&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000080285 | BALLAST UNDERCUT TURNOUT REACTIVE | GA | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 138273 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [8 empty] | GA | [13 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080274&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000080274 | BALLAST UNDERCUT TURNOUT REACTIVE | MA | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 138273 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [8 empty] | MA | [13 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080287&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000080287 | BALLAST UNDERCUT TURNOUT REACTIVE | NL | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 138273 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [8 empty] | NL | [13 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104252&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104252 | C13 Turnout U/C Abbot Point 9A/B | TO000101 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | ABBOT POINT | KAILI | 0.0459 | KM | NL02BL16 | 0.7229 | NL02BL16 | 0.769 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 1.7 | 2 | 4.1 | 1 | 17.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104238&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104238 | C13 Turnout B/U Duaringa 10A Pts | TO000723 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | AROONA | DUARINGA | 0.0369 | KM | BW04ML104 | 0.1029 | BW04ML104 | 0.14 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 3.4 | 2 | 3.6 | 1 | 13.4 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104237&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104237 | C13 Turnout B/U Duaringa 11C/D | TO000722 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | AROONA | DUARINGA | 0.049 | KM | BW04ML102 | 0.8269 | BW04ML102 | 0.778 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 3.4 | 2 | 3.6 | 1 | 13.4 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104239&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104239 | C13 Turnout B/U Duaringa 9A Pts | TO000724 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | AROONA | DUARINGA | 0.033 | KM | BW04ML104 | 0.808 | BW04ML104 | 0.775 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 3.4 | 2 | 3.6 | 1 | 13.4 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115797&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115797 | C13 Turnout B/U Balook 7A/B | TO000322 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | BALOOK | BALOOK | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 74.598 | 74.647 | 2027-06-30 | GA-02ML |  |  |  | 3.8 | 4.8 | 2 | 4.2 | 1 | 16 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080102&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080102 | C13 Turnout B/U Blackwater 11C/D | TO000732 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BLACKWATER | BLACKWATER | 0.048 | KM | BW04ML187 | 0.7269 | BW04ML187 | 0.679 | KM |  |  |  |  | 187.728 | 187.728 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.15 |  |  |  | 11 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080101&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080101 | C13 Turnout B/U Blackwater 10A/B | TO000692 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BLACKWATER | BLACKWATER | 0.049 | KM | BW04ML188 | 0.7269 | BW04ML188 | 0.776 | KM |  |  |  |  | 188.727 | 188.727 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.15 |  |  |  | 11 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104232&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104232 | C13 Turnout B/U Blackwater 9A/B | TO000644 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BLACKWATER | SAGGITARIUS | 0.047 | KM | BW03ML189 | 0.5979 | BW03ML189 | 0.551 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 3.2 | 2 | 3.6 | 1 | 14.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104229&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104229 | C13 Turnout B/U Sagittarius 12C/D | TO000660 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BLACKWATER | SAGGITARIUS | 0.0749 | KM | BW03ML191 | 0.9699 | BW03ML191 | 0.895 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.1 | 3.2 | 2 | 3.6 | 1 | 14.9 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104222&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104222 | C13 Turnout B/U Blackwater 7A/B | TO000643 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BLACKWATER | SAGGITARIUS | 0.048 | KM | BW03ML189 | 0.6969 | BW03ML189 | 0.7449 | KM |  |  |  |  | 189.697 | 189.745 | 2027-06-30 |  |  |  |  | 4 | 3.2 | 2 | 3.6 | 1 | 14.3 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104234&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104234 | C13 Turnout B/U Blackwater 12C/D | TO000647 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BOONAL | BLACKWATER | 0.047 | KM | BW03ML187 | 0.542 | BW03ML187 | 0.4949 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 3.2 | 2 | 3.6 | 1 | 14.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104233&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104233 | C13 Turnout B/U Blackwater 47A/B | TO000645 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BOONAL | BLACKWATER | 0.0359 | KM | BW03ML187 | 0.687 | BW03ML187 | 0.7229 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.1 | 3.2 | 2 | 3.6 | 1 | 14.9 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104221&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104221 | C13 Turnout B/U Blackwater 8A/B | TO000627 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BOONAL | BLACKWATER | 0.042 | KM | BW04ML189 | 0.3719 | BW04ML189 | 0.33 | KM |  |  |  |  | 189.33 | 189.372 | 2027-06-30 |  |  |  |  | 3.9 | 3.2 | 2 | 3.6 | 1 | 14 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115748&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115748 | C13 Turnout B/U Braeside 8A/B | TO000463 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | BRAESIDE | BRAESIDE | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 107.702 | 107.75 | 2027-06-30 | GA-05PL |  |  |  | 3.9 | 4.4 | 2 | 4 | 1 | 15.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115750&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115750 | C13 Turnout B/U Braeside 12A/B | TO000313 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | BRAESIDE | BRAESIDE | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 107.822 | 107.87 | 2027-06-30 | GA-05PL |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115749&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115749 | C13 Turnout B/U Braeside 12C/D | TO000244 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | BRAESIDE | BRAESIDE | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 107.872 | 107.92 | 2027-06-30 | GA-05PL |  |  |  | 3.6 | 4.4 | 2 | 4 | 1 | 14.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104208&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000104208 | C13 Turnout B/U Comet 2D Pts | TO000633 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BURNGROVE | NOGA | 0.0229 | KM | BW03ML224 | 0.1479 | BW03ML224 | 0.171 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 1.7 | 2 | 2.8 | 1 | 11.1 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104209&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000104209 | C13 Turnout B/U Comet 7A Pts | TO000684 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | BURNGROVE | NOGA | 0.032 | KM | BW03ML224 | 0.449 | BW03ML224 | 0.4169 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 1.7 | 2 | 2.8 | 1 | 11.1 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104184&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104184 | C13 Turnout B/U Callemondah 210A Pts | TO001157 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.028 | KM | BW17YR0 | 0.378 | BW17YR0 | 0.406 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.6 | 0.9 | 2 | 2.3 | 1 | 8.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104188&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104188 | C13 Turnout B/U Callemondah 231B Pts | TO001179 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.028 | KM | BW09XR0 | 0.264 | BW09XR0 | 0.2359 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 0.9 | 2 | 2.3 | 1 | 8.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104200&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104200 | C13 Turnout B/U Clarke 7A Pts | TO000940 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Moura | CLARKE | FRY | 0.0359 | KM | MA01ML63 | 0.9469 | MA01ML63 | 0.911 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080234&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080234 | C13 Turnout U/C Coppabella 45C/D | TO000226 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | COPPABELLA | COPPABELLA | 0.048 | KM | GA01ML147 | 0.879 | GA01ML147 | 0.8309 | KM |  |  |  |  | 147.879 | 147.879 | 2027-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 |  | 4.1 |  | 16.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Moderately rough, fairly near D7 top and twist (Jan 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104205&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104205 | C13 Turnout U/C German Creek 12A/B | TO000401 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | COPPABELLA | OAKY CREEK | 0.035 | KM | GA03ML132 | 0.004 | GA03ML131 | 0.9679 | KM | [6 empty] | 2027-06-30 | GA-03ML |  |  |  | 3.4 | 1.2 | 2 | 2.8 | 1 | 9.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115746&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115746 | C13 Turnout B/U DAL BAY DL45C/D Pts. | TO000484 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 132953 | Goonyella | DAL BAY | DAL BAY | 0.047 | KM | GA03BA4 | 0.0109 | GA03BA3 | 0.9499 | KM |  |  |  |  | 3.95 | 4.011 | 2027-06-30 | BW-17YR |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115747&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115747 | C13 Turnout B/U DAL BAY DL46A/B Pts. | TO000488 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 132953 | Goonyella | DAL BAY | DAL BAY | 0.0439 | KM | GA04BA4 | 0.0299 | GA04BA3 | 0.9749 | KM |  |  |  |  | 3.975 | 4.03 | 2027-06-30 | BW-17YR |  |  |  | 3.5 | 2.6 | 2 | 3.3 | 1 | 9.1 |  | 2023-10-13 |  | Turnout Undercutting - C13 | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Notification in process | SCPR |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104213&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104213 | C13 Turnout U/C Daly Bay 47C/D | TO000487 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY ARRIVAL RD 4 | DALY BAY ARRIVAL RD 4 | 0.05 | KM | GA04BA4 | 0.1449 | GA04BA4 | 0.095 | KM | [6 empty] | 2027-06-30 | GA-04BA |  |  |  | 4.1 | 2.6 | 2 | 3.1 | 1 | 12.5 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104247&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104247 | C13 Turnout U/C Daly Bay 7A/B | TO000490 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY ARRIVAL RD 4 | DALY BAY ARRIVAL RD 4 | 0.0459 | KM | GA04BD2 | 1.0069 | GA04BD2 | 0.9609 | KM | [6 empty] | 2027-06-30 | GA-04BA |  |  |  | 3.6 | 2.6 | 2 | 3.9 | 1 | 15.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104216&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104216 | C13 Turnout U/C Daly Bay 8A/B | TO000491 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY ARRIVAL RD 5 | DALY BAY ARRIVAL RD 5 | 0.049 | KM | GA05BD3 | 0.0529 | GA05BD3 | 0.004 | KM | [6 empty] | 2027-06-30 | GA-05BA |  |  |  | 3.6 | 2.6 | 2 | 3.2 | 1 | 12.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104194&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104194 | C13 Turnout U/C Goonyella 8A/B | TO000452 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | DALY BAY JCT | NORTH GOONYELLA JCT | 0.0379 | KM | GA01ML195 | 0.4099 | GA01ML195 | 0.448 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 2.4 | 2 | 2.5 | 1 | 9.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104190&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104190 | C13 Turnout U/C Balook 8C/D | TO000323 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY JCT | NORTH GOONYELLA JCT | 0.0299 | KM | GA02ML74 | 0.5759 | GA02ML74 | 0.546 | KM | [6 empty] | 2027-06-30 | GA-02ML |  |  |  | 3.9 | 4.8 | 2 | 2.5 | 1 | 11.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Notification postponed | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104262&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104262 | C13 Turnout U/C Jilalan 8A/B | TO000352 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | DALY BAY JCT | WONTONGA | 0.033 | KM | GA02ML17 | 0.4869 | GA02ML17 | 0.52 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4.8 | 2 | 4.2 | 1 | 16.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104263&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104263 | C13 Turnout U/C Praguelands 12A/B | TO000471 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | DALY BAY JCT | WONTONGA | 0.05 | KM | GA02ML14 | 0.4769 | GA02ML14 | 0.527 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 4.6 | 2 | 4.2 | 1 | 15.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104217&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104217 | C13 Turnout U/C Jilalan 12C/D | TO000345 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY JCT | WONTONGA | 0.035 | KM | GA02ML23 | 0.4929 | GA02ML23 | 0.458 | KM | [6 empty] | 2027-06-30 | GA-02ML |  |  |  | 3.7 | 4.8 | 2 | 3.2 | 1 | 13.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104203&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104203 | C13 Turnout U/C Yukan 12A/B | TO000334 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY JCT | WONTONGA | 0.0449 | KM | GA02ML29 | 0.933 | GA02ML29 | 0.9779 | KM | [6 empty] | 2027-06-30 | GA-02ML |  |  |  | 3.7 | 4.8 | 2 | 2.8 | 1 | 11.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080084&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080084 | C13 Turnout B/U Dingo 11A/B | TO000689 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | DINGO | DINGO | 0.048 | KM | BW03ML140 | 0.7489 | BW03ML140 | 0.797 | KM |  |  |  |  | 140.749 | 140.749 | 2027-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115698&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115698 | C13 Turnout B/U Dingo 11C/D | TO000731 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | DINGO | DINGO | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 140.804 | 140.852 | 2027-06-30 | BW-04ML |  |  |  | 3.9 | 3.35 | 2 | 3.6 | 1 | 14 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104201&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104201 | C13 Turnout B/U Dumgree 7A Pts | TO000942 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Moura | DUMGREE | BOUNDRY HILL JCT | 0.0369 | KM | MA01ML109 | 0.7229 | MA01ML109 | 0.686 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 1.3 | 2 | 2.6 | 1 | 9.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080105&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080105 | C13 Turnout B/U Edungalba 12A/B | TO000717 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | EDUNGALBA | EDUNGALBA | 0.0359 | KM | BW04ML84 | 0.7149 | BW04ML84 | 0.751 | KM |  |  |  |  | 84.694 | 84.694 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080123&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080123 | C13 Turnout B/U Epala 12A/B | TO000906 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | EPALA | EPALA | 0.0459 | KM | BW02ML575 | 0.8519 | BW02ML575 | 0.806 | KM |  |  |  |  | 575.851 | 575.851 | 2027-06-30 | BW-02ML |  |  |  | 3.5 | 4.1 |  |  |  | 14.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080104&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080104 | C13 Turnout B/U Epala 7C/D | TO000907 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | EPALA | EPALA | 0.049 | KM | BW02ML577 | 0.7359 | BW02ML577 | 0.785 | KM |  |  |  |  | 577.735 | 577.735 | 2027-06-30 | BW-02ML |  |  |  | 3.5 | 4.1 |  |  |  | 14.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080095&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080095 | C13 Turnout B/U Epala 7A/B | TO000848 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | EPALA | EPALA | 0.04 | KM | BW01ML577 | 0.8349 | BW01ML577 | 0.795 | KM |  |  |  |  | 577.828 | 577.828 | 2027-06-30 | BW-01ML |  |  |  | 3.5 | 4.1 |  |  |  | 14.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080261&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080261 | C13 Turnout U/C German Creek 2A | TO000413 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | GERMAN CK | GERMAN CK | 0.032 | KM | GA22ML135 | 0.8 | GA22ML135 | 0.768 | KM |  |  |  |  | 135.8 | 135.8 | 2027-06-30 | GA-22ML |  |  |  | 3.5 | 1.4 |  |  |  | 4.9 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 top and twist (Mar 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080149&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080149 | C13 Turnout B/U Gracemere 10A/B | TO000763 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | GRACEMERE | GRACEMERE | 0.049 | KM | BW04ML8 | 0.9539 | BW04ML9 | 0.008 | KM |  |  |  |  | 8.954 | 8.954 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115699&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115699 | C13 Turnout B/U Gracemere 9C/D | TO000764 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | GRACEMERE | GRACEMERE | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 9.133 | 9.179 | 2027-06-30 | BW-04ML |  |  |  | 3.9 | 3.35 | 2 | 3.6 | 1 | 14 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115702&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115702 | C13 Turnout B/U Grantleigh 7A/B | TO000712 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 68.137 | 68.186 | 2027-06-30 | BW-04ML |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080085&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080085 | C13 Turnout B/U Grantleigh 7C/D | TO000667 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0.0459 | KM | BW03ML68 | 0.234 | BW03ML68 | 0.188 | KM |  |  |  |  | 68.24 | 68.24 | 2027-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104228&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104228 | C13 Turnout B/U Tunnel 7C/D | TO000636 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | GRANTLEIGH | TUNNEL | 0.047 | KM | BW03ML75 | 0.9519 | BW03ML75 | 0.905 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 3.6 | 1 | 13.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104260&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104260 | C13 Turnout U/C Hay Point 12A/B | TO000104 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | HAY POINT ARRIVAL RD 1 | HAY POINT ARRIVAL RD 1 | 0.049 | KM | GA02BA3 | 0.4349 | GA02BA3 | 0.386 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.3 | 2.3 | 2 | 4.2 | 1 | 16.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104212&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104212 | C13 Turnout U/C Abbot Point 7A/B | TO000126 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | HAY POINT ARRIVAL RD 2 | HAY POINT ARRIVAL RD 2 | 0.048 | KM | NL02BL16 | 0.638 | NL02BL16 | 0.686 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 2.3 | 2 | 3.1 | 1 | 11.5 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104261&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104261 | C13 Turnout U/C Abbot Point 8C/D | TO000125 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | HAY POINT ARRIVAL RD 2 | HAY POINT ARRIVAL RD 2 | 0.047 | KM | NL02BL16 | 0.6179 | NL02BL16 | 0.5709 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.6 | 2.3 | 2 | 4.2 | 1 | 17.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080217&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080217 | C13 Turnout U/C Jilalan 47A/B | TO000566 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | JILALAN | JILALAN | 0.033 | KM | GA01ML17 | 0.4929 | GA01ML17 | 0.526 | KM |  |  |  |  | 17.493 | 17.493 | 2027-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 |  | 4.1 |  | 16.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Not as bad as the others (Jan 2021)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115800&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115800 | C13 Turnout B/U Jilalan 9C/D | TO000507 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | JILALAN | JILALAN | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 19.969 | 20.004 | 2027-06-30 | GA-01ML |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 16.3 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115798&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115798 | C13 Turnout B/U Jilalan 10A/B | TO000508 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | JILALAN | JILALAN | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 20.201 | 20.234 | 2027-06-30 | GA-01ML |  |  |  | 3.6 | 4.8 | 2 | 4.2 | 1 | 14.9 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115796&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115796 | C13 Turnout B/U Jilalan 12A/B | TO000513 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | JILALAN | JILALAN | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 23.422 | 23.456 | 2027-06-30 | GA-02ML |  |  |  | 3.9 | 4.8 | 2 | 4.2 | 1 | 16.3 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080083&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080083 | C13 Turnout B/U Kabra 109A/B | TO000743 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | KABRA | KABRA | 0.0459 | KM | BW03ML20 | 0.4289 | BW03ML20 | 0.383 | KM |  |  |  |  | 20.428 | 20.428 | 2027-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104240&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104240 | C13 Turnout B/U Kabra 108A/B | TO000741 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | KABRA | STANWELL | 0.0739 | KM | BW03ML20 | 0.651 | BW03ML20 | 0.7249 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 3.6 | 1 | 13.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115728&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115728 | C13 Turnout B/U Mallawa 101A | TO000289 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | MALLAWA | MALLAWA | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 168.712 | 168.748 | 2027-06-30 | BW-03ML |  |  |  | 3.8 | 2.4 | 2 | 3.2 | 1 | 12.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115729&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115729 | C13 Turnout B/U Mallawa 102B | TO000290 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | MALLAWA | MALLAWA | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 169.021 | 168.055 | 2027-06-30 | BW-03ML |  |  |  | 4.1 | 2.4 | 2 | 3.2 | 1 | 13.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080137&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080137 | C13 Turnout B/U Mt Miller 10C/D | TO000574 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | MT MILLER | MT MILLER | 0.058 | KM | BW02ML542 | 0.2129 | BW02ML542 | 0.271 | KM |  |  |  |  | 542.212 | 542.212 | 2027-06-30 | BW-02ML |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080266&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080266 | C13 Turnout B/U Mt Rainbow 12A Pts | TO000955 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Moura | MT RAINBOW | MT RAINBOW | 0.0359 | KM | MA01ML89 | 0.66 | MA01ML89 | 0.6959 | KM |  |  |  |  | 89.656 | 89.692 | 2027-06-30 | MA-01ML |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080271&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080271 | C13 Turnout B/U Mt Rainbow 7A Pts | TO000956 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Moura | MT RAINBOW | MT RAINBOW | 0.0309 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7179 | KM |  |  |  |  | 91.747 | 91.716 | 2027-06-30 | MA-01ML |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080250&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080250 | C13 Turnout U/C Oaky Creek 9A | TO000474 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | OAKY CK | OAKY CK | 0.034 | KM | GA03ML149 | 0.6059 | GA03ML149 | 0.5719 | KM |  |  |  |  | 149.605 | 149.605 | 2027-06-30 | GA-03ML |  |  |  | 3.5 | 1 |  |  |  | 3.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 top and twist (Mar 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104231&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104231 | C13 Turnout B/U Walton 7C/D | TO000582 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | PARNABAL | WALTON | 0.04 | KM | BW03ML163 | 0.6099 | BW03ML163 | 0.5699 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.8 | 3.4 | 2 | 3.6 | 1 | 13.7 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080259&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080259 | C13 Turnout U/C Peak Downs 9Pts | TO000552 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Goonyella | PEAK DNS | PEAK DNS | 0.032 | KM | GA17ML49 | 0.2409 | GA17ML49 | 0.2089 | KM |  |  |  |  | 43.883 | 43.883 | 2027-06-30 | GA-17ML |  |  |  | 3.5 | 2.1 |  |  |  | 7.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 top and twist (Mar 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104264&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000104264 | C13 Turnout B/U Raglan 8A/B | TO000909 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | RAGLAN | MARMOR | 0.05 | KM | BW02ML586 | 0.1499 | BW02ML586 | 0.1 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 4.9 | 2 | 4.2 | 1 | 15.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080114&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080114 | C13 Turnout B/U Raglan 11A/B | TO000847 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | RAGLAN | RAGLAN | 0.05 | KM | BW01ML583 | 0.9529 | BW01ML584 | 0.003 | KM |  |  |  |  | 583.955 | 583.955 | 2027-06-30 | BW-01ML |  |  |  | 3.5 | 4.9 |  |  |  | 17.2 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080116&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000080116 | C13 Turnout B/U Raglan 7A/B | TO000839 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | RAGLAN | RAGLAN | 0.05 | KM | BW01ML586 | 0.191 | BW01ML586 | 0.1409 | KM |  |  |  |  | 586.181 | 586.181 | 2027-06-30 | BW-01ML |  |  |  | 3.5 | 4.9 |  |  |  | 17.2 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104266&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104266 | C13 Turnout B/U Rangal 7A/B | TO000657 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | RANGAL | BURNGROVE | 0.0709 | KM | BW03ML198 | 0.2849 | BW03ML198 | 0.2139 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.8 | 2.1 | 2 | 3 | 1 | 11.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080072&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080072 | C13 Turnout B/U Rangal 11A/B | TO000658 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | RANGAL | RANGAL | 0.067 | KM | BW03ML195 | 0.252 | BW03ML195 | 0.319 | KM |  |  |  |  | 195.261 | 195.261 | 2027-06-30 | BW-03ML |  |  |  | 3.5 | 2.85 |  |  |  | 10 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080213&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080213 | C13 Turnout U/C Saraji 9A/B | TO000395 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | SARAJI | SARAJI | 0.05 | KM | GA03ML65 | 0.192 | GA03ML65 | 0.2419 | KM |  |  |  |  | 65.192 | 65.192 | 2027-06-30 | GA-03ML |  |  |  | 3.5 | 1.8 |  | 2.9 |  | 6.3 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 twist and top (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104236&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104236 | C13 Turnout B/U Dingo 2B Pts | TO000680 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | TRYPHINIA | DINGO | 0.0369 | KM | BW04ML141 | 0.389 | BW04ML141 | 0.4259 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.6 | 3.4 | 2 | 3.6 | 1 | 12.8 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115703&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115703 | C13 Turnout B/U Tryphinia 8C/D | TO000729 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | TRYPHINIA | TRYPHINIA | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 130.254 | 130.254 | 2027-06-30 | BW-04ML |  |  |  | 3.9 | 3.4 | 2 | 3.6 | 1 | 14 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104245&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104245 | C13 Turnout B/U Edungalba 11C/D | TO000716 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | TUNNEL | EDUNGALBA | 0.048 | KM | BW04ML84 | 0.668 | BW04ML84 | 0.6199 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 3.7 | 3.8 | 2 | 3.8 | 1 | 14.1 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115700&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115700 | C13 Turnout B/U Tunnel 7A/B | TO000715 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | TUNNEL | TUNNEL | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 75.852 | 75.892 | 2027-06-30 | GA-01ML |  |  |  | 3.7 | 3.75 | 2 | 3.8 | 1 | 14.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080124&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080124 | C13 Turnout B/U Wallaroo 11C/D | TO000726 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WALLAROO | WALLAROO | 0.034 | KM | BW04ML114 | 0.9919 | BW04ML114 | 0.9579 | KM |  |  |  |  | 114.989 | 114.989 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080125&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080125 | C13 Turnout B/U Wallaroo 12A/B | TO000727 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WALLAROO | WALLAROO | 0.0359 | KM | BW04ML115 | 0.003 | BW04ML115 | 0.0389 | KM |  |  |  |  | 115.005 | 115.005 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104235&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104235 | C13 Turnout B/U Bluff 12A/B | TO000654 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WALTON | BLUFF | 0.0509 | KM | BW03ML168 | 0.8549 | BW03ML168 | 0.906 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.1 | 3.4 | 2 | 3.6 | 1 | 14.9 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080164&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080164 | C13 Turnout B/U Walton 7A/B | TO000592 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WALTON | WALTON | 0.0459 | KM | BW04ML163 | 0.468 | BW04ML163 | 0.514 | KM |  |  |  |  | 163.4 | 163.4 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115701&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115701 | C13 Turnout B/U Windah 11C/D | TO000707 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WINDAH | WINDAH | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 55.161 | 55.195 | 2027-06-30 | BW-04ML |  |  |  | 4 | 3.4 | 2 | 3.6 | 1 | 14.6 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080109&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080109 | C13 Turnout B/U Windah 8A/B | TO000669 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WINDAH | WINDAH | 0.0729 | KM | BW03ML57 | 0.55 | BW03ML57 | 0.6229 | KM |  |  |  |  | 57.55 | 57.55 | 2027-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080098&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080098 | C13 Turnout B/U Windah 8C/D | TO000708 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WINDAH | WINDAH | 0.0719 | KM | BW04ML57 | 0.6959 | BW04ML57 | 0.6239 | KM |  |  |  |  | 57.698 | 57.698 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080097&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080097 | C13 Turnout B/U Windah 7A/B | TO000709 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WINDAH | WINDAH | 0.049 | KM | BW04ML57 | 0.7249 | BW04ML57 | 0.774 | KM |  |  |  |  | 57.725 | 57.725 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115730&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115730 | C13 Turnout B/U Wotonga 9A/B | TO000294 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | WONTONGA | WONTONGA | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 173.989 | 174.053 | 2027-06-30 | BW-09SD |  |  |  | 3.8 | 2.4 | 2 | 3.2 | 1 | 12.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080208&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080208 | C13 Turnout U/C Wotonga 7A/B | TO000293 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | WOTONGA | WOTONGA | 0.0739 | KM | GA02ML173 | 0.8709 | GA02ML173 | 0.9449 | KM |  |  |  |  | 173.871 | 173.871 | 2027-06-30 | GA-02ML |  |  |  | 3.5 | 2.4 |  | 3.2 |  | 8.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Recent near D7 twist after turnout (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080181&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080181 | C13 Turnout B/U Wycarbah 12C/D | TO000701 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WYCARBAH | WYCARBAH | 0.0459 | KM | BW04ML36 | 0.203 | BW04ML36 | 0.157 | KM |  |  |  |  | 36.21 | 36.21 | 2027-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115697&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115697 | C13 Turnout B/U Wycarbah ER.2B | TO000702 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | WYCARBAH | WYCARBAH | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 37.064 | 37.099 | 2027-06-30 | BW-03ML |  |  |  | 3.7 | 3.35 | 2 | 3.6 | 1 | 13.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080239&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080239 | C13 Turnout U/C Yukan 48A/B | TO000336 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | YUKAN | YUKAN | 0.033 | KM | GA02ML29 | 0.398 | GA02ML29 | 0.4309 | KM |  |  |  |  | 29.38 | 29.38 | 2027-06-30 | GA-02ML |  |  |  | 3.5 | 4.8 |  | 4.2 |  | 16.8 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 twist and rough top (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080240&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000080240 | C13 Turnout U/C Yukan 49B/C | TO000335 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | YUKAN | YUKAN | 0.035 | KM | GA02ML29 | 0.793 | GA02ML29 | 0.758 | KM |  |  |  |  | 29.774 | 29.774 | 2027-06-30 | GA-02ML |  |  |  | 3.5 | 4.8 |  | 4.2 |  | 16.8 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Near D7 top and moderate twist (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104176&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000104176 | C20-BR-BW-BOB'S CK-UP-616.685KM | BR101434-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.044 | KM | 400000 | Blackwater | ARCHER | MIDGEE | 0.0439 | KM | BW02ML618 | 0.8239 | BW02ML618 | 0.8679 | KM |  |  |  |  | 616.685 | 616.729 | 2027-06-30 | UP |  |  |  | 2.9 | 4.1 | 3 | 4.3 | 1 | 12 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104163&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104163 | C20-BR-NL-BOWEN RIVER-MAIN-99.411KM | BR300497-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.425 | KM | 1350000 | Newlands | BIRRALEE | COCKOOL | 0.4249 | KM | NL01ML99 | 0.3079 | NL01ML99 | 0.7329 | KM |  |  |  |  | 99.411 | 99.836 | 2027-06-30 | MAIN |  |  |  | 3.9 | 1.4 | 3 | 3.2 | 1 | 5.5 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104155&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104155 | C20-BR-BW-SPRINGTON CK-UP-143.284KM | BR100579-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.138 | KM | 750000 | Blackwater | DINGO | UMOLO | 0.138 | KM | BW04ML143 | 0.2839 | BW04ML143 | 0.4219 | KM |  |  |  |  | 143.284 | 143.422 | 2026-06-30 | UP |  |  |  | 3.4 | 3.4 | 3 | 4 | 1 | 11.4 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY26 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104157&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104157 | C20-BR-BW-CHARLEVUE CK-UP-148.085KM | BR100599-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.064 | KM | 450000 | Blackwater | DINGO | UMOLO | 0.064 | KM | BW04ML147 | 0.9429 | BW04ML147 | 1.0069 | KM |  |  |  |  | 148.085 | 148.149 | 2027-06-30 | UP |  |  |  | 4.1 | 3.4 | 3 | 4 | 1 | 13.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 1/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104153&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104153 | C20-BR-BW-NEERKOL CK-DOWN-21.320KM | BR100358-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.093 | KM | 600000 | Blackwater | KABRA | WARREN | 0.0929 | KM | BW03ML21 | 0.32 | BW03ML21 | 0.4129 | KM |  |  |  |  | 21.32 | 21.413 | 2025-06-30 | DOWN |  |  |  | 3.8 | 3.4 | 3 | 4 | 1 | 12.8 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY25 3/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104162&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104162 | C20-BR-NL-CORAL CK-MAIN-82.971KM | BR300468-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.079 | KM | 500000 | Newlands | MCNAUGHTON JCT | SONOMA JCT | 0.079 | KM | NL01ML82 | 0.681 | NL01ML82 | 0.76 | KM |  |  |  |  | 82.791 | 82.87 | 2027-06-30 | MAIN |  |  |  | 3.3 | 1.3 | 3 | 3.2 | 1 | 4.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104167&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104167 | C20-BR-BW-STOCK CROSSING-MAIN-65.691KM | BR100877-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.018 | KM | 400000 | Blackwater | MEEMOOLOO | ROLLESTON | 0.0179 | KM | BW06ML65 | 0.6909 | BW06ML65 | 0.7089 | KM |  |  |  |  | 65.691 | 65.709 | 2027-06-30 | MAIN |  |  |  | 3.86 | 2.3 | 2 | 3.2 | 1 | 12.4 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104169&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104169 | C20-BR-BW-CATTLE CROSSING-MAIN-73.041KM | BR100884-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.019 | KM | 400000 | Blackwater | MEEMOOLOO | ROLLESTON | 0.0189 | KM | BW06ML73 | 0.04 | BW06ML73 | 0.0589 | KM |  |  |  |  | 73.041 | 73.06 | 2027-06-30 | MAIN |  |  |  | 3.6 | 2.3 | 3 | 3.6 | 1 | 8.2 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104168&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104168 | C20-BR-BW-WATERWAY-MAIN-75.290KM | BR100869-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.019 | KM | 400000 | Blackwater | MEEMOOLOO | ROLLESTON | 0.0189 | KM | BW06ML75 | 0.2889 | BW06ML75 | 0.3079 | KM |  |  |  |  | 75.29 | 75.309 | 2027-06-30 | MAIN |  |  |  | 4.1 | 2.3 | 3 | 3.6 | 1 | 9.4 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104151&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104151 | C20-BR-BW-4 MILE CK-UP-1.816KM | BR100680-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.105 | KM | 600000 | Blackwater | ROCKLANDS | GRACEMERE | 0.1049 | KM | BW04ML1 | 0.799 | BW04ML1 | 0.904 | KM |  |  |  |  | 1.816 | 1.921 | 2026-06-30 | UP |  |  |  | 3.2 | 3.4 | 3 | 4 | 1 | 10.9 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY26 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104172&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104172 | C20-BR-BW-BURNGROVE-DOWN-200.0002KM | BR100682-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.092 | KM | 600000 | Blackwater | SAGITTARIUS | RANGAL | 0.0919 | KM | BW03ML200 | 0.032 | BW03ML200 | 0.1239 | KM |  |  |  |  | 200.002 | 200.094 | 2027-06-30 | DOWN |  |  |  | 3.5 | 2.9 | 3 | 3.8 | 1 | 9.9 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104158&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104158 | C20-BR-BW-STEWARTS CK-DOWN-24.616KM | BR100142-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.074 | KM | 500000 | Blackwater | WARREN | WARREN | 0.049 | KM | BW03ML24 | 0.629 | BW03ML24 | 0.678 | KM |  |  |  |  | 24.616 | 24.69 | 2028-06-30 | DOWN |  |  |  | 3.3 | 3.4 | 3 | 4 | 1 | 11.2 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY28 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104154&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104154 | C20-BR-BW-NEERKOL CK-UP-31.758KM | BR100201-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.065 | KM | 450000 | Blackwater | WARREN | WYCARBAH | 0.065 | KM | BW04ML31 | 0.758 | BW04ML31 | 0.8229 | KM |  |  |  |  | 31.758 | 31.823 | 2027-06-30 | UP |  |  |  | 3.91 | 3.4 | 2 | 3.6 | 1 | 14.1 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094379&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000094379 | C20-BR-GA-ISAAC RIVER-DOWN-191.086KM. | BR200866-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.199 | KM | 875865 | Goonyella | WOTONGA | MORANBAH NORTH | 0.199 | KM | GA01ML191 | 0.0859 | GA01ML191 | 0.2849 | KM |  |  |  |  | 191.086 | 191.285 | 2027-06-30 | DOWN |  |  |  | 2.92 | 2.9 | 2 | 3.5 | 1 | 10.2 |  | 2022-03-31 |  | Bridge Roll Out | LIKE FOR LIKE | HIGH | HIGH | LOW | MEDIUM | Outstanding notification | SCPR |  | 20270926 | Permanent handrail installation (structures) planned as part of the roll out
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066460&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000066460 | C20-BR-GA-PLANE CK-UP-16.880KM | BR201192-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 80 | METERS | 480000 | Goonyella | PRAGUELANDS | JILALAN | 0 | KM | GA02ML16 | 0.92 | GA02ML16 | 0.92 | KM |  |  |  |  | 16.88 | 16.96 | 2027-06-30 | UP |  |  |  | 3 | 4.6 |  |  |  | 13.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044190&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000044190 | C20-BR-BW-STOCK CROSSING-MAIN-78.491KM | BR100827-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 15 | METERS | 89760 | Blackwater | STARLEE | STARLEE | 0 | KM | BW06ML78 | 0.4989 | BW06ML78 | 0.4989 | KM |  |  |  |  | 78.492 | 78.507 | 2027-06-30 | MAIN |  |  |  | 3.74 | 2.3 | 2 | 3.2 | 1 | 12 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000112786&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000112786 | Burngrove to Nogoa Fencing FY27 | NC-09CR | CIVIL | CORRIDOR SECURITY & FENCING |  | REACTIVE WORKS | 1 | LUMPSUM | 60000 | Blackwater | BURNGROVE | NOGOA | 60.883 | KM | NC09ML202 | 0.2849 | NC09ML263 | 0.1499 | KM |  |  |  |  | 202.36 | 263.15 | 2027-06-30 |  |  |  |  | 5 |  |  | 5 | 1 | 25 |  |  |  | Corridor Fencing and Security | [5 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077890&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077890 | FORMATION GEOTECH DESIGN | BW | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 30000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077891&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077891 | FORMATION GEOTECH DESIGN | GA | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 30000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077892&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077892 | FORMATION GEOTECH DESIGN | MA | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 20000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077893&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077893 | FORMATION GEOTECH DESIGN | NL | CIVIL | FORMATION |  | DESIGN | 1 | LUMPSUM | 20000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052741&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000052741 | C05-FR-GA-SARAJI-79.350km | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 1.05 | KM | 2205000 | Goonyella |  |  | 1.0489 | KM | GA03ML79 | 0.3499 | GA03ML80 | 0.4 | KM |  |  |  |  | 79.35 | 80.4 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052743&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000052743 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.88 | KM | 1186500 | Goonyella |  |  | 0.879 | KM | GA03ML84 | 0.75 | GA03ML85 | 0.63 | KM |  |  |  |  | 84.75 | 85.63 | [5 empty] | 3 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052737&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000052737 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 1260000 | Goonyella |  |  | 0.5999 | KM | GA03ML95 | 0 | GA03ML95 | 0.5999 | KM |  |  |  |  | 95 | 95.6 | 2025-06-30 |  |  |  |  | 3 | [8 empty] | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20270630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052745&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000052745 | Formation Renewal | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 420000 | Goonyella |  |  | 0.199 | KM | GA02ML170 | 0.8 | GA02ML171 | 0 | KM |  |  |  |  | 170.8 | 171 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077823&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077823 | Formation Renewal | BW-04ML | CIVIL | FORMATION |  | RENEWAL | 1.1 | KM | 2400000 | Blackwater | AROONA | DUARINGA | 198.257 | KM | BW04ML0 | 0 | BW04ML198 | 0.2839 | KM |  |  |  |  | 97.9 | 99 | 2026-06-30 | UP | [13 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077824&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077824 | Formation Renewal | BW-04ML | CIVIL | FORMATION |  | RENEWAL | 2 | KM | 2715000 | Blackwater | AROONA | DUARINGA | 1.502 | KM | BW04ML99 | 0 | BW04ML100 | 0.5 | KM |  |  |  |  | 99 | 100.5 | 2027-06-30 | UP | [13 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077785&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077785 | Formation Renewal | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 0.7 | KM | 1750000 | Blackwater | BAJOOL | ARCHER | 0.6959 | KM | BW02ML611 | 0.8 | BW02ML612 | 0.5 | KM |  |  |  |  | 611.8 | 612.5 | 2025-06-30 | DN | [13 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 27.05.2021 11:02:21 AUSQLD Tracy Holmes (R870040) * next highest priority in section
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077786&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077786 | Formation Renewal | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 1 | KM | 2250000 | Blackwater | BAJOOL | ARCHER | 1.0009 | KM | BW02ML612 | 0.5 | BW02ML613 | 0.5 | KM |  |  |  |  | 612.5 | 613.5 | 2026-06-30 | DN | [13 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077787&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077787 | Formation Renewal | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 2 | KM | 3500000 | Blackwater | BAJOOL | ARCHER | 2.007 | KM | BW02ML613 | 0.5 | BW02ML615 | 0.5 | KM |  |  |  |  | 613.5 | 615.5 | 2027-06-30 | DN | [13 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078182&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000078182 | Formation Renewal | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.485 | KM | 2182500 | Moura | BELLDEEN | MOURA MINE JCT | 0.4849 | KM | MA01ML173 | 0.4949 | MA01ML173 | 0.9799 | KM |  |  |  |  | 173.495 | 173.98 | 2027-06-30 |  |  |  |  | 3 | 1.1 | 3.5 | 3.3 | 1 | 9.9 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077826&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000077826 | Formation Renewal | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.5 | KM | 829500 | Blackwater | BLUFF | BOONAL | 0.4989 | KM | BW03ML175 | 0.5 | BW03ML176 | 0 | KM |  |  |  |  | 175.5 | 176 | 2025-06-30 | DN |  |  |  | 3.5 | 3.95 |  |  |  | 14.7 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20270630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115207&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000115207 | C05-FR-GA-BOLINGBROKE-71.4km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 1329238 | Goonyella | BOLINGBROKE | BALOOK | 0.2 | KM | GA02ML71 | 0.4 | GA02ML71 | 0.5999 | KM |  |  |  |  | 71.4 | 71.6 | 2026-06-30 | UP |  |  |  | 2.8 | 5 | 3 | 4.5 | 1 | 12.8 |  | 2023-09-01 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 71.100km to 71.680km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 71.600km to 71.800km GA-02ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Note – includes level crossing ID5768 • FY24 Ballast Undercut 71.400km-74.450km (noti # 2000094867) • Scope nominated by district – to be confirmed with DCP’s
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115198&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000115198 | C05-FR-BW-BOONAL-187.150km | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.33 | KM | 1798894 | Blackwater | BOONAL | BLACKWATER | 0.33 | KM | BW03ML187 | 0.1499 | BW03ML187 | 0.4799 | KM |  |  |  |  | 187.15 | 187.48 | 2027-06-30 | DOWN |  |  |  | 3.7 | 3.2 | 3 | 3.9 | 1 | 14.3 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 187.115km to 187.550km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115212&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000115212 | C05-FR-GA-BROADLEA-164.970km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.545 | KM | 2385000 | Goonyella | BROADLEA | MALLAWA | 0.545 | KM | GA01ML164 | 0.9699 | GA01ML165 | 0.5 | KM |  |  |  |  | 164.97 | 165.5 | 2027-06-30 | DOWN |  |  |  | 3.2 | 2.5 | 3.5 | 3.9 | 1 | 12.4 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Note: Ties into previous strategic renewal • GA-03ML 164.450 - 164.970km (FY24 2000052735) Formation Renewal Requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from xxx.xxxkm to xxx.xxxkm both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • BMF Survey <(>&<)> Design should reinstate renewal location to design ballast depth and install Rail Level data plaques in reference to top of formation design level if not already present. Refer to AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115217&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115217 | C05-FR-MA-Callemondah-11.750km. | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 1157150 | Moura | CALLEMONDAH | BYELLEE | 0.2 | KM | MA01ML11 | 0.75 | MA01ML11 | 0.9499 | KM |  |  |  |  | 11.75 | 11.95 | 2025-06-30 | MAIN |  |  |  | 4.1 | 1.3 | 3 | 3.2 | 1 | 13.1 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 11.620km to 12.230km LHS / Field side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 12.050km to 12.450km MA-01ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Gladstone depot proposed scope (A/Track Inspector Matt Dingle), potentially will require intervention through FoF prior to FY25 (E xperiencing issues March 2023) • Reactive formation completed in 2022, 12.442 - 12.512km <(>&<)> 12.862 - 12.892km (2000083051 <(>&<)> 2000098924) • Poor track geometry 11.750 - 12.200km. Top <(>&<)> twist significant deterioration at 11.900km in 2023 (multiple D1-D7 top and twist).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115218&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115218 | C05-FR-MA-Callemondah-11.750km | MA-01PL | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 1157150 | Moura | CALLEMONDAH | BYELLEE | 0.2 | KM | MA01PL11 | 0.75 | MA01PL11 | 0.9499 | KM |  |  |  |  | 11.75 | 11.95 | 2025-06-30 | PASSING LOOP |  |  |  | 4.1 | 1.3 | 3 | 3.2 | 1 | 13.1 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 11.620km to 12.230km LHS / Field side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Opportunity scope put forwards for completion in conjunction with Notification 002000115217 due to expected constructability benefits <(>&<)> efficiencies
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133264&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133264 | C05-FR-MA-CLARKE-70.050km | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 1800000 | Moura | CLARKE | FRY | 0.4 | KM | MA01ML70 | 0.05 | MA01ML70 | 0.45 | KM |  |  |  |  | 70.05 | 70.45 | 2026-06-30 | SINGLE |  |  |  | 4.5 | 1.3 | 3.5 | 3.4 | 1 | 15.3 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 69.850km to 70.650km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Linked to Geotech testing 70.050 – 71.200km (Investigation for future renewals) • Forms part of proposed multi year renewals scope 70.450 - 70.850km (FY27), 70.850 - 71.200km (FY28) • FY24 Completed scope 71.200 – 71.500km (2000067365) 27/03/2024: Postponed from FY26 to later years due to capital constraint as directed by NAM leadership.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000067366&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000067366 | Formation Renewal | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.35 | KM | 1575000 | Moura | CLARKE | FRY | 0.3499 | KM | MA01ML70 | 0.8499 | MA01ML71 | 0.2 | KM |  |  |  |  | 70.85 | 71.2 | 2027-06-30 | SINGLE |  |  |  | 4.4 | 1.3 | 3 | 3.2 | 1 | 14.1 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20270630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134379&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000134379 | C05-FR-NL-COCKOOL-116.300km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.5 | KM | 2250000 | Newlands | COCKOOL | HAVILAH | 0.5 | KM | NL01ML116 | 0.2999 | NL01ML116 | 0.8 | KM |  |  |  |  | 116.3 | 116.8 | [5 empty] | 4.6 | 1.4 | 3.5 | 3.5 | 1 | 16 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Important Notes: • Existing sleeper type is Fist, replace fist sleepers in conjunction with formation renewal refer notification XXXXXXX for sleeper renewal. Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 113.900km to 115.000km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077821&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077821 | Formation Renewal | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.55 | KM | 912450 | Blackwater | GRANTLEIGH | GRANTLEIGH | 0.552 | KM | BW03ML66 | 0.5 | BW03ML67 | 0.05 | KM |  |  |  |  | 66.5 | 67.05 | 2025-06-30 | DN |  |  |  | 3.5 | 3.9 |  |  |  | 14.7 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 29.11.2021 Tim Griffin (r8788533). Moved from FY25 and initial 1.1km Scope split across FY26 <(>&<)> FY27 to meet 23Nov2021 FY24_FY27 MRSB forecast allocations from HoNAM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077820&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000077820 | Formation Renewal | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.5 | KM | 829500 | Blackwater | GRANTLEIGH | TUNNEL | 0.4909 | KM | BW03ML67 | 0.5999 | BW03ML68 | 0.1 | KM |  |  |  |  | 67.6 | 68.1 | 2025-06-30 | DN |  |  |  | 3.5 | 3.85 |  |  |  | 13.3 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20270630 | 29.11.2021 Tim Griffin (r878533). Notification split across FY25 and FY26 delivery years and descoped from overall 1km to meet FY24_FY27 23Nov2021 MRSB forecast from HoNAM and Aroona CL Formation lowering scope. Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088642&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000088642 | Formation Renewal | BW-03ML | CIVIL | FORMATION |  | RENEWAL | 0.5 | KM | 1175000 | Blackwater | GRANTLEIGH | TUNNEL | 0.5 | KM | BW03ML68 | 0.1 | BW03ML68 | 0.5999 | KM |  |  |  |  | 68.1 | 68.6 | 2025-06-30 | DN |  |  |  | 3.5 | 3.95 |  |  |  | 14.7 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 29.112021 Tim Griffin (r878533. Adjoining linked notification to FY24 scope delivery (N4 : 2000077820) to meet MRSB FY24_FY27 forecasts set by HoNAM 23Nov2021.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115210&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000115210 | C05-FR-GA-HATFIELD-58.7km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 1329238 | Goonyella | HATFIELD | BOLINGBROKE | 0.2 | KM | GA02ML58 | 0.6999 | GA02ML58 | 0.9 | KM |  |  |  |  | 58.7 | 58.9 | 2025-06-30 | UP |  |  |  | 2.7 | 5 | 3 | 4.5 | 1 | 12 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 58.350km to 59.120km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 58.900km to 59.200km GA-02ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • FY22 Ballast undercutting 58.450km-59.400km (noti # 2000052406) – Actuals August 2021 80104568 Hatfield - Bolingbroke Up 58.887 - 59.400 • FY24 Ballast undercutting 58.450km-58.887km (noti # 20000104106) • Nominated by district – confirm with DCPs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134433&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000134433 | C05-FR-NL-HAVILAH-137.000km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.465 | KM | 2092500 | Newlands | HAVILAH | NEWLANDS JUNCTION | 0.465 | KM | NL01ML137 | 0 | NL01ML137 | 0.465 | KM |  |  |  |  | 137 | 137.465 | [5 empty] | 3.6 | 1.4 | 3.5 | 3.5 | 1 | 12.5 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280125 | Important Notes: • Existing sleeper type is Fist, replace fist sleepers in conjunction with formation renewal refer notification XXXXXXX for sleeper renewal. Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 113.900km to 115.000km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077825&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000077825 | Formation Renewal | BW-04ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 671895 | Blackwater | TRYPHINIA | DINGO | 0.405 | KM | BW04ML137 | 0.8 | BW04ML138 | 0.2 | KM |  |  |  |  | 137.8 | 138.2 | 2025-06-30 | UP | [12 empty] | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20270630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115119&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000115119 | C05-FR-BW-YARWUN-554.059km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.481 | KM | 2164500 | Blackwater | YARWUN | ALDOGA | 0.4809 | KM | BW01ML554 | 0.0589 | BW01ML554 | 0.54 | KM |  |  |  |  | 554.059 | 554.54 | 2026-06-30 | UP |  |  |  | 4 | 4.1 | 3.5 | 4.4 | 1 | 17.6 |  | 2023-09-01 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20270630 | 06/10/2023 - Scope deferred from FY25 to FY26 due to capital constraint 06/03/2024 - Scope deferred from FY26 to FY27 due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 553.930km to 554.755km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 554.540km to 555.000km BW-01ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Track Geometry - Twist and top defects (D7 top w/ near D7 twist (3 <(>&<)> 10), previous TSR history • Rerail Completed FY23 (2000066543), TLM Track Upgrade Completed FY22 (002000044078)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077838&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077838 | Formation C05 Reactive Works | BW | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1950000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077840&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077840 | Formation C05 Reactive Works | GA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1259500 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077839&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077839 | Formation C05 Reactive Works | MA | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 1700000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 450m of fix on fail at $3800/m
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077841&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077841 | Formation C05 Reactive Works | NL | CIVIL | FORMATION | C05 | REACTIVE WORKS | 1 | LUMPSUM | 468500 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090991&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000090991 | Formation Renewal Aroona Dn Rd | BW-03ML | CIVIL | FORMATION | RENEWAL | RENEWAL | 0.595 | KM | 1450000 | Blackwater | AROONA | DUARINGA | 0.5939 | KM | BW03ML94 | 0.4 | BW03ML95 | 0 | KM |  |  |  |  | 94.4 | 95 | 2024-06-30 | DOWN |  |  |  | 3.85 |  |  |  |  | 16.45 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 21.01.2022 Tim Griffin (r878533) Central Line Down Road has excessive ballast height (due to minimal formation depth) and was C14 Undercutt in FY22 to hold / match Crossovers from Up Rd (BW-04ML) until this planned formation renewal. Linked to Western End Formation Renewal notification 2000090992 (BW03ML being 250m in Scope). Noting N4 : 2000054902 in FY22 ballast undercut. See notification attachment files.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077873&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077873 | CIVIL GPR RUN BLACKWATER | BW | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 624000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 27.05.2021 12:03:41 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE. APPROX KM BASED ON FY21 SCOPE = 954.068KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077874&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077874 | CIVIL GPR RUN GOONYELLA | GA | CIVIL | GPR RUN |  | ASSESSMENT | 1 | LUMPSUM | 590000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 27.05.2021 12:03:56 AUSQLD Tracy Holmes (R870040) * INCLUDE SCREENABILITY IN THE SCOPE FOR FUTURE YEARS SCOPE HANDOVER. SCOPE BASED ON FY21 SUBMISSION IS 796.421KM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083404&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000083404 | C58-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 220000 | Goonyella | GA | GA | 220.507 | KM |  | 0 |  | 0 | [15 empty] | 25 |  | 25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102010&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000102010 | C58-LX-GA-JILALAN-28.84km | LX003500 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 805800 | Goonyella | JILALAN | YUKAN | 0 | KM | GA01ML28 | 0.8409 | GA01ML28 | 0.8409 | KM |  |  |  |  | 28.84 |  | 2027-06-30 | BORGS ACCESS RD |  |  |  | 2.52 | 4.2 |  |  |  | 10.58 |  |  |  | Level Crossing Renewals | [5 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000042354&DY_MAB=X&~OKCODE=ONLI | FY27 |  | STRATEGIC | COAL | 002000042354 | C58-LX-BW-SAGITARIUS-189.7km | LX020210 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 1438067 | Blackwater | SAGITARIUS | BLACKWATER | 0 | KM | BW03ML189 | 0.6999 | BW03ML189 | 0.6999 | KM |  |  |  |  | 189.7 | 189.7 | 2026-06-30 |  | BOTH |  |  | 10 | 3.15 | 2 | 10 | 1 | 100 |  | 2023-03-31 |  | Level Crossing Renewals | BESPOKE DESIGN |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630 | * 16.08.2019 12:21:05 AUSQLD Jeremy Stevenson (R867415) * Emergency Crossing for Maintenance Asset ID 20210 - Condition 2.0- * Emergency Crossing with Nil crossing controls under Aurizon jurisdiction. * Electrified * 15.01.2020 10:57:24 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY20 to FY21 due to funding * ID20210 - FLOC needs to be updated once created in NAMS, Contact Al Rayner * 15.01.2020 11:10:34 AUSQLD Sanjna Rajagopalan (R884639) * Updated cost to $800,000 due to change in unit rate for FY21 * 30.01.2020 11:54:52 AUSQLD Sharbaree Biswas (R865006) * Due to funding cap of $5m, this is now being delayed till FY22. * 09.03.2020 11:31:21 AUSQLD Sharbaree Biswas (R865006) * Pushed again into FY23 due to funding restriction in FY22. Pushed again into FY23 due to funding restriction in FY22. Pushed again into FY23 due to funding restriction in FY22. 5 JULY 2021 The design work for this crossing is dependent on TMR's project completion at Ardurad Road. TMR design on intersection upgrade has not been communicated to us as yet. This is why this scope has been pushed out to FY25 construction.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041192&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000041192 | C58-LX-MA-PARANA-532.2km | LX000788 | CIVIL | LEVEL CROSSINGS | CCTV | RENEWAL | 1 | SITE | 64665 | Moura | PARANA | CALLEMONDAH | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 532.2 | 532.2 | 2026-06-30 | CALLEMONDAH DRIVE NCL |  |  |  | 10 | 2 | 2 | 10 | 1 | 100 |  | 2019-03-22 |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 07.08.2019 14:02:21 AUSQLD Jeremy Stevenson (R867415) * CCTV Installation <(>&<)> LED UPGRADE FY19 Blain Drive CCTV Installation <(>&<)> LED UPGRADE FY19 Blain Drive 07.08.2019 14:02:21 AUSQLD Jeremy Stevenson (R867415) CCTV Installation <(>&<)> LED UPGRADE FY19 Blain Drive Not a Civil scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120596&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000120596 | C58-LX-BW-BOORGOON-34.95km | LX006954 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 35692 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML34 | 0.912 | BW06ML34 | 0.912 | KM |  |  |  |  | 34.95 | 34.95 | 2027-06-30 | HUMBOLDT ROAD |  |  |  | 4.6 | 2.3 | 2 | 3.16 | 1 | 14.7 | 5758 | 2023-09-01 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 22.09.2023 Civil Assets spoke with IM about the timing of renewal. IM advised this crossing could be delayed to FY28. This crossing was showing severe ballast and geometry defects and undercut in FY23. FY24 DESIGN (IFP) FY25 DESIGN (IFC) for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122915&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000122915 | C58-LX-NL-BUCKLEY-15.516km | LX003279 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Newlands | BUCKLEY | ARMUNA | 0 | KM | NL01ML15 | 0.516 | NL01ML15 | 0.516 | KM |  |  |  |  | 15.516 | 15.516 | 2027-06-30 | 88A BOWEN DEVELOPMENT ROAD |  |  |  | 3.5 | 1.7 | 2 | 3 | 1 | 10.5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | IV.00459 | 20270630 | 13.02.2024 Sharbaree Biswas (R865006) Design, Plan and Execute this LX renewal with Formation Renewal 2000134434 (FY28 execution). 20.02.2020 11:25:51 AUSQLD Sharbaree Biswas (R865006) This crossing is having an undercut in 2020. The crossing will be monitored over the next several years and thus renewal if required is delayed till FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137536&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000137536 | C58-LX-GA-BURTON-168.375 | LX020259 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | BURTON DOWNS | MALLAWA | 0 | KM | GA01ML168 | 0.375 | GA01ML168 | 0.375 | KM | 6 |  |  |  | 168.375 | 168.375 |  | BURTON MINE ACCESS RIAD |  |  |  | 10 | 2.4 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120592&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000120592 | C58-LX-MA-CALLE-22.165km | LX005755 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 32930 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML22 | 0.164 | MA01ML22 | 0.164 | KM |  |  |  |  | 22.165 | 22.165 | 2027-06-30 | JIM WHYTE WAY |  |  |  | 3.9 | 2.6 | 2 | 3.31 | 1 | 12.87 | 5758 | 2023-09-01 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Kept in FY26 Design (IFP) FY27 Design (IFC) for FY28 Renewal as per the discussion with Geoff on 5 Sept <(>&<)> previous mtgs with other IM team and asset management team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122912&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic | FUTURE SCOPE | NON-COAL | 002000122912 | C58-LX-BW-COMET-242.44km | LX001087 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Blackwater | COMET | YAMALA | 0 | KM | BW03ML242 | 0.4349 | BW03ML242 | 0.4349 | KM |  |  |  |  | 242.44 |  | 2027-06-30 |  |  |  |  | 4.4 | 1.7 | 2 | 3 | 1 | 13.2 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133824&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000133824 | C58-LX-GA-MINDI-127.043km | LX006644 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28000 | Goonyella | MINDI | SOUTHWALKER | 0 | KM | GA01ML127 | 0.0429 | GA01ML127 | 0.0429 | KM |  |  |  |  | 127.043 | 127.043 | 2028-06-30 | MINE ACCESS ROAD |  |  |  | 3.5 | 4 | 2 | 4 | 1 | 14 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 DESIGN -IFC. Integration with Formation Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127710&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000127710 | C58-LX-BW-WALTON-166.675km | LX005563 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 28000 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML166 | 0.675 | BW03ML166 | 0.675 | KM |  |  |  |  | 166.675 | 166.675 | 2027-06-30 | ROCKVIEW ROAD |  |  |  | 3.6 | 3.64 | 2 |  | 1 | 14.56 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | FY27 DESIGN-IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083390&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000083390 | C58-LX-MA-BELLDEEN-172.2km | LX006054 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML172 | 0.2 | MA01ML172 | 0.2 | KM |  |  |  |  | 172.2 | 172.2 |  | BARFIELD ROAD |  |  |  | 3 | 1 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Pushed to FY27 Design for FY29 Renewal as per the mtg on 28 July with the IM team. FY26 DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079990&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000079990 | C58-LX-NL-BIRRALEE-103.07km | LX003315 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML103 | 0.07 | NL01ML103 | 0.07 | KM |  |  |  |  | 103.07 | 103.07 |  | PRIVATE CATTLE CROSSING | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY26 DESIGN, FY27 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068859&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000068859 | C58-LX-BW-BOONAL-181.293km | LX005614 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Blackwater | BOONAL | BLACKWATER | 0 | KM | BW03ML181 | 0.2929 | BW03ML181 | 0.2929 | KM |  |  |  |  | 181.293 | 181.293 | 2023-06-30 | COLUMBA ACCESS ROAD |  |  |  | 1.6 | 3.4 |  |  |  | 5.4 | 5701 | 2021-03-31 | 2021-10-05 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20260630 | PCR 5701. Moved FY23 Design to FY27 (IFP). This crossing was pushed to renew in FY27 to align with the Boonal turnout 8CD. This is a low priority design (and geotech investigation activity) because of the move/push. Originally it was a FY23 design, which was programmed to design in FY22. DD30 <(>&<)> IFC to be delivered as of 24/06/2022 <(>&<)> 16/09/2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103581&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000103581 | C58-LX-MA-CALLEMONDAH-6.33km | LX000963 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML6 | 0.339 | MA01ML6 | 0.339 | KM |  |  |  |  | 6.33 | 6.33 | 2029-06-30 | MERCURY ROAD |  |  |  | 3.3 | 1.3 | 2 | 3 | 1 | 8.55 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 15.03.2024 This crossing is holding well since FoF reactive works in 2023. Original plan was for FY26 IFP, FY27 IFC, FY28 Renewal. Due to good condition at FY26 MRSB submission time Civil Assets have pushed out by 1 year to FY27 IFP, FY28 IFC, FY29 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110069&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000110069 | C58-LX-MA-CALLE-7.116km | LX005953 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 28824 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML7 | 0.116 | MA01ML7 | 0.116 | KM |  |  |  |  | 7.116 | 7.116 | 2025-06-30 | WHITNEY ST |  |  | RENEWAL DESIGN | 2.6 | 1.3 | 2 | 3 | 1 | 7.8 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | 28/03/2024- Deferred to FY27 (IFP) due to FY26 cashflow limit <(>&<)> design resource limitation. FY25 DESIGN FOR FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068863&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000068863 | C58-LX-MA-CLARKE-72.6km | LX005995 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | CLARKE | FRY | 0 | KM | MA01ML72 | 0.5999 | MA01ML72 | 0.5999 | KM |  |  |  |  | 72.6 | 72.6 | 2029-06-30 | DUCKHOLE ROAD |  |  |  | 3.2 | [5 empty] | 4873 | 2021-03-31 | [7 empty] | Notification in process | SCPR |  | 20270630 | Pushed to FY27 for FY29 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079985&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000079985 | C58-LX-MA-DAKENBA-2.28km | LX006406 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Moura | DAKENBA | CALLIDE | 0 | KM | MA07ML2 | 0.28 | MA07ML2 | 0.28 | KM |  |  |  |  | 2.28 | 2.28 |  | DUDARKOS ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Pushed to FY27 Design for FY29 Delivery, as per the discussion on 28 July with the IM team. Pushed the design work out of FY24 and placed in FY26.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101986&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000101986 | C58-LX-GA-DALY BAY-0.071km | LX020244 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA04BA0 | 0.0769 | GA04BA0 | 0.0769 | KM |  |  |  |  | 0.076 | 0.076 | 2027-06-30 | MAINTENANCE ACCESS RD |  |  |  | 2.5 | 4.2 | 2 | 4 | 1 | 10 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20250630 | Moved to FY27 IFP due to fund limit. IM team will be notified. PCR to be submitted. FY25 Design for FY27 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083376&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000083376 | C58-LX-BW-EDUNGALBA-89.321km | LX005557 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Blackwater | EDUNGALBA | AROONA | 0 | KM | BW03ML89 | 0.33 | BW03ML89 | 0.33 | KM |  |  |  |  | 89.321 | 89.321 | 2027-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.6 | 3 | 2 | 4 | 1 | 10.4 |  | 2023-10-13 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270630 | 28/3/24- Deferred to FY27 (IFP) due to FY26 cashflow and civil design resource limit. FY25 DESIGN FOR FY27 CONSTRUCTION. Crossing review revealed the corrected km was 89.321km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068865&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000068865 | C58-LX-GA-GERMAN CREEK-136.47km | LX003636 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Goonyella | GERMAN CREEK | OAKY CREEK | 0 | KM | GA03ML136 | 0.4699 | GA03ML136 | 0.4699 | KM |  |  |  |  | 136.47 | 136.47 | 2023-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.3 | 1.1 |  |  |  | 2.5 |  | 2021-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | FY23 IN | 20270630 | * 22.03.2021 20:25:10 AUSQLD Sharbaree Biswas (R865006) * ADDED THE LINEAR DATA Supported by Reagan Case (RAP Team). PCR 5124 added. 22.03.2021 20:25:10 AUSQLD Sharbaree Biswas (R865006) ADDED THE LINEAR DATA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083375&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000083375 | C58-LX-MA-GRAHAM-29.828km | LX005969 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Moura | GRAHAM | STIRRAT | 0 | KM | MA01ML29 | 0.8279 | MA01ML29 | 0.8279 | KM |  |  | 29.828 | 29.828 | 29.828 | 29.828 |  | HOOKE ROAD |  |  |  | 2 | 1 |  |  |  | 2 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Lower priority over ID6090/ID5755/ID5753. Moved to FY27 Design for FY29 Renewal. FY24 DESIGN for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068864&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000068864 | C58-LX-GA-MIDDLEMT-127.104km | LX003632 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Goonyella | MIDDLEMOUNT | BUNDOORA | 0 | KM | GA03ML127 | 0.1039 | GA03ML127 | 0.1039 | KM |  |  |  |  | 127.104 | 127.104 | 2023-06-30 | PRIVATE ACCESS ROAD |  |  |  | 1 | 1.5 |  |  |  | 1.5 |  | 2021-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | FY23 IN | 20270630 | * 22.03.2021 20:16:00 AUSQLD Sharbaree Biswas (R865006) * FIXED THE LINEAR DATA FIXED THE LINEAR DATA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101987&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000101987 | C58-LX-GA-PRAGUELANDS-19.671km | LX007287 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | PRAGUELANDS | JILALAN | 0 | KM | GA01YR19 | 0.67 | GA01YR19 | 0.67 | KM |  |  |  |  | 19.671 | 19.671 | 2025-06-30 | ENTRANCE TO STATION NEW |  |  |  | 3.6 | 4.2 | 2 | 4 | 1 | 14.4 |  |  |  | Rail Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Moved to FY27 Design for FY29 Renewal. FY25 DESIGN For FY27 CONSTRUCTION. Five tracks.For now it is included in FY25 Design. Only if it is determined that a relocation as part of the ICAR GA project is warranted, a change paper shall be submitted for removal of the scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051929&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000051929 | C58-LX-BW-SAGITARIUS-195.02km | LX003431 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 46118 | Blackwater | SAGITARIUS | RANGAL | 0 | KM | BW03ML195 | 0.07 | BW03ML195 | 0.07 | KM |  |  |  |  | 195.02 | 195.02 | 2027-06-30 | SUBSTATION ACCESS ROAD |  |  |  | 3.5 | 2.85 | 2 | 3 | 1 | 10.5 | 4873 | 2023-10-13 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270630 | 28/3/24- Deferred to FY27 (IFP) due to FY26 cashflow and Civil Design resource limitation. Km review was done and found to be 195.060km. Brought forward to FY25 Design as per the mtg on 9 Sept 2022. Moved to FY26 Design for FY28 Renewal as per the mtg on 31 Aug 2022 with the IM team. Moved to FY24 Design <(>&<)> FY26 Delivery. LX seems to be holding okay so postponed in FY22/FY23 for more critical scope. Originally scoped in 2019 for FY22 delivery.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088577&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000088577 | C58-LX-GA-WINCESTER-45.32km | LX003230 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | WINCESTER | PEAK DOWNS | 0 | KM | GA03ML45 | 0.32 | GA03ML45 | 0.32 | KM |  |  | 45.32 | 45.32 | 45.32 | 45.32 | 2025-06-30 | PRIVATE ACCESS ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 1.7 | 3.93 | 2 | 4 | 1 | 6.8 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20250221 | PCR 5701- moved to FY27 IFP, FY28 IFC <(>&<)> FY29 Renewal. 29 March 2022- PCR 5338- moved to FY23 DESIGN for FY25 RENEWAL. There is water pooling and to be surveyed and designed to direct water from the corridor. S Biswas comments on 15 March 2022: Condition assessment and overall condition is not reflective and supportive to the other supporting documents. This is an issue that the Superintendent Engineering Civil is accountable. For FY25, adequate overall condition is expected.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083394&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000083394 | C58-LX-BW-YARWUN-559.674km | LX005584 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | YARWUN | MOUNT LARCOM | 0 | KM | BW01ML559 | 0.674 | BW01ML559 | 0.674 | KM |  |  | 559.674 | 559.674 | 559.674 | 559.674 | 2027-06-30 | PORT CURTIS WAY |  |  |  | 3.1 | 4.5 | 2 | 4.1 | 1 | 12.71 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Due to cash flow limit, moved to FY27 IFP as of 22 Mar 24. FY26 Design for FY28 MAJOR RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068858&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000068858 | C58-LX-GA-YUKAN-27.88km | LX003499 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML27 | 0.88 | GA01ML27 | 0.88 | KM |  |  |  |  | 27.88 | 27.88 | 2026-06-30 | THE GLEN ACCESS ROAD |  |  |  | 10 | 4 | 2 | 10 | 1 | 100 | 4929 | 2021-03-31 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | Moved to FY27 Design for FY29 Delivery (Signal Design confirmed). Added $90k to cover both Civil and Signal design in FY26 (Rob Love to lead the signal design). Need agreement on stakeholder financial contributions in FY25 e.g. how much QR/Landowner will pay into the project.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135363&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000135363 | C58-LX-MA-FRY-MA-01ML-89.560km | LX006516 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1000000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.56 | MA01ML89 | 0.56 | KM | 2 |  | 0.22 | 0.22 | 89.56 | 89.56 | 2027-06-30 | MAINTENANCE ACCESS ROAD |  |  |  | 4.17 | 2.66 | 2 | 3.34 | 1 | 10.8 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | PCR 5859 to include LX006516 with CU400615 renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102011&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000102011 | C58-LX-GA-HAY POINT-0.066km | LX006470 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1438067 | Goonyella | HAY POINT | PRAGUELANDS | 0 | KM | GA01BA0 | 0.066 | GA01BA0 | 0.066 | KM | 4 |  |  |  | 0.066 | 0.066 | 2026-06-30 | HAY POINT RD |  |  |  | 2.88 | 2.3 | 2 | 3 | 1 | 9.2 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Deferred to FY27 due to corporate cash flow limit as of 22 March 2024 (Ian Filosi). To be monitored closely by Ian Filosi.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083391&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000083391 | C58-LX-BW-MT LARCOM-570.366km | LX000640 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 859655 | Blackwater | MOUNT LARCOM | EPALA | 0 | KM | BW01ML570 | 0.3639 | BW01ML570 | 0.3639 | KM | 4 |  | 0.432 |  | 570.366 | 570.366 | 2026-06-30 | DARTS CREEK ROAD |  |  |  | 3.3 | 4.1 | 2 | 4 | 1 | 13.2 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | PCR 5858 to defer the renewal with TOs. The renewal is now dependent on the Geotech investigation, the formation condition, the company resources and time for an integrated renewal of the crossing and the turnouts. FY26 MAJOR RENEWAL <(>&<)> FY24 Design
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044065&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000044065 | C58-LX-BW-MT LARCOM-576.77km | LX005586 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | MAJOR RENEWAL | 1 | SITE | 815000 | Blackwater | MOUNT LARCOM | EPALA | 0 | KM | BW01ML576 | 0.77 | BW01ML576 | 0.77 | KM |  |  | 576.77 | 576.77 | 576.77 | 576.77 |  | EPALAN LANE |  |  |  | 3.14 | 4.1 |  |  |  | 12.87 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 21.01.2020 11:26:39 AUSQLD Sanjna Rajagopalan (R884639) * moved from FY22 due to low priority moved from FY22 due to low priority moved from FY22 due to low priority
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068846&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000068846 | C58-LX-BW-GREGORY JUNCTION-74.829km | LX003654 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 1300000 | Blackwater | GREGORY JUNCTION | OAKY CREEK | 0 | KM | BW08ML74 | 0.8289 | BW08ML74 | 0.8289 | KM | 2 |  |  |  | 74.829 | 74.829 | 2026-06-30 | OAKY CK MINE ACCESS RD |  |  |  | 3.3 | 1 | 2 | 2 | 1 | 7.8 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Deferred to FY27 due to funding limit. Increased the base cost due to the requirements of including two culverts are on either side. Need to be considered in the design and construction. If the overall estimates for FY25 (in Aug-Sept 2023) is calculated to be lower than the original allocation, this crossing shall be brought back in FY25. 30.03.2023 Civil Assets were instructed to cut MRSB scope across the board. Discussion with IM was that this crossing could be deferred 12mths to FY26 renewal however would definitely need renewal in FY26 (no further deferral). FY25 RENEWAL (FY23 Design). DD50 ADDED IN SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103559&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000103559 | C58-LX-BW-WALTON-163.87km | LX005562 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 815000 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML163 | 0.9569 | BW03ML163 | 0.9569 | KM |  |  |  |  | 163.87 |  | 2027-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 2 | 3.4 | 2 | 4 | 1 | 7.32 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041183&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000041183 | C58-LX-MA-CALLE-533.89km | LX000708 | CIVIL | LEVEL CROSSINGS | MINOR UPGRADE-BOOM GATES | RENEWAL | 1 | SITE | 54350 | Moura | CALLEMONDAH | CALLEMONDAH | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 533.89 | 533.89 | 2023-06-30 |  |  |  |  | 4 | 2.4 |  |  |  | 9.6 |  | 2021-03-31 | 2021-10-05 | Level Crossing Other | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF | FY23 IN | 20270630 | * 07.08.2019 14:01:08 AUSQLD Jeremy Stevenson (R867415) * Replacement * Control Systems: Callemondah Drive LX, Replace S60 boom mechs with S40 Install * 12.04.2021 16:21:48 AUSQLD Jeremy Stevenson (R867415) * No design, geotech or BMF complete for this N4 - n eed to determine if it is std or bespoke design an * d if geotech and/or BMF is needed. Is this N4 on a curve or adjacent to curve? *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083403&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000083403 | C58-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 600000 | Blackwater | BW | BW | 633.538 | KM |  | 0 |  | 0 | [15 empty] | 25 |  | 25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083405&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000083405 | C58-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 600000 | Moura | MA | MA | 192.36 | KM |  | 0 |  | 0 | [15 empty] | 25 |  | 25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083406&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000083406 | C58-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Newlands | NL | NL | 214.038 | KM |  | 0 |  | 0 | [15 empty] | 25 |  | 25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000111105&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000111105 | C58-LX-NL-COLLINSVILLE-77.186km | LX003301 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 659076 | Newlands | COLLINSVILLE | MCNAUGHTON | 0 | KM | NL01ML77 | 0.1859 | NL01ML77 | 0.1859 | KM |  |  |  |  | 77.186 | 77.186 | 2027-06-30 | BOWEN DEVELOPMENT ROAD |  |  |  | 3.2 | 2.5 | 2 | 3 | 1 | 10.6 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137533&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000137533 | C58-LX-GA-NORWICH PARK-120.756 | LX003629 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 1300000 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM | 2 |  |  |  | 120.756 |  | 2027-06-30 | BOOROONDARRA ROAD |  |  |  | 4.5 | 1.5 | 2 | 4 | 1 | 18 | 5706 |  |  | Level Crossing Design | [5 empty] | Outstanding notification | NWSC |  | 20250630 | Civil Renewal to support the Signal Upgrade in FY27.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101689&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101689 | C58-LX-MA-CALLE-16.416km | LX005753 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML16 | 0.4179 | MA01ML16 | 0.4179 | KM |  |  |  |  | 16.416 | 16.416 | 2026-06-30 | JEFFERIES ROAD |  |  |  | 3.2 | 2.6 |  |  |  | 8.3 |  |  |  | Level Crossing Renewals | [5 empty] | Outstanding notification | NWSC |  | 20270630 | Moved to FY27 Renewal due to poor condition. Kept in FY28 Renewal as per the discussion with the IM team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123447&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123447 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123451&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123451 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123448&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123448 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123452&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123452 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123449&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123449 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123453&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123453 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123450&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123450 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123454&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123454 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123420&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000123420 | C58-LX-GA-MALLAWA-168.375km | LX020259 | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 343369 | Goonyella | BURTON DOWNS | MALLAWA | 0 | KM | GA01ML168 | 0.375 | GA01ML168 | 0.375 | KM |  |  |  |  | 168.375 | 168.375 | 2025-06-30 |  |  |  | DESIGN SIGNAL | 10 | 2.4 | 2 | 10 | 1 | 100 |  | 2023-09-01 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | SIGNAL DESIGN-IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123435&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123435 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123436&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123436 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123438&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123438 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123437&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123437 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123459&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123459 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123463&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123463 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123460&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123460 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123461&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123461 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123464&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123464 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123462&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123462 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123465&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000123465 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123424&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000123424 | C58-LX-GA-NORWICH PARK-120.756km | LX003629 | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 0 | KM | GA03ML120 | 0.756 | GA03ML120 | 0.756 | KM |  |  |  |  | 120.756 | 120.756 | 2027-06-30 |  |  |  | UPGRADE SIGNAL | 10 | 1.5 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20260630 | SIGNAL UPGRADE-FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070990&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070990 | Rail Renewal | CV002833 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.2899 | KM | GA01ML10 | 0.8499 | GA01ML11 | 0.1459 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070984&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070984 | Rail Renewal | CV002865 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.4349 | KM | GA01ML22 | 0.0519 | GA01ML22 | 0.4869 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058688&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000058688 | Rail Renewal | CV002904 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.226 | KM | GA02ML40 | 0.0619 | GA02ML40 | 0.2879 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071026&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071026 | Rail Renewal | CV002908 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.0779 | KM | GA02ML41 | 0.1439 | GA02ML41 | 0.222 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071028&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071028 | Rail Renewal | CV002913 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.1209 | KM | GA01ML41 | 0.7229 | GA01ML41 | 0.8439 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080698&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000080698 | Rail Renewal | CV002914 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.445 | KM | GA01ML42 | 0.0379 | GA01ML42 | 0.4829 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071022&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071022 | Rail Renewal | CV002925 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.0869 | KM | GA01ML43 | 0.786 | GA01ML43 | 0.8729 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071024&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071024 | Rail Renewal | CV002929 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.192 | KM | GA01ML44 | 0.255 | GA01ML44 | 0.447 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071013&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071013 | Rail Renewal | CV002953 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.2429 | KM | GA01ML56 | 0.2819 | GA01ML56 | 0.525 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070939&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070939 | Rail Renewal | CV002977 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.446 | KM | GA01ML69 | 0.402 | GA01ML69 | 0.8479 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070759&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070759 | Rail Renewal | CV002981 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.336 | KM | GA01ML71 | 0.642 | GA01ML71 | 0.9779 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070934&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070934 | Rail Renewal | CV002999 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.501 | KM | GA01ML81 | 0.8379 | GA01ML82 | 0.336 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070683&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070683 | Rail Renewal | CV003039 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.6049 | KM | GA02ML121 | 0.6149 | GA02ML122 | 0.221 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063186&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000063186 | Rail Renewal | CV003053 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.033 | KM | GA01ML142 | 0.404 | GA01ML142 | 0.4369 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070684&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070684 | Rail Renewal | CV003054 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.034 | KM | GA02ML142 | 0.524 | GA02ML142 | 0.558 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063183&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000063183 | Rail Renewal | CV003062 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.396 | KM | GA01ML149 | 0.0389 | GA01ML149 | 0.4349 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072861&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000072861 | Rail Renewal | CV003104 | CIVIL | RAIL | [5 empty] | Goonyella |  |  | 0.0299 | KM | GA02ML100 | 0.4729 | GA02ML100 | 0.503 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070952&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070952 | Rail Renewal | CV005663 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.628 | KM | BW04ML7 | 0.201 | BW04ML7 | 0.8289 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070947&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070947 | Rail Renewal | CV005685 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.44 | KM | BW01ML544 | 0.759 | BW01ML545 | 0.2 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070718&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070718 | Rail Renewal | CV005697 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.223 | KM | BW01ML550 | 0.406 | BW01ML550 | 0.629 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070719&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070719 | Rail Renewal | CV005699 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.22 | KM | BW01ML550 | 0.629 | BW01ML550 | 0.8489 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070705&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070705 | Rail Renewal | CV005712 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.262 | KM | BW01ML552 | 0.7199 | BW01ML553 | 0.017 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071112&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000071112 | Rail Renewal | CV005852 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.536 | KM | BW01ML537 | 0.1 | BW01ML537 | 0.636 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070698&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070698 | Rail Renewal | CV005934 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.5819 | KM | BW01ML599 | 0.192 | BW01ML599 | 0.774 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070693&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070693 | Rail Renewal | CV005944 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.6179 | KM | BW01ML602 | 0.7309 | BW01ML603 | 0.34 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070876&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070876 | Rail Renewal | CV006069 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.279 | KM | BW03ML32 | 0.26 | BW03ML32 | 0.539 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071095&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071095 | Rail Renewal | CV006084 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.3549 | KM | BW03ML38 | 0.263 | BW03ML38 | 0.6179 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070866&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070866 | Rail Renewal | CV006130 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.189 | KM | BW04ML49 | 0.54 | BW04ML49 | 0.7289 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000064299&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000064299 | Rail Renewal | CV006177 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.668 | KM | BW04ML72 | 0.047 | BW04ML72 | 0.7149 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060637&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000060637 | Rail Renewal | CV006197 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.202 | KM | BW03ML79 | 0.16 | BW03ML79 | 0.3619 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070853&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070853 | Rail Renewal | CV006201 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.343 | KM | BW03ML80 | 0.684 | BW03ML81 | 0.004 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071135&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071135 | Rail Renewal | CV006219 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.266 | KM | BW03ML88 | 0.7049 | BW03ML88 | 0.9709 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070909&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070909 | Rail Renewal | CV006226 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.627 | KM | BW03ML92 | 0.45 | BW03ML93 | 0.0759 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070900&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070900 | Rail Renewal | CV006229 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.386 | KM | BW03ML94 | 0.162 | BW03ML94 | 0.548 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071137&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071137 | Rail Renewal | CV006234 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.0379 | KM | BW03ML97 | 0.4899 | BW03ML97 | 0.528 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070902&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070902 | Rail Renewal | CV006248 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.315 | KM | BW03ML105 | 0.1219 | BW03ML105 | 0.4369 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071130&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000071130 | Rail Renewal | CV006254 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.468 | KM | BW03ML107 | 0.1179 | BW03ML107 | 0.5859 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070904&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070904 | Rail Renewal | CV006255 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.2949 | KM | BW03ML107 | 0.6139 | BW03ML107 | 0.909 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070895&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070895 | Rail Renewal | CV006265 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.2909 | KM | BW03ML110 | 0.8359 | BW03ML111 | 0.127 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000072844&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000072844 | Rail Renewal | CV006285 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.3649 | KM | BW04ML132 | 0.626 | BW04ML133 | 0.012 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070891&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070891 | Rail Renewal | CV006314 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.449 | KM | BW03ML158 | 0.7019 | BW03ML159 | 0.1469 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070883&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070883 | Rail Renewal | CV006588 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.6239 | KM | BW01ML562 | 0.38 | BW01ML563 | 0.006 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073632&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000073632 | Rail Renewal | CV006985 | CIVIL | RAIL | [5 empty] | Moura |  |  | 0.2839 | KM | MA01ML46 | 0.1069 | MA01ML46 | 0.391 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070813&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070813 | Rail Renewal | CV007022 | CIVIL | RAIL | [5 empty] | Moura |  |  | 0.7179 | KM | MA01ML84 | 0.4729 | MA01ML85 | 0.1859 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071053&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000071053 | Rail Renewal | CV007488 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.4129 | KM | BW01ML581 | 0.8659 | BW01ML582 | 0.272 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071040&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000071040 | Rail Renewal | CV007892 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.52 | KM | BW01ML629 | 0.8309 | BW01ML630 | 0.3509 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070790&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070790 | Rail Renewal | TN000046 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.0519 | KM | BW01ML544 | 0.2989 | BW01ML544 | 0.3509 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070791&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000070791 | Rail Renewal | TN000057 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.032 | KM | BW01ML551 | 0 | BW01ML551 | 0.032 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071038&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000071038 | Rail Renewal | TN000126 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.0229 | KM | BW01ML598 | 0.4719 | BW01ML598 | 0.4949 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000063134&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000063134 | Rail Renewal | TN000290 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.125 | KM | BW02ML600 | 0.768 | BW02ML600 | 0.893 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000058599&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000058599 | Rail Renewal | TN000424 | CIVIL | RAIL | [5 empty] | Blackwater |  |  | 0.0359 | KM | BW03ML50 | 0.781 | BW03ML50 | 0.8169 | KM | [21 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080700&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | NON-COAL | 002000080700 | Rail Renewal | CV007273 | CIVIL | RAIL |  | RENEWAL |  |  |  | Moura |  |  | 0.0219 | KM | NC02ML528 | 0.928 | NC02ML528 | 0.9499 | KM | [6 empty] | 2026-06-30 | [13 empty] | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | This is non coal scope waiting to be reviewed and refined
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070925&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000070925 | C17 GA BALOOK WANDOO UP 81.818-82.357KM | CV003000 | CIVIL | RAIL |  | RENEWAL | 1.08 | RAIL KM | 487440 | Goonyella | BALOOK | WANDOO | 0.542 | KM | GA02ML81 | 0.8179 | GA02ML82 | 0.3579 | KM | 10 |  | 1.08 | 0.542 | 81.818 | 82.358 | 2026-06-30 | UP | BOTH |  |  | 3.5 | 4.8 | 1 | 3.8 | 1 |  |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Can be pushed if there are capital constraints
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107799&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000107799 | C17 GA BLACK MOUNTAIN 45.797 - 46.621 | CV002937 | CIVIL | RAIL |  | RENEWAL | 1.728 | RAIL KM | 779903 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.8209 | KM | GA02ML45 | 0.797 | GA02ML46 | 0.6209 | KM | 16 |  | 1.728 | 0.824 | 45.797 | 46.621 | 2027-06-30 | UP | BOTH |  |  | 3.8 | 5 | 1 | 3.9 | 1 | 14.82 | 283 | 2024-03-28 |  | Rail Renewal | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | CANNOT BE PUSHED OUT OF FY26 Post Scope Walkout: The scope was pushed to FY27 due to condition.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000107753&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000107753 | C17 GA COPPABELLA 142.524 - 142.595 | CV003054 | CIVIL | RAIL |  | RENEWAL | 0.216 | RAIL KM | 78258 | Goonyella | MCARTHUR | COPPABELLA | 0.034 | KM | GA02ML142 | 0.524 | GA02ML142 | 0.558 | KM | 2 |  | 0.216 | 0.071 | 142.524 | 142.595 | 2026-06-30 | UP | BOTH |  |  | 3.5 | 4.6 | 1 | 3.7 | 1 | 12.95 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Notification completed | NWSC |  | 20260630 | 20/03/24 - Removed per conversation with Sanjna Reddy. Covered off in 2000107950 C17 GA TOT-COB UP RERAIL 142.346-142.561KM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108737&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000108737 | C17 GA TOOTOOLAH 135.130 - 135.337 | GA-02ML | CIVIL | RAIL |  | RENEWAL | 0.432 | RAIL KM | 335124 | Goonyella | TOOTOOLAH | MCARTHUR | 0.2069 | KM | GA02ML135 | 0.13 | GA02ML135 | 0.337 | KM | 4 |  | 0.432 | 0.207 | 135.13 | 135.337 | 2026-06-30 | UP | BOTH |  |  | 3.5 | 4.7 | 1 | 3.8 | 1 | 13.3 | 263 | 2023-09-01 |  | Rail Renewal | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060639&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060639 | C17 TUNNEL 80.684 - 81.004 | CV006201 | CIVIL | RAIL |  | RENEWAL | 0.648 | RAIL KM | 299775 | Blackwater | TUNNEL | EDUNDALBA | 0.343 | KM | BW03ML80 | 0.684 | BW03ML81 | 0.004 | KM | 6 |  | 0.648 | 0.32 | 80.684 | 81.004 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 3.75 | 1 | 3.4 | 1 | 12.92 |  |  |  | Rail Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | REJC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110844&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000110844 | C18 GA MINDI 120.639 - 121.585 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 1380 | SLEEPERS | 895620 | Goonyella | HATFIELD | SOUTH WALKER | 0.9469 | KM | GA01ML120 | 0.64 | GA01ML121 | 0.5849 | KM |  | 1380 |  | 0.947 | 120.64 | 121.585 | 2026-06-30 | DOWN |  |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110843&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000110843 | C18 GA MINDI 119.505 - 120.501 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 1440 | SLEEPERS | 934560 | Goonyella | MINDI | SOUTHWALKER | 0.9859 | KM | GA01ML119 | 0.505 | GA01ML120 | 0.501 | KM |  | 1440 |  | 0.986 | 119.505 | 120.501 | 2026-06-30 | DOWN |  |  |  | 3.5 | 4.4 | 1 | 3.7 | 1 | 12.95 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108981&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000108981 | C18 GA Wandoo 90.460 - 92.002 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 2252 | SLEEPERS | 1461548 | Goonyella | WANDOO | WAITARA | 1.5489 | KM | GA01ML90 | 0.46 | GA01ML92 | 0.002 | KM |  | 2252 |  | 1.542 | 90.46 | 92.002 | 2026-06-30 | DOWN |  |  |  | 3.5 | 5 | 1 | 1.365 | 1 | 18 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108984&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000108984 | C18 GA WANDOO 92.215- 94.853 | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 3852 | SLEEPERS | 2499948 | Goonyella | WANDOO | WAITARA | 2.6299 | KM | GA01ML92 | 0.2149 | GA01ML94 | 0.8529 | KM |  | 3852 |  | 2.638 | 92.215 | 94.853 | 2026-06-30 | DOWN |  |  |  | 3.5 | 5 | 1 | 18 | 1 | 3900 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114710&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000114710 | C18 BW MORANBAH HOLDING 1 16.828 - 18.83 | GA-75YR | CIVIL | SLEEPERS | SIDING | RENEWAL | 15 | SLEEPERS | 15105 | Goonyella | MORANBAH HOLDING ROAD 1 | MORANBAH HOLDING ROAD 1 | 0.0089 | KM | GA75YR16 | 0.8279 | GA75YR16 | 0.8369 | KM |  | 15 |  | 0.009 | 16.828 | 16.837 | 2026-06-30 | HOLDING ROAD 1 |  |  |  | 4 | 1.5 | 1 | 2 | 1 | 8 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | T0s required between CP and 1.2A Pts 15 Sleepers required Re use existing rail DO NOT PUSH FROM FY27, SCOPE HAS BEEN DEFFERED FROM FY25 TO FY26 AND NOW FY27 - Due to capital constraints, please complete first half of FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114770&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000114770 | C18 GA MORANBAH HOLDING 2 16.875-16.925 | GA-76YR | CIVIL | SLEEPERS | SIDING | RENEWAL | 75 | SLEEPERS | 75525 | Goonyella | MORANBAH HOLDING ROAD 2 | MORANBAH HOLDING ROAD 2 | 0.05 | KM | GA76YR16 | 0.875 | GA76YR16 | 0.925 | KM |  | 75 |  | 0.05 | 16.875 | 16.925 | 2026-06-30 | HOLDING ROAD 2 | BOTH |  |  | 4 | 1.5 | 1 | 2 | 1 | 8 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | DO NOT PUSH FROM FY27, SCOPE HAS BEEN DEFFERED FROM FY25 TO FY26 AND NOW FY27 - Due to capital constraints, please complete first half of FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114772&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000114772 | C18 GA MORANBAH HOLDING 2 16.934-18.127 | GA-76YR | CIVIL | SLEEPERS | SIDING | RENEWAL | 1750 | SLEEPERS | 1764264 | Goonyella | MORANBAH HOLDING ROAD 2 | MORANBAH HOLDING ROAD 2 | 1.193 | KM | GA76YR16 | 0.934 | GA76YR18 | 0.127 | KM |  | 1750 |  | 1.193 | 16.934 | 18.127 | 2026-06-30 | MORANBAH HOLDING ROAD 2 | BOTH |  |  | 4 | 1.5 | 1 | 2 | 1 | 8 |  |  |  | Sleeper Renewal | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | CP of 1.2A Pts - join into concrete sleepers of previous renewal Remove transition sleepers from higher chainage end and use at CP end 1750 Sleepers required DO NOT PUSH FROM FY27, SCOPE HAS BEEN DEFFERED FROM FY25 TO FY26 AND NOW FY27 - Due to capital constraints, please complete first half of FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092991&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000092991 | GREGORY SINK HOLES | BW-08CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 75000 | Blackwater | RANGAL | MACKENZIE | 0.0219 | KM | BW08ML17 | 0.2439 | BW08ML17 | 0.266 | KM |  |  |  |  | 17.244 | 17.266 | 2023-03-03 |  |  |  |  | 4 | 10 | 1 | 4 | 10 | 16 |  | 2022-03-31 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC | FY24 IN | 20270630 | 07.02.2022 Tim Griffin (r878533) $75,000 Design and Cost Estimate for Mackenzie sink holes on Blackwater Branch System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092992&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000092992 | GREGORY SINK HOLES | BW-08CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 75000 | Blackwater | RANGAL | MACKENZIE | 0.1219 | KM | BW08ML17 | 0.4 | BW08ML17 | 0.522 | KM |  |  |  |  | 17.4 | 17.522 | 2023-03-03 |  |  |  |  | 3 | 3 | 1 | 10 | 10 | 9 |  | 2022-03-31 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC | FY24 IN | 20270630 | 07.02.2022 Tim Griffin (r878533) $75,000 Design and Cost Estimate for Mackenzie sink holes on Blackwater Branch System for Construction in FY26, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092994&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000092994 | GREGORY SINK HOLES | BW-08CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 75000 | Blackwater | RANGAL | MACKENZIE | 0.1429 | KM | BW08ML17 | 0.544 | BW08ML17 | 0.687 | KM |  |  |  |  | 17.544 | 17.687 | 2023-03-03 |  |  |  |  | 3 | 3 | 1 | 10 | 10 | 9 |  | 2022-03-31 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC | FY24 IN | 20270630 | 07.02.2022 Tim Griffin (r878533) $75,000 Design and Cost Estimate for Mackenzie sink holes on Blackwater Branch System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092933&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000092933 | TUNNEL SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 100000 | Blackwater | TUNNEL | EDUNGALBA | 0.25 | KM | BW03ML76 | 0 | BW03ML76 | 0.25 | KM |  |  |  |  | 76 | 76.25 | 2026-06-30 |  |  |  |  | 3 | 3 | 1 | 3 | 10 | 9 |  | 2022-03-31 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC | FY24 IN | 20270630 | 21/02/2024: Postponed to FY27 due to design resources (levelling effort over financial years). As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). 07.02.2022 Tim Griffin (r878533) $100,000 Design and Cost Estimate for TUNNEL slope stability on Blackwater System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092930&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000092930 | TUNNEL SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 100000 | Blackwater | TUNNEL | EDUNGALBA | 0.203 | KM | BW03ML76 | 0.14 | BW03ML76 | 0.343 | KM |  |  |  |  | 76.14 | 76.343 | 2026-06-30 |  |  |  |  | 3 | 3 | 1 | 6 | 10 | 9 |  | 2022-03-31 | 2021-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC | FY24 IN | 20270630 | 21/02/2024: Postponed to FY27 due to design resources (levelling effort over financial years). As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). 07.02.2022 Tim Griffin (r878533) $100,000 Design and Cost Estimate for TUNNEL slope stability on Blackwater System for Construction in FY25, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092738&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000092738 | BLACK MOUNTAIN SLOPE STABILITY | GA-01CR | CIVIL | SLOPE STABILITY |  | RENEWAL | 1 | LUMPSUM | 1650000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.1 | KM | GA01ML44 | 0.25 | GA01ML44 | 0.3499 | KM |  |  |  |  | 44.25 | 44.35 | 2025-10-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Slope Stability | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 21/02/2024 - Postponed to FY27 due to insufficient design progress in previous years notification and Finance decision to flatten cost forecast across financial years. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). 31/03/2023 - Postponed from FY25 to FY26 - management decision. 04.03.2022 Tim Griffin (r8788533) Linked to FY23 Slope Stability Design N4 notification which requires design and costing to be completed by Q1FY23 (Sept 2022) so that construction delivery costs are accurate. See attached email to Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077854&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000077854 | C38-SS-GA-BLACK MOUNTAIN-44.240KM | GA-01CR | CIVIL | SLOPE STABILITY | CONSTRUCTION | RENEWAL | 1 | LUMPSUM | 2650000 | Goonyella | BLACK MOUNTAIN | HATFIELD | 0.08 | KM | GA01ML44 | 0.2399 | GA01ML44 | 0.32 | KM |  |  |  |  | 44.24 | 44.32 | 2026-06-30 |  |  |  |  | 3 | 5 | 3 | 4 | 1 | 13.5 |  | 2022-03-31 |  | Slope Stability | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20270630 | 21/02/2024 - Postponed to FY27 due to insufficient design progress in previous years notification and Finance decision to flatten cost forecast across financial years. As discussed and agreed in meeting 20/02/2024 with Design Team Leader (Simon Larsen), Project Manager (Faruk Khondaker) <(>&<)> Civil Assets Team Leader (Steven Roduner). 31/03/2023 - Postponed from FY25 to FY26 - management decision. 03.08.2022 - updated delivery year to FY25 once design is received. Updated CRA and required end dates to be realistic and aligning with site conditions. 31.03.2022 Tim Griffin (r878533) Linked to N4 : 2000067638 Design from FY23 required by 30 Sept 2022 to enable accurate costing. D<(>&<)>C option with Geovert Pty Ltd contractor suggested by PM Ken Veale to progress from fortnightly AM/PM meeting on 29/3/2021. See photo in attachment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092977&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000092977 | GREGORY EMBANKMENT SLOPE STABILSE | BW-08ML | CIVIL | SLOPE STABILITY | EMBANKMENT | DESIGN | 1 | LUMPSUM | 75000 | Blackwater | RANGAL | MACKENZIE | 0.6019 | KM | BW08ML17 | 0.2429 | BW08ML17 | 0.8449 | KM |  |  |  |  | 17.243 | 17.845 | 2023-09-30 |  |  |  |  | 4 | 4 | 1 | 4 | 1 | 16 |  | 2022-03-31 | 2022-10-05 | Slope Stability | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC | FY24 IN | 20270630 | 03/08/2022 - WSchuh - Deferred to FY27 to align with design and construct timeframes. Site based scoping required. 07.02.2022 Tim Griffin (r878533) $75,000 Design and Cost Estimate for Mackenzie embankment slope stabilisation (Constructed back in 1980) on Blackwater Branch System for Construction in FY26, pending pipeline of external contractor works from Goonyella Black Mountain area. 07.03.2022 Tim Griffin (r878533) Design needs to be completed by Q3FY24 (31March2023) to ensure FY25 Construction Costs into MRSB N4 notification. See attached email requesting Project Mgr to progress.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136080&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136080 | B52 -ST-BW-Aldoga-552.230km | CU101304 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ALDOGA- |  | 0 | KM | BW01ML552 | 0.23 | BW01ML552 | 0.23 | KM |  |  |  |  | 552.23 | 552.23 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.1 | 3 | 4 | 1 | 12.9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136083&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136083 | B52 -ST-BW-Aldoga-564.690km | CU101216 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ALDOGA- |  | 0 | KM | BW01ML564 | 0.6899 | BW01ML564 | 0.6899 | KM |  |  |  |  | 564.69 | 564.69 | 2028-06-30 |  |  | CIPP |  | 3 | 4.5 | 3 | 4 | 1 | 13.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136085&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136085 | B52 -ST-BW-Archer-608.480km | CU101494 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML608 | 0.4799 | BW01ML608 | 0.4799 | KM |  |  |  |  | 608.48 | 608.48 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.1 | 4.5 | 3 | 4 | 1 | 13.5 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136091&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136091 | B52 -ST-BW-Archer-608.480km | CU101494 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML608 | 0.4799 | BW01ML608 | 0.4799 | KM |  |  |  |  | 608.48 | 608.48 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.1 | 4.5 | 3 | 4 | 1 | 13.5 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136086&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136086 | B52 -ST-BW-Archer-609.330km | CU101197 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML609 | 0.33 | BW01ML609 | 0.33 | KM |  |  |  |  | 609.33 | 609.33 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.5 | 3 | 4 | 1 | 13.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136090&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136090 | B52 -ST-BW-Archer-609.330km | CU101197 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML609 | 0.33 | BW01ML609 | 0.33 | KM |  |  |  |  | 609.33 | 609.33 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.5 | 3 | 4 | 1 | 13.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Proposed:Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066495&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000066495 | B52 -ST-GA-Moorvale-008.080km | CU200404 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 39200 | Goonyella | BIDGERLEY JUNCTION | BIDGERLEY JUNCTION | 0 | KM | GA03ML8 | 0.08 | GA03ML8 | 0.08 | KM |  |  |  |  | 8.08 |  | 2026-06-30 |  |  |  |  | 3 | 5 |  |  |  | 15 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 20.10.2020 16:23:26 AUSQLD Edward Brooks (R884255) * Defect: Minor to moderate spalling in culvert walls and minor cracks in hauches. * Proposed: CIPP Lining or Remove and Replace
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136070&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136070 | B52 -ST-BW-Crew-020.640km | CU101115 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | CREW-02 |  | 0 | KM | BW08ML20 | 0.64 | BW08ML20 | 0.64 | KM |  |  |  |  | 20.64 | 20.64 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.2 | 3 | 3 | 1 | 9.3 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:LHS severe corrosion in invert, otherwise suitableProposed:Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136072&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136072 | B52 -ST-BW-Fairhill-040.700km | CU101105 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Blackwater | FAIRHIL |  | 0 | KM | BW08ML40 | 0.6999 | BW08ML40 | 0.6999 | KM |  |  |  |  | 40.7 | 40.7 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.1 | 3 | 3 | 1 | 9.3 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:spalling in ceiling at joint, to be confirmed in next inspection. Recommend repairs and monitoring. Culvert is also not free draining, which need rectificationProposed:Final:Risk:Reason:5/9/18 12 units long Middle units look to have some spalling in the ceiling however access limited by water in culvert.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136098&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136098 | B52 -ST-MA-Fry-079.330km | CU400166 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 40000 | Moura | FRY-079 |  | 0 | KM | MA01ML79 | 0.33 | MA01ML79 | 0.33 | KM |  |  |  |  | 79.33 | 79.33 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.3 | 3 | 0 | 1 | 9.6 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Invert moderately corroded with local spots of severe corrosion, mostly on outlet side. Proposed:CIPP lining if hydro confirms suitable. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043805&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000043805 | B52 -ST-BW-Burngrove-008.260km | CU101143 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 21170 | Blackwater | TIKARDI | TIKARDI | 0 | KM | BW08ML8 | 0.258 | BW08ML8 | 0.258 | KM |  |  |  |  | 8.26 | [6 empty] | 3 | 1 |  |  |  | 3 |  | 2019-07-15 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Minor to moderate spalling in localised areas Proposed: Concrete lining TBC by hydro, otherwise remove and replace. Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000047830&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000047830 | 4485 Structures Design | CU100539 | CIVIL | STRUCTURES |  | DESIGN | 1 | UNIT | 29907 | Blackwater | UMOLO |  | 0 | KM | BW03ML150 | 0.4099 | BW03ML150 | 0.4099 | KM |  |  |  |  | 150.41 |  | 2021-06-30 |  |  |  |  | 3 | 3.5 |  |  |  | 10.5 |  |  | 2019-11-29 | Culvert Design | [5 empty] | Notification completed | SCPR |  | 00000000 | * 05.05.2020 16:07:58 AUSQLD Edward Brooks (R884255) * Design not required and needs to be removed from FY21 scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077631&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077631 | Structures Reactive Works | BW | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 2973600 | Blackwater | BW |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 | 3541 | 2021-03-31 |  |  | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 22.05.2021 08:51:49 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077638&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077638 | Structures Reactive Works | GA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 2973600 | Goonyella | GA |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 | 3541 | 2021-03-31 |  |  | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 22.05.2021 09:00:21 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077634&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077634 | Structures Reactive Works | MA | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 1982400 | Moura | MA |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 | 3541 | 2021-03-31 |  |  | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 22.05.2021 08:55:28 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077642&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000077642 | Structures Reactive Works | NL | CIVIL | STRUCTURES |  | REACTIVE WORKS | 1 | LUMPSUM | 1982400 | Newlands | NL |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 25 |  | 25 | 3541 |  |  |  | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 22.05.2021 09:07:48 AUSQLD Edward Brooks (R884255) * Included for unexpected inspection identified critical works.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122762&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000122762 | B12 -ST-GA-Bolingbroke-052.570km | BR200004 | CIVIL | STRUCTURES | BRIDGE BEARING PAD | RENEWAL | 1 | SITE | 1500000 | Goonyella | BOLINGBROKE | HATFIELD | 0.1069 | KM | GA01ML52 | 0.5 | GA01ML52 | 0.6069 | KM |  |  |  |  | 52.57 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 5 | 3 | 4.8 | 1 | 16.8 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240725 | Defect: Pier 6 bearing pad 50% fallen out, at risk of falling completely out and degrading girders. Plan for renewal in FY27 to avoid further damage. Proposed: Remove <(>&<)> Replace Bearing pads. Final: Drawing: Risk: HIgh Reason: If fall out, the time involved in replaced the pads if not planned may cause irrepairable damage to the bridge girder which will be far more expensive to renew than bearing pads.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133303&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133303 | B12 -ST-BW-Aroona-101.450km | BR100239 | CIVIL | STRUCTURES | BRIDGE RELIEVING | RENEWAL | 1 | SITE | 500000 | Blackwater | AROONA |  | 0.1559 | KM | BW03ML101 | 0.3579 | BW03ML101 | 0.514 | KM |  |  |  |  | 101.45 |  | 2027-06-30 |  |  | RELIEVING SLAB R&R |  | 3.5 | 3.4 | 4 | 4.3 | 1 | 15.1 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250109 | Defect: Down Rd Relieveing slab failing to be put into Bridge rollout Proposed: Remove <(>&<)> Replace relieving slabs during next rollout. Final: Drawing: Risk: Mod-HIgh Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131106&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000131106 | B12 -ST-BW-Rocklands-000.950km | BR100576 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | RENEWAL | 1 | SITE | 2000000 | Blackwater | ROCKLANDS |  | 0.0619 | KM | BW03ML0 | 0.9449 | BW03ML0 | 1.0069 | KM |  |  |  |  | 0.95 |  | 2027-06-30 |  |  | STRENGTHEN & RELIEV SLABS |  | 3.5 | 3.35 | 4 | 4 | 1 | 14 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241201 | BR100576 BURNETT HIGHWAY - B12 -ST-BW-Rocklands-000.950km Defect: LHS Handrails required. Also severe crack visible in high chainage relieving slab. Proposed: Strengthening design required of pier walls. Handrails also required. and relieving slab replacement due to severe cracking. Faast tracked as believe some design for this work already completed. Final: Drawing: Risk: HIgh Reason: Deterioation of the pier walls are the most concening defect on this bridge that needs to be rectified to ensure the structural adequacy of the bridge longer term.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044248&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000044248 | B12 -ST-NL-Birralee-099.520km | BR300497 | CIVIL | STRUCTURES | BRIDGE STRENGTHENING | DESIGN | 1 | SITE | 100000 | Newlands | BOWEN RIVER |  | 0 | KM | NL01ML99 | 0.521 | NL01ML99 | 0.521 | KM |  |  |  |  | 99.52 | [6 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Cracks in top flange of girders and in piers. " Proposed: Level 3 Inspections, measurements, Strengthening cracking in girders and piers. Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043467&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000043467 | B12 -ST-NL-Sonoma-082.720km | BR300468 | CIVIL | STRUCTURES | BRIDGE STRENGTHENING | DESIGN | 1 | SITE | 81170 | Newlands | COLLINSVILLE | SONOMA | 0 | KM | NL01ML82 | 0.7199 | NL01ML82 | 0.7199 | KM |  |  |  |  | 82.72 | [9 empty] | 0.1 |  | 100 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Top flange cracking in spans 1, 2 <(>&<)> 3" Proposed: Level 3 Inspections, measurements, Strengthening for cracking in girders and piers as required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092318&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000092318 | Bridge 191.190km WTMN Isaac River | BR200866 | CIVIL | STRUCTURES | BRIDGE-HANDRAILS & REL SLAB | RENEWAL | 1 | SITE | 890000 | Goonyella | MORANBAH NORTH | WOTONGA | 0.1449 | KM | GA01ML191 | 0.115 | GA01ML191 | 0.26 | KM |  |  |  |  | 191.19 |  | 2027-06-30 |  |  | REL SLAB & HANDRAILS |  | 10 | 10 | 4 | 10 | 1 | 100 | 184 | 2022-03-31 |  | Bridges Renewal | STRATEGIC | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20270630 | Aligned with bridge rollout in FY27 Defect: No Handrails LHS or RHS, to be designed for rollout install. HIgh bridge and long therefore high risk. some top of line issues on entry and exit of bridge. Proposed: Install new handrails and remove concrete platforms and install relieving slabs. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043900&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000043900 | B12 -ST-NL-Aberdeen-033.020km | BR300145 | CIVIL | STRUCTURES | BRIDGE-STRENGTHENING | DESIGN | 1 | SITE | 81170 | Newlands | ARMUNA | ABERDEEN | 0 | KM | NL01ML33 | 0.032 | NL01ML33 | 0.032 | KM |  |  |  |  | 33.02 | [6 empty] | 3.5 | 2.5 |  |  |  | 8.8 |  | 2019-07-15 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270629 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Span 3 girders are impacting abutment and concrete concrete interface is causing cracks in the girder. " Proposed: Level 3 Inspections, measurements, Strengthening for shear, resolve moving girders.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136099&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136099 | B52 -ST-MA-Annandale-121.400km | CU400117 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Moura | ANNANDA |  | 0 | KM | MA01ML121 | 0.4 | MA01ML121 | 0.4 | KM |  |  |  |  | 121.4 | 121.4 | 2028-06-30 |  |  | CIPP |  | 3 | 1.1 | 3 | 0 | 1 | 9.3 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Severe Corrosion and holes in CMP, NMP looking to replace WL with CMP to get to renewalProposed:CIPP Line or remove and reoplace pending hydro. Final:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136110&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136110 | B52 -ST-GA-Norwich Park-116.710km | CU200609 | CIVIL | STRUCTURES | CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | NORWICH |  | 0 | KM | GA03ML116 | 0.7099 | GA03ML116 | 0.7099 | KM |  |  |  |  | 116.71 | 116.71 | 2028-06-30 |  |  | CIPP |  | 3 | 1.5 | 3 | 3 | 1 | 9.9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Moderate corrosion above invert lining concrete, but major issue is at joint which appears to be worsening over last 2 year, approx 100 deformed and material visible. Risk of errosion from water during weather event. Proposed:CIPP line or remove and replace confirm in designFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133501&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133501 | B52 -ST-GA-Balook-068.860km | CU200976 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 494000 | Goonyella | BALOOK |  | 0 | KM | GA01ML68 | 0.8599 | GA01ML68 | 0.8599 | KM |  |  |  |  | 68.86 |  | 2027-06-30 |  |  | CIPP |  | 4 | 5 | 3 | 4.5 | 1 | 18 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250111 | Defect: Moderate to severe corrosion on invert of culvert from 4-8 oclock. RHS visibly worse than LHS Proposed: CIPP pending hydro Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087567&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000087567 | B52 -ST-GA-Balook-078.690km | CU200687 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 500000 | Goonyella | BALOOK | WANDOO | 0 | KM | GA01ML78 | 0.6899 | GA01ML78 | 0.6899 | KM |  |  |  |  | 78.69 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.8 | 3 | 4.5 | 1 | 15.6 | 5542 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate corrosion throughout invert with localised severe. Proposed: CIPP Line. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085996&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085996 | B52 -ST-BW-Kenmare-018.220km | CU100848 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 238500 | Blackwater | BW-CL |  | 0 | KM | BW06ML18 | 0.22 | BW06ML18 | 0.22 | KM |  |  |  |  | 18.22 |  | 2026-06-30 |  |  |  |  | 3.5 | 2.6 |  |  |  | 13.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: severe corrosion in invert of inlet and outlet. Proposed: CIPP Lining Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100559&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100559 | B52 -ST-GA-Black Mountain-035.000km | CU200628 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 500000 | Goonyella | GA |  | 0 | KM | GA01ML35 | 0 | GA01ML35 | 0 | KM |  |  |  |  | 35 |  | 2028-06-30 |  |  |  |  | 3.5 | 1.2 | 3 | 3.1 | 1 | 10.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate to sereve corrosion from 2 to 10 oclock. Proposed: CIPP Lining or remove and replace. Could be pushed in Fy28, if condition holds up in next few years. Highest risk of vehicle on acces rd Final: Drawing: Risk: Moderate Reason: Moderate to track however most severe corrosion in under the access rd which puts employees at risk iun vehicles. Yearly inspection to monitor risk, so mod-high risk to access rd users and mod to trackk.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100365&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100365 | B52 -ST-GA-Black Mountain-043.790km | CU200973 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 660000 | Goonyella | GA |  | 0 | KM | GA01ML43 | 0.79 | GA01ML43 | 0.79 | KM |  |  |  |  | 43.79 |  | 2027-06-30 |  |  | CIPP LINING |  | 3.5 | 2.6 | 3 | 3.7 | 1 | 13.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Localised section of severe corrosion and holes. Invert moderate to severe throughout Proposed: CIPP Lining Final: Drawing: Risk: Mod-High Reason: severe corrosion in cmp can often be too late to renew with a lining option which does not cause track disruptions. Therefore when assets are at moderate to severe corrosion this is a better time to line with CIPP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109349&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109349 | B52 -ST-GA-Jilalan-019.084km | CU200948 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 300000 | Goonyella | GA - JILALAN |  | 0 | KM | GA01ML19 | 0.084 | GA01ML19 | 0.084 | KM |  |  |  |  | 19.084 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.7 | 3 | 4.4 | 1 | 15.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate to severe corrosion in invert and too small to maintain. Proposed: CIPP Line pending Hydro. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086079&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086079 | B52 -ST-GA-MacArthur-138.270km | CU200653 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 440000 | Goonyella | GA-NG |  | 0 | KM | GA01ML138 | 0.27 | GA01ML138 | 0.27 | KM |  |  |  |  | 138.27 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.6 |  |  |  | 15.4 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Large services hdpe pipe through culvert cell 2. Moderate corrosion from 4-8 oclock. Proposed: CIPP line if hydro suitable Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133682&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133682 | B52 -ST-MA-Graham-033.530km | CU400079 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 200000 | Moura | GRAHAM |  | 0 | KM | MA01ML33 | 0.53 | MA01ML33 | 0.53 | KM |  |  |  |  | 33.53 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: invert lining too low and not in widening. NMp look at lengthening. Moderate to severe corrosion up to half way. Proposed: CIPP line note partially concrete lined. Otherwise remove and replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133489&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133489 | B52 -ST-GA-Harrow-062.530km | CU200507 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 1000000 | Goonyella | HARROW |  | 0 | KM | GA03ML62 | 0.53 | GA03ML62 | 0.53 | KM |  |  |  |  | 62.53 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.8 | 3 | 3.4 | 1 | 11.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate to severe corrosion throughout culvert. Risk if left beyond FY27, that remove and replace will be required as corrosion too bad Proposed: CIPP lining to be confirmed by Hrdo. Final: Drawing: Risk: High Reason: Risk we will be unable to line if pushed beyond FY27 due to condition.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133626&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133626 | B52 -ST-NL-Kaili-005.480km | CU300080 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 667000 | Newlands | KAILI |  | 0 | KM | NL02ML5 | 0.4809 | NL02ML5 | 0.4809 | KM |  |  |  |  | 5.48 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 3.2 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Pipe dropped under track and hevily silted on outlet. Small culvert Proposed: CIPP or Remove and replace or grout if not required in hydro Final: Drawing: Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133681&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000133681 | B52 -ST-MA-Parana-008.230km | CU400026 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 650000 | Moura | PARANA |  | 0 | KM | MA01ML8 | 0.23 | MA01ML8 | 0.23 | KM |  |  |  |  | 8.23 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: severe corrosion with holes in invert adjoining RCP. RCP on WL. Proposed: CIPP Line pending hydro requirements. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133625&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133625 | B52 -ST-GA-South Walker-127.450km | CU201139 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 247000 | Goonyella | SOUTH WALKER |  | 0 | KM | GA01ML127 | 0.45 | GA01ML127 | 0.45 | KM |  |  |  |  | 127.45 |  | 2027-06-30 |  |  | CIPP |  | 4 | 4.5 | 3 | 4.4 | 1 | 17.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate to localised severe corrosion onlower half of culvert Proposed: CIPP lining pedning Hyrdo Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122763&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000122763 | B52 -ST-GA-Stephens-097.480km | CU200567 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 250000 | Goonyella | STEPHENS |  | 0 | KM | GA03ML97 | 0.4799 | GA03ML97 | 0.4799 | KM |  |  |  |  | 97.48 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.4 | 3 | 3.7 | 1 | 14.8 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270725 | Defect: Moderate to severe corrosion in invert of CMP. Needs to be lined prior to deteriorating. Proposed: CIPP pending Hydro Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133352&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000133352 | B52 -ST-BW-Gregory-065.450km | CU101939 | CIVIL | STRUCTURES | CMP-CONCRE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | GREGORY |  | 0 | KM | BW08ML65 | 0.45 | BW08ML65 | 0.45 | KM |  |  |  |  | 65.45 |  | 2029-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250110 | CU101939 - B52 -ST-BW-Gregory-065.450km Defect: Localised sectionof widening is showing corrosion in the top half of the CMP, suggesting corrosio from outside in But looks to be only 3-4m long. Proposed: Concrete Line pending hydro. Final: Drawings: Risk: Mod Reason: Risk hard to assess due to corrosion appears to be coming from outside in and therefore extent could be far larger on outside of CMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125083&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000125083 | B52 -ST-GA-German Creek-147.880km | CU200381 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 600000 | Goonyella | GA |  | 0.02 | KM | GA03ML147 | 0.9 | GA03ML147 | 0.88 | KM |  |  |  |  | 147.88 |  | 2027-06-30 |  |  | CONCRETE LINE |  | 3 | 4.6 | 3 | 4.4 | 1 | 13.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280801 | Defect: Moderate corrosion in spots in ceiling of the CMP. Localised sever corrosion with holes in steel. Not possible to fix from inside. Thereforece renewal required. Proposed: Concrete Line Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086050&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086050 | B52 -ST-GA-Oaky Creek-151.880km | CU200559 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 900000 | Goonyella | GA-OC |  | 0 | KM | GA03ML151 | 0.88 | GA03ML151 | 0.88 | KM |  |  |  |  | 151.88 |  | 2027-06-30 |  |  |  |  | 3.5 | 1 |  |  |  | 10.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Heavy corrosion above invert concrete lining in Span 4, corrosion present in other spans Proposed: Line with Concrete Line if hydro suitable, span 4 first priority Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133043&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133043 | B52 -ST-BW-Memooloo-050.890km | CU100939 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 7000000 | Blackwater | MEMOOLOO |  | 0 | KM | BW06ML50 | 0.89 | BW06ML50 | 0.89 | KM |  |  |  |  | 50.89 |  | 2027-06-30 |  |  | CONCRETE LINE S1 |  | 3.5 | 2.3 | 3 | 3.6 | 1 | 12.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: Corrosion in top halg of culvert suggesting corrosion from outside in. High risk of sectional loss. Proposed: "Concrete Line in Stage 1, Cells 3,4,5,6,7,10,11,12,13,17,22" Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000128729&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000128729 | B52-ST-MA-0-002.850km | CU400022 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 1566000 | Moura | QAL JUNCTION | CALLEMONDAH | 0 | KM | MA01ML2 | 0.8499 | MA01ML2 | 0.8499 | KM |  |  |  |  | 2.85 |  | 2027-06-30 |  |  | LINE |  | 3.5 | 1.1 | 3 | 3.1 | 1 | 10.7 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severe coorosion formed above the concrete invert Proposed: Concrete Line or Remove <(>&<)> Replace Confirm with Hydro Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086012&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086012 | B52 -ST-GA-Villafranca-027.890km | CU200187 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 957000 | Goonyella | VILLAFRANCA |  | 0 | KM | GA05ML27 | 0.89 | GA05ML27 | 0.89 | KM |  |  |  |  | 27.89 |  | 2027-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 1.2 | 3 | 3.1 | 1 | 12.4 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Corrosion holes throughout and appear to be starting on outside of pipe, however this has not been confirmed. Proposed: Concrete Line or remove and replace, hyrdo to be confirmed Final: Concrete Line or GRP line Drawing: AUR-Q-0918-4017 Risk: Mod-High Reason: Severe cracking in CMP increases risk of collapse corrosion appears to be coming from outside to inside which means section thickness and asociated strength of cmp severely compromised. Risk of collapse high and being 1.8m diameter likely to cause significant track impact.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085883&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085883 | B52 -ST-BW-Memooloo-051.150km | CU100909 | CIVIL | STRUCTURES | CMP-CONCRETE LINE-S1 | RENEWAL | 1 | SITE | 4000000 | Blackwater | BW-BA |  | 0 | KM | BW06ML51 | 0.1499 | BW06ML51 | 0.1499 | KM |  |  |  |  | 51.15 |  | 2026-06-30 |  |  | CONCRETE LINE |  | 3.5 | 2.3 | 3 | 4.2 | 1 | 12.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Corrosion in all inverts. Most severe in cells 6-9, 11, 14 <(>&<)> 15 Proposed: Concrete Line pending Hydro Check. Remove and replace would mean the renewal will get pushed out to FY27-30. Concrete line proposed in staged construction, Cells 1, 2, 3, 4, 6, 7, 8, 14, 15, 20 first priority Remainder completed in FY27/28 when condition worsens Risk: Mod-High Reason: Moved to FY26 purely to save money in FY25. This is due to budget restrictions only not based on condition. Risk is with the business if failure occurs as recommendation is for these cells to be completed in FY25 due to risk of failure from sectional loss from outside of CMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136071&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136071 | B52 -ST-BW-Fairhill-038.360km | CU101125 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | FAIRHIL |  | 0 | KM | BW08ML38 | 0.3599 | BW08ML38 | 0.3599 | KM |  |  |  |  | 38.36 | 38.36 | 2028-06-30 |  |  | CONCRETE LINE |  | 3 | 1.1 | 3 | 3 | 1 | 9.3 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:cracking and spalling in ceiling and walls particularkly at joints, reinspect after repairs Proposed:Tunnel line or remove <(>&<)> replace. Final:Risk:Reason:5/9/18 units 6/7 spalling in ceiling Unit 9 spalling in ceiling and severe cracking in both walls.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136106&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136106 | B52 -ST-GA-Lake Vermont-087.670km | CU200481 | CIVIL | STRUCTURES | CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Goonyella | LAKE VE |  | 0 | KM | GA03ML87 | 0.67 | GA03ML87 | 0.67 | KM |  |  |  |  | 87.67 | 87.67 | 2028-06-30 |  |  | CONCRETE LINE |  | 3 |  | 3 |  | 1 |  |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Cell 2-5<(>&<)>6 <(>&<)> C1-8 severe cracking at joints <(>&<)> spalling in legs. Exposed corroded reinforcement. Proposed:Consider concrete lining in hydro, no notes on pumping, but legs suggest possible. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109359&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109359 | B52 -ST-BW-Umolo-141.650km | CU100691 | CIVIL | STRUCTURES | ELIMINATE | RENEWAL | 1 | SITE | 50000 | Blackwater | UMOLO |  | 0 | KM | BW36YR141 | 0.65 | BW36YR141 | 0.65 | KM |  |  |  |  | 141.65 |  | 2027-06-30 |  |  | ELIMINATE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Overall condition is poor, impact damage has caused the units to separate. looking to replace 141.630km with drop chute to take drainage from 141.650km Location: Dingo Siding - Track Machine use. Proposed: Eliminate
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085957&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000085957 | B52 -ST-BW-Comet-241.996km | CU100345 | CIVIL | STRUCTURES | NON-MRSB RCBC | RENEWAL | 1 | SITE | 430000 | Blackwater | MINERVA |  | 0 | KM | BW03ML241 | 0.9959 | BW03ML241 | 0.9959 | KM |  |  |  |  | 241.996 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 11.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | NWSC | NON MRSB | 20270630 | Burngrove-Nogoa Scope NON-MRSB Defect: Insitu section had moderate cracking in ceiling and severe vertical cracking in walls and along base slab. Propose: Remove <(>&<)> Replace, consolidate with 241.982 into one RCBC system. Risk: Mod-High Reason: 16/2/22 EB re-prioritised due to change in frequency and loading with no coal services on this section. moved from FY25 to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085956&DY_MAB=X&~OKCODE=ONLI | FY27 | Non Coal Traffic |  | NON-COAL | 002000085956 | B52 -ST-BW-Comet-241.982km | CU100328 | CIVIL | STRUCTURES | NON-MRSB RCBC-ELIMINATE | RENEWAL | 1 | SITE | 150000 | Blackwater | MINERVA |  | 0 | KM | BW03ML241 | 0.9819 | BW03ML241 | 0.9819 | KM |  |  |  |  | 241.982 |  | 2028-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 11.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | NWSC | NON MRSB | 20270630 | Burngrove-Nogoa Scope NON-MRSB Defect: Insitu section had moderate cracking in base slab and severe vertical cracking in walls. Propose: Grout <(>&<)> Divert to 241.996 into one RCBC system. Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136082&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136082 | B52 -ST-BW-Aldoga-564.390km | CU101353 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | ALDOGA- |  | 0 | KM | BW01ML564 | 0.39 | BW01ML564 | 0.39 | KM |  |  |  |  | 564.39 | 564.39 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.1 | 4.5 | 3 | 4 | 1 | 13.7 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Moderate to sever spalling and exposed reinf throughout, patches planned in FY23Proposed:Remove and ReplaceFinal:Risk:Reason:AA Condition 3 listing
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136093&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136093 | B52 -ST-MA-Annandale-002.400km | CU400504 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Moura | ANNANDA |  | 0 | KM | MA03ML2 | 0.4 | MA03ML2 | 0.4 | KM |  |  |  |  | 2.4 | 2.4 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1 | 3 | 0 | 1 | 9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:moderate to sever spalling in ceilingProposed:Remove <(>&<)> ReplaceFinal:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136087&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136087 | B52 -ST-BW-Archer-619.240km | CU101513 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML619 | 0.2399 | BW01ML619 | 0.2399 | KM |  |  |  |  | 619.24 | 619.24 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.1 | 3 | 4 | 1 | 12.9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Base slab is failing with severe cracks from units 1-6 on all cells. Looks to be subgrade issue. Proposed:Remove and ReplaceF inal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136092&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000136092 | B52 -ST-BW-Archer-619.240km | CU101513 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | ARCHER- |  | 0 | KM | BW01ML619 | 0.2399 | BW01ML619 | 0.2399 | KM |  |  |  |  | 619.24 | 619.24 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.1 | 3 | 4 | 1 | 12.9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Base slab is failing with severe cracks from units 1-6 on all cells. Looks to be subgrade issue. Proposed:Remove and ReplaceF inal:Risk:Mod-HighReason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136112&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136112 | B52 -ST-GA-Carborough Downs-158.810km | CU201163 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Goonyella | CARBORO |  | 0 | KM | GA01ML158 | 0.81 | GA01ML158 | 0.81 | KM |  |  |  |  | 158.81 | 158.81 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 2.5 | 3 | 4 | 1 | 11.1 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Pumping in each cell under train, approx 10mm. Noise heard suggesting subgrade and material around CMP is holding water and c ompromising condition of compacted materialProposed:Remove and replace with RCBC as subgrade material appears to be in poor condition. Final:Risk:Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136029&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136029 | B52 -ST-BW-Clinton-002.960km | CU101698 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Blackwater | CLINTON |  | 0 | KM | BW11BL2 | 0.9599 | BW11BL2 | 0.9599 | KM |  |  |  |  | 2.96 | 2.96 | 2030-06-30 |  |  |  |  | 4 | 1 | 3 | 3 | 1 | 12 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Subgrade issues and sinking under track and full of silt regularly Proposed: Remove <(>&<)> Replace Final: Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136114&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000136114 | B52 -ST-NL-Kaili-007.029km | CU300039 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Newlands | KAILI-0 |  | 0 | KM | NL02ML7 | 0.029 | NL02ML7 | 0.029 | KM |  |  |  |  | 7.029 | 7.029 | 2028-06-30 |  |  | REMOVE & REPLACE |  | 2.5 | 1.7 | 3 | 3 | 1 | 8.5 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect:Moderate spalling and cracking. Localised severe spalling with corroded reinf in ceiling. Proposed:Monitor annually until renewed with remove and replace. Final:Risk:ModReason:5/19 Minor silting in culvert condition 2.5. Minor settlement in both cells. Approx 10mm under ab loop. Overall condition 2.5 no renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084952&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000084952 | B52 -ST-GA-Millennium Junction-018.930km | CU200595 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 436800 | Goonyella |  |  | 0 | KM | GA03ML18 | 0.93 | GA03ML18 | 0.93 | KM |  |  |  |  | 18.93 |  | 2025-06-30 |  |  |  |  | 3.5 | 2.5 |  |  |  | 13 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect - Visible pumping on first joint between units1/2 Proposed - Remove and Replace 2 /1200x1200 RCBC Drawing - AUR-Q-0692-4019 Risk: Mod-High Reason: Pumping under the track is high risk of cracking and joints opening up and undermining track stability. Holding still based on last inspection in 2021, so believed will last until FY27, however may need to be brought forward if track stability undermined.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086053&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086053 | B52 -ST-NL-Aberdeen-026.070km | CU300273 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 448000 | Newlands | ABERDEEN |  | 0 | KM | NL01ML26 | 0.07 | NL01ML26 | 0.07 | KM |  |  |  |  | 26.07 |  | 2027-06-30 |  |  |  |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Base slab severly cracked, however movement limited. Severe cracking in walls of insitu section, both sides. Unusual construction. Proposed: Remove and Replace due to base slab <(>&<)> Insitu concrete Drawing: AUR-Q-0881-4271 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043722&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000043722 | B52 -ST-NL-Almoola-062.180km | CU300115 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 848000 | Newlands | ALMOOLA |  | 0 | KM | NL01ML62 | 0.1829 | NL01ML62 | 0.1829 | KM |  |  |  |  | 62.18 |  | 2027-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate cracking throughout culvert, with primary issue being the circumference cracking. Proposed: Remove and replace with large RCBC or RCP. Likely 1/1500x1500 RCBC Drawing: Risk: Mod Reason: Additional loading and frequency from new customers on the Newlands line may deteriorate this culvert quicker than originally planned. Need latest photos from 2023 inspection.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109564&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109564 | B52 -ST-NL-Aberdeen-025.400km | CU300389 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 550000 | Newlands | ARMUNA |  | 0 | KM | NL01ML25 | 0.4 | NL01ML25 | 0.4 | KM |  |  |  |  | 25.4 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Drain made up of 600mm long non reinforced units that are misaligned and appear to be breaking up causing risk of collapse Proposed Remove <(>&<)> Replace Final: Drawing Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133680&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133680 | B52 -ST-NL-Birralee-103.690km | CU300583 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 832000 | Newlands | BIRRALEE |  | 0 | KM | NL01ML103 | 0.6899 | NL01ML103 | 0.6899 | KM |  |  |  |  | 103.69 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Cell 3 pumping and significant movement and cracking present throughout cell. Minor movement and cracking in other cells. Cell 3 has been HDPE grouted in due to risk of collapse and low load capacity of M160. Placed on renewal as hydro been changed for the site by cell 3 grouting and other cells expected to go in similar fashion. Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133500&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133500 | B52 -ST-GA-Black Mountain-039.610km | CU200708 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Goonyella | BLACK MOUNTAIN |  | 0 | KM | GA01ML39 | 0.6099 | GA01ML39 | 0.6099 | KM |  |  |  |  | 39.61 |  | 2027-06-30 |  |  | CIPP OR R&R |  | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Inlet RHS severe to moderate corrosion but also half silted. Moderate spalling in drop chute. Remote shows severe corrosion in CMP invert at pit with large section of invert lost to corrosion. Proposed: CIPP Lining, need to confirm cipp will work with suck a large sectional loss at pit. Est based on remove and replace due to risk to cipp Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133026&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133026 | B52 -ST-BW-Blackwater-187.240km | CU100041 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 759000 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML187 | 0.2399 | BW03ML187 | 0.2399 | KM |  |  |  |  | 187.24 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 3.2 | 3 | 3.9 | 1 | 17.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: Exposed reinf in multiple units in the roof and some units appears to be breaking up and likely to collapse Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109451&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000109451 | B52 -ST-GA-Balook-061.730km | CU201032 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Goonyella | BOLINGBROKE |  | 0 | KM | GA01ML61 | 0.7299 | GA01ML61 | 0.7299 | KM |  |  |  |  | 61.73 |  | 2027-06-30 |  |  |  |  | 4 | 5 | 3 | 4.5 | 1 | 18 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severe waterway blocked from ballast and moderate corrosion throughout pipe. Proposed: CIPP LIning Final: Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086037&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086037 | B52 -ST-GA-Braeside-108.720km | CU200905 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 470000 | Goonyella | BRAESIDE |  | 0 | KM | GA01ML108 | 0.7199 | GA01ML108 | 0.7199 | KM |  |  |  |  | 108.72 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Base slab cracks and moderate spalling in units 7<(>&<)>8. Minor to moderate cracking in haunches units 3-6. Pumping in unit 3-7 Proposed: Remove and replace Drawing: AUR-Q-0881-4222 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133628&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133628 | B52 -ST-NL-Armuna-014.720km | CU300204 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 455000 | Newlands | BUCKLEY | ARMUNA | 0 | KM | NL01ML14 | 0.7199 | NL01ML14 | 0.7199 | KM |  |  |  |  | 14.72 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.6 | 243 |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severe crcaking in ceiling and sides of culvert Proposed: Remove <(>&<)> Replace, Consider elimination due to renewal of near by bridge site. Final: Drawing: Risk: High Reason: High risk of colapse, however as this is a 350 diamatere culvert the imapct to track may be limited. Important to get this asset renewed to prevent poetntial track impacts in teh future.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086039&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086039 | B52 -ST-GA-Bundoora-128.420km | CU200603 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1305000 | Goonyella | BUNDOORA |  | 0.02 | KM | GA03ML128 | 0.4 | GA03ML128 | 0.4199 | KM |  |  |  |  | 128.42 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate spalling througout cell, with localised sever spalling with corroded exposed reinf in units 2,3 <(>&<)> 8 Proposed: Long Culvert 30m Remove and replace Drawing: AUR-Q-0881-4234 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094596&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000094596 | B52 -ST-BW-Rocklands-003.370km | CU100423 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 4616300 | Blackwater | BW-CL |  | 0 | KM | BW03ML3 | 0.3699 | BW03ML3 | 0.3699 | KM |  |  |  |  | 3.37 |  | 2027-06-30 |  |  | REPLACE WITH BRIDGE - UNICELL |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: CU100423 with strengthening steel beams on ceiling. Pumping severely 15-20mm under loaded train, sheared bolt in strengthening steel. Proposed: Remove and Replace. Ideally with bridge or unibox. Cost comparison. Drawing: Risk: High Reason: Pumping could lead to derailments and high likelihood of top of alignment issue with track and regular resurfacing requirements. FY26 scoping review - moved to FY27 following scope review (28.03.24)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085937&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085937 | B52 -ST-BW-Aroona-086.350km | CU100384 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 773800 | Blackwater | BW-CL |  | 0.05 | KM | BW03ML86 | 0.4 | BW03ML86 | 0.3499 | KM |  |  |  |  | 86.35 |  | 2025-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate spalling in cast in situ section and unit 5 far leg spalling. Proposed: design with 86.320 and consolidate two culverts into 1. Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125055&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000125055 | B52 -ST-BW-Duaringa-106.590km | CU100198 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 666210 | Blackwater | BW-CL |  | 0 | KM | BW03ML106 | 0.5899 | BW03ML106 | 0.5899 | KM |  |  |  |  | 106.59 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  | 2023-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: pumping severely, visible on track as well Proposed: remove and replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100364&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100364 | B52 -ST-BW-Wallaroo-117.620km | CU100338 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 660000 | Blackwater | BW-CL |  | 0 | KM | BW03ML117 | 0.6199 | BW03ML117 | 0.6199 | KM |  |  |  |  | 117.62 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.7 | 3 | 3.4 | 1 | 13.4 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Unit 7 both cells dropped and pumping approx 1-2mm under loaded traffic. Moderate cracking in ceiling Proposed: Remove and Replace Final: Drawing: Risk: High Reason: Pumping box culvert means well under strength, in this case 22TAL and operating 27TAL. The track will lose top of line and units are being pushed down by the constant pumping action.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085953&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085953 | B52 -ST-BW-Wallaroo-120.690km | CU100711 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 664200 | Blackwater | BW-CL |  | 0 | KM | BW03ML120 | 0.6899 | BW03ML120 | 0.6899 | KM |  |  |  |  | 120.69 |  | 2027-06-30 |  |  |  |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Overall condition is poor. Units 3, 4, 7 and 8, have dropped in most cells and base slab appears to have severe cracsk. Proposed: Remove <(>&<)> Replace 5/1200x900 RCBC 12.02m long Drawing: AUR-Q-0740-4120 Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100368&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100368 | B52 -ST-BW-Parnabal-156.590km | CU100055 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Blackwater | BW-CL |  | 0 | KM | BW03ML156 | 0.5899 | BW03ML156 | 0.5899 | KM |  |  |  |  | 156.59 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.5 | 3 | 4.4 | 1 | 15.3 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: C1-5 <(>&<)>6 severe exposed reinf in ceiling <(>&<)> walls <(>&<)> severe crack in low leg. Pumping under loaded trains. Insitu section also severe cracks Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Mod-High Reason: severe crack and spalling and pumping of reinforced cconcrete will lead to an unexpected failure which will likely cause a track alignment issue.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100367&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100367 | B52 -ST-BW-Bluff-175.450km | CU100151 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 600000 | Blackwater | BW-CL |  | 0 | KM | BW03ML175 | 0.45 | BW03ML175 | 0.45 | KM |  |  |  |  | 175.45 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.35 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severe Spalling and exposed reinforcements, difficult to repair due to size. Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Mod-High Reason: severe crack and spalling and pumping of reinforced cconcrete will lead to an unexpected failure which will likely cause a track alignment issue.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043832&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000043832 | B52 -ST-BW-Curragh-007.080km | CU101725 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 352980 | Blackwater | BW-CU |  | 0 | KM | BW12ML7 | 0.08 | BW12ML7 | 0.08 | KM |  |  |  |  | 7.08 |  | 2026-06-30 |  |  |  |  | 3.5 | 1 |  |  |  | 10.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 25.09.2020 19:09:37 AUSQLD Edward Brooks (R884255) * Defect; Insitu section had moderate cracking in ceiling and severe vertical cracking in walls and along base slab. * Propose: Remove <(>&<)> Replace, consolidate with 241.982 into one RCBC system. Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043723&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000043723 | B52 -ST-BW-Marmor-588.650km | CU101533 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 3895000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML588 | 0.65 | BW01ML588 | 0.65 | KM |  |  |  |  | 588.65 |  | 2027-06-30 |  |  |  |  | 4 | 4.9 |  |  |  | 18 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250817 | Defect: All cells unit 4 sinking 75mm Unit 3-1 exposed reinf <(>&<)> unit 6-6 minor crack 7<(>&<)>8 oclock. Crack to be monitored. Proposed: Remove <(>&<)> replace. 6 / 1200x900 RCBC Drawing: AUR-Q-0740-4250 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100369&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000100369 | B52 -ST-BW-Marmor-597.350km | CU101195 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML597 | 0.3499 | BW01ML597 | 0.3499 | KM |  |  |  |  | 597.35 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: failing leg of culvert Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: Moderate Reason: failing leg of box will lead to pumping track and top of line misalignments.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085997&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000085997 | B52 -ST-BW-Marmor-602.690km | CU101482 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 636000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML602 | 0.6899 | BW01ML602 | 0.6899 | KM |  |  |  |  | 602.69 |  | 2027-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 2.5 | 4.1 | 3 | 4.3 | 1 | 10.8 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: upgrade with 602.600 for afflux issues on TMR rd and for construction timeframes. Proposed: remove and replace 2/3000x3750 unibox, Replace with culvert at 602.600km. Drawing: Risk: Moderate Reason: Being replaced with 602.600km as this is the overflow for the same waterway. Must be completed in conjunction with this culvert.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100362&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000100362 | B52 -ST-BW-Bajool-605.130km | CU101367 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 660000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML605 | 0.13 | BW01ML605 | 0.13 | KM |  |  |  |  | 605.13 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.8 | 3 | 3.4 | 1 | 11.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Remote inspection shows cell pumping. Proposed: Remove and replace Final: Drawing: Risk: Mod-High Reason: Pumping in RCBC means it is under capacity and the base slab has normally failed and units are starting to fail or deteriorate quicker. Unable to repair a 300 high culvert, remove and replace only option. if left will collapse and this will impact drainage and increase risk of washout or lead to top of line issues in track.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000099884&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000099884 | B52 -ST-BW-Archer-619.240km | CU101513 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 40000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML619 | 0.2399 | BW01ML619 | 0.2399 | KM |  |  |  |  | 619.24 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.7 | 3 | 3.2 | 1 | 10.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Severe spalling in ceiling and severe cracking in legs of unit 6 in cells. Units also dropping <(>&<)> severe cracks in CBS Proposed: Remove and Replace Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133684&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133684 | B52 -ST-MA-Callide-009.580km | CU400514 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 240000 | Moura | CALLIDE |  | 0 | KM | MA07ML9 | 0.5799 | MA07ML9 | 0.5799 | KM |  |  |  |  | 9.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1 | 3 | 3 | 1 | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Sinking and circumference cracking. Joints opening and wing walls serevely damaged. Proposed: Remove <(>&<)> Replace Drawing: Risk:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130442&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000130442 | B52 -ST-BW-Clinton-003.360km | CU101652 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 378000 | Blackwater | CLINTON |  | 0 | KM | BW11BL3 | 0.3599 | BW11BL3 | 0.3599 | KM |  |  |  |  | 3.36 |  | 2028-06-30 |  |  | REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241122 | Defect: Unit 3 sunk severely, estimated 75mm, erosion through formation material above starting to occur. Proposed: Remove and Replace Drawing: Risk: High Reason: High risk to track impact from the gap between the sunken unit and neighbouring. top of line issue and loss of ballast around sleepers high risk.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123257&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000123257 | B52 -ST-BW-Curragh-012.060km | CU101721 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 350000 | Blackwater | CURRAGH |  | 0 | KM | BW12ML12 | 0.0599 | BW12ML12 | 0.0599 | KM |  |  |  |  | 12.06 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1 | 3 | 3 | 1 | 13.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240803 | Defect: Severe spalling in ceiling of multiple units with corrosion visible of reinforcement Proposed: Remove <(>&<)> Replace Final: Drawing: Risk: HIgh Reason: Conidtion is very poor with significant reinforcement apearing to be lost from ceiling which is the main span. High risk of further movement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000128772&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000128772 | B52 -ST-MA-Fry-089.570km | CU400255 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 693000 | Moura | FRY | MOUNT RAINBOW | 0 | KM | MA01ML89 | 0.5699 | MA01ML89 | 0.5699 | KM |  |  |  |  | 89.57 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Found during Hydro Study of Mt Rainbow Proposed: Additional Culverts - Consider additional barrels to structure to achieve 1% TOR immunity. 3/1200 x 600mm RCBC's required to achieve immunity. Potential to investigate options of regrading the upstream table drain. Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100664&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100664 | B52 -ST-GA-Moranbah North-188.630km | CU200668 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 800000 | Goonyella | GA |  | 0 | KM | GA01ML188 | 0.63 | GA01ML188 | 0.63 | KM |  |  |  |  | 188.63 |  | 2028-06-30 |  |  | REMOVE AND REPLACE |  | 3.5 | 1.1 | 3 | 4 | 1 | 10.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Minor to moderate spalling in all spans, worst around units 3-4 with cracks in base slab. Some spalling repaired. C1-U1-4 pumping. head wall are comig away and falling off. Old repairs failing again. Design strength est M160/220, could last to FY28 Proposed: Remove and replace with RCBC Risk: Mod-High Reason: Units are pumping under trains in unit 1-4 in all cells. This will deteriorate the culvert faster and creates higher risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086018&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086018 | B52 -ST-GA-Blair Athol-118.970km | CU201278 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2211300 | Goonyella | GA- |  | 0 | KM | GA29ML118 | 0.9699 | GA29ML118 | 0.9699 | KM |  |  |  |  | 118.97 |  | 2025-06-30 |  |  |  |  | 4 | 1 |  |  |  | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Cracks up to 0.45mm in all units <(>&<)> deformed in shape Proposed: Remove and Replace. Consider lining alternatives Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109410&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109410 | B52 -ST-GA-Waitara-104.580km | CU200715 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Goonyella | GA - NEBO |  | 0 | KM | GA01ML104 | 0.5799 | GA01ML104 | 0.5799 | KM |  |  |  |  | 104.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON-MRSB | 20270630 | Defect: Pumping under loaded train. Spalling and concrete damage related to pumping. Previously patch repaired by failing again and more spalling. Proposed: Remove <(>&<)> Replace RCBC Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133487&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133487 | B52 -ST-GA-German Creek-142.570km | CU200470 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1539000 | Goonyella | GERMAN CREEK |  | 0.0299 | KM | GA03ML142 | 0.5999 | GA03ML142 | 0.5699 | KM |  |  |  |  | 142.57 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.1 | 3 | 3.1 | 1 | 12.4 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Regular spalling in ceilling in majority of cells difficult to maintain due to size. Proposed: Remove and replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086059&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086059 | B52 -ST-GA-German Creek-144.580km | CU200410 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Goonyella | GERMAN CREEK |  | 0.02 | KM | GA03ML144 | 0.5999 | GA03ML144 | 0.5799 | KM |  |  |  |  | 144.58 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.3 | 3 | 3.1 | 1 | 10.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: CMP under acces rd crushing <(>&<)> need to be replaced. moderate corrosion just above invert lining. 2m cover Proposed: concrete line, if hydro suitable or remove and replace Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109454&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109454 | B52 -ST-BW-0-066.580km | CU101958 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 740000 | Blackwater | GOGANGO | GRANTLEIGH | 0 | KM | BW03ML66 | 0.5799 | BW03ML66 | 0.5799 | KM |  |  |  |  | 66.58 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Multiple types of culvert CMP, old RCBC. Major misalignment in middle with severe cracking in haunches and base slab. Proposed: Remove and Replace Final: Risk: Reason: Drawing;
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086026&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086026 | B52 -ST-NL-Havilah-141.060km | CU300467 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 308000 | Newlands | HAVILAH |  | 0 | KM | NL01ML141 | 0.0599 | NL01ML141 | 0.0599 | KM |  |  |  |  | 141.06 |  | 2027-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Notif Pumping , spalling in ceiling. And dropping 30mm. Also design loading of M160 and although concrete spalling repaired, only extended life 5-10 years. Proposed: Remove and replace 1/1200x900 RCBC 8.42m long Drawing: AUR-Q-0854-4042 Risk: Mod-High Reason: Being only design for 15TAl when 26.5TAl this is the main reason fro the renewal. This understrength is causing the unit to pump and spall over time and will not be fixed other than with removal and replacement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093104&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000093104 | B52 -ST-GA-Hay Point-000.420km | CU201297 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2012322 | Goonyella | HAY POINT |  | 0.01 | KM | GA01BD0 | 0.4359 | GA01BD0 | 0.446 | KM |  |  |  |  | 0.42 |  | 2027-06-30 |  |  |  | 2 / 1200X900 RCBC | 4 | 2.3 | 3 | 3 | 1 | 14.5 | 5786 | 2023-10-13 |  | Culvert Renewals | BESPOKE DESIGN | MEDIUM | LOW | HIGH | MEDIUM | Outstanding notification | SCPR |  | 20270630 | Defect: Sereve spalling in ceiling of units with exposed reinforcement. Currently propped to make safe. Incorrectly called up as Bridge, when in fact 2 Cell RCBC Culvert. Proposed: Remove and replace with RCBC Final: 2/1200x900 RCBC Drawing: Risk: High Reason: Exposed corroded reinforcement and therefore high risk of collapse. Urgent to get replaced. Propped for safety currently. 8/12/23 EB Remote inspection confirmed condition of track culverts is better than under access rd and based on this deferreing delivery to FY26 to allow adeqaute time to finalise IFC design. FY26 scoping update - deferred to FY27 based on no risk to rail traffic and low risk to road traffic based on propping. Need to understand what correspondence we've had with Hay Point, what they're contributing etc 23.03.24 RJC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084079&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000084079 | B52 -ST-MA-Stirrat-059.910km | CU400140 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 511500 | Moura | MA |  | 0 | KM | MA01ML59 | 0.91 | MA01ML59 | 0.91 | KM |  |  |  |  | 59.91 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 11.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Corrosion under invert lining an issue. Lining separated from steel pipe. FY19 Stirrat-Clarje flood study Proposed: Remove and replace with RCBC (CIPP could be considered however concrete invert lining be good to remove) Risk: Moderate Reason: Corrosion around invert lining is visibal at top, but expecte dto be worse behind lining. Mderate risk of crushing as corrosio in side walls and this will impact track alignment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086057&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086057 | B52 -ST-MA-Fry-089.250km | CU400402 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Moura | MA |  | 0 | KM | MA01ML89 | 0.25 | MA01ML89 | 0.25 | KM |  |  |  |  | 89.25 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.3 |  |  |  | 11.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Corrosion in CMP Proposed: for culvert to have immunity remove and replace with 900 x 600mm RCBC Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132517&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000132517 | B52 -ST-BW-Marmor-592.550km | CU101241 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 300000 | Blackwater | MARMOR |  | 0 | KM | BW01ML592 | 0.55 | BW01ML592 | 0.55 | KM |  |  |  |  | 592.55 |  | 2027-06-30 |  |  | REPLACE |  | 4 | 4.9 | 3 | 4.5 | 1 | 18 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | CU101241 - B52 -ST-BW-Marmor-592.550km Defect: Base slab severely failed. Spalling of some precast and large sections of insitu section. On 12 monthly inspections. Proposed: Remove and Replace Drawing: Risk: High Reason: High risk to track impact from movement of units and failed base slab.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120874&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000120874 | B52 -ST-BW-Mount Larcom-567.000km | CU101461 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1800000 | Blackwater | MT LARCOM |  | 0 | KM | BW01ML567 | 0 | BW01ML567 | 0 | KM |  |  |  |  | 567 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240620 | Defect: Cell 3 grout filled with HDPE due to significant cracking in top half of the RCP. Waterway capacity reduced and increased risk of track washout. Proposed: REmove <(>&<)> REplace with RCBC Final: Drawing: Risk: HIgh Reason: Cell 3 has had to be grouted urgently to stop and severely crcaked RCP which has increased the risk of track washout and impacts to above rail services. Other 2 cells also cracked and being monitored on an increased frequency.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090969&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000090969 | B52 -ST-BW-Epala-580.690km | CU101314 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Blackwater | NCL |  | 0 | KM | BW01ML580 | 0.6899 | BW01ML580 | 0.6899 | KM |  |  |  |  | 580.69 |  | 2027-06-30 |  |  |  |  | 3.5 | 4.1 |  |  |  | 14.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Notif 2000076768 Unit dropped approx 40-75mm, suggesting failure. Observed under loaded train and no pumping was visible. Proposed: Remove and replace with RCBC Risk: Mod-High Reason: Units are sinking under track which will result in top of rail alignment issue and more resurfacing and increased risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124897&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000124897 | B52 -ST-NL-Armuna-016.430km | CU300435 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Newlands | NL |  | 0 | KM | NL01ML16 | 0.4299 | NL01ML16 | 0.4299 | KM |  |  |  |  | 16.43 |  | 2027-06-30 |  |  | REMOVE AND REPLACE |  | 4.5 | 1.7 | 3 | 3.4 | 1 | 15.3 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280728 | Defect: Remote required but appears to be crushing under track. Asset is CP's Proposed: Remove and replace. Final: Drawing: Risk: High Reason: As unreinforced pipe, no slower ductile failure from steel reinforcement, more at risk of catastrophic brittle collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000128771&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000128771 | B52 -ST-GA-Red Mountain-025.730km | CU200401 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 450000 | Goonyella | RED MOUNTAIN | WINCHESTER | 0 | KM | GA03ML25 | 0.7299 | GA03ML25 | 0.7299 | KM |  |  |  |  | 25.73 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 2.1 | 3 | 3.5 | 1 | 12.4 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Pumping under loaded trains, which has caused legs of box to spall and have some areas of exposed reinforcement. Unable to repair pumping and is progressively getting worse each inspection. Proposed: Remove and Replace Drawing: Risk: Mod-High Reason: Pumping is tytpically linked to a structural deficiency in the structure or subgrade. Once started it is difficult and expensive to repair and generally will not last. the pumping damages the units and base under the track first and eventually impacts top of line which we have seen recently on OC line. If left top of line issues expected and emergency works likely.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133488&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000133488 | B52 -ST-GA-Saraji-081.440km | CU200492 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 277000 | Goonyella | SARAJI |  | 0 | KM | GA03ML81 | 0.44 | GA03ML81 | 0.44 | KM |  |  |  |  | 81.44 |  | 2026-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1.6 | 3 | 3.3 | 1 | 14.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: severe cracks in ceiling and walls in both units. Annual inspection required. Reactive found in FY24. Proposed: Remove and Replace Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130444&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000130444 | B52 -ST-BW-Tryphinia-130.360km | CU100160 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 462000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML130 | 0.3599 | BW03ML130 | 0.3599 | KM |  |  |  |  | 130.36 |  | 2027-06-30 |  |  | REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Units severely cracked both in legs and ceiling. Proposed: Remove and Replace Drawing: Risk: High Reason: Severe cracking in legs could lead to unexpected collapse of units under loaded section of track. High risk of derailment should this occur. in current condition if this was delay the likelihood will be unmanageable.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000116446&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000116446 | B52 -ST-BW-Umolo-141.630km | CU100560 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1200000 | Blackwater | UMOLO |  | 0 | KM | BW36YR141 | 0.63 | BW36YR141 | 0.63 | KM |  |  |  |  | 141.63 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 1.3 | 3 | 3 | 1 | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect - Remote inspection found severe cracks 12 oclock in RCP units and sereve sinking of some units, most damage under siding rd. moderate large sections of ceiling spalling in insitu BC. WR RCP's has severe cracking longitudinally and circumference. very poor condition. RCP WL, insitu BC O, RCP WR. Proposed Remove and Replace RCBC Risk: High Reason: Severe cracks in ceiling of RCP under track, could deteriorate faster now they have opened up into structural cracks which will cause pumping in track and potentially need grouting to hold until renewed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109595&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109595 | B52 -ST-GA-Balook-080.390km | CU200671 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Goonyella | WANDOO |  | 0 | KM | GA01ML80 | 0.39 | GA01ML80 | 0.39 | KM |  |  |  |  | 80.39 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 4 | 4.8 | 3 | 4.5 | 1 | 18 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severely Corroded throughout Proposed Renewal - CIPP if possible, otherwise remove and replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093968&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000093968 | B52 -ST-BW-Warren-028.030km | CU100690 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1750000 | Blackwater | WARREN |  | 0 | KM | BW03ML28 | 0.0299 | BW03ML28 | 0.0299 | KM |  |  |  |  | 28.03 |  | 2026-06-30 |  |  | REMOVE & REPLACE LHS INSITU |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: pumping in insitu section. Severe cracks in walls and ceiling of insitu section. LHS are 300A RCBC in good condition. Scouring on outlet side. Proposed: Remove and Replace EHS insitu section. Drawing: AUR-Q-0575-0051 Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086013&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000086013 | B52 -ST-GA-Yukan-028.500km | CU201131 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 957000 | Goonyella | YUKAN |  | 0 | KM | GA01ML28 | 0.4919 | GA01ML28 | 0.4919 | KM |  |  |  |  | 28.5 |  | 2027-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 4.4 | 3 | 4.3 | 1 | 17.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Unit 1 and 2 have dropped under track. NCL Affected. QR closure required. Proposed: Remove and replace. Final : 1/1500x600 RCBC remove and replace 22.84m Long Drawing: AUR-Q-0881-4221 Risk: Mod Reason: Sinking under mainline which increases risk of top alignment issues with the track increasing risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044225&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000044225 | B52 -ST-BW-Burngrove-005.100km | CU101081 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 4313988 | Blackwater | BW-GG |  | 0 | KM | BW08ML5 | 0.1 | BW08ML5 | 0.1 | KM |  |  |  |  | 5.1 |  | 2027-06-30 |  |  |  |  | 3.5 | 1.2 |  |  |  | 10.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250817 | * 25.09.2020 19:05:30 AUSQLD Edward Brooks (R884255) * Defect: Insitu section had moderate cracking in base slab and severe vertical cracking in walls. * Propose: Remove <(>&<)> Replace, consolidate with 241.996 into one RCBC system.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085882&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085882 | B52 -ST-BW-Mackenzie-032.600km | CU101158 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 957000 | Blackwater | MACKENZIE |  | 0 | KM | BW08ML32 | 0.5999 | BW08ML32 | 0.5999 | KM |  |  |  |  | 32.6 |  | 2026-06-30 |  |  |  | CONCRETE LINE | 3.5 | 1.1 | 3 | 3.1 | 1 | 10.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Moved to FY26 base on Ryan Bell deciding to defer. Defect: severe spalling in multiple units in ceiling and legs. Proposed: Remove and Replace. Appears to be too small to concrete line. Final: Concrete Line, 150mm thick Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043884&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000043884 | B52 -ST-BW-Marmor-602.600km | CU101313 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 4541000 | Blackwater | MARMOR | BAJOOL | 0 | KM | BW01ML602 | 0.5999 | BW01ML602 | 0.5999 | KM |  |  |  |  | 602.6 |  | 2027-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270630 | * 10.03.2020 08:30:53 AUSQLD Peter Rayner (R003851) * Defect - Spalling and cracking in ceiling and walls, worst in cells 2 <(>&<)> 3, however still present in other three cells. Cells 2 <(>&<)> 3 hold ground water. - Proposed Renewal - Tunnel Lining cells 1,4,5 and remove and replace and lifting the base slab of cells 2<(>&<)>3 if possible. * Remove and replace 5/3000x3000 * Remove and replace 4/3000x3750 unibox raise invert by 1m and upgrade overflow culvert to 602.700 to 2/3000x3750 unibox * 12.05.2020 16:17:24 AUSQLD Edward Brooks (R884255) * Scope deferred from FY22 to FY23 due to FY22 budget limitations. 28/2/23 EB-Condition holding so deferred to FY26 delivery
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085886&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085886 | B52 -ST-BW-Aroona-086.320km | CU100432 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 636000 | Blackwater | BW-CL |  | 0.02 | KM | BW03ML86 | 0.2999 | BW03ML86 | 0.32 | KM |  |  |  |  | 86.32 |  | 2025-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: base sab severely cracked. Spalling throughout. Check hydro to see if needd. Proposed: hydro check and eliminate if possible. May need to upgrade 86.350 culvert Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129791&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000129791 | B52 -ST-BW-Boorgoon-002.240km | CU100004 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 1006992 | Blackwater | BOORGOON |  | 0 | KM | BW23ML2 | 0.2399 | BW23ML2 | 0.2399 | KM |  |  |  |  | 2.24 |  | 2027-06-30 |  |  | RCP |  | 4 | 1 | 3 | 3 | 1 | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241109 | Defect: Mine pipes and runoff from mine operations has severely compromised the waterway. And head wall and wing walls have collapsed. Proposed: Additional RCP cells likely required. Replacement of headwall. Mine should be involved in funding. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100662&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100662 | B52 -ST-BW-Umolo-151.290km | CU100187 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 500000 | Blackwater | BW-CL |  | 0 | KM | BW03ML151 | 0.2899 | BW03ML151 | 0.2899 | KM |  |  |  |  | 151.29 |  | 2027-06-30 |  |  | REMOVE & REPLACE RCP |  | 3.5 | 4.5 | 3 | 4.4 | 1 | 13.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Box culvert severely crack and spalling, head wall severe cracked and falling off. WR already upgraded with RCPs. Proposed: Remove and replac with RCP to match widening right and 8 cells. Final: Drawing: Risk: Mod-High Reason: Box culvert has sereve cracking and spalling which is being worsen by ongoing traffic over. It is under design capacity for the line and at risk of faster deterioration and possible collapse. Head wall collapse will lead to loss of ballast around the track sleepers compromising track condition.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082460&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000082460 | B52 -ST-BW-Marmor-596.240km | CU101368 | CIVIL | STRUCTURES | RCP | RENEWAL | 1 | SITE | 1400000 | Blackwater | MARMOR |  | 0 | KM | BW01ML596 | 0.2399 | BW01ML596 | 0.2399 | KM |  |  |  |  | 596.24 |  | 2026-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 3.5 | 4.1 | 3 | 4.3 | 1 | 15.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Defect: Severe corrosion through CMP on outlet side. Unable to vac lean due to risk of damaging CMP. Proposed: Remove and Replace RCBC. Can inlet be raised or else drop chute may be required. Also a causeway required on access rd to direct council drain flow into new culvert. Final Remove <(>&<)> Replace 1/900RCP Risk: Mod-High Reason: Severe corrosion on outlet side is prevent cleaning silt due to risk of corrosion and loss of section thickness. Risk of collapse is mod-high and arch under track also deteriorated.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109453&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000109453 | B52 -ST-GA-Bundoora-127.440km | CU200383 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 40000 | Goonyella | NORWICH PARK | BUNDOORA | 0.04 | KM | GA03ML127 | 0.4 | GA03ML127 | 0.44 | KM |  |  |  |  | 127.44 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Exposed reinf at joints of multiple units. Cracking though some units. Proposed: Cipp pending Hydro. Final: Risk: Reason: Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066499&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000066499 | B52 -ST-BW-Tikardi-008.780km | CU101042 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 37100 | Blackwater | TIKARDI |  | 0 | KM | BW05ML8 | 0.78 | BW05ML8 | 0.78 | KM |  |  |  |  | 8.78 |  | 2028-06-30 |  |  | CIPP |  | 3 | 1.7 | 3 | 3.4 | 1 | 10.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 20.10.2020 16:43:42 AUSQLD Edward Brooks (R884255) * Defect: Units are separating and allowing material to fall through the joints. May lead to top of line issues. * Proposed: CIPP Lining Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133067&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000133067 | B52 -ST-BW-Archer-620.900km | CU101283 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 200000 | Blackwater | ARCHER |  | 0 | KM | BW01ML620 | 0.9 | BW01ML620 | 0.9 | KM |  |  |  |  | 620.9 |  | 2027-06-30 |  |  | CIPP |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Moderate to severe cracks at 12 oclcok through every unit. Proposed: CIPP line or Remove and replace pedning hydro. Final: Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133629&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133629 | B52 -ST-NL-Birralee-106.330km | CU300539 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 924000 | Newlands | BIRRALEE |  | 0 | KM | NL01ML106 | 0.33 | NL01ML106 | 0.33 | KM |  |  |  |  | 106.33 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Culverts moving apart and letting material fall through approx moving apart up to 75mm. Reinf exposed at joint due to broken recessed joint Proposed: CIPP may be an options, however concerned about subgrade issues with opening of joints. Underbore new RCP may also be an option. Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043847&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000043847 | B52 -ST-BW-Umolo-142.700km | CU100285 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 3000000 | Blackwater | BW-CL |  | 0 | KM | BW03ML142 | 0.6999 | BW03ML142 | 0.6999 | KM |  |  |  |  | 142.7 |  | 2027-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: cracking throughout pipes under up road. Minor to mod cracks in 1-1,1-2,11-4,12-5,15-1,21-2 severe in 1.2 Proposed: CIPP lining to strengthen Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100363&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100363 | B52 -ST-BW-Umolo-147.200km | CU100350 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 2145000 | Blackwater | BW-CL |  | 0 | KM | BW03ML147 | 0.2 | BW03ML147 | 0.2 | KM |  |  |  |  | 147.2 |  | 2028-06-30 |  |  | CIPP OR GRP LINING |  | 4 | 2.3 | 3 | 3.6 | 1 | 14.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Minor to Severe cracking throughout. Designed slightly earlier in case reactive orks need to some of worst cells. Proposed: Consider for CIPP lining (max 1600 <(>&<)> grout annulus), otherwise consider for GRP, if not suitable remove and replace. Final: Drawing: Risk: Mod-High Reason: Moderate to severe horizontal cracking in RCP are difficult to repair and reinforcement tends to be corroded quite quickly and cracks tend to be full depth due to the relative thin wall tichkness meaning injection is not possible. To renew this asset without a closure lining is worth catching a little earlier.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133683&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000133683 | B52 -ST-MA-Parana-004.340km | CU400154 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 150000 | Moura | PARANA |  | 0 | KM | MA01ML4 | 0.34 | MA01ML4 | 0.34 | KM |  |  |  |  | 4.34 |  | 2027-06-30 |  |  | CIPP |  | 4 | 1.3 | 3 | 3.2 | 1 | 12.8 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: Severe corrosion in invert, holes regularly allow culvert. LHS under access rd upgraded with rcp but under track still an issue Proposed: CIPP lining preferred to be confirmed by hydro. Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133502&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000133502 | B52 -ST-GA-South Walker-131.090km | CU201090 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 739000 | Goonyella | SOUTH WALKER |  | 0 | KM | GA01ML131 | 0.0899 | GA01ML131 | 0.0899 | KM |  |  |  |  | 131.09 |  | 2027-06-30 |  |  | CIPP |  | 3.5 | 4.7 | 3 | 4.4 | 1 | 15.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON-MRSB | 20270630 | Defect: Misalignment in units 1-3. Failed head wall on RHS. Proposed: CIPP Lining if possible with misalignment and potential associated ground issue. Otherwise remove and replace. Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100356&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000100356 | B12 -ST-BW-Umolo-147.940km | BR100659 | CIVIL | STRUCTURES | RELEIVING SLAB | DESIGN | 1 | SITE | 33402 | Blackwater | BW-CL |  | 0.064 | KM | BW03ML147 | 0.9399 | BW03ML147 | 1.004 | KM |  |  |  |  | 147.94 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.8 | 4 | 3.8 | 1 | 11.5 |  | 2023-03-31 |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270630 | Defect: Relieving slab looks to be moving, damaged ballast wall. Joint covers at abutment moved away from girders causing them to fall down. Upgrade in next rollout Proposed: Replace Relieving slab and improve sugrade to prevent sinking. Reapir ballast wall and provide longer joint covers. Should be done with rollout Final: Drawing: Risk: Moderate Reason: deteriorated releiving slabs lead to top of line issues with the bridge and can contribute to ballast deterioration and more resurfacing requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131120&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000131120 | C21 NORWICH PARK 90.594 - 92.500 | GA-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.906 | TRACK KM | 2810908 | Goonyella | LAKE VERMONT | NORWICH PARK | 1.9059 | KM | GA03ML90 | 0.5939 | GA03ML92 | 0.5 | KM | 36 | 2783 | 3.888 | 1.906 | 90.594 | 92.5 | 2026-06-30 | SINGLE | BOTH |  |  | 3.1 | 1.4 | 1 | 1.9 | 1 | 5.89 |  |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131121&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000131121 | C21 NORWICH PARK 93.184 - 101.506 | GA-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 8.322 | TRACK KM | 12273019 | Goonyella | LAKE VERMONT | NORWICH PARK | 8.3209 | KM | GA03ML93 | 0.1839 | GA03ML101 | 0.506 | KM | 155 | 17989 | 16.74 | 8.322 | 93.184 | 101.56 | 2026-06-30 | SINGLE | BOTH |  |  | 3.1 | 1.4 | 1 | 1.9 | 1 | 5.89 |  |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131122&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000131122 | C21 NORWICH PARK 103.06 - 108.011 | GA-03ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 4.951 | TRACK KM | 7301576 | Goonyella | LAKE VERMONT | NORWICH PARK | 4.9509 | KM | GA03ML103 | 0.0599 | GA03ML108 | 0.0109 | KM | 92 | 7068 | 9.936 | 4.841 | 103.06 | 108.011 | 2026-06-30 | SINGLE | BOTH |  |  | 3.1 | 1.4 | 1 | 1.9 | 1 | 5.89 |  |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110845&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000110845 | C21 MINDI-SOUTHWALKER 124.696-125.720 | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.024 | TRACK KM | 1510162 | Goonyella | MIDDLEMOUNT | GERMAN CREEK | 1.0169 | KM | GA01ML124 | 0.6959 | GA01ML125 | 0.7199 | KM | 19 | 1452 | 2.052 | 1.024 | 124.696 | 125.72 | 2026-06-30 | DOWN | BOTH |  |  | 3.5 | 1.4 | 1 | 1.9 | 1 | 6.65 |  |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Tie into 2015 RR - Cut in end Cut out end stopping before Bridge 200996 Equality 124km 993m = 125km (-7m)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114432&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000114432 | C21 BRAESIDE-MINDI DN 122.260-123.389KM | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.128 | TRACK KM | 1860267 | Goonyella | NORWICH PARK | MIDDLEMOUNT | 1.1279 | KM | GA01ML122 | 0.26 | GA01ML123 | 0.389 | KM | 21 | 1644 | 2.268 | 1.129 | 122.26 | 123.389 | 2026-06-30 | DOWN | BOTH |  |  | 3.8 | 1.5 | 1 | 3.8 | 1 | 7.6 |  |  |  | Track Upgrade | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | FATIGUE SCOPE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115809&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal GAPE Traffic | FUTURE SCOPE | COAL | 002000115809 | TURNOUTS ¦ DESIGN ¦ IFC ¦ LR12A | TO000135 | CIVIL | TURNOUTS |  | DESIGN | 1 | TURNOUT | 6480 | Newlands | LEICHARDT RANGE | LR12A | 0.05 | KM | NL01ML153 | 0.5759 | NL01ML153 | 0.626 | KM |  |  |  |  | 153.627 | 153.677 | 2027-06-30 |  |  |  |  | 2 | 3 | 3.5 | 4 |  | 12.3 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFC due by FY25, FY26 Construction. Heany Mainteance - Crossing replacement + some signalling modification POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH Major Component - Crossing (from RBM to SNX steel and supporting signinalling design). 01/11/2023 PCR 5771. Projet construction is deferred and as well as DESIGN IFP and IFC to keep the project timeline aligned.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124101&DY_MAB=X&~OKCODE=ONLI | FY27 |  | REACTIVE RENEWALS | COAL | 002000124101 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 3493875 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124102&DY_MAB=X&~OKCODE=ONLI | FY27 |  | REACTIVE RENEWALS | COAL | 002000124102 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 3811500 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124103&DY_MAB=X&~OKCODE=ONLI | FY27 |  | REACTIVE RENEWALS | COAL | 002000124103 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 698775 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124104&DY_MAB=X&~OKCODE=ONLI | FY27 |  | REACTIVE RENEWALS | COAL | 002000124104 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 698775 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123744&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000123744 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ AE11C/D | TO000851 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | AMBROSE | AE 11C/D | 0.049 | KM | BW01ML570 | 0.111 | BW01ML570 | 0.16 | KM |  |  |  |  | 568.002 | 567.962 | 2027-06-30 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 14.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270724 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115841&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000115841 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ AE12A/B | TO000850 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | AMBROSE | AE 12A/B | 0.04 | KM | BW01ML570 | 0.334 | BW01ML570 | 0.2939 | KM |  |  |  |  | 568.002 | 567.962 | 2027-06-30 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 14.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123741&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000123741 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ AE11A/B | TO000904 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | AMBROSE | AE11A/B | 0.048 | KM | BW02ML570 | 0.2099 | BW02ML570 | 0.162 | KM |  |  |  |  | 568.002 | 567.962 | 2027-06-30 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 14.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123498&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000123498 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ AE12C/D | TO000905 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | AMBROSE | AE12C/D | 0.05 | KM | BW02ML570 | 0.232 | BW02ML570 | 0.2819 | KM |  |  |  |  | 568.002 | 567.962 | 2027-06-30 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 14.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (11/08//2023) PCR-5717 Ambrose 12A/B design/construction be deferred by one year allowing holistic designs be developed Currently: FY24 - IFP; FY25 - IFC; and FY26 - construction Proposed: FY25 - IFP; FY26 - IFC; and FY27 - construction
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138737&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000138737 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦BFER3.3D | TO000738 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1080000 | Blackwater | BLUFF | ER3.3D | 0.0259 | KM | BW04PL169 | 0.897 | BW04PL169 | 0.8709 | KM |  |  |  |  | 169.897 | 169.897 | 2027-06-30 |  |  | 169.942 |  | 5 | 4 | 3 | 4 | 1 | 21 |  |  |  | Turnout Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Alex Rohweder (R872340) Std Design w/ Bespoke Elements - FY25 design Change Board and PCR is required. HIstoric MIC (MIC-CIV-2019-09) is no longer effective - exprired engineering control (2019) - due to the temporary nature of the MIC and operational risks due to asset condition (and location) criticality. Stage 1 bluff loop turnout permanant solution (Stage 2 - permanant Level crossing solution).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115856&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115856 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦HDER1.2A | TO000273 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Goonyella | HATFIELD | HD ER1.2A | 0.0369 | KM | GA01ML49 | 0.334 | GA01ML49 | 0.3709 | KM |  |  |  |  | 127.108 | 127.18 | 2027-06-30 |  |  |  |  | 3.5 | 5 | 4.8 | 5 |  | 16.8 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115855&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115855 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦HDER2.2B | TO000329 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Goonyella | HATFIELD | HD ER2.2B | 0.035 | KM | GA02ML49 | 0.331 | GA02ML49 | 0.3659 | KM |  |  |  |  | 127.264 | 127.193 | 2027-06-30 |  |  | POINTS & X 60KG/M 12 CS 400UHC |  | 3.5 | 5 | 4.8 | 5 |  | 16.8 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 25 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder 9R872340)24/01/2024 PCR5779 agreed with PM, Original schedule: IFPs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 28th Feb 2025 (FY25) IFCs - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 1st May 2026 (FY26) Construction - SOUTH WALKER SW 7AB <(>&<)> SW 7CD are to be released by 30 June 2027 (FY27) Revised schedule: IFPs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 28th Feb 2025 (FY25) IFCs - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 1st May 2026 (FY26) Construction - Hatfield HDER2.2B <(>&<)> HDER2.2A are to be released by 30 June 2027 (FY27)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115859&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115859 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ HD11A/B | TO000328 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Goonyella | HATFIELD | HD11A/B | 0.048 | KM | GA02ML49 | 0.8729 | GA02ML49 | 0.8249 | KM |  |  |  |  | 49.753 | 49.705 | 2027-06-30 |  |  |  |  | 4 | 4 | 4 | 5 | 1 | 19.2 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFC due by 30 June 2025, FY26 Construction. Three TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115858&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115858 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ HD12A/B | TO000261 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Goonyella | HATFIELD | HD12A/B | 0.048 | KM | GA35XR49 | 0.775 | GA35XR49 | 0.8229 | KM |  |  |  |  | 49.775 | 49.823 | 2027-06-30 |  |  |  |  | 4 | 4 | 4 | 3 | 1 | 19.2 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFC due by 30 June 2025, FY26 Construction. Three TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27. PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates. Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115857&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115857 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ HD12C/D | TO000207 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Goonyella | HATFIELD | HD12C/D | 0.049 | KM | GA01ML49 | 0.922 | GA01ML49 | 0.8729 | KM |  |  |  |  | 49.8 | 49.751 | 2027-06-30 |  |  |  |  | 3.5 | 4 | 4 | 4 | 1 | 16.8 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFC due by 30 June 2025, FY26 ConstructionThree TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) Alex Rohweder (R872340) 21 03 2024 IFP in FY24 is not accepted by Scope turnoutover to IFC in FY25 and Construct in FY27. The existing IFP due date is extended out to 30.02.2025 (FY25), IFC to FY26 and Construction FY27 (TBC). PCR and Change Board is due, and there is no alternative option but to extend the IFP version 2 dates, if to renew these turnouts.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115827&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000115827 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ ML 10A | TO000910 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | MT LARCOM | ML10A | 0.0359 | KM | BW02ML564 | 0.885 | BW02ML564 | 0.921 | KM |  |  |  |  | 562.963 | 562.999 | 2027-06-30 |  |  |  |  | 3.5 | 3 | 4.1 | 3 |  | 13.5 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | IFP due by FY24, IFC due by FY25, FY26 Construction POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077233&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000077233 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦YNER2.2B | TO000443 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1000000 | Goonyella | YUKAN | ER2.2B | 0.0219 | KM | GA01ML29 | 0.2839 | GA01ML29 | 0.262 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.5 | [8 empty] | Turnout Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 13.05.2021 11:19:28 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Alex Rohweder TOR construction incorrectly captured in FY25. Moved to FY27. Allocate to the correct asset renewal construction dates paired with the design requriements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124127&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124127 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH210A | TO001157 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW17YR0 | 0.378 | BW17YR0 | 0.406 | KM |  |  |  |  | 0.378 | [21 empty] | Outstanding notification | NWSC |  | 20270527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124124&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124124 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH213B | TO001156 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH |  | 0.0269 | KM | BW17YR0 | 0.466 | BW17YR0 | 0.439 | KM |  |  |  |  | 0.466 | [21 empty] | Outstanding notification | NWSC |  | 20270527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124130&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124130 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH211A | TO001159 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH | CH 211A | 0.016 | KM | BW17YR0 | 0.2999 | BW17YR0 | 0.316 | KM |  |  |  |  | 0.3 | [21 empty] | Outstanding notification | NWSC |  | 20270527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124121&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124121 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 213A | TO001174 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH | CH 213A | 0.028 | KM | BW20YR0 | 0.4099 | BW20YR0 | 0.438 | KM |  |  |  |  | 0.41 | [21 empty] | Outstanding notification | NWSC |  | 20270527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115846&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000115846 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BL 9A | TO000572 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 68273 | Blackwater | BAJOOL | BL 9A | 0.0299 | KM | BW01ML605 | 0.5649 | BW01ML605 | 0.535 | KM |  |  |  |  | 603.078 | 603.048 | 2027-05-27 |  |  |  |  | 3.5 | 4 | 4.2 | 4 |  | 14.7 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270527 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 22/11/2023 Alex Rohweder (R872340) Change to Design FY to better align with Construction year (that suits corporate budget). IFP from FY24 to FY27. IFC from FY26 to FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115825&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000115825 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BL 9B | TO000918 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 68273 | Blackwater | BAJOOL | BL 9B | 0.021 | KM | BW02PL605 | 0.4929 | BW02PL605 | 0.514 | KM |  |  |  |  | 605.493 | 605.514 | 2027-05-27 |  |  |  |  | 3.5 | 4 | 3.9 | 4 |  | 14.7 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270527 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM MO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (R872340) TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ BL9B FY25 IFP - $41,850 FY26 IFC - $41,850 FY27 CONST 22/11/2023 Alex Rohweder (R872340) Change to Design FY to better align with Construction year (that suits corporate budget). IFP from FY24 to FY27.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115824&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000115824 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BL 46A | TO000919 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 68273 | Blackwater | BAJOOL | BL46A | 0.0219 | KM | BW02PL605 | 0.4779 | BW02PL605 | 0.456 | KM |  |  |  |  | 605.478 | 605.456 | 2027-05-27 |  |  | POINTS & X 60KG/M 12 CS SWCMN |  | 3.5 | 4 | 3.9 | 4 |  | 13.7 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270527 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 22/11/2023 Alex Rohweder (R872340) Change to Design FY to better align with Construction year (that suits corporate budget). IFP from FY24 to FY27. IFC from FY26 to FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052826&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000052826 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 212A | TO001158 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 53550 | Blackwater | CALLEMONDAH | CH 212A | 0 | KM | BW17YR0 | 0.326 | BW17YR0 | 0.326 | KM | [6 empty] | 2027-05-27 |  |  |  |  | 4 | 1 |  |  |  | 4 | 4882 | 2022-03-31 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270527 | * 28.02.2020 13:39:11 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade turnout rail size * 16.10.2020 12:49:33 AUSQLD Lachlan Prescott (R881571) * Correction: FY22 execution (subject to design and possessions) * 10.05.2021 11:03:08 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124050&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124050 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 212B | TO001173 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 53550 | Blackwater | CALLEMONDAH | CH 212B | 0.032 | KM | BW20YR0 | 0.402 | BW20YR0 | 0.3699 | KM | [6 empty] | 2027-05-27 |  |  |  |  | 4 | 1 |  |  |  | 4 | 4882 | 2022-03-31 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | 28.02.2020 13:39:24 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution 16.10.2020 12:53:10 AUSQLD Lachlan Prescott (R881571) Correction: FY22 execution (subject to design and possessions) 10.05.2021 11:03:09 AUSQLD Lachlan Prescott (R881571) To be moved to FY23 pending PCR4882
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124866&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124866 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 233A | TO001175 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 53550 | Blackwater | CALLEMONDAH | CH 233A | 0.029 | KM | BW20YR0 | 0.511 | BW20YR0 | 0.54 | KM | [6 empty] | 2027-05-27 |  |  |  |  | 4 | 4.8 |  |  |  | 17.6 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | 30.09.2020 07:09:28 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044002
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124861&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124861 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 233B | TO001181 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 53550 | Blackwater | CALLEMONDAH | CH 233B | 0.0259 | KM | BW07XR0 | 0.6079 | BW07XR0 | 0.5819 | KM | [6 empty] | 2026-02-27 |  |  |  |  | 4 | 4.8 |  |  |  | 19.36 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | 30.09.2020 07:09:51 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044003 Alex Rohweder (R872340) Design IFP 26, IFC - FY27, CONSTRUCT - FY30
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123828&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000123828 | TURNOUTS ¦ DESIGN ¦ IFC ¦ DA 12A/B | TO000119 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 53550 | Newlands | DURROBURRA | 12A/B | 0.0709 | KM | NL02ML0 | -0.2099 | NL02ML0 | -0.139 | KM |  |  |  |  | 12.3 |  | 2027-05-27 |  |  |  |  | 3 | [6 empty] | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270725 | TURNOUTS ¦ DESIGN ¦ IFC ¦ DA 12A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $18,740 out of $187,400 30.03.2022 Alex Rohweder (R872349( Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123827&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000123827 | TURNOUTS ¦ DESIGN ¦ IFC ¦ DA 10A/B | TO000151 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 59500 | Newlands | DURROBURRA | DA 10A/B | 0.05 | KM | NC03ML1158 | 0.4979 | NC03ML1158 | 0.448 | KM |  |  |  |  | 1158.498 |  | 2027-05-27 |  |  |  |  | 3.5 | 2.5 | 4 | 4.1 |  | 14.35 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270527 | TURNOUTS ¦ EARLY DESIGN ¦ IFC ¦ DA 10A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction. 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $11,900 out of $119,000 30.03.2022 Alex Rohweder (R872349) Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133957&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal GAPE Traffic | FUTURE SCOPE | COAL | 002000133957 | TURNOUTS ¦ DESIGN ¦ IFC ¦ LR12A | TO000135 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 12960 | Newlands | LEICHARDT RANGE | LR12A | 0.05 | KM | NL01ML153 | 0.5759 | NL01ML153 | 0.626 | KM | [6 empty] | 2027-05-27 |  |  | SNX |  | 4 | 3 | 3.5 | 4 |  | 12.3 | 4882 | 2022-03-31 | 2020-11-13 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | 28.02.2020 13:41:28 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:05:36 AUSQLD Lachlan Prescott (R881571) To be moved to FY25 pending PCR4882 FY24 Design budget adjusted to 10% off the total design budget = $25,000 out of $50,000 28.02.2020 13:41:28 AUSQLD Peter Rayner (R003851) Design to be completed in FY22 for FY23 execution. Work is to upgrade vee to SNX 10.05.2021 11:05:36 AUSQLD Lachlan Prescott (R881571) To be moved to FY25 pending PCR4882 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY25 construction. TURNOUTS ¦ DETAILED DESIGN ¦ RENEWAL ¦LR12A 11/01/2023 Alex Rohweder (R972340) FY24 IFC, FY26 Construction. CROSSING REPLACEMENT ONLY RBM to SNX, Bundle with LR7A, very simular configuration. FY24 Design budget adjusted to 10% off the total design budget = $25,000 out of $50,000
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115810&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal GAPE Traffic | FUTURE SCOPE | COAL | 002000115810 | TURNOUTS ¦ DESIGN ¦ IFC ¦ LR7A | TO000136 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 12960 | Newlands | LEICHARDT RANGE | LR7A | 0.049 | KM | NL01ML155 | 0.4799 | NL01ML155 | 0.4309 | KM |  |  |  |  | 155.53 | 155.481 | 2202-05-27 |  |  |  |  | 2 | 3 | 3.5 | 4 |  | 12.3 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | IFC due by FY25, FY26 Construction. Heany Mainteance - Crossing replacement + some signalling modification POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH Major Component - Crossing (from RBM to SNX steel and supporting signinalling design). ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115852&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000115852 | TURNOUTS ¦ DESIGN ¦ IFC ¦ ME 11C/D | TO000840 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 71400 | Blackwater | MIDGEE | MIER1.2A | 0.0439 | KM | BW01ML623 | 0.137 | BW01ML623 | 0.1809 | KM |  |  |  |  | 620.653 | 620.697 | 2027-05-27 |  |  |  |  | 4 | 4 | 4.2 | 3 |  | 16.5 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115845&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | FUTURE SCOPE | COAL | 002000115845 | TURNOUTS ¦ DESIGN ¦ IFC ¦ ME 11A/B | TO000876 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 99201 | Blackwater | MIDGEE | MIER1.2A | 0.047 | KM | BW02ML623 | 0.2349 | BW02ML623 | 0.188 | KM |  |  |  |  | 621.092 | 621.045 | 2027-05-27 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 12.6 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270527 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121156&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000121156 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WA 10C | TO000369 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 75330 | Goonyella | WAITARA | WA 10C | 0.033 | KM | GA02PL100 | 0.453 | GA02PL100 | 0.4199 | KM | [6 empty] | 2026-05-01 |  |  |  |  | 2 | 4.4 |  |  |  | 17.6 | 5669 | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20270501 | 30.09.2020 07:10:13 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000044004 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124990&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124990 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WA 12A | TO001028 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 28692 | Goonyella | WAITARA | WA 12A | 0.047 | KM | GA46XR100 | 0.4829 | GA46XR100 | 0.53 | KM | [6 empty] | 2027-05-27 |  |  |  |  | 3 | 5 |  |  |  | 14.4 | 5669 | 2021-03-31 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20270527 | 30.09.2020 06:59:51 AUSQLD Peter Rayner (R003851) Design to be completed in FY23 for FY24 execution. Construction notification N4 is 002000043322 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) 27/07/2023 Alex Rohweder (R872340) Extend the IFP and IFC due date as per the planned construction dates. PCR - 5669 Recommended change from PM - IFP due 28th Feb 2025 (FY25); - IFC due 1st May 2026 (FY26) Why: Construction is cited in the SPM as FY28. Asset Mgr confirmed FY28 construction <(>&<)> and FY27 required for preconstruction etc. activities. Note: WA 10C <(>&<)> WA12A construction remains unchanged being FY28 WA 10C <(>&<)> WA12A construction remains unchanged being FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124177&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124177 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BFER3.2E | TO000739 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | BLUFF |  | 0.0229 | KM | BW04PL169 | 0.5979 | BW04PL169 | 0.6209 | KM |  |  |  |  | 169.598 |  | 2027-02-27 |  |  |  |  | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20270227 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Remove TO000742 (169.645KM ER3.2E(SDG) TURNOUT BLUFF) as part of the renewal. Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124174&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124174 | TURNOUTS ¦ DESIGN ¦ IFP ¦ BFER3.3D | TO000738 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | BLUFF |  | 0.0259 | KM | BW04PL169 | 0.897 | BW04PL169 | 0.8709 | KM |  |  |  |  | 169.897 |  | 2027-02-27 |  |  |  |  | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20270227 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124180&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000124180 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH205A | TO001155 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW17YR0 | 0.4829 | BW17YR0 | 0.511 | KM |  |  |  |  | 0.483 | [21 empty] | Outstanding notification | NWSC |  | 20270227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124171&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124171 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 214A | TO001172 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | CALLEMONDAH | CH 214A | 0.029 | KM | BW08YR533 | 0.779 | BW08YR533 | 0.808 | KM |  |  |  |  | 533.779 | [21 empty] | Outstanding notification | NWSC |  | 20270227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124186&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124186 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 215B | TO001177 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | CALLEMONDAH | CH 215B | 0.028 | KM | BW21YR0 | 0.127 | BW21YR0 | 0.099 | KM |  |  |  |  | 0.127 | [21 empty] | Outstanding notification | NWSC |  | 20270227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094141&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000094141 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 217A/B | TO001183 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 71000 | Blackwater | CALLEMONDAH | 217 A/B | 0.032 | KM | BW21YR2 | 0.3119 | BW21YR2 | 0.28 | KM |  |  |  |  | 534.698 |  | 2027-02-27 |  |  |  |  | 3 | 5 |  |  |  | 12.3 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20270227 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 217A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 235A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over to CH217 turnout (from CH 274). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts. PCR 5349 PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124055&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124055 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 235A/B | TO001182 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 71000 | Blackwater | CALLEMONDAH | 235A/B | 0.0309 | KM | BW21YR2 | 0.199 | BW21YR2 | 0.168 | KM |  |  |  |  | 2.178 | 2.147 | 2027-02-27 |  |  |  |  | 3 | 5 |  |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270227 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 235A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over with CH 235A/B turnout (from CH 276A). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124070&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000124070 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 281A/B | TO001139 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 71000 | Blackwater | CALLEMONDAH | 281A/B | 0.033 | KM | BW11BL2 | 0.4949 | BW11BL2 | 0.528 | KM |  |  |  |  | 2.495 | 2.528 | 2027-02-27 |  |  |  |  | 4.2 | 5 |  |  |  | 14.7 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270227 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CH 281A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115804&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000115804 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WA46A | TO000697 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 43550 | Blackwater | WARREN | WA46A | 0.0379 | KM | BW04ML25 | 0.444 | BW04ML25 | 0.406 | KM | [6 empty] | 2027-02-27 |  |  |  |  | 3.5 | 3.5 | 3.3 | 4 | 1 | 14.35 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270304 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM TR RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) Deferred IFP to FY27 and IFC to FY28 to align with Construction in FY29
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118523&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000118523 | TURNOUTS ¦ DESIGN ¦ IFP¦ WA45A | TO000698 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 43550 | Blackwater | WARREN | WR45A | 0.0359 | KM | BW04ML25 | 0.541 | BW04ML25 | 0.505 | KM |  |  |  |  | 24.536 | 24.5 | 2027-05-27 |  |  |  |  | 3.5 | 3.5 | 4.1 | 3 | 1 | 14.35 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270304 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115850&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000115850 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WD 7B/C | TO000670 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 93700 | Blackwater | WESTWOOD | WD7B/C | 0.0369 | KM | BW03ML47 | 0.505 | BW03ML47 | 0.468 | KM |  |  |  |  | 46.507 | 46.47 | 2027-06-30 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 12.6 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270227 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115851&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000115851 | TURNOUTS ¦ DESIGN ¦ IFP ¦ WD ER1.2A | TO000705 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 84330 | Blackwater | WESTWOOD | WDER1.2A | 0.0359 | KM | BW04ML46 | 0.767 | BW04ML46 | 0.7309 | KM |  |  |  |  | 45.774 | 45.738 | 2027-02-27 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 13.5 |  | 2023-09-01 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20270630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085760&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085760 | Asset Protection Renewal BW | BW | CONTROL SYSTEMS | ASSET PROTECTION | ALL | RENEWAL | 1 | UNIT | 1642000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085761&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085761 | Asset Protection Renewal GA | GA | CONTROL SYSTEMS | ASSET PROTECTION | ALL | RENEWAL | 1 | UNIT | 2642000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137028&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000137028 | CS MA CCTV Design 1 Site | MA | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | DESIGN | 1 | SITE | 20000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 2 | 2 | 1 | 8 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20260630 | Site is Jefferis Road.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136848&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000136848 | CS Auckland Street CCTV Renewal | LX000786-34 | CONTROL SYSTEMS | ASSET PROTECTION | CCTV | RENEWAL | 1 | SITE | 50000 | Moura | AUCKLAND STREET | AUCKLAND STREET | 0 | KM | NC02ML529 | 0.5659 | NC02ML529 | 0.5659 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 2 |  | 2 | 1 | 8 |  |  |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115471&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115471 | Wotonga HBD Renewal | ST005400-07 | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | RENEWAL | 1 | UNIT | 820000 | Goonyella | WOTONGA |  | 0 | KM | GA01ML173 | 0.8169 | GA01ML173 | 0.8169 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 5 |  | 1 | 1 | 10 |  |  |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137021&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000137021 | MA RMS Scada Contribution | MA | CONTROL SYSTEMS | ASSET PROTECTION | RMS SCADA | RENEWAL | 1 | SYSTEM | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 5 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137022&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000137022 | NL RMS Scada Contrib | NL | CONTROL SYSTEMS | ASSET PROTECTION | RMS SCADA | RENEWAL | 1 | SYSTEM | 10000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 2 | 5 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115370&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000115370 | Boorgoon Weighbridge Renewal | ST002460-01 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHER | RENEWAL | 1 | UNIT | 1110000 | Blackwater | BOORGOON | BOORGOON | 0 | KM | BW23ML2 | 0.23 | BW23ML2 | 0.23 | KM |  |  |  |  | 2.23 | 2.23 | 2026-06-30 |  |  |  |  | 4 | 4.8 |  | 4.8 | 1 | 19.2 |  | 2023-09-01 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | HIGH | HIGH | Outstanding notification | SCPR |  | 20260630 | Boorgoon Weighbridge Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085335&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000085335 | CSI Equipment Room Renewal | ST006290 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 300000 | Blackwater | ARCHER CER | ARCHER CER | 0 | KM | BW01ML614 | 0.9839 | BW01ML614 | 0.9839 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 5 |  | 5 |  | 25 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090598&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000090598 | CS CER Relocation Balook | ST003880 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 200000 | Goonyella | BALOOK CER | BALOOK CER | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | RRIG |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090668&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000090668 | CS CER Relocation | ST004540 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 220000 | Goonyella | BRAESIDE CER | BRAESIDE CER | 0 | KM | GA01ML107 | 0.6949 | GA01ML107 | 0.6949 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105945&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105945 | CS Equipment Room Renewal | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 200000 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105947&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105947 | CS Equipment Room Renewal | ST003460 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 600000 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 4 | 1 | 4 | 1 | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090669&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000090669 | CS CER Relocation | ST004820 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 220000 | Goonyella | MINDI CER | MINDI CER | 0 | KM | GA01ML120 | 0.445 | GA01ML120 | 0.445 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101394&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101394 | CSI Dehydrator Renewal | ST005520-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Blackwater | BLUFF | BLUFF | 0 | KM | BW54CR0 | 0 | BW54CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101393&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101393 | CSI Dehydrator Renewal | ST002940-18 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Blackwater | CLERMONT | CLERMONT | 0 | KM | BW03ML100 | 0.26 | BW03ML100 | 0.26 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085400&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085400 | CSI Dehydrator Renewal | ST005540-31 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Blackwater | GOGANGO MWR | GOGANGO MWR | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085379&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085379 | CSI Dehydrator Renewal | ST005960-12 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 40000 | Goonyella | NANYA MWR | NANYA MWR | 0 | KM | GA42CR0 | 0 | GA42CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085420&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085420 | CSI Generator Renewal | ST006020-81 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 160000 | Goonyella | COPPABELLA MW | COPPABELLA MW | 0 | KM | GA01ML145 | 0.2999 | GA01ML145 | 0.2999 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078692&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000078692 | CSI Generator Renewal | ST003020-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 170000 | Blackwater | EMERALD | EMERALD | 0 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  |  | 2021-10-05 | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Notification in process | RRIG | FY23 IN | 20270630 | * 10.06.2021 17:23:11 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085430&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085430 | CSI NMS Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 140000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085429&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085429 | CSI NMS Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086583&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000086583 | CSI OF Renewal | ST008540-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1700 | METERS | 153000 | Goonyella | BIDGERLEY MI0 | BIDGERLEY SER | 1.7099 | KM | GA06ML6 | 0.2999 | GA06ML8 | 0.01 | KM |  |  |  |  | 6.301 | 8.011 | 2026-06-30 |  |  |  |  | 10 | 1.2 | 1 | 10 | 1 | 100 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086914&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000086914 | CSI OF Renewal | ST008540-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 90000 | Goonyella | BIDGERLEY MI0 | HAIL CREEK AT SOUTH | 0.014 | KM | GA06ML6 | 0.2999 | GA06ML6 | 0.2859 | KM |  |  |  |  | 6.301 | 6.287 | 2026-06-30 |  |  |  |  | 10 | 1.2 | 1 | 10 | 1 | 100 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086586&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086586 | CSI OF Renewal | ST003910-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 700000 | Goonyella | BLACK MOUNTAIN SER | HATFIELD AT | 4.6879 | KM | GA01ML40 | 0.936 | GA01ML45 | 0.6199 | KM | [6 empty] | 2027-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086585&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086585 | CSI OF Renewal | ST007490-50 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5500 | METERS | 770000 | Goonyella | BLACK MOUNTAIN TSC | BLACK MOUNTAIN SER | 5.4919 | KM | GA01ML35 | 0.4829 | GA01ML40 | 0.9599 | KM | [6 empty] | 2027-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086524&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000086524 | CSI OF Renewal | ST006130-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 120000 | Blackwater | BOONAL MIE |  | 0.9379 | KM | BW03ML178 | 0.5 | BW03ML179 | 0.439 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086587&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000086587 | CSI OF Renewal | ST005780-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4500 | METERS | 630000 | Goonyella | HATFIELD AT | HATFIELD SER | 4.54 | KM | GA01ML45 | 0.225 | GA01ML49 | 0.76 | KM | [6 empty] | 2027-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086911&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000086911 | CSI OF Renewal | ST006160-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4000 | METERS | 480000 | Blackwater | TIKARDI CER | BOORGOON CER | 4.0529 | KM | BW05ML5 | 0.511 | BW05ML9 | 0.56 | KM |  |  |  |  | 5.504 | 9.557 | 2026-06-30 |  |  |  |  | 10 | 1.2 | 1 | 10 | 1 | 100 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085351&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085351 | CSI Radome Renewal FY26 | MA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 58000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  |  |  | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085352&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085352 | CSI Radome Renewal FY26 | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 58000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  |  |  | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085359&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085359 | CSI Radome Renewal FY27 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 60000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085358&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085358 | CSI Radome Renewal FY27 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 60000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085355&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085355 | CSI Radome Renewal FY27 | MA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 60000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085356&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085356 | CSI Radome Renewal FY27 | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 60000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085558&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085558 | CSI Structure Renewal | ST006380-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 20000 | Goonyella | BLAIR ATHOL |  | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085559&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085559 | CSI Structure Renewal | ST005950-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 20000 | Blackwater | CAPELLA |  | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085556&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085556 | CSI Structure Renewal | ST005280-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 20000 | Blackwater | CROCKER PEAK |  | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085557&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085557 | CSI Structure Renewal | ST005510-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 20000 | Blackwater | GREGORY |  | 0 | KM | BW08ML62 | 0.2469 | BW08ML62 | 0.2469 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085554&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000085554 | CSI Structure Renewal | ST006260-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 200000 | Blackwater | RAGLAN SOUTH |  | 0 | KM | BW01ML582 | 0.439 | BW01ML582 | 0.439 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085555&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085555 | CSI Structure Renewal | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 20000 | Blackwater | WALLAROO |  | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137348&DY_MAB=X&~OKCODE=ONLI | FY27 |  | STRATEGIC | COAL | 002000137348 | Cyber Security Strengthening FY26 | MA | CONTROL SYSTEMS | CYBER SECURITY STRENGTHENING |  | RENEWAL | 1 | SYSTEM | 20000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [13 empty] | Transmission & Data Renewals | STRATEGIC |  |  |  |  | Outstanding notification | NWSC |  | 20250228
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085681&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085681 | Data Network Renewal BW | BW | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 700000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085660&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085660 | Data Network Renewal GA | GA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 700000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085715&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085715 | Data Network Renewal MA | MA | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085700&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085700 | Data Network Renewal NL | NL | CONTROL SYSTEMS | DATA NETWORK | ROUTERS SWITCHES FIREWALLS | RENEWAL | 1 | UNIT | 200000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074219&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000074219 | SIG_Interlocking Renewal - CH Stg2C_Com | ST003460-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | CALLEMONDAH STRATEGY | RENEWAL | 1 | UNIT | 500000 | Blackwater | CALLEMONDAH |  | 0 | KM | BW50CR533 | 0.9899 | BW50CR533 | 0.9899 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 16.03.2021 17:46:33 AUSQLD Robert Love (R111379) * Complete the Renewal/Commissioning phase of Callemondah Stage 2B - Install and commission the data in the SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124722&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000124722 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124065&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000124065 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124364&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000124364 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115500&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000115500 | SIG_Interlocking Renewal_GA_Balook_Bld | ST003880-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN | 1 | STATION | 1500000 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM |  |  |  |  | 74.63 | 74.63 | 2027-06-30 |  |  |  |  | 10 | 10 |  | 10 |  | 100 |  | 2023-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20270630 | This is EARLY WORKS to complete the interlocking renewal in a later year. The majority of the works will be completed in a following year. Final scope: Replace Relays with PBI, Digital Telem, Add VDRs, Split detection on crossovers, Replace SER, Replace identified signals. Associated works with separate notifications to be done in coordination with these works are M23A replacements for BK7A, BK7D, BK8A and BK8D.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065399&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000065399 | SIG_Interlocking Renewal - BO_Des | ST003940-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN | 1 | STATION | 1274432 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML60 | 0.6199 | GA01ML60 | 0.6199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 | 2021-10-05 | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Outstanding notification | RRIG | FY23 IN | 20240630 | * 28.09.2020 09:17:10 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065492&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000065492 | SIG_Interlocking Renewal_GA_Yukan_Des | ST004060-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 1040000 | Goonyella | YUKAN |  | 0 | KM | GA01ML28 | 0.806 | GA01ML28 | 0.806 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 28.09.2020 10:32:53 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073617&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000073617 | SIG_Interlocking Renewal - BW_ME_Com | ST004310-05 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 1385000 | Blackwater | MIDGEE |  | 0 | KM | BW01ML624 | 0.5899 | BW01ML624 | 0.5899 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  | HIGH | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20270630 | 30.08.2022: Rob Love - Rescheduled due to resources.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065473&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000065473 | SIG_Interlocking Renewal _GA_WO_Com | ST004050-02 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 820747 | Goonyella | WANDOO |  | 0 | KM | GA01ML85 | 0.917 | GA01ML85 | 0.917 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Outstanding notification | RRIG |  | 20270630 | * 28.09.2020 10:19:29 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104557&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000104557 | SIG_Interlocking Renewal_MA_Stowe_Des | ST003860-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | STOWE | GRAHAM | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM |  |  |  |  | 26.35 | 26.35 | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | HIGH | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | Design the replacement of VPI Graham and replacement of Graham Interlocking with Object Controller of Stowe if required. Replacement of Graham to Stirrat AzS600 axlecounter with Frauscher axlecounter from Stowe to Stirrat.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101079&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000101079 | SIG_Interlocking Renewal_MA_Stirrat_Pln | ST003830-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 114315 | Moura | STIRRAT | STIRRAT | 0 | KM | MA01ML39 | 0.404 | MA01ML39 | 0.404 | KM |  |  |  |  | 39.404 | 39.404 | 2030-06-30 |  |  |  |  | 5 | 1.2 | 5 | 5 |  | 25 |  | 2023-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20250630 | Replace Stirrat VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104805&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000104805 | SIG_Interlocking Renewal_MA_Dumgree_Com | ST003600 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 755000 | Moura | DUMGREE | DUMGREE | 0 | KM | MA01ML108 | 0.545 | MA01ML108 | 0.545 | KM |  |  |  |  | 108.545 | 108.545 | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  | 2023-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20270630 | Construction phase for the replacement of the VPI at Dumgree AND the replacement of the Annandale-Dumgree axle counter AzS600. PBI expected to be an eSmIO. Axle counter expected to be Frauscher. Working components from the removed VPI are to be placed into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094338&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000094338 | SIG_Interlocking Renewal - GA_JB_Pln | ST006030-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | WESTLOCK REPLACEMENT | ASSESSMENT | 1 | SITE | 100000 | Goonyella | JILALAN BYPASS | JILALAN | 0 | KM | GA01ML20 | 0.0299 | GA01ML20 | 0.0299 | KM | [11 empty] | 5 | 4 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20270630 | Plan the replacement of Jilalan Bypass and Jilalan Yard master interlocking. Consider technology, supplier arrangement, schedule, ch anges to housings and power supplies, interfaces to other interlockings and maintenance, and resourcing with regards to other projects.Review splitting the bypass and yard into 2 separate interlockings with separate telemetry.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060182&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060182 | SIG_Replace M23A_GA_OC10_Com | TO000475-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | OAKY CREEK | OAKY CREEK | 0 | KM | GA03ML149 | 0.635 | GA03ML149 | 0.635 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20310630 | * 23.06.2020 12:39:19 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060183&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060183 | SIG_Replace M23A_GA_OC9_Com | TO000474-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | OAKY CREEK | OAKY CREEK | 0 | KM | GA03ML149 | 0.5809 | GA03ML149 | 0.5809 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20310630 | * 23.06.2020 12:39:28 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060185&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060185 | SIG_Replace M23A_GA_PD12A_Com | TO000391-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML45 | 0.883 | GA03ML45 | 0.883 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:39:46 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060186&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060186 | SIG_Replace M23A_GA_PD12B_Com | TO000391-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML45 | 0.883 | GA03ML45 | 0.883 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:39:54 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060187&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060187 | SIG_Replace M23AMkI_GA_PD7A_Com | TO000388-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.5999 | GA03ML43 | 0.5999 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:40:03 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060188&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060188 | SIG_Replace M23AMkI_GA_PD7B_Com | TO000388-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.5999 | GA03ML43 | 0.5999 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:40:13 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060189&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060189 | SIG_Replace M23AMkI_GA_PD8A_Com | TO000387-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA03ML43 | 0.65 | GA03ML43 | 0.65 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:40:23 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060190&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060190 | SIG_Replace M23AMkI_GA_PD9_Com | TO000552-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | PEAK DOWNS | PEAK DOWNS | 0 | KM | GA17ML43 | 0.883 | GA17ML43 | 0.883 | KM | [11 empty] | 4 | [14 empty] | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:40:31 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060234&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060234 | SIG_Replace M23A_GA_WO12A_Com | TO000319-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | WANDOO | WANDOO | 0 | KM | GA02ML86 | 0.057 | GA02ML86 | 0.057 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20260630 | * 23.06.2020 12:47:01 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060235&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060235 | SIG_Replace M23A_GA_WO8A_Com | TO000215-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | WANDOO | WANDOO | 0 | KM | GA01ML85 | 0.9439 | GA01ML85 | 0.9439 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20270630 | * 23.06.2020 12:47:10 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060236&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000060236 | SIG_Replace M23A_GA_WO8C_Com | TO000321-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | WANDOO | WANDOO | 0 | KM | GA02ML86 | 0.0359 | GA02ML86 | 0.0359 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | RRIG INIF |  | 20270630 | * 23.06.2020 12:47:19 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104865&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104865 | SIG_Train Detection_NL_Almoola_Des | ST008620 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | DESIGN | 2 | UNIT | 406000 | Newlands | ALMOOLA | BRIABA | 0 | KM | NL01ML71 | 0.921 | NL01ML71 | 0.921 | KM | [11 empty] | 4 | 2 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630 | Design phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The blocks are 2 blocks btn Almoola and Briaba and a block between Briaba and Binbee. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126553&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000126553 | SIG_Train Detection_NL_Binbee_Pln | ST008070-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 6 | UNITS | 50000 | Newlands | BINBEE | ARMUNA | 8.0579 | KM | NL01ML36 | 0.1469 | NL01ML44 | 0.2089 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Commissioning phase for the replacement of both 2 Siemens AzS350U axlecounter blocks with an axlecounter. Consider how block information between Almoola and Briaba will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065529&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000065529 | SIG_Train Detection_BW_Westwood_CSEE_Des | ST004440 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 41 | UNIT | 2255000 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW03ML46 | 0.6939 | BW03ML46 | 0.6939 | KM | [6 empty] | 2022-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20270630 | * 28.09.2020 11:01:12 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065527&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000065527 | SIG_Train Detection_BW_Wycarbah_CSEE_Des | ST004480 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 40 | UNIT | 2200000 | Blackwater | WYCARBAH | WYCARBAH | 0 | KM | BW03ML36 | 0.115 | BW03ML36 | 0.115 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20260630 | * 28.09.2020 10:59:54 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC 30.08.2022: Rob Love - Rescheduled due to resources
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066594&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000066594 | SIG_Train Detection_BW_Windah_CSEE_Pln | ST000200 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | PLANNING | 18 | UNIT | 108000 | Blackwater | WINDAH |  | 0 | KM | BW03ML53 | 0.1799 | BW03ML53 | 0.1799 | KM | [11 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000139982&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000139982 | SIG_Train Detection_BW_Warren_CSEE_Com | ST005190 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 38 | UNIT | 3500000 | Blackwater | WARREN | WARREN | 0 | KM | BW03ML25 | 0.4749 | BW03ML25 | 0.4749 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4.5 | 4 | 4 | 4 | 1 | 18 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20270630 | Complete build and commission upgrade of obsolete CSEE tracks (and DC tracks) with Thales axle counters. Continuing on from the build notification 2000065526,
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065528&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000065528 | SIG_Train Detection_BW_Wycarbah_CSEE_Com | ST004480 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 40 | UNIT | 5500000 | Blackwater | WYCARBAH | WYCARBAH | 0 | KM | BW03ML36 | 0.115 | BW03ML36 | 0.115 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20270630 | * 28.09.2020 11:00:33 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125265&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000125265 | SIG_Train Detection_GA_Goonyella_ML_Des | ST004740-04 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 300000 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA13ML195 | 0.4199 | GA13ML195 | 0.4199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Planning phase to replace 5 ML track circuits in the balloon loop (freq E,F) with 2 Frauscher tracks. Tracks with ML freq are 17BBT(1xF) and 17B5AT-17BA2AT(2xE,2xF). This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103824&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000103824 | SIG_Train Detection_GA_Moorvale_ML_Des | ST006650 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 935000 | Goonyella | MOORVALE | MOORVALE | 0 | KM | GA03ML8 | 0.5999 | GA03ML8 | 0.5999 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20270630 | Replace all track circuits (primarily defunct ML tracks) with 17 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085349&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085349 | SIG_Train Detection_GA_Moorvale_ML_Pln | ST006650 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 102460 | Goonyella | MOORVALE | MOORVALE | 0 | KM | GA03ML8 | 0.5999 | GA03ML8 | 0.5999 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20260630 | Replace all track circuits (primarily defunct ML tracks) with 17 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125890&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000125890 | SIG_Train Detection_GA_Broadlea_ML_Pln | ST004580 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 120000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML156 | 0.264 | GA01ML156 | 0.264 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Replace all track circuits (primarily defunct ML tracks) with 20 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125263&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000125263 | SIG_Train Detection_GA_Ingsdon_ML_Com | ST004770-09 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 4393000 | Goonyella | INGSDON | INGSDON | 0 | KM | GA03ML11 | 0 | GA03ML11 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Replace all track circuits (primarily defunct ML tracks) with 17 axlecounter blocks. This is the Renewal phase.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104766&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000104766 | SIG_Train Detection_GA_Riverview_ML_Con | ST005050 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 600000 | Goonyella | RIVERSIDE | RIVERSIDE | 0 | KM | GA01ML200 | 0.0929 | GA01ML200 | 0.0929 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20270630 | Planning phase to replace 4 ML track circuits in the balloon loop (freq E,F) with 2 Frauscher tracks. Tracks with ML freq are 19BBT(1xE) and 19BA2-4T(1xE,2xF). Consider replacing 16CT, 19AT amd 19A1T (6 ML tracks) if cost is minimal. This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113363&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000113363 | CS Transmission DMR Planning | MA | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | PLANNING | 1 | LUMPSUM | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 1 | 3 | 1 | 12 |  | 2023-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113362&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000113362 | CS Transmission DMR Planning | NL | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | PLANNING | 1 | LUMPSUM | 15000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 4 | 4 | 1 | 3 | 1 | 12 |  | 2023-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100904&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100904 | CS Transmission DMR Link | ST005730-56 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 130000 | Newlands | COLLINSVILLE | BRIABA | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100903&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100903 | CS Transmission DMR Link | ST005540-15 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 130000 | Blackwater | GOGANGO | WALLAROO | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085528&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085528 | CS Transmission DMR Renewal | ST005900-27 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 130000 | Goonyella | SARINA | THREE SISTERS | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085527&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085527 | CS Transmission DMR Renewal | ST006270-21 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 130000 | Blackwater | TABLE MOUNTAIN | GOGANGO | 0 | KM | BW63CR0 | 0 | BW63CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101862&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101862 | CS Transmission GPS Clock | ST006120-70 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Blackwater | BLACKWATER | BLACKWATER | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101816&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101816 | CS Transmission GPS Clock | ST005730-54 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Newlands | COLLINSVILLE MWR | COLLINSVILLE MWR | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101819&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101819 | CS Transmission GPS Clock | ST006020-50 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | GA01ML144 | 0.0519 | GA01ML144 | 0.0519 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101861&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101861 | CS Transmission GPS Clock | ST005510-66 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Blackwater | GREGORY | GREGORY | 0 | KM | BW59CR0 | 0 | BW59CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101818&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101818 | CS Transmission GPS Clock | ST005860-89 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Goonyella | MACKAY | MACKAY | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101864&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101864 | CS Transmission GPS Clock | ST005580-46 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Moura | MAURICE HILL | MAURICE HILL | 0 | KM | NC07CR0 | 0 | NC07CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101860&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101860 | CS Transmission GPS Clock | ST009550-27 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Goonyella | MORANBAH | MORANBAH | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101863&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101863 | CS Transmission GPS Clock | ST005490-G1 | CONTROL SYSTEMS | TRANSMISSION | GPS CLOCK | RENEWAL | 1 | SITE | 30000 | Blackwater | ROCKHAMPTON | ROCKHAMPTON | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000096310&DY_MAB=X&~OKCODE=ONLI | FY27 |  | STRATEGIC | COAL | 002000096310 | CS Transmission IOT Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | IOT | DESIGN | 1 | LUMPSUM | 30000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 10 | 10 |  | 10 |  | 100 |  | 2023-03-31 |  | Transmission & Data Renewals | STRATEGIC | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000096312&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000096312 | CS Transmission IOT Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | IOT | DESIGN | 1 | LUMPSUM | 30000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 10 | 1 | 10 | 1 | 100 |  | 2023-03-31 |  | Transmission & Data Renewals | STRATEGIC | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100958&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100958 | CS Transmission IOT | BW | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 100000 | Blackwater | BLACKWATER STATIONS | BLACKWATER STATIONS | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [9 empty] | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100959&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100959 | CS Transmission IOT | GA | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella | GOONYELLA STATIONS | GOONYELLA STATIONS | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [9 empty] | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100957&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100957 | CS Transmission IOT | NL | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 80000 | Newlands | NEWLANDS STATIONS | NEWLANDS STATIONS | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100970&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100970 | CS Transmission IOT | NL | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 80000 | Newlands | NEWLANDS STATIONS | NEWLANDS STATIONS | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [9 empty] | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085228&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085228 | CS Transmission Power Supply | ST003990-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Goonyella |  |  | 0 | KM | GA01BA3 | 0.1469 | GA01BA3 | 0.1469 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101292&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101292 | CS Transmission Power Supply | ST008620-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Newlands | ALMOOLA SER | ALMOOLA SER | 0 | KM | NL01ML71 | 0.921 | NL01ML71 | 0.921 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101239&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101239 | CS Transmission Power Supply | ST000050-29 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | BLUFF FSS | BLUFF FSS | 0 | KM | BW03ML173 | 0.2049 | BW03ML173 | 0.2049 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078635&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000078635 | CS Transmission Power Supply | ST002730-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Newlands | BRIABA MWR | BRIABA MWR | 0 | KM | NL01ML57 | 0.8 | NL01ML57 | 0.8 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 10.06.2021 15:43:35 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101235&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101235 | CS Transmission Power Supply | ST007620-19 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | CALLEMONDAH MI | CALLEMONDAH MI | 0 | KM | BW50CR536 | 0.22 | BW50CR536 | 0.22 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101237&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101237 | CS Transmission Power Supply | ST009210-50 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Goonyella | CARBOROUGH DOWNS TSC | CARBOROUGH DOWNS TSC | 0 | KM | GA01ML162 | 0.192 | GA01ML162 | 0.192 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100533&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000100533 | CS Transmission Power Supply | ST006630-69 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | DUARINGA FS | DUARINGA FS | 0 | KM | BW03ML103 | 0.8469 | BW03ML103 | 0.8469 | KM |  |  |  |  | 101.71 | 101.71 | 2026-06-30 |  |  |  |  | 5 | 4.7 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100519&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000100519 | CS Transmission Power Supply | ST008430-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | EAGLEFIELD CREEK SER | EAGLEFIELD CREEK SER | 0 | KM | NL01ML203 | 0.9 | NL01ML203 | 0.9 | KM |  |  |  |  | 203.061 | 203.061 | 2026-06-30 |  |  |  |  | 5 | 3.2 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100575&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000100575 | CS Transmission Power Supply | ST009050-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | EPALA PSC 575KM | EPALA PSC 575KM | 0 | KM | BW01ML575 | 0.8149 | BW01ML575 | 0.8149 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100574&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000100574 | CS Transmission Power Supply | ST009070-03 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | EPALA PSC 577KM | EPALA PSC 577KM | 0 | KM | BW01ML577 | 0.75 | BW01ML577 | 0.75 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085223&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085223 | CS Transmission Power Supply | ST009190-37 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Goonyella | GROSVENOR TSC | GROSVENOR TSC | 0 | KM | GA05ML8 | 0.44 | GA05ML8 | 0.44 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085227&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085227 | CS Transmission Power Supply | ST005990-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Goonyella | HAY POINT PSC | HAY POINT PSC | 0 | KM | GA01BA1 | 0.2099 | GA01BA1 | 0.2099 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078656&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000078656 | CS Transmission Power Supply | ST005760-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Newlands | KAILI CER |  | 0 | KM | NC03ML1165 | 0.878 | NC03ML1165 | 0.878 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 10.06.2021 16:06:23 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085226&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000085226 | CS Transmission Power Supply | ST005880-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Goonyella | KERLONG MW | KERLONG MW | 0 | KM | GA40CR0 | 0 | GA40CR0 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2.4 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100593&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000100593 | CS Transmission Power Supply | ST008390-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | LEICHHARDT RANGE SER | LEICHHARDT RANGE SER | 0 | KM | NL01ML154 | 0.5999 | NL01ML154 | 0.5999 | KM |  |  |  |  | 154.65 | 154.65 | 2026-06-30 |  |  |  |  | 5 | 3.2 | 1 | 3 | 1 | 15 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085240&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085240 | CS Transmission Power Supply | ST005860-61 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 60000 | Goonyella | MACKAY MWR | MACKAY MWR | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085241&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085241 | CS Transmission Power Supply | ST005860-77 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 60000 | Goonyella | MACKAY SYS B | MACKAY SYS B | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100537&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic | BASELOAD | COAL | 002000100537 | CS Transmission Power Supply | ST007730-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | MOUNT LARCOM TSC | MOUNT LARCOM TSC | 0 | KM | BW01ML568 | 0.81 | BW01ML568 | 0.81 | KM |  |  |  |  | 565.332 | 565.332 | 2026-06-30 |  |  |  |  | 5 | 4.5 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101293&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101293 | CS Transmission Power Supply | ST008300-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Newlands | NEWLANDS SER | NEWLANDS SER | 0 | KM | NL06ML146 | 0.1049 | NL06ML146 | 0.1049 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100578&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100578 | CS Transmission Power Supply | ST005480-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | RAGLAN HILL MW | RAGLAN HILL MW | 0 | KM | BW60CR0 | 0 | BW60CR0 | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100579&DY_MAB=X&~OKCODE=ONLI | FY27 | Dual Traffic |  | COAL | 002000100579 | CS Transmission Power Supply | ST006260-21 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | RAGLAN SOUTH | RAGLAN SOUTH | 0 | KM | BW01ML582 | 0.439 | BW01ML582 | 0.439 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101290&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101290 | CS Transmission Power Supply | ST005490-87 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 60000 | Blackwater | ROCKHAMPTON CER SYS A | ROCKHAMPTON CER SYS A | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101291&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101291 | CS Transmission Power Supply | ST005490-88 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 60000 | Blackwater | ROCKHAMPTON CER SYS B | ROCKHAMPTON CER SYS B | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078653&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000078653 | CS Transmission Power Supply | ST007790-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | SPRING CREEK ATS 40.4KM |  | 0 | KM | BW03ML40 | 0.4249 | BW03ML40 | 0.4249 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 10.06.2021 16:03:04 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100595&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100595 | CS Transmission Power Supply | ST008380-11 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Newlands | SUTTOR CREEK SER | SUTTOR CREEK SER | 0 | KM | NL01ML179 | 0.8519 | NL01ML179 | 0.8519 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100591&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000100591 | CS Transmission Power Supply | ST008530-40 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Blackwater | UMOLO TSC | UMOLO TSC | 0 | KM | BW03ML153 | 0.1189 | BW03ML153 | 0.1189 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078651&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000078651 | CS Transmission Power Supply | ST005530-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | WALLAROO MW |  | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 10.06.2021 16:00:52 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101238&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000101238 | CS Transmission Power Supply | ST005120-22 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 35000 | Goonyella | WOTONGA SER | WOTONGA SER | 0 | KM | GA01ML174 | 0.08 | GA01ML174 | 0.08 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093802&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000093802 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEW | 10 | SITE | 140000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093801&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000093801 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEW | 10 | SITE | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093775&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000093775 | CS Transmission SDH to IP | NL | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 10 | SITE | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093778&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000093778 | CS Transmission SDH to IP | NL | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 10 | SITE | 140000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093783&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000093783 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEW | 1 | LUMPSUM | 110000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093782&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000093782 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEW | 1 | LUMPSUM | 110000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093767&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000093767 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 110000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 10 | 4 | 1 | 10 | 1 |  |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101321&DY_MAB=X&~OKCODE=ONLI | FY27 |  | FUTURE SCOPE | COAL | 002000101321 | CS Transmission TDM Replacement Planning | NL | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | PLANNING | 1 | LUMPSUM | 80000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 4 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101255&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000101255 | CS Transmission TDM Replacement | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101256&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000101256 | CS Transmission TDM Replacement | GA | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101257&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000101257 | CS Transmission TDM Replacement | NL | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120130&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000120130 | CS Transmission Tele Battery Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120131&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000120131 | CS Transmission Tele Battery Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120009&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000120009 | CS Transmission Tele Battery Renewal | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Moura | TBC | TBC | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120132&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000120132 | CS Transmission Tele Battery Renewal | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085257&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085257 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 1 | GOONYELLA 1 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100688&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100688 | CS Transmission Tele Battery | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Goonyella | GOONYELLA 2 | GOONYELLA 2 | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085259&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085259 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Moura | MOURA 1 | MOURA 1 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100678&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000100678 | CS Transmission Tele Battery | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Moura | MOURA 2 | MOURA 2 | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085258&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000085258 | CS Transmission Tele Battery | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | SITE | 13000 | Newlands | NEWLANDS 1 | NEWLANDS 1 | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 |  |  |  |  | 5 | 3 | 1 | 3 | 1 |  |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20260630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102838&DY_MAB=X&~OKCODE=ONLI | FY27 |  | BASELOAD | COAL | 002000102838 | CS TETRA AP Site Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | LUMPSUM | 100000 | Blackwater | BLACKWATER SYSTEM | BLACKWATER SYSTEM | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | REJC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132383&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000132383 | CS TETRA RADIO | ST003490-09 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 300000 | Moura | CALLIDE | CALLIDE | 0 | KM | MA07ML14 | 0.0529 | MA07ML14 | 0.0529 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 20 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132820&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000132820 | CS TETRA RADIO | ST005490-H5 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 200000 | Blackwater | ROCKHAMPTON FLR 6 | ROCKHAMPTON FLR 6 | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085476&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085476 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085477&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085477 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085478&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085478 | CS TETRA RADIO | NL | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085039&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085039 | Dig Telem GA Renewal | GA | CONTROL SYSTEMS | UTC DTC | DIGITAL TELEMETRY | RENEWAL | 8 | SITE | 620000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | UTC DTC | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085038&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085038 | UTC DTC Renewal BW | BW | CONTROL SYSTEMS | UTC DTC | UTC |  | 1 | UNIT | 840000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  | UTC DTC | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085082&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085082 | UTC DTC Renewal GA | GA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 840000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  | UTC DTC | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085087&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085087 | UTC DTC Renewal MA | MA | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 105000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  | UTC DTC | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085085&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085085 | UTC DTC Renewal NL | NL | CONTROL SYSTEMS | UTC DTC | UTC | RENEWAL | 1 | UNIT | 315000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  | UTC DTC | BESPOKE DESIGN | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127880&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | FUTURE SCOPE | COAL | 002000127880 | South Gladstone – Scoping, Planning and | BW-0512 | ELECTRICAL | OVERHEAD |  | DESIGN | 1 | UNIT | 25000 | Blackwater | SOUTH GLADSTONE |  | 14.996 | KM | N/522/147/M | 0 | N/537/143/D | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | South Gladstone – Scoping, Planning and Estimating for removal of permanently earthed OHLE Develop a plan for the removal of all permanently earthed OHLE equipment and estimate the cost of execution taking account of the likely scrap value of the recovered equipment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085279&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000085279 | OVERHEAD¦FW CLEARANCE¦RENEWAL¦BALOOK | GA-0212-00212B | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 200000 | Goonyella | BALOOK | BALOOK | 11.458 | KM | GA/74/565/D | 0 | GA/86/023/D | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | AREQ |  | 20270630 | 01-03-24 EK: Update MOD-ID and Renewal year to FY27 for design planned in FY25, to align with Renewal Strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000071617&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | STRATEGIC | COAL | 002000071617 | OVERHEAD¦FW CLEARANCE¦RENEWAL¦BLUFF | BW-0852 | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 500000 | Blackwater | BLUFF |  | 20.102 | KM | CW/153/1002/D | 0 | CW/173/202/D | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  | FW and Clearance Improvement | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | AREQ |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085194&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085194 | OVERHEAD¦GOONYELLA PORTS OHL¦RENEWAL | GA-0912 | ELECTRICAL | OVERHEAD | GOONYELLA PORTS OHL RENEWAL | RENEWAL | 1 | SITE | 7686000 | Goonyella | DALRYMPLE BAY | HAY POINT | 9.6679 | KM | DL/-0/068/DR1 | 0 | GA/9/600/D | 0 | KM | [6 empty] | 2027-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. 1/9/22: Estimate updated based on Phasing and Fund Release Plan (Rev. I)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085190&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085190 | Overhead Headspan Renewal | GA-0321 | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 6 | UNIT | 480000 | Goonyella | DYSART | DYSART | 33.8059 | KM | OC/71/320/U | 0 | OC/105/126/U | 0 | KM | [6 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000070375&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000070375 | Overhead Headspan Renewal | GA-0311 | ELECTRICAL | OVERHEAD | HEADSPANS | STRUCTURES | 5 |  | 337500 | Goonyella | PEAK DOWNS |  | 29.295 | KM | OC/41/976/M | 0 | OC/71/271/U | 0 | KM | [21 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085184&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085184 | POWER SYSTEMS¦SI/ NS RENEWAL¦RENEWAL | BW | ELECTRICAL | OVERHEAD | SI/NS | RENEWAL | 2 | UNIT | 150000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder for renewal of 2 units at $75k each.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085187&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085187 | POWER SYSTEMS¦SI/ NS RENEWAL¦RENEWAL | GA | ELECTRICAL | OVERHEAD | SI/NS | RENEWAL | 2 | UNIT | 150000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [14 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder for renewal of 2 units at $75k each.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084407&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000084407 | Small Component Renewals | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | LUMPSUM | 1000000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084461&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000084461 | Small Component Renewals | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | LUMPSUM | 1000000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105115&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105115 | AT¦BLACK MTN HATFIELD AT2¦RENEWAL | ST001300-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | BLACK MTN | BLACK MTN | 0 | KM | GA01ML45 | 0.225 | GA01ML45 | 0.225 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105117&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105117 | AT¦BROADLEA AT1¦RENEWAL | ST001440-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML154 | 0.1739 | GA01ML154 | 0.1739 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105109&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105109 | AT¦NORWICH PARK AT1¦RENEWAL | ST001400-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 600000 | Goonyella | NORWICH PARK | NORWICH PARK | 0 | KM | GA03ML115 | 0.4 | GA03ML115 | 0.4 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Notification in process | AREQ |  | 20260630 | 13-09-23 EK: This notification is to be deleted and removed. Notification changed based on assessed condition of AT at Norwich Park which is better than Villafranca AT2. Priority to be given for renewal of VillaFranca AT2 in FY26.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105118&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105118 | AT¦ROCKLANDS AT2¦RENEWAL | ST000160-21 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105119&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105119 | AT¦ROCKLANDS AT4¦RENEWAL | ST000160-23 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105120&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000105120 | AT¦ROCKLANDS AT5¦RENEWAL | ST000160-24 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075920&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000075920 | MI Renewal 431/4 Blair Athol | SQ030241 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 80460 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | BA/103/783/S1 | 0 | BA/103/783/S1 | 0 | KM |  |  |  |  | 103.783 | 103.783 | 2027-06-30 |  |  |  |  | 3.67 | 1.2 | 2 | 2.5 | 1 | 9.18 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20270630 | 11/3/2022 R.Licis: Scope and Inspection form attached. 13.01.2023 PCR 5557. Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support. This reduce the demand for overheads and allows for typical trends of deferred scope. Scope moved from FY24 to FY25. 6/3/2023 R.Licis: Moved to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075935&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000075935 | MI Renewal 251/3 Broadlea | SQ030502 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 46107 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA/158/300/U | 0 | GA/158/300/U | 0 | KM |  |  |  |  | 158.3 | 158.3 | 2027-06-30 |  |  |  |  | 3 | 2.5 | 2 | 3.3 | 1 | 9.9 |  | 2022-03-31 |  | Motorised Isolator Renewal | LIKE FOR LIKE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Notification in process | RRIG |  | 20270630 | 18/3/2022 R.Licis: Scope Inspection forms attached. To be done in FY24 This one swapped with Mallawa 622/4 (to be renewed in FY25) 5/1/2023 R.Licis: B2 template attached. 13.01.2023 PCR 5557. Historically a portion of scope defers from previous years (25% approx). Suggest to defer 7 MI's requiring the heaviest traction support. This reduce the demand for overheads and allows for typical trends of deferred scope. Scope moved from FY24 to FY25. 6/3/2023 R.Licis: Moved to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074292&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000074292 | MI Renewal 902D/907C Jilalan | SQ030558 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 34185 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/480/PR1 | 0 | GA/22/480/PR1 | 0 | KM |  |  |  |  | 22.46 | 22.46 | 2027-06-30 |  |  |  |  | 3.9 | 4.6 | 2 | 4.1 | 1 | 15.99 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY23 IN | 20270630 | * 31.03.2021 19:20:33 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 17/3/2022 R.Licis: Inspected in March 2022. No issue with access for plant or operator. Just need to hand rail at the back of the mast Scope: 1. Install handrail in FY24 2. Renew MI and B service (template C) in FY25 This noti will be moved to FY25 and replaced by Jilalan 906/3 (to be done in FY23. 5/3/2023 R.Licis: Hand rail installation only was moved from FY24 to FY25 after RIG/Aurizon review. MI renewal itself (this noti) will now be done in FY26 17/7/2023 R.Licis: Renewal to be done in FY27. 2/10/2013 R.Licis: Scope Type B2 Single 2/10/2013 R.Licis: OHW cost breakdown TRACTION CONSTRUCTION $30,665 SCADA UPDATE $1,100 TRACTION DESIGN ASBUILT $2,420
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075944&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000075944 | MI Renewal 241/20 Moorvale | SQ030472 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MOORVALE | MOORVALE | 0 | KM | MP/0/142/L | 0 | MP/0/142/L | 0 | KM |  |  |  |  | 0.142 | 0.142 | 2027-06-30 |  |  |  |  | 3.02 | 0.9 | 2 | 2.3 | 1 | 6.95 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 7/3/2023 R.Licis: Moved to FY27 31/8/2023 R.Licis: - Scope and inspection form attached - Photo attached - This is a bespoke design due to potential repositioning of CD box to incorporate new Driescher MI box. Single pole isolator blade to be replaced with a Stanger. Keep existing isolator steelworks support. - Design to be done in FY25, Procurement in FY26 and renewal in FY27.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053159&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000053159 | MI Renewal 542/3 Raglan | SQ030184 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54828 | Blackwater | RAGLAN | RAGLAN | 0 | KM | N/586/058/L | 0 | N/586/058/L | 0 | KM |  |  |  |  | 586.058 | 586.058 | 2027-06-30 |  |  |  |  | 4.1 | 4.9 | 2 | 4.2 | 1 | 17.22 |  | 2020-03-06 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20270630 | * 06.03.2020 14:25:25 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 542/3 Robin Chen's project - 2-4 April Closure PCR5324 to remove from FY22. Currently pushed to FY25 (L.Schneider 6/5/22) 6/3/2023 R.Licis: Access issue. Civil will cut embankment to create opening for isolator operator in FY24. Require G template to be designed in FY25. New design noti for FY25 to be entered. The actual renewal in FY27 (this noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053190&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000053190 | MI Renewal 542/4 at Raglan CW586k091L | SQ030185 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54828 | Blackwater | RAGLAN | RAGLAN | 0 | KM | N/586/091/L | 0 | N/586/091/L | 0 | KM |  |  |  |  | 586.091 | 586.091 | 2027-06-30 |  |  |  |  | 4.1 | 4.9 | 2 | 4.2 | 1 | 17.22 |  | 2020-03-06 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20270630 | * 06.03.2020 14:26:10 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 542/4 Robin Chen's project - 2-4 April Closure 27.1.2022 still awaiting confirmation 11/7/2022 R.Licis: This renewal has been moved to FY25. PCR 5324 has been submitted to cover this. To be done once the retaining wall modification has been completed by Civil(N4: 2000094343). 6/3/2022 R.Licis: Require G template to be designed. New design noti for FY25 to be entered and Renewal in FY27 (this noti) for renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043236&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000043236 | MI Renewal 811/5 Stanwell | SQ030005 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 56600 | Blackwater | STANWELL | STANWELL | 0 | KM | CW/25/376/U | 0 | CW/25/376/U | 0 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 4 | 1.65 | 2 | 2.8 | 1 | 11.2 | 4699 | 2019-07-15 | 2019-11-29 | Other Power Systems Renewals | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20270630 | * 10.11.2020 14:54:08 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 13.11.2020 10:06:03 AUSQLD Zane Hooton (R875021) * pushed out in error. Recloser study has found this is not required. Refer to PCR-4699 UPDATE: Moved construction date of this MI to FY24 since there will be turnout 45/46 pts upgrade. This upgrade work be done together with OHW mods by Simon McPherson for the turnout. Advise received from Alex Roehweder on timeline. 11/2/2022 R.Licis: Spoke to design manager Alex Rohweder and she advise the design for OHW by Simon will be in FY23 but the construction for this is in FY25. Therefore MI notification will be moved to FY25 instead of FY24 6/3/2023 R.Licis: Date unclear. Moved to FY26 in the interim 17/7/2023 R.Licis: BESPOKE design to be done in FY25, Procurement in FY26, and Renewal in FY27. 21/8/2023 R.Licis: Site Photos attached. 21/8/2023 R.Licis: SCOPE: 1. Remove Existing isolator support and isolator blade on top of EPT Portal 2. Remove existing ABB motor drive unit 3. Install new isolator support and single pole isolator blade on top of EPT portal 4. Install new Driescher MI and earth mat 5. Install bird nest deterrent 6. Renew feed-in jumpers 7. Coordinate the work with installation of CD. Scope to be provided by others. 22/8/2023 R.Licis: OHW COST BREAKDOWN 1. Construction $56,000 2. Asbuilt $600
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075946&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000075946 | MI Renewal 321/4 Stephens | SQ030518 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | STEPHENS | STEPHENS | 0 | KM | OC/98/875/U | 0 | OC/98/875/U | 0 | KM |  |  |  |  | 98.875 | 98.875 | 2027-06-30 |  |  |  |  | 3.44 | 1.4 | 2 | 2.5 | 1 | 9.29 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 7/3/2023 R.Licis: Moved to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093006&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000093006 | MI Renewal 181/2 Yan Yan | SQ030522 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | YAN YAN | YAN YAN | 0 | KM | GG/49/999/M | 0 | GG/49/999/M | 0 | KM |  |  |  |  | 52.055 | 52.055 | 2025-06-30 |  |  |  |  | 3.44 | 1 | 2 | 2.4 | 1 | 8.26 |  |  |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY25 OUT | 20270630 | 8/3/2022 R.Licis: N4 created for FY25. Inspected scope attached. 6/3/2023 R.Licis: Moved to FY27 12/03/2024: moved back to Design notification stage to wait for FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093007&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000093007 | MI Renewal 181/3 Yan Yan | SQ030523 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | YAN YAN | YAN YAN | 0 | KM | GG/50/035/L | 0 | GG/50/035/L | 0 | KM |  |  |  |  | 52.055 | 52.055 | 2025-06-30 |  |  |  |  | 3.44 | 1 | 2 | 2.4 | 1 | 8.26 |  |  |  | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY25 OUT | 20270630 | 8/3/2022 R.Licis: N4 created for FY25. Inspected scope attached. 6/3/2023 R.Licis: Moved to FY27 12/03/2024 - Moved back to Engineering to wait for FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091916&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000091916 | MI Renewal 181/4 Yan Yan | SQ030520 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | YAN YAN | YAN YAN | 0 | KM | GG/52/055/L | 0 | GG/52/055/L | 0 | KM |  |  |  |  | 52.055 | 52.055 | 2027-06-30 |  |  |  |  | 3.44 | 1 | 2 | 2.4 | 1 | 8.26 |  |  |  | Motorised Isolator Renewal | LIKE FOR LIKE | HIGH |  | HIGH | HIGH | Notification in process | NWSC | FY24 OUT | 20270630 | 15/2/2022 R.Licis: N4 created for FY24. Inspected scope attached. There is a 48V DC earth fault here. To be investigated. Potential the renewal to be swapped to FY25. 11/3/2022 R.Licis: On the interim moved to FY25. 6/3/2023 R.Licis: Moved to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044490&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000044490 | MI Renewal 202/3 at Yukan Yard GA29k830 | SQ030299 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54170 | Goonyella | YUKAN | YUKAN | 0 | KM | GA/29/830/D | 0 | GA/29/830/D | 0 | KM |  |  |  |  | 29.83 | 29.83 | 2027-06-30 |  |  |  |  | 4.1 | 4.8 | 2 | 4.2 | 1 | 17.22 |  | 2019-07-15 | 2019-11-29 | Other Power Systems Renewals | HEAVY MAINTENANCE |  |  |  |  | Notification completed | NWSC |  | 20270630 | 13/9/2021 R.Licis: STATUS 1. Work cancelled. Unable to secure NCL access from QE 2. Awaiting advise from PM to move this FY22 MI Renewal 3. Tentatively programmed for May 2022. All materials have been received. 4. Notification was put in process again. Dates and MOD ID to be updated once given the go ahead by PM. 5/7/2022 R.Licis: Design drawings showing scope is attached to noti. Scope is basically relocation isolator 202/3 at GA/29/830 headspan to the adjacent headspan mast GA/29/878. Isolator will be relocated to the other side of the track. Work requires NCL closure. Existing headspan to inspected for any damaged equipment before actual construction. Also components have been delivered to Jilalan Yard. Mod-id changed from FY21 to FY25. PCR 5299 has been approved by PM 10/10/22: Will need to source another 2 pole isolator. Has been used and taken since the start of 2021. 1 used from NMP but needs to be confirmed. 6/3/2023 R.Licis: Unable to access QR NCL closure. Moved to FY26 in the interim. 17/7/2023 R.Licis: After discussion with Hayden.Moved to FY27. 2/10/2023 R.Licis: OHW Cost breakdown: TRACTION CONSTRUCTION $53,570 TRACTION DESIGN ASBUILT $600
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044491&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000044491 | MI Renewal 202/2 at Yukan Yard GA30k121 | SQ030300 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54170 | Goonyella | YUKAN | YUKAN | 0 | KM | GA/30/121/D | 0 | GA/30/121/D | 0 | KM |  |  |  |  | 30.121 | 30.121 | 2027-06-30 |  |  |  |  | 4.1 | 4.8 | 2 | 4.2 | 1 | 17.22 |  | 2019-07-15 | 2019-11-29 | Other Power Systems Renewals | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20270630 | 13/9/2021 R.Licis: STATUS 1. Work cancelled. Unable to secure NCL access from QE 2. Awaiting advise from PM to move this FY22 MI Renewal 3. Tentatively programmed for May 2022. All materials have been received. 4. Notification was put in process again. Dates and MOD ID to be updated once given the go ahead by PM. 9/2/21 R.Licis: Mod-id changed from FY21 to FY25. PCR 5299 has been approved by PM 5/7/2022 R.Licis: Design drawings showing scope is attached to noti. Scope is basically relocating isolator 202/2 at GA/30/121 headspan to the opposite side of the headspan mast. Work requires NCL closure (TBC). Existing headspan to inspected for any damaged equipment before actual construction. Also components have been delivered to Jilalan Yard and stock taken. 10/10/2022 K. Robinson: Will need to source another 2 pole isolator. Has been used and taken since the start of 2021. 1 used from NMP but needs to be confirmed. 6/3/2023 R.Licis: Unable to access QR NCL Closure. Moved to FY26 on the interim. 17/7/2023 R.Licis: After discussion with Hayden, noti moved to FY27 2/10/2023 R.Licis: OHW cost breakdown TRACTION CONSTRUCTION $53,570 TRACTION DESIGN ASBUILT $600
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105470&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000105470 | BRAESIDE 107.800 PSC SITE RENEWAL | GA | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | 1 | 250000 | Goonyella | BRAESIDE | BRAESIDE | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 107.8 | 107.8 | 2027-06-30 |  |  |  |  | 3.5 | 5 | 0.5 | 3.7 | 1 | 13 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105472&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000105472 | COPPABELLA 142.748 PSC SITE RENEWAL | GA | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | 1 | 250000 | Goonyella | COPPABELLA | COPPABELLA | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 142.748 | 142.748 | 2027-06-30 |  |  |  |  | 3.5 | 4.6 | 0.5 | 3.5 | 1 | 12.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105473&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000105473 | COPPABELLA 145.381 PSC SITE RENEWAL | GA | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | 1 | 250000 | Goonyella | COPPABELLA | COPPABELLA | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 145.381 | 145.381 | 2027-06-30 |  |  |  |  | 3.5 | 4.6 | 0.5 | 3.5 | 1 | 12.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105474&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000105474 | MIDGEE 623.280 PSC SITE RENEWAL | BW | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | 1 | 250000 | Blackwater | MIDGEE | MIDGEE | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 623.28 | 623.28 | 2027-06-30 |  |  |  |  | 3.5 | 4.5 | 0.5 | 3.5 | 1 | 12.3 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105471&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  |  | 002000105471 | WAITARA 98.160 PSC SITE RENEWAL | GA | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | 1 | 250000 | Goonyella | WAITARA | WAITARA | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 98.16 | 98.16 | 2027-06-30 |  |  |  |  | 3.5 | 5 | 0.5 | 3.7 | 1 | 13 | [9 empty] | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085314&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085314 | Boonal 178.505km PSC Site Renewal | ST006130-08 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 150000 | Blackwater | BOONAL | BOONAL | 0 | KM | BW03ML178 | 0.505 | BW03ML178 | 0.505 | KM | [6 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder for PSC Site Renewals. Renewal year may change.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085313&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085313 | Edungalba 88.885km PSC Site Renewal | ST008130-13 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 150000 | Blackwater | EDUNGALBA | EDUNGALBA | 0 | KM | BW03ML88 | 0.885 | BW03ML88 | 0.885 | KM | [6 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder for PSC Site Renewals. Renewal year may change.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000081064&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000081064 | JILALAN YARD PSC BUILDING 21.971KM | ST001540-02 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA01ML21 | 0.9709 | GA01ML21 | 0.9709 | KM |  |  |  |  | 21.917 | 21.917 | 2026-06-30 |  |  |  |  | 3.5 | 4.8 | 0.5 | 3.6 | 1 | 12.6 |  | 2022-03-31 |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | RRIG |  | 20240630 | RENEWAL OF PSC BUILDING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105467&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000105467 | MARMOR 594.900 PSC SITE RENEWAL | ST001880-03 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Blackwater | MARMOR | MARMOR | 0 | KM | BW01ML594 | 0.9 | BW01ML594 | 0.9 | KM |  |  |  |  | 594.9 | 594.9 | 2026-06-30 |  |  |  |  | 3.5 | 4.9 | 0.5 | 3.7 | 1 | 13 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | AREQ |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000105465&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000105465 | MT MILLER 540.355 PSC SITE RENEWAL | ST002080-01 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 250000 | Blackwater | MT MILLER | MT MILLER | 0 | KM | BW01ML540 | 0.3549 | BW01ML540 | 0.3549 | KM |  |  |  |  | 540.355 | 540.355 | 2026-06-30 |  |  |  |  | 3.5 | 4.8 | 0.5 | 3.6 | 1 | 12.6 |  |  |  | Power Supply Cubicle (PSC) Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | AREQ |  | 20260630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085312&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic |  | COAL | 002000085312 | Tunnel 73.632km PSC Site Renewal | ST007680-02 | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 1 | SITE | 150000 | Blackwater | TUNNEL | TUNNEL | 0 | KM | BW03ML73 | 0.632 | BW03ML73 | 0.632 | KM | [6 empty] | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder for PSC Site Renewals. Renewal year may change.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136619&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136619 | PROTECTION RELAY - RANGAL- RL/BS1-2 | ST000340-52 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2.85 | 1 | 3 | 1 | 13 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270531 | 27-02-24 EK: Renewal notification for FY27 Relay Renewal with standard design with bespoke elements. Final renewal estimates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136694&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136694 | PROTECTION RELAY - RANGAL- RL/BS2-3 | ST000340-55 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2.85 | 1 | 3 | 1 | 13 | [9 empty] | Outstanding notification | NWSC |  | 20270227 | 27-02-24 EK: Renewal notification for FY27 Relay Renewal with standard with bespoke elements. Final renewal estimtates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136658&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136658 | PROTECTION RELAY - RANGAL- RL/C15 | ST000340-51 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2.85 | 1 | 3 | 1 | 13 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270531 | 26-02-24 EK: Renewal Notification for FY27 Relay Renewal with standard design with bespoke elements. Final renewal estimates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136660&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136660 | PROTECTION RELAY - RANGAL- RL/C17 | ST000340-57 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2.85 | 1 | 3 | 1 | 13 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270531 | 26-02-24 EK: Renewal Notification for FY27 Relay Renewal with standard design with bespoke elements. Final renewal estimates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136659&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136659 | PROTECTION RELAY - RANGAL- RL/O16 | ST000340-54 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | RANGAL | RANGAL | 0 | KM | BW03ML194 | 0.9699 | BW03ML194 | 0.9699 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 5 | 2.85 | 1 | 3 | 1 | 13 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270531 | 26-02-24 EK: Renewal Notification for FY27 Relay renewa with standard design with bespoke elements. Final renewal estimates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136701&DY_MAB=X&~OKCODE=ONLI | FY27 | Coal Traffic | BASELOAD | COAL | 002000136701 | PROTECTION RELAY - ROCKLAND - RD/BS1-2 | ST000160-29 | ELECTRICAL | POWER SYSTEMS | RELAYS | RENEWAL | 1 | UNIT | 53437 | Blackwater | ROCKLANDS | ROCKLANDS | 0 | KM | BW03ML1 | 0.56 | BW03ML1 | 0.56 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 4.5 | 1 | 4 | 1 | 17.5 | [9 empty] | Outstanding notification | NWSC |  | 20270227 | 27-02-24 EK: Renewal notification for FY27 Relay Renewal with standard design with bespoke elements. Final renewal estimates to be confirmed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085332&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085332 | Traction Substation Renewals | BW | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 8 | SITES | 13446894 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. See cashflow spreadsheet attached to N4 for details. Estimate updated based on revised cashflow 7.9.22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085331&DY_MAB=X&~OKCODE=ONLI | FY27 |  |  | COAL | 002000085331 | Traction Substation Renewals | GA | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 14 | SITES | 6031617 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2027-06-30 | [7 empty] | 0.1 |  | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Placeholder N4 to provide an indicative cashflow - CONCEPT level. See cashflow spreadsheet attached to N4 for details. Estimate updated based on revised cashflow 7/9/22.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103922&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103922 | FY28 ACCESS POINT DESIGN | GA | CIVIL | ACCESS POINTS |  | DESIGN | 1 | SITE | 60000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103928&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103928 | FY28 ACCESS POINT DESIGN | NL | CIVIL | ACCESS POINTS |  | DESIGN | 1 | SITE | 60000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103921&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103921 | FY28 ACCESS POINT REACTIVE WORKS | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103924&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103924 | FY28 ACCESS POINT REACTIVE WORKS | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103927&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103927 | FY28 ACCESS POINT REACTIVE WORKS | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103930&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103930 | FY28 ACCESS POINT REACTIVE WORKS | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103926&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103926 | FY28 ACCESS POINT RENEWAL | MA | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103929&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103929 | FY28 ACCESS POINT RENEWAL | NL | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103920&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000103920 | FY28 ACCESS POINT RENEWAL | AP100421 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Blackwater | BURNGROVE | TOLMIES | 0 | KM | NC09ML203 | 0.318 | NC09ML203 | 0.318 | KM |  |  |  |  | 203.32 | 203.32 | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121216&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000121216 | FY28 ACCESS POINT RENEWAL | AP200335 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Goonyella | COPPABELLA | BROADLEA | 0 | KM | GA02ML151 | 0.276 | GA02ML151 | 0.276 | KM |  |  |  |  | 151.5 | 151.5 | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103923&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000103923 | FY28 ACCESS POINT RENEWAL | AP200359 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA01ML12 | 0.811 | GA01ML12 | 0.811 | KM |  |  |  |  | 12.811 | 12.811 | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121214&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000121214 | FY28 ACCESS POINT RENEWAL | AP200151 | CIVIL | ACCESS POINTS |  | RENEWAL | 1 | SITE | 321000 | Goonyella | MIDDLEMOUNT | BUNDOORA | 0 | KM | GA27SD128 | 0.328 | GA27SD128 | 0.328 | KM |  |  |  |  | 128.32 | 128.32 | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103919&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103919 | FY28 ACCESS POINT DESIGN | BW | CIVIL | ACCESS POINTS | DESIGN | DESIGN | 1 | SITE | 18000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103925&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103925 | FY28 ACCESS POINT DESIGN-IFC | MA | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 18000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN-IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103895&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103895 | FY28 ACCESS POINT DESIGN IFP | BW | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103898&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103898 | FY28 ACCESS POINT DESIGN IFP | GA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103901&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103901 | FY28 ACCESS POINT DESIGN IFP | MA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103904&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103904 | FY28 ACCESS POINT DESIGN IFP | NL | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052260&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000052260 | FY28- Access Points Upgrade | BW | CIVIL | ACCESS POINTS | UPGRADE | RENEWAL | 1 | SITE | 321000 | Blackwater | WARREN | WYCARBAH | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 37.19 | 37.19 | 2023-06-30 | CAPRICORN HIGHWAY |  |  |  | 4 | 3.4 |  |  |  | 13.6 | 5660 | 2021-03-31 | 2021-10-05 | Access Points & Rds | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | HIGH | Outstanding notification | RRIG INIF | FY23 IN | 20280630 | * 30.03.2021 21:05:09 AUSQLD Sharbaree Biswas (R865006) * OLD ASSET ID CAP1059 * 12.04.2021 16:21:04 AUSQLD Jeremy Stevenson (R867415) * No design complete * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094933&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000094933 | C01-BU-BW-BLUFF-174.300km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.861 | KM | 1784832 | Blackwater | BLUFF | BOONAL | 3.861 | KM | BW04ML174 | 0.2999 | BW04ML178 | 0.1499 | KM |  |  |  |  | 174.3 | 178.15 | 2026-06-30 | UP |  |  |  | 3.5 | 3.4 | 2 | 4 | 1 | 12.6 | 193 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Moderately fouled ballast with severe patches Moderately rough track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 11/07/2022: Scope Change Request # 193 Created Melissa Durnsford 11/07/2022: Uploaded Site Inspection Document
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094940&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000094940 | C01-BU-BW-KINROLA JCT-2.900km-MN | BW-06ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.599 | KM | 1199112 | Blackwater | KINROLA JCT | KENMARE | 2.599 | KM | BW06ML2 | 0.9 | BW06ML5 | 0.5 | KM |  |  |  |  | 2.9 | 5.5 | 2026-06-30 | MAINLINE |  |  |  | 3.8 | 1.2 | 2 | 3 | 1 | 9.4 | 209 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Highly fouled ballast Near D7 top to moderately rough track geometry Lachlan Crow 07/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document FY26 scoping update - deferred due to lack of maintenance works history, reasonable geometry and a short section. In hindsight could have added to FY25 with tie in scope, but opportunity has passed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000094929&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000094929 | C01-BU-BW-UMOLO-148.660km-UP | BW-04ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 3.125 | KM | 1448159 | Blackwater | UMOLO | PARNABAL | 3.125 | KM | BW04ML148 | 0.66 | BW04ML151 | 0.8 | KM |  |  |  |  | 148.66 | 151.8 | 2026-06-30 | UP |  |  |  | 3.5 | 3.4 | 2 | 4 | 1 | 12.6 | 181 | 2022-03-31 |  | Mainline Undercutting - C01 | LIKE FOR LIKE |  | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20260630 | Highly fouled ballast Moderate to okay track geometry Lachlan Crow 05/07/2022 (R888582) Updating the ZPM_NAMS_ Class with the 2021 80th Percentile PVC for the scope. Melissa Durnsford 07/07/2022: Uploaded Walkout Inspection Document Melissa Durnsford 11/07/2022: Scope Change Request # 181 created to update the cut in to 148.660km FY26 scoping - was in FY26 but fouling improved in 2021 (last available data at this time due to 2022 missed and 2023 delayed), was only undercut between 2016 and 2020 in parts, no mud hole history and okay geometry - therefore defer
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080130&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000080130 | C13 Turnout B/U Bajool 7C/D | TO000872 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BAJOOL | BAJOOL | 0.041 | KM | BW02ML606 | 0.28 | BW02ML606 | 0.321 | KM |  |  |  |  | 606.28 | 606.28 | 2028-06-30 | BW-02ML |  |  |  | 3.5 | 4.5 |  |  |  | 15.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080093&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080093 | C13 Turnout B/U Boonal 10A/B | TO000686 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BOONAL | BOONAL | 0.0429 | KM | BW04ML178 | 0.5649 | BW04ML178 | 0.6079 | KM |  |  |  |  | 178.568 | 178.568 | 2028-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080138&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080138 | C13 Turnout B/U Boonal 8C/D | TO000626 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BOONAL | BOONAL | 0.0429 | KM | BW04ML181 | 0.2829 | BW04ML181 | 0.2399 | KM |  |  |  |  | 181.283 | 181.283 | 2028-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080152&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080152 | C13 Turnout B/U Boonal 7A/B | TO000687 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BOONAL | BOONAL | 0 | KM | BW04ML181 | 0.38 | BW04ML181 | 0.38 | KM |  |  |  |  | 181.38 | 181.38 | 2028-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080092&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080092 | C13 Turnout B/U Boorgoon 10A Pts | TO000778 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BOORGOON | BOORGOON | 0.034 | KM | BW23ML0 | 0.161 | BW23ML0 | 0.195 | KM |  |  |  |  | 0.161 | 0.161 | 2028-06-30 | BW-23ML |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080087&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080087 | C13 Turnout B/U Boorgoon 12A/B | TO000814 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BOORGOON | BOORGOON | 0.035 | KM | BW05ML9 | 0.549 | BW05ML9 | 0.5839 | KM |  |  |  |  | 9.55 | 9.55 | 2028-06-30 | BW-05ML |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104210&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000104210 | C13 Turnout B/U Nogoa 8A Pts | TO000753 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | BURNGROVE | NOGA | 0.028 | KM | BW03ML263 | 0.0229 | BW03ML263 | 0.0509 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.5 | 1.7 | 2 | 2.8 | 1 | 12.5 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080140&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000080140 | C13 Turnout B/U Callemondah 294C/D | TO000890 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | CALLEMONDAH | CALLEMONDAH | 0.04 | KM | BW02ML536 | 0.885 | BW02ML536 | 0.8449 | KM |  |  |  |  | 536.889 | 536.889 | 2028-06-30 | BW-02ML |  |  |  | 3.5 | 4.8 |  |  |  | 16.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104187&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104187 | C13 Turnout B/U Callemondah 232A Pts | TO001180 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.029 | KM | BW21YR0 | 0.2989 | BW21YR0 | 0.328 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 3.6 | 0.9 | 2 | 2.3 | 1 | 8.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104186&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104186 | C13 Turnout B/U Callemondah 233A Pts | TO001175 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.029 | KM | BW20YR0 | 0.511 | BW20YR0 | 0.54 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.1 | 0.9 | 2 | 2.3 | 1 | 9.3 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080203&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000080203 | C13 Turnout U/C Coppabella 11A/B | TO000228 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | COPPABELLA | COPPABELLA | 0.048 | KM | GA01ML145 | 0.389 | GA01ML145 | 0.4369 | KM |  |  |  |  | 145.39 | 145.39 | 2028-06-30 | GA-01ML |  |  |  | 3.5 | 4.6 |  | 4.1 |  | 16.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Near D7 top and twist (Jan 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104214&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104214 | C13 Turnout U/C Winchester 12A/B | TO000380 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | COPPABELLA | OAKY CREEK | 0.041 | KM | GA03ML33 | 0.451 | GA03ML33 | 0.4099 | KM | [6 empty] | 2028-06-30 | GA-03ML |  |  |  | 4 | 2.1 | 2 | 3.2 | 1 | 11.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104259&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104259 | C13 Turnout U/C Daly Bay 9A/B | TO000481 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY ARRIVAL RD 3 | DALY BAY ARRIVAL RD 3 | 0.0729 | KM | GA03BA8 | 0.33 | GA03BA8 | 0.257 | KM | [6 empty] | 2028-06-30 | GA-03BA |  |  |  | 4 | 2.6 | 2 | 4.2 | 1 | 15.6 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104204&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104204 | C13 Turnout U/C Yukan 47C/D | TO000337 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | DALY BAY JCT | WONTONGA | 0.035 | KM | GA02ML29 | 0.387 | GA02ML29 | 0.3519 | KM | [6 empty] | 2028-06-30 | GA-02ML |  |  |  | 3.4 | 4.8 | 2 | 2.8 | 1 | 10.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080269&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080269 | C13 Turnout B/U Fry 12A Pts | TO000945 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Moura | FRY | FRY | 0.0359 | KM | MA01ML73 | 0.1 | MA01ML73 | 0.136 | KM |  |  |  |  | 73.09 | 73.126 | 2028-06-30 | MA-01ML |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080270&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080270 | C13 Turnout B/U Fry 7A Pts | TO000946 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Moura | FRY | FRY | 0.0359 | KM | MA01ML75 | 0.17 | MA01ML75 | 0.134 | KM |  |  |  |  | 75.161 | 75.125 | 2028-06-30 | MA-01ML |  |  |  | 3.5 | 1.3 |  |  |  | 4.6 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Fouled and moderately rough top
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080071&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080071 | C13 Turnout B/U Kenmare 12A/B | TO000821 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | KENMARE | KENMARE | 0.048 | KM | BW06ML24 | 0.197 | BW06ML24 | 0.2449 | KM |  |  |  |  | 24.197 | 24.197 | 2028-06-30 | BW-06ML |  |  |  | 3.5 | 2.3 |  |  |  | 8.1 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104193&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104193 | C13 Turnout U/C Lake Vermont 9A/B | TO000563 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | LAKE VERMONT JCT | LAKE VERMONT MINE | 0.034 | KM | GA19ML11 | 0.9969 | GA19ML12 | 0.0299 | KM | [6 empty] | 2028-06-30 | GA-19ML |  |  |  | 3.2 | 1 | 2 | 2.5 | 1 | 8.5 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115694&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000115694 | C13 Turnout B/U Midgee 11A/B | TO000876 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | MIDGEE | MIDGEE | 0.047 | KM | BW02ML623 | 0.188 | BW02ML623 | 0.2349 | KM |  |  |  |  | 623.188 | 623.235 | 2028-06-30 | GA-04BA |  |  |  | 3.7 | 4.5 | 2 | 4.1 | 1 | 15.2 |  | 2023-03-31 |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630 | Renewal currently in FY28 - defer pending outcome
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104248&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000104248 | C13 Turnout B/U Mt 7A/B | TO000852 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | MOUNT LARCOM | AMBROSE | 0.049 | KM | BW01ML566 | 0.8589 | BW01ML566 | 0.81 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 3.5 | 4.1 | 2 | 3.9 | 1 | 13.5 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080088&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000080088 | C13 Turnout B/U Mt 11A/B | TO000901 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | MT LARCOM | MT LARCOM | 0.0439 | KM | BW02ML564 | 0.8489 | BW02ML564 | 0.805 | KM |  |  |  |  | 564.849 | 564.849 | 2028-06-30 | BW-02ML |  |  |  | 3.5 | 4.5 |  |  |  | 15.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080214&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000080214 | C13 Turnout U/C Mt Mclaren 7A/B | TO000505 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | MT MCLAREN | MT MCLAREN | 0.034 | KM | GA05ML58 | 0.9979 | GA05ML59 | 0.033 | KM |  |  |  |  | 59 | 59 | 2028-06-30 | GA-05ML |  |  |  | 3.5 | 1.2 |  | 2.5 |  | 4.2 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Near D7 top and twist (Mar 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104218&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104218 | C13 Turnout U/C Mt Mclaren ER1.3A | TO000504 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | MT MCLAREN PASSING LOOP | MT MCLAREN PASSING LOOP | 0.024 | KM | GA14PL59 | 0.8669 | GA14PL59 | 0.891 | KM | [6 empty] | 2028-06-30 | GA-14PL |  |  |  | 3.4 | 1.2 | 2 | 3.3 | 1 | 13.1 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080128&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000080128 | C13 Turnout B/U Nogoa 12A Pts | TO000612 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | NOGOA | NOGOA | 0.032 | KM | BW03ML261 | 0.5979 | BW03ML261 | 0.63 | KM |  |  |  |  | 261.598 | 261.598 | 2028-06-30 | BW-03ML |  |  |  | 3.5 | 1.65 |  |  |  | 5.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080134&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000080134 | C13 Turnout B/U Nogoa 9B Pts | TO000681 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | NOGOA | NOGOA | 0.032 | KM | BW03ML262 | 0.9709 | BW03ML262 | 0.9389 | KM |  |  |  |  | 262.97 | 262.97 | 2028-06-30 | BW-03ML |  |  |  | 3.5 | 1.65 |  |  |  | 5.8 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080150&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000080150 | C13 Turnout B/U Parnabal 12C/D | TO000589 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | PARNABAL | PARNABAL | 0.0449 | KM | BW04ML156 | 0.516 | BW04ML156 | 0.4709 | KM |  |  |  |  | 156.52 | 156.52 | 2028-06-30 | BW-04ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104211&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000104211 | C13 Turnout U/C Pring 95A | TO000149 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | PRING RD 1 | PRING RD 1 | 0.0459 | KM | NL01YR5 | 0.403 | NL01YR5 | 0.3569 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 3.4 | 1.7 | 2 | 2.9 | 1 | 10.8 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104195&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000104195 | C13 Turnout U/C Pring 93A | TO000156 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | PRING RD 2 | PRING RD 2 | 0.033 | KM | NL04YR5 | 0.189 | NL04YR5 | 0.1559 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 3.4 | 1.7 | 2 | 2.5 | 1 | 7.6 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104196&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000104196 | C13 Turnout U/C Pring 94A | TO000159 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Newlands | PRING RD 3 | PRING RD 3 | 0.0449 | KM | NL03YR5 | 0.322 | NL03YR5 | 0.277 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 3.4 | 1.7 | 2 | 2.5 | 1 | 7.6 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080099&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000080099 | C13 Turnout B/U Tikardi 12A/B | TO000812 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | TIKARDI | TIKARDI | 0.035 | KM | BW05ML5 | 0.012 | BW05ML5 | 0.047 | KM |  |  |  |  | 5.006 | 5.006 | 2028-06-30 | BW-05ML |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Severely Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080212&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000080212 | C13 Turnout U/C Winchester 7A/B | TO000382 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | WINCHESTER | WINCHESTER | 0.048 | KM | GA03ML31 | 0.035 | GA03ML31 | 0.083 | KM |  |  |  |  | 31.036 | 31.036 | 2028-06-30 | GA-03ML |  |  |  | 3.5 | 2.1 |  | 3.1 |  | 7.4 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Near D7 twist, moderate top (Feb 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080223&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000080223 | C13 Turnout U/C Yukan 2A | TO000517 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Goonyella | YUKAN | YUKAN | 0.024 | KM | GA01ML28 | 0.891 | GA01ML28 | 0.915 | KM |  |  |  |  | 28.889 | 28.889 | 2028-06-30 | GA-01ML |  |  |  | 3.5 | 4.8 |  | 4.2 |  | 16.8 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Near D7 top (Jan 21)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104175&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104175 | C20-BR-GA-COOPER CK-UP-110KM | BR200900-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.175 | KM | 850000 | Goonyella | BRAESIDE | MINDI | 0.1189 | KM | GA02ML110 | 0.029 | GA02ML110 | 0.1479 | KM |  |  |  |  | 110 | 110.175 | 2028-06-30 | UP |  |  |  | 3.08 | 4.4 | 2 | 4 | 1 | 12.3 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104180&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000104180 | C20-BR-BW-CALLIOPE CK-DOWN-537.725KM | BR101583-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.292 | KM | 1100000 | Blackwater | CALLEMONDAH | WIGGINS ISLAND JCT | 0.2919 | KM | BW02ML537 | 0.7229 | BW02ML537 | 1.0149 | KM |  |  |  |  | 537.725 | 538.017 | 2028-06-30 | DOWN |  |  |  | 3 | 4.8 | 3 | 4.5 | 1 | 14.6 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104161&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal GAPE Traffic | BASELOAD | COAL | 002000104161 | C20-BR-NL-FARMERS ROAD-MAIN-173.819KM | BR300691-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.03 | KM | 400000 | Newlands | LEICHARDT RANGE | SUTTOR CREEK | 0.0299 | KM | NL01ML173 | 0.769 | NL01ML173 | 0.799 | KM |  |  |  |  | 173.819 | 173.849 | 2028-06-30 | MAIN |  |  |  | 3.2 | 1.2 | 3 | 3.1 | 1 | 3.9 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104177&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000104177 | C20-BR-BW-HUT CK-DOWN-57.891KM | BR101471-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.136 | KM | 750000 | Blackwater | MOUNT LARCOM | RAGLAN | 0.0459 | KM | BW02ML573 | 0.006 | BW02ML573 | 0.0519 | KM |  |  |  |  | 570.891 | 571.027 | 2028-06-30 | DOWN |  |  |  | 2.8 | 4.1 | 3 | 4.3 | 1 | 11.3 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104170&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104170 | C20-BR-BW-HUMBOLT CREEK-MAIN-52.758KM | BR100832-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.091 | KM | 600000 | Blackwater | STARLEE | MEEMOOLOO | 0.0909 | KM | BW06ML52 | 0.758 | BW06ML52 | 0.8489 | KM |  |  |  |  | 52.758 | 52.849 | 2028-06-30 | MAIN |  |  |  | 3.7 | 2.3 | 3 | 3.6 | 1 | 8.6 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104171&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000104171 | C20-BR-BW-STOCK CROSSING-MAIN-89.364KM | BR100859-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.071 | KM | 475000 | Blackwater | STARLEE | ROLLESTON | 0.0189 | KM | BW06ML89 | 0.391 | BW06ML89 | 0.4099 | KM |  |  |  |  | 89.364 | 89.435 | 2028-06-30 | MAIN |  |  |  | 3.3 | 2.3 | 3 | 3.6 | 1 | 7.5 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 2/3
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104160&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal GAPE Traffic | BASELOAD | COAL | 002000104160 | C20-BR-NL-FARMERS ROAD-MAIN-189.501KM | BR300661-91-01 | CIVIL | BRIDGE ROLLOUTS |  | RENEWAL | 0.03 | KM | 400000 | Newlands | SUTTOR CREEK | EAGLEFIELD CREEK | 0.0299 | KM | NL01ML189 | 0.45 | NL01ML189 | 0.4799 | KM |  |  |  |  | 189.501 | 189.531 | 2028-06-30 | MAIN |  |  |  | 3.74 | 1.2 | 2 | 2.5 | 1 | 9.4 |  |  |  | Bridge Roll Out | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052748&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000052748 | Formation Renewal | GA-05ML | CIVIL | FORMATION |  | RENEWAL | 0.2 | KM | 420000 | Goonyella |  |  | 0.2 | KM | GA05ML45 | 0.8 | GA05ML46 | 0 | KM |  |  |  |  | 45.8 | 46 | [5 empty] | 3 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115197&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000115197 | C05-FR-BW-BAJOOL-606.670km | BW-02ML | CIVIL | FORMATION |  | RENEWAL | 0.155 | KM | 1325534 | Blackwater | BAJOOL | ARCHER | 0.23 | KM | BW02ML606 | 0.67 | BW02ML606 | 0.9 | KM |  |  |  |  | 606.665 | 606.82 | 2027-06-30 | DOWN |  |  |  | 3.8 | 4.5 | 3 | 4.4 | 1 | 16.9 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20280630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 606.260km to 606.900km Down Road side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 606.900km to 607.200km BW-02ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Tie into formation completed in conjunction with Magazine Road Level Crossing Renewal FY23 (002000043428)606.633 – 606.665km Down (32m) (Completed April 2023) • Reactive Formation (Notification 2000107343), 606.820 - 606.904km Down (84m) (Completed May 2023)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000134434&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000134434 | C05-FR-NL-BUCKLEY-15.400km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.14 | KM | 630000 | Newlands | BUCKLEY | ARMUNA | 0.14 | KM | NL01ML15 | 0.4 | NL01ML15 | 0.54 | KM |  |  |  |  | 15.4 | 15.54 | 2028-06-30 |  |  |  |  | 4.2 | 1.7 | 3.5 | 3.6 | 1 | 15.2 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Important Notes: • Plan <(>&<)> execute in conjunction with level crossing renewal notification 2000053664 planned FY28. Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 113.900km to 115.000km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104124&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104124 | C57-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | LUMPSUM | 220000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 5 | 2 |  | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044068&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044068 | C58-LX-GA-JILALAN-27.881km | LX003499 | CIVIL | LEVEL CROSSINGS | CONTROL SYSTEMS | CONTROL SYSTEMS UPGRADE | 1 | SITE | 1700000 | Goonyella | JILALAN | BLACK MOUNTAIN | 0 | KM | GA01ML27 | 0.88 | GA01ML27 | 0.88 | KM |  |  | 27.881 | 27.881 | 27.881 | 27.881 | 2028-06-30 | THE GLEN ACCESS ROAD |  |  |  | 10 | 4 | 2 | 10 | 1 | 100 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Design is in FY26 and the delivery is in FY28 as per the conversation with Rob Love.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122947&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122947 | C58-LX-MA-BELLDEEN-172.2km | LX006054 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Moura | BELLDEEN | MOURA MINE | 0 | KM | MA01ML172 | 0.2469 | MA01ML172 | 0.2469 | KM |  |  |  |  | 172.2 | 172.2 |  | BARFIELD ROAD |  |  |  | 3 | 1 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Pushed to FY27 Design for FY29 Renewal as per the mtg on 28 July with the IM team. FY26 DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122917&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122917 | C58-LX-NL-BIRRALEE-103.07km | LX003315 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML103 | 0.066 | NL01ML103 | 0.066 | KM |  |  |  |  | 103.07 | 103.07 |  | PRIVATE CATTLE CROSSING | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | FY26 DESIGN, FY27 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122909&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122909 | C58-LX-BW-BOONAL-181.293km | LX005614 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Blackwater | BOONAL | BLACKWATER | 0 | KM | BW03ML181 | 0.2929 | BW03ML181 | 0.2929 | KM |  |  |  |  | 181.293 | 181.293 | 2023-06-30 | COLUMBA ACCESS ROAD |  |  |  | 1.6 | 3.4 |  |  |  | 5.4 | 5701 | 2021-03-31 | 2021-10-05 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20280630 | PCR 5701. Moved FY23 Design to FY27 (IFP). This crossing was pushed to renew in FY27 to align with the Boonal turnout 8CD. This is a low priority design (and geotech investigation activity) because of the move/push. Originally it was a FY23 design, which was programmed to design in FY22. DD30 <(>&<)> IFC to be delivered as of 24/06/2022 <(>&<)> 16/09/2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122911&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000122911 | C58-LX-MA-CALLEMONDAH-6.33km | LX000963 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML6 | 0.339 | MA01ML6 | 0.339 | KM |  |  |  |  | 6.33 |  | 2029-06-30 | MERCURY ROAD |  |  |  | 3.3 | 1.3 | 2 | 3 | 1 | 8.55 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | 15.03.2024 This crossing is holding well since FoF reactive works in 2023. Original plan was for FY26 IFP, FY27 IFC, FY28 Renewal. Due to good condition at FY26 MRSB submission time Civil Assets have pushed out by 1 year to FY27 IFP, FY28 IFC, FY29 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120603&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000120603 | C58-LX-MA-CALLE-7.116km | LX005953 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML7 | 0.116 | MA01ML7 | 0.116 | KM |  |  |  |  | 7.116 | 7.116 | 2026-06-30 | WHITNEY ST |  |  | RENEWAL DESIGN | 2.6 | 1.3 | 2 | 3 | 1 | 7.8 |  | 2023-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | 28/3/2024- Deferred to FY28 (IFC) due to FY26 cashflow limit <(>&<)> Design resource limitation. FY25 DESIGN FOR FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122945&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122945 | C58-LX-MA-CLARKE-72.6km | LX005995 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Moura | CLARKE | FRY | 0 | KM | MA01ML72 | 0.658 | MA01ML72 | 0.658 | KM |  |  |  |  | 72.6 | 72.6 | 2029-06-30 | DUCKHOLE ROAD |  |  |  | 3.2 | [5 empty] | 4873 | 2021-03-31 | [7 empty] | Outstanding notification | NWSC |  | 20280630 | IFC to be completed in FY28 for FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079984&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000079984 | C58-LX-MA-DAKENBA-0.316km | LX006405 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 32000 | Moura | DAKENBA | CALLIDE | 0 | KM | MA07ML0 | 0.316 | MA07ML0 | 0.316 | KM |  |  | 0.316 | 0.316 | 0.316 | 0.316 | 2028-06-30 | JAMBIN DAKENBA ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 3.3 | 1 | 2 | 2 | 1 | 6.6 | 5338 | 2023-10-13 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20250630 | Moved further to FY28 IFC. PCR 5701- FY23 Design was pushed to FY25 (IFC). 29 March- PCR 5338 moved to FY23 design for FY25 construction All supporting documents are added in SPM as of 12 Oct 2021. FY24 DESIGN for FY25 Delivery/Renewal. Standard Renewal Details has been added as supporting doc as of 20.03.2022. 30.03.2022 R888068 Ben Crozier Revised condition assessment received 30.03.22 however flangeways and track pumping were not scored. No flangeways are installed so flangeway score revised by Civil Assets from 0.0 to 4.5. Comment was made on condition assessment that Track pumping was 'sound' but scored 0.0. All other components with a comment of 'sound' had a score of 2.5 so Track pumping was revised by Civil Assets to 2.5. These changes resulted in overall condition score lifting from 2.25 to 2.76.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122948&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122948 | C58-LX-MA-DAKENBA-2.28km | LX006406 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Moura | DAKENBA | CALLIDE | 0 | KM | MA07ML2 | 0.281 | MA07ML2 | 0.281 | KM |  |  |  |  | 2.28 | 2.28 |  | DUDARKOS ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Pushed to FY27 Design for FY29 Delivery, as per the discussion on 28 July with the IM team. Pushed the design work out of FY24 and placed in FY26.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120606&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000120606 | C58-LX-GA-DALY BAY-0.071km | LX020244 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA04BA0 | 0.0759 | GA04BA0 | 0.0759 | KM |  |  |  |  | 0.076 | 0.076 | 2028-06-30 | MAINTENANCE ACCESS RD |  |  |  | 2.5 | 4.2 | 2 | 4 | 1 | 10 |  | 2023-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Moved to FY28 IFC for FY29 Renewal due to fund limit.FY25 Design for FY27 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120607&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000120607 | C58-LX-BW-EDUNGALBA-89.321km | LX005557 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | EDUNGALBA | AROONA | 0 | KM | BW03ML89 | 0.321 | BW03ML89 | 0.321 | KM |  |  |  |  | 89.321 | 89.321 | 2028-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.6 | 3 | 2 | 4 | 1 | 10.4 |  | 2023-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 28/3/2024- Deferred to FY28 (IFC) due to cashflow and design resource limitation. FY25 DESIGN FOR FY27 CONSTRUCTION. Crossing review revealed the corrected km was 89.321km.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122906&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122906 | C58-LX-GA-GERMAN CREEK-136.47km | LX003636 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Goonyella | GERMAN CREEK | OAKY CREEK | 0 | KM | GA03ML136 | 0.4779 | GA03ML136 | 0.4779 | KM |  |  |  |  | 136.47 | 136.47 | 2023-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.3 | 1.1 |  |  |  | 2.5 |  | 2021-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20280630 | 22.03.2021 20:25:10 AUSQLD Sharbaree Biswas (R865006) ADDED THE LINEAR DATA Supported by Reagan Case (RAP Team). PCR 5124 added. 22.03.2021 20:25:10 AUSQLD Sharbaree Biswas (R865006) ADDED THE LINEAR DATA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122944&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122944 | C58-LX-MA-GRAHAM-29.828km | LX005969 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 35692 | Moura | GRAHAM | STIRRAT | 0 | KM | MA01ML29 | 0.8379 | MA01ML29 | 0.8379 | KM |  |  | 29.828 | 29.828 | 29.828 | 29.828 |  | HOOKE ROAD |  |  |  | 2 | 1 |  |  |  | 2 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Lower priority over ID6090/ID5755/ID5753. Moved to FY27 Design for FY29 Renewal. FY24 DESIGN for FY26 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122905&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122905 | C58-LX-GA-MIDDLEMOUNT-127.104km | LX003632 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Goonyella | MIDDLEMOUNT | BUNDOORA | 0 | KM | GA03ML127 | 0.1029 | GA03ML127 | 0.1029 | KM |  |  |  |  | 127.104 | 127.104 | 2023-06-30 | PRIVATE ACCESS ROAD |  |  |  | 1 | 1.5 |  |  |  | 1.5 |  | 2021-03-31 |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20280630 | 22.03.2021 20:16:00 AUSQLD Sharbaree Biswas (R865006) FIXED THE LINEAR DATA FIXED THE LINEAR DATA
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122951&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000122951 | C58-LX-GA-PRAGUELANDS-19.671km | LX007287 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Goonyella | PRAGUELANDS | JILALAN | 0 | KM | GA01YR19 | 0.671 | GA01YR19 | 0.671 | KM |  |  |  |  | 19.671 | 19.671 | 2025-06-30 | ENTRANCE TO STATION NEW |  |  |  | 3.6 | 4.2 | 2 | 4 | 1 | 14.4 |  |  |  | Rail Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Moved to FY26 Design for FY28 Renewal. FY25 DESIGN For FY27 CONSTRUCTION. Five tracks.For now it is included in FY25 Design. Only if it is determined that a relocation as part of the ICAR GA project is warranted, a change paper shall be submitted for removal of the scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120610&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000120610 | C58-LX-BW-SAGITARIUS-195.06km | LX003431 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | SAGITARIUS | RANGAL | 0 | KM | BW03ML195 | 0.0599 | BW03ML195 | 0.0599 | KM |  |  |  |  | 195.06 | 195.06 | 2028-06-30 | SUBSTATION ACCESS ROAD |  |  |  | 3.5 | 2.85 | 2 | 3 | 1 | 10.5 | 4873 | 2023-03-31 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 28/3/24- Deferred to FY28 (IFC) due to FY26 cashflow and Civil Design resource limit. Km review was done and found to be 195.060km. Brought forward to FY25 Design as per the mtg on 9 Sept 2022. Moved to FY26 Design for FY28 Renewal as per the mtg on 31 Aug 2022 with the IM team. Moved to FY24 Design <(>&<)> FY26 Delivery. LX seems to be holding okay so postponed in FY22/FY23 for more critical scope. Originally scoped in 2019 for FY22 delivery.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122914&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122914 | C58-LX-GA-WINCESTER-45.32km | LX003230 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Goonyella | WINCESTER | PEAK DOWNS | 0 | KM | GA03ML45 | 0.321 | GA03ML45 | 0.321 | KM |  |  | 45.32 | 45.32 | 45.32 | 45.32 | 2025-06-30 | PRIVATE ACCESS ROAD |  | AS PER RENEWAL DESIGN | AS PER RENEWAL DESIGN | 1.7 | 3.93 | 2 | 4 | 1 | 6.8 | 5338 | 2025-06-30 | 2022-03-31 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | PCR 5701- moved to FY27 IFP, FY28 IFC <(>&<)> FY29 Renewal. 29 March 2022- PCR 5338- moved to FY23 DESIGN for FY25 RENEWAL. There is water pooling and to be surveyed and designed to direct water from the corridor. S Biswas comments on 15 March 2022: Condition assessment and overall condition is not reflective and supportive to the other supporting documents. This is an issue that the Superintendent Engineering Civil is accountable. For FY25, adequate overall condition is expected.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122908&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000122908 | C58-LX-BW-YARWUN-559.674km | LX005584 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Blackwater | YARWUN | MOUNT LARCOM | 0 | KM | BW01ML559 | 0.675 | BW01ML559 | 0.675 | KM |  |  | 559.674 | 559.674 | 559.674 | 559.674 | 2027-06-30 | PORT CURTIS WAY |  |  |  | 3.1 | 4.5 | 2 | 4.1 | 1 | 12.71 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | FY27 IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122930&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000122930 | C58-LX-GA-YUKAN-27.881km | LX003499 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML27 | 0.881 | GA01ML27 | 0.881 | KM |  |  |  |  | 27.881 | 27.881 | 2027-06-30 | THE GLEN ACCESS ROAD |  |  |  | 10 | 4 | 2 | 10 | 1 | 100 | 4929 | 2021-03-31 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Delayed by a year. Added $90k to cover both Civil and Signal design in FY26 (Rob Love to lead the signal design). Need agreement on stakeholder financial contributions in FY25 e.g. how much QR/Landowner will pay into the project.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127711&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000127711 | C58-LX-BW-WALTON-166.675km | LX005563 | CIVIL | LEVEL CROSSINGS | IFC | MAJOR | 1 | RENEWAL | 1500000 | Blackwater | WALTON | BLUFF | 0 | KM | BW03ML166 | 0.675 | BW03ML166 | 0.675 | KM |  |  |  |  | 166.675 | 166.675 | 2028-06-30 | ROCKVIEW ROAD |  |  |  | 3.6 | 3.64 | 2 |  | 1 | 14.56 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | FY28 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083373&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000083373 | C58-LX-NL-BIRRALEE-94.201km | LX003314 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML94 | 0.203 | NL01ML94 | 0.203 | KM |  |  |  |  | 94.201 | 94.201 | 2030-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.57 | 2.14 | 2 | 3 | 1 | 7.71 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | This crossing had a Ballast Undercut in Aug 2023. DCP's were taken at this time and low strength formation was identified on the higher km side of the crossing. Despite this issue if the Mine ceases watering the crossing (as they have agreed via the Customer team) renewal can be delayed. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing 2 years to FY28 IFP, FY29 IFC, FY30 Renewal. This crossing will continue to be monitored and bought forward if required. FY26 DESIGN. Scoped on 11 May 2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079983&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000079983 | C58-LX-BW-BLACKWATER-0.941km | LX005881 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Blackwater | BLACKWATER | KOORILGAH | 0 | KM | BW13ML0 | 0.9409 | BW13ML0 | 0.9409 | KM |  |  |  |  | 0.941 | 0.941 |  | PONY CLUB ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | FY28 Design for FY30 Delivery. FY24 DESIGN The renewal of this crossing is delayed till FY27 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051923&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000051923 | C58-LX-MA-GLADSTONE-19.73km | LX005961 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 32000 | Moura | GLADSTONE | STOWE | 0 | KM | MA01ML19 | 0.7299 | MA01ML19 | 0.7299 | KM |  |  |  |  | 19.73 | 19.73 | 2022-06-30 | BATTERY ROAD |  |  |  | 3.08 | 1.3 |  |  |  | 4 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20280630 | Pushed to FY28 Design for FY30 renewal as per the mtg on 28 July 2022 with the IM team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051940&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000051940 | C58-LX-BW-RANGAL-198.37km | LX003432 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | RANGAL | BURNGROVE | 0 | KM | BW03ML198 | 0.3649 | BW03ML198 | 0.3649 | KM |  |  |  |  | 198.37 | 198.37 | 2028-06-30 | TOLMIES CREEK ROAD |  |  |  | 2.67 | 2.05 |  |  |  | 5.47 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20260630 | AS per the mtg with Trevor on 13 Dec, moved this design to FY28. AS per the mtg on 31 Aug 2022 with the IM team, the design was moved to FY26. Possible to add in FY24 DESIGN <(>&<)> FY26 DELIVERY. Scope development is required before it cab be brought forward.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044035&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044035 | C58-LX-GA-WOTONGA-0.428km | LX005813 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 32000 | Goonyella | WOTONGA | MORANBAH | 0 | KM | GA05ML0 | 0.4279 | GA05ML0 | 0.4279 | KM |  |  |  |  | 0.428 | 0.428 | 2022-06-30 |  |  |  |  | 2.75 | 2.5 |  |  |  | 5 | 4873 | 2022-06-30 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | IV.00459.E.6.M | 20280630 | * 13.03.2020 13:38:29 AUSQLD Sharbaree Biswas (R865006) * I * 13.03.2020 13:44:22 AUSQLD Sharbaree Biswas (R865006) ID5813.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068857&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000068857 | C58-LX-BW-TOLMIES-221.69km | LX002761 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN- SIGNAL | 1 | SITE | 30000 | Blackwater | TOLMIES | COMET | 0 | KM | BW03ML221 | 0.6899 | BW03ML221 | 0.6899 | KM |  |  | 221.69 | 221.69 | 221.69 | 221.69 |  | COMET RIVER ROAD |  |  |  | 1.4 | 1.4 |  |  |  | 2.31 | 4929 | 2025-06-30 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20280630 | As per the mtg on 31 Aug 2022 with the IM team in Blackwater, this crossing was requested to be upgraded to flashing lights and boom gates due to the heavy use by trucks and long vehicles. Possible to add in FY24 DESIGN COMPARING THE PRIORITY OVER OTHER CROSSINGS FOR FY26 DELIVERY. Scope development is required before b ringing in to FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133825&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000133825 | C58-LX-GA-MINDI-127.043km | LX006644 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1500000 | Goonyella | MINDI | SOUTHWALKER | 0 | KM | GA01ML127 | 0.0429 | GA01ML127 | 0.0429 | KM |  |  |  |  | 127.043 | 127.043 | 2028-06-30 | MINE ACCESS ROAD |  |  |  | 3.5 | 4 | 2 | 4 | 1 | 14 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | FY28 MAJOR RENEWAL. Integration with Formation Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068848&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000068848 | C58-LX-BW-BOORGOON-53.09km | LX006952 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 953704 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML53 | 0.0899 | BW06ML53 | 0.0899 | KM |  |  |  |  | 53.09 | 53.09 | 2025-06-30 | STRAUN ROAD |  |  |  | 3.66 | 2.3 | 2 | 3 | 1 | 11 | 5758 | 2023-09-01 |  | Level Crossing Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630 | FY25 RENEWAL- DD50 Design Doc added in SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104123&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104123 | C57-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 600000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 5 | 2 |  | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104125&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104125 | C57-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 600000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 5 | 2 |  | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104126&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104126 | C57-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | LUMPSUM | 150000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 5 | 2 |  | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000137535&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000137535 | C58-LX-GA-BURTON-168.375km CIVIL | LX020259 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 1500000 | Goonyella | BURTON DOWNS | MALLAWA | 0 | KM | GA01ML168 | 0.375 | GA01ML168 | 0.375 | KM | 6 |  |  |  | 168.375 | 168.375 | 2028-06-30 | BURTON MINE ACCESS RIAD |  |  |  | 10 | 2.4 | 2 | 10 | 1 | 100 | 5706 |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | CIVIL RENEWAL in FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103556&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000103556 | C58-LX-BW-BOORGOON-34.95km | LX006954 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 659076 | Blackwater | BOORGOON | MEMOOLOO | 0 | KM | BW06ML34 | 0.913 | BW06ML34 | 0.913 | KM |  |  |  |  | 34.95 |  | 2028-06-30 | HUMBOLDT ROAD |  |  |  | 4.6 | 2.3 | 2 | 3.16 | 1 | 14.7 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | 22.09.2023 Civil Assets spoke with IM about the timing of renewal. IM advised this crossing could be delayed to FY28. This crossing was showing severe ballast and geometry defects and undercut in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053664&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000053664 | C58-LX-NL-BUCKLEY-15.516km | LX003279 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Newlands | BUCKLEY | ARMUNA | 0 | KM | NL01ML15 | 0.516 | NL01ML15 | 0.516 | KM |  |  |  |  | 15.516 | 15.516 | 2028-06-30 | 88A BOWEN DEVELOPMENT ROAD |  |  |  | 3.5 | 1.7 | 2 | 3 | 1 | 10.5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 13.02.2024 Sharbaree Biswas (R865006) Design, Plan and Execute this LX renewal with Formation Renewal 2000134434 (FY28 execution). FY26 design in for FY28 renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101688&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000101688 | C58-LX-MA-CALLE-22.165km | LX005755 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML22 | 0.164 | MA01ML22 | 0.164 | KM |  |  |  |  | 22.165 | 22.165 | 2028-06-30 | CALLEMONDAH DRIVE |  |  |  | 3.9 | 2.6 | 2 | 3 | 1 | 12.87 |  |  |  | Level Crossing Renewals | [5 empty] | Outstanding notification | NWSC |  | 20280630 | Moved to FY28 renewal due to FY25 scope cuts. Kept in FY27 renewal as per the discussion with the IM team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104128&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic | BASELOAD | NON-COAL | 002000104128 | C58-LX-BW-COMET-242.44km | LX001087 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 454000 | Blackwater | COMET | YAMALA | 0 | KM | BW03ML242 | 0.4359 | BW03ML242 | 0.4359 | KM |  |  |  |  | 242.44 |  | 2028-06-30 |  |  |  |  | 4.4 | 1.7 | 2 | 3 | 1 | 13.2 | [9 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123439&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000123439 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123440&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000123440 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123441&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000123441 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123442&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000123442 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123430&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000123430 | C58-LX-GA-YUKAN-27.881km | LX003499 | CIVIL | LEVEL CROSSINGS | SIGNAL DESIGN | DESIGN | 1 | SITE | 250000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML27 | 0.881 | GA01ML27 | 0.881 | KM |  |  |  |  | 27.881 | 27.881 | 2028-06-30 |  |  |  | RENEWAL | 10 | 4 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280630 | Signal Design (to be conducted by Signal Team). Signal construction is in FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123425&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000123425 | C58-LX-GA-BURTON-168.486km | LX020259 | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 2500000 | Goonyella | MALLAWA | ISAAC PLAINS | 0 | KM | GA01ML168 | 0.375 | GA01ML168 | 0.375 | KM |  |  |  |  | 168.375 | 168.375 | 2028-06-30 |  |  |  | UPGRADE SIGNAL | 10 | 2.4 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20260630 | SIGNAL UPGRADE- FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078184&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000078184 | ROCKLANDS WEDGE SLOPE STABILITY | BW-03CR | CIVIL | SLOPE STABILITY |  | DESIGN | 1 | LUMPSUM | 375000 | Blackwater | ROCKLANDS | GRACEMERE | 0 | KM | BW03ML0 | 0.5 | BW03ML0 | 0.5 | KM |  |  |  |  | 0.5 |  | 2027-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066496&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000066496 | B52 -ST-BW-Burngrove-000.215km | CU101118 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 37100 | Blackwater | GG |  | 0 | KM | BW08ML0 | 0.2149 | BW08ML0 | 0.2149 | KM |  |  |  |  | 0.215 | [6 empty] | 3 | 4 |  |  |  | 12 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Severe crack for full height of wall. Exposed reinforcement. Access difficult as overhead lines on ceiling. Proposed: Remove and replace likely as overhead lines on ceiling and reducing height will likely cause issues track. Risk: Moderate Reason: Drawings:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043442&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000043442 | B52 -ST-BW-Kenmare-004.080km | CU100938 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 21170 | Blackwater | KINROLA | KENMARE | 0 | KM | BW06ML4 | 0.08 | BW06ML4 | 0.08 | KM |  |  |  |  | 4.08 | [6 empty] | 3 | 1.5 |  |  |  | 4.5 |  | 2019-07-15 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Painted in FY21, monitor performance at next inspection. Defect: Section loss in invert of culvert Proposed: Concrete Line or Remove and Replace. Final: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109427&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000109427 | B52 -ST-GA-Dalrymple-000.330km | CU200346 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 500000 | Goonyella | GA - DALRYMPLE BL |  | 0 | KM | GA05BD0 | 0.335 | GA05BD0 | 0.335 | KM |  |  |  |  | 0.335 |  | 2028-06-30 |  |  |  |  | 4.5 | 2.6 | 3 | 3.7 | 1 | 16.65 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 08.12.2022 Max Holzschuher (R887760) There are cracks in the hocks of most units. Threr is some minor rust stains in the legs of most units in widening 2 right. Minor - moderate spalling and cracks throughout culvert. Propose Remove and Replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132535&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000132535 | B12 -ST-BW-Bajool-605.690km | BR101279 | CIVIL | STRUCTURES | BRIDGE BEARING | RENEWAL | 1 | SITE | 2000000 | Blackwater | BAJOOL |  | 0.0539 | KM | BW01ML605 | 0.635 | BW01ML605 | 0.6889 | KM |  |  |  |  | 605.69 |  | 2028-06-30 |  |  | BEARING PADS & STRENGTHENING |  | 4 | 4.1 | 4 | 4.3 | 1 | 17.2 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241229 | BR101279 SIX MILE CREEK - B12 -ST-BW-Bajool-605.690km Defect: Bearing pad moveing out from girder at abutment 2 and at same location girder ends appear to have shear cracking. Proposed: Bearing pad replacement and end of girder crack improvements Final: Drawing: Risk: High Reason: Further deteration of bearing ad will lead to concrete concrete interface and girder being damaged requiring full replacement which will require long closure and significantly more cost.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132543&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000132543 | B12 -ST-GA-Bolingbroke-052.570km | BR200823 | CIVIL | STRUCTURES | BRIDGE BEARING | RENEWAL | 1 | SITE | 2500000 | Goonyella | BOLINGBROKE |  | 0.1089 | KM | GA02ML52 | 0.4979 | GA02ML52 | 0.6069 | KM |  |  |  |  | 52.57 |  | 2028-06-30 |  |  | BEARING PADS & STRENGTHENING |  | 3.5 | 5 | 4 | 4.5 | 1 | 15.8 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241229 | BR200823 BOLINGBROKE CREEK - B12 -ST-GA-Bolingbroke-052.570km Defect: Bearing pad pier 1 girder 4. cracks in girder 2 span 1. Proposed: Bearing Pad Replacement and remove escape platforms and patch. Consider strengthening options for cracks in girders Final: Drawing: Risk: High Reason: Further deteration of bearing ad will lead to concrete concrete interface and girder being damaged requiring full replacement which will require long closure and significantly more cost.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133685&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000133685 | B12 -ST-GA-Dalrymple-009.514km | BR200725 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | RENEWAL | 1 | SITE | 2000000 | Goonyella | DALRYMPLE |  | 0.0459 | KM | GA01ML9 | 0.508 | GA01ML9 | 0.554 | KM |  |  |  |  | 9.514 |  | 2028-06-30 |  |  | STRENGTHENING |  | 3.5 | 4.6 | 4 | 4.7 | 1 | 16.5 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | BR200725 GRASSTREE BEACH ROAD - B12 -ST-GA-Dalrymple-009.514km Defect: Severe cracks forming on top flange of girders longitudinally. Design assessment required. ASR cracking longitudinally requires ASR identification testing and monitoring of crack width. Inspect bridge annually. Seal cracks after confirmed to be dead and ASR. NMP at present Proposed: Considering strengthening methods or whether remove and replace required. Final: Drawing: Risk: High Reason: Aim for this design phase is to ideally strengthen girder before full replacement required. If full replacement required then structures management plan to be developed.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131108&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic | FUTURE SCOPE | NON-COAL | 002000131108 | B12 -ST-NO-Parana-526.300km | BR101585 | CIVIL | STRUCTURES | BRIDGE STRENGTHEN | RENEWAL | 1 | SITE | 2000000 | Moura | PARANA |  | 0.048 | KM | NC02ML526 | 0.276 | NC02ML526 | 0.324 | KM |  |  |  |  | 526.3 |  | 2028-06-30 |  |  | STRENGTHEN |  | 3.5 | 1.8 | 4 | 3.4 | 1 | 11.9 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | BR101585 NORTH COAST LINE - B12 -ST-NO-Parana-526.300km Defect: Severe Cracking on Piers, majority of piers impacted and many headstocks also severely cracked. Proposed: Strengthening design required Final: Drawing: Risk: HIgh Reason: Deterioation of the pier walls are the most concening defect on this bridge that needs to be rectified to ensure the structural adequacy of the bridge longer term.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109379&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000109379 | B52 -ST-BW-Kenmare-013.250km | CU100911 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 400000 | Blackwater | KENMARE |  | 0 | KM | BW06ML13 | 0.25 | BW06ML13 | 0.25 | KM |  |  |  |  | 13.25 |  | 2027-06-30 |  |  | CIPP |  | 4 | 2.6 | 3 | 3.7 | 1 | 15 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Mpderate to severe corosion from 2-10 oclock which means holds considerable water, difficult to maintain as smaller culvert. Proposed: CIPP Line pending Hydro Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133042&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000133042 | B52 -ST-BW-Kenmare-019.290km | CU100928 | CIVIL | STRUCTURES | CMP-CIPP | RENEWAL | 1 | SITE | 100000 | Blackwater | KENMARE |  | 0 | KM | BW06ML19 | 0.2899 | BW06ML19 | 0.2899 | KM |  |  |  |  | 19.29 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 2.6 | 3 | 3.7 | 1 | 13 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | CU100928 - B52 -ST-BW-Kenmare-019.290km Defect: painted FY21. Severe corrosion in invert. line bfore corrosion goes too far Proposed: CIPP Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000099883&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000099883 | B52 -ST-GA-Moranbah North-187.940km | CU200807 | CIVIL | STRUCTURES | CMP-CIPP LINE | RENEWAL | 1 | SITE | 840000 | Goonyella | GA-GA |  | 0 | KM | GA01ML187 | 0.9399 | GA01ML187 | 0.9399 | KM |  |  |  |  | 187.94 |  | 2028-06-30 |  |  | CIPP LINE |  | 3.5 | 1.3 | 3 | 3.2 | 1 | 11.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Deflecting in shape in last inspection. Under annual inspection, tentative scope Proposed: CIPP lining to be considered pending hydro Drawing: Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085871&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085871 | B52 -ST-BW-Kenmare-004.367km | CU100901 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 750000 | Blackwater |  |  | 0 | KM | BW06ML4 | 0.3669 | BW06ML4 | 0.3669 | KM |  |  |  |  | 4.367 |  | 2028-06-30 |  |  | CONCRETE LINE | CONCRETE LINE | 3.5 | 2.6 | 3 | 4 | 1 | 15.3 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: 50% or greater section loss in invert 1/3 of culvert. Invert was painted in FY21, should delay renewal for 5-10 years. Proposed: 200-250mm Concrete lining, confirmed in design Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102547&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000102547 | B52 -ST-BW-Memooloo-051.150km | CU100909 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 4000000 | Blackwater | BW-BA |  | 0 | KM | BW06ML51 | 0.1499 | BW06ML51 | 0.1499 | KM |  |  |  |  | 51.15 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 2.3 | 3 | 4.2 | 1 | 12.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Corrosion in all inverts. Most severe in cells 6-9, 11, 14 <(>&<)> 15 Proposed: Concrete Line pending Hydro Check. Remove and replace would need to hold longer. Remaining Cells 5,9,10,11,12,13,16,17,18,19,21. Stage 2 construction Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091960&DY_MAB=X&~OKCODE=ONLI | FY28 | Non Coal Traffic |  | NON-COAL | 002000091960 | B52 -ST-BW-Nogoa-257.771km | CU100262 | CIVIL | STRUCTURES | NON-MRSB RCBC-ELIMINATE | RENEWAL | 1 | SITE | 369940 | Blackwater | YAMALA | NOGOA | 0 | KM | BW03ML257 | 0.771 | BW03ML257 | 0.771 | KM |  |  |  |  | 257.77 |  | 2028-06-30 |  |  |  |  | 3 | 1.7 |  |  |  | 11.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20280630 | Defect: Severe cracking in wall and ceiling. Peaked sediment in middle of culvert suggests gap in walls and ceiling. Proposed: Remove <(>&<)> replace or diversion to larger culverts 150m down track. IFC: GHD design Eliminate and Divert to 257.600km large culvert Drawing: None required Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136166&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000136166 | B52 -ST-NL-Birralee-102.000km | CU300502 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 3326000 | Newlands | BIRRALEE |  | 0 | KM | NL01ML102 | 0 | NL01ML102 | 0 | KM |  |  |  |  | 102 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4.5 | 1.4 | 3 | 3.2 | 1 | 14.4 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280616 | CU300502 WATER - B52 -ST-NL-Birralee-102.000km Defect: Severe cracks in pipe, with podering at cracks suggesting pumping and movement in cracks. Proposed: Remove <(>&<)> Replace due to condition Final: Drawing: Risk: High Reason: Severe cracking and movement suggest collapse is getting closer and therefore should not be delays. It made need additional maintenance just to get to FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044250&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044250 | B52 -ST-NL-Binbee-050.050km | CU300404 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 40000 | Newlands | NL |  | 0 | KM | NL01ML50 | 0.05 | NL01ML50 | 0.05 | KM |  |  |  |  | 50.05 |  | 2030-06-30 | MOD |  | REMOVE & REPLACE |  | 3 | 3.4 | 3 | 4 | 1 | 12 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: 29% 20-26.5TAL load intensity increase, no cover of pipe. Minor corrosion issues, but holding ok, push out Proposed: Remove <(>&<)> Replace with RCBC as cover is limited Final: Drawing: Risk: Moderate Reason: Only minor corrosion and movement in the pipe. Will renew when condition warrants, but is in long term renewal due to under strength of CMP and insufficient cover on CMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109419&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000109419 | B52 -ST-BW-Blackwater-187.111km | CU100081 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 7000000 | Blackwater | BLACKWATER |  | 0 | KM | BW03ML187 | 0.08 | BW03ML187 | 0.08 | KM |  |  |  |  | 187.08 |  | 2028-06-30 |  |  | CONCRETE LINE OR REPLACE |  | 4.5 | 3.2 | 3 | 3.9 | 1 | 17.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect - pumping in cell 6 units 2<(>&<)>3 approx 3-5mm. moderate cracking throughout cells. Proposed - Remove and Replace or concrete line, however pumping may not allow for lining. Final - Drawing - Risk - Mod-High Reason -
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085879&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085879 | B52 -ST-BW-Mackenzie-032.110km | CU101100 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 460000 | Blackwater | BW-GG |  | 0 | KM | BW08ML32 | 0.11 | BW08ML32 | 0.11 | KM |  |  |  |  | 32.11 |  | 2028-06-30 |  |  | CONCRETE LINE | 1 / 2400X2100 RCBC R&R | 3.5 | 1.3 | 3 | 3 | 1 | 11.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: severe spalling in ceiling and legs. pumping 1-2mm. Proposed: Remove <(>&<)> Replace 1 / 2400x2100 RCBC 12.024m LONG Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078780&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000078780 | B52 -ST-BW-Ambrose-573.960km | CU101325 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 600000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML573 | 0.9599 | BW01ML573 | 0.9599 | KM |  |  |  |  | 573.96 |  | 2028-06-30 |  |  |  |  | 3.5 | 4.1 |  |  |  | 14.9 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Pumping under loaded trains Proposed: Remove and Replace Drawing: Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132847&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000132847 | B52 -ST-BW-Gracemere-005.610km | CU101061 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 870000 | Blackwater | GRACEMERE |  | 0 | KM | BW03ML5 | 0.6099 | BW03ML5 | 0.6099 | KM |  |  |  |  | 5.61 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | CU101061 - B52 -ST-BW-Gracemere-005.610km Defect: Units 3 and 4 (LHS) pumping and will be propped from units 2 to 5. Bolts missing in strengthening beam and previously beam fell down from loss of connection. Regularly holds water in culvert, look to raise invert slightly. RHS has 300A units, consider partial replacements. Proposed: Remove and Replace Drawing: Risk: Mod-High Reason: Pumping of units increases risk of track geometry defects and deteriorates units faster, increasing risk of more severe defects forming suddenly.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093506&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000093506 | B52 -ST-BW-Marmor-591.120km | CU101534 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 1373760 | Blackwater | MARMOR | RAGLAN | 0 | KM | BW01ML591 | 0.1199 | BW01ML591 | 0.1199 | KM |  |  |  |  | 591.12 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 4.9 | 3 | 4.5 | 1 | 15.8 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20280802 | Defect - Units 1,2 dropped 50mm base slab failure and roof severe spalling in cast insitu. Proposed - Remove and replace with 1/1500x900 RCBC Risk: Mod-High Reason: Severe spalling of ceiling in situ section under north coast line which takes passenger services. Dip in track visible which means regular resurfacing required. Risk of derailment with track alignm,ent issues. Inspected by remote 18/01/2023 CR S - 1 BC - 1 Spalling, Severe, Roof. Mod Crack, roof, Minor spall far leg and roof S - 1 BC - 1 Pumping, Severe, Evidence on previous photos S - 1 BC - 2 Pumping, Severe, Evidence on previous photos. Appears unit is dropping 45mm
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086038&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000086038 | B52 -ST-GA-Norwich Park-124.000km | CU200540 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 905000 | Goonyella | NORWICH PARK |  | 0 | KM | GA03ML124 | 0 | GA03ML124 | 0 | KM |  |  |  |  | 124 |  | 2028-06-30 |  |  |  |  | 3.5 | 1.5 | 3 | 3.3 | 1 | 11.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: moderate spalling thorughout with localsied sever corrosion. Proposed: Remove and replace Final: Drawing: AUR-Q-0881-4232 Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086022&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000086022 | B52 -ST-GA-Norwich Park-110.900km | CU200053 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 900000 | Goonyella | NORWICH PARK | NORWICH PARK | 0 | KM | GA20ML110 | 0.9 | GA20ML110 | 0.9 | KM |  |  |  |  | 110.9 |  | 2028-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 4 | 1.4 | 3 | 3.2 | 1 | 12.8 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Severe Corrosion in CMP's. This work only needs to be completed for Norwich Park balloon to be brought back into operations. Therefore this may need to be brought forward into FY24 or pushed out to align with Norwich Park customer planning. Proposed: Remove and Replace 1/1200x1200 RCBC Drawing: AUR-Q-0575-4152 Risk: Mod-High Reason: Severe corrosion in CMP of 600 szie are extremely difficult to monitor and are at risk of collapse unexpectedly. This collapse will like cause a top issue with track and increase risk of derailment. This work is only in FY25 tentatively as this work will be delivered with Mine's strategy on when to open. If not opened, renewal is not required as risk to trains greatly reduced.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000131150&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000131150 | B52 -ST-GA-Red Mountain-026.210km | CU200396 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 4176000 | Goonyella | RED MOUNTAIN |  | 0 | KM | GA03ML26 | 0.2099 | GA03ML26 | 0.2099 | KM |  |  |  |  | 26.21 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 2.1 | 3 | 3.5 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | CU200396 UNKNOWN - B52 -ST-GA-Red Mountain-026.210km Defect: Minor to moderate cracking in haunches and legs. Water coming through some of the haunch cracks increasing risk of reinf corrosion. Spalling at joints of loaded units 2/3. more severe in unit 10-3, 13-3/4, 16-3. Inspectors call up units 2/3/4 pumping in all cells. Proposed: Remove and replace. Final: Drawing: Risk: Mod-High Reason: Propped currently to hold until renewal can be completed. Haunch cracks are worsening over time and moistire coming through them increasing risk of collapse and impacting track seriously as cover limited.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132695&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000132695 | B52 -ST-BW-Tryphinia-131.680km | CU100166 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 462000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML131 | 0.68 | BW03ML131 | 0.68 | KM |  |  |  |  | 131.68 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 3.35 | 3 | 4 | 1 | 16 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | CU100166 DRAIN - B52 -ST-BW-Tryphinia-131.680km Defect: Severe cracks in ceiling of insitu section. Severe cracks in base slab. Proposed: Remove and Replace Drawing: Risk: mod-High Reason: High risk to track impact cracks in ceiling of culvert
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133040&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000133040 | B52 -ST-BW-Umolo-143.210km | CU100431 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 3100000 | Blackwater | UMOLO |  | 0 | KM | BW03ML143 | 0.2999 | BW03ML143 | 0.2999 | KM |  |  |  |  | 143.21 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: bolts failed in bracing and main support steel beams. Units pumping under loaded trains. Proposed: Concrete Lining or Remove and replace. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133029&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000133029 | B52 -ST-BW-Umolo-143.310km | CU100389 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 3600000 | Blackwater | UMOLO |  | 0 | KM | BW03ML143 | 0.38 | BW03ML143 | 0.38 | KM |  |  |  |  | 143.31 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: strengthening struts failed evidence of pumping. Proposed: Concrete Lining or Remove and replace. Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135517&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000135517 | B52 -ST-BW-Warren-033.810km | CU100419 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2100000 | Blackwater | WARREN |  | 0 | KM | BW03ML33 | 0.81 | BW03ML33 | 0.81 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20280630 | Defect - Pumping 2-3mm, some are 300A, but minor cracking and spalling from movement. With large gaps between cells, looks like old bridge replacement. Proposed - Remove and Replace Final - Risk - Mod-high Reason - Pumping will lead to top of line issues with the track and likely TSR's
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000099418&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000099418 | B52 -ST-BW-Gracemere-009.500km | CU100107 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 1008000 | Blackwater | BW-CL |  | 0 | KM | BW03ML9 | 0.5 | BW03ML9 | 0.5 | KM |  |  |  |  | 9.5 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.8 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Unit 4-7 pumping 2-4mm. and movement in legs 25mm similar movement in surrounding units. This unit propped due to crushing of legs. Proposed: Concrete lining to be considered pending hydro and pumping issue in cell 4. Otherwise Remove and replace Drawing: Risk: Moderate - High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044212&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044212 | B52 -ST-BW-Rangal-001.160km | CU101044 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 400000 | Blackwater | BW-KA |  | 0 | KM | BW05ML1 | 0.085 | BW05ML1 | 0.085 | KM |  |  |  |  | 1.16 |  | 2028-06-30 |  |  |  |  | 3 | 3.5 |  |  |  | 10.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Spalling in legs and roof. Poor concrete material with limited fines in areas. Concerned throughout. Proposed: Concrete Line, hydro to confirm.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000128773&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000128773 | B52 -ST-NL-Pring-004.440km | CU300333 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 6000000 | Newlands | PRING |  | 0 | KM | NL01ML4 | 0.44 | NL01ML4 | 0.44 | KM |  |  |  |  | 4.44 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.7 | 3 | 3.4 | 1 | 11.8 | 184 | 2022-03-31 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Spalling in multiple units in multiple locations. Holds water for much of the year. Proposed: Concrete Lining confirmed by Hydro. If remove and replace, invert raising may be beneficial as holds water a lot of the year. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089491&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000089491 | B52 -ST-BW-Bluff-177.120km | CU100032 | CIVIL | STRUCTURES | RCBC-ELIMINATE | RENEWAL | 1 | SITE | 100000 | Blackwater | BLUFF | BOONAL | 0 | KM | BW03ML177 | 0.4199 | BW03ML177 | 0.4199 | KM |  |  |  |  | 177.12 |  | 2025-06-30 |  |  | ELIMINATE |  | 4 | 3.4 | 3 | 4 | 1 | 16.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Blocked with concrete, need to confirm hydrology if needs to be replaced. Proposed: Eliminate or remove and replace. Drawing: Risk: High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086014&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000086014 | B52 -ST-GA-Black Mountain-030.740km | CU200722 | CIVIL | STRUCTURES | RCP WIDENING | RENEWAL | 1 | SITE | 300000 | Goonyella | BLACK MOUNTAIN |  | 0 | KM | GA01ML30 | 0.7399 | GA01ML30 | 0.7399 | KM |  |  |  |  | 30.74 |  | 2028-06-30 |  |  | REMOVE & REPLACE | REMOVE & REPLACE | 3.5 | 4.4 | 3 | 4.3 | 1 | 15.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Widening under access road miss-shaped due to pooor construction. Proposed: Replace widening only 5m with class 4 2400 dia RCP Final: Replace widening only 5m with class 4 2400 dia RCP Drawing: AUR-Q-0575-4132 Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043727&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000043727 | B52 -ST-NL-Havilah-142.520km | CU300491 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 39000 | Newlands | HAVILAH | NEWLANDS | 0 | KM | NL01ML142 | 0.52 | NL01ML142 | 0.52 | KM |  |  |  |  | 142.52 |  | 2030-06-30 |  |  | CIPP |  | 3 | 1.4 | 3 | 3.2 | 1 | 9.6 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | Defect: Cracks throughout RCP Proposed: CIPP lining or remove and replace pending hydro.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135519&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000135519 | B52 -ST-BW-Aroona-091.900km | CU100456 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 1900000 | Blackwater | AROONA |  | 0 | KM | BW03ML91 | 0.9 | BW03ML91 | 0.9 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | CIPP OR R&R |  | 4 | 3.4 | 3 | 4 | 1 | 16 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20280630 | Defect - Regular minor to severe cracking and differential settlement in majority of units. Proposed - CIPP or Remove and Replace pending hydro Final - Risk - Mod-high Reason - May lead to top of line issue with additional settlement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000132477&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000132477 | B52 -ST-BW-Aroona-092.350km | CU100091 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 2930000 | Blackwater | AROONA |  | 0 | KM | BW03ML92 | 0.3499 | BW03ML92 | 0.3499 | KM |  |  |  |  | 92.35 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 3.35 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250630 | CU100091 - B52 -ST-BW-Aroona-092.350km Defect: Failing headwall. Butress wall have no pile and appear to be rotating. First 2 units and some third units all cells with cracks horizontal (minor to moderate) Proposed: CIPP RCP, confirm 1530 Ok to line. Remove and replace head wall, may benfit from 1-2 more units to get headwall away from track. Risk: Mod Reason: Including this now with CIPP may prevent more costing remove and replace of 22 cell system in the future.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133338&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000133338 | B52 -ST-NO-Callemondah-529.000km | CU101580 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 760000 | Moura | CALLEMONDAH |  | 0 | KM | NC02ML529 | 0 | NC02ML529 | 0 | KM |  |  |  |  | 529 |  | 2028-06-30 |  |  | CIPP |  | 4 | 1.8 | 3 | 3.4 | 1 | 13.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250110 | CU101580 - B52 -ST-NO-Callemondah-529.000km Defect: Small section partially collapsed. Seevere cracking in other units and spalling. Proposed: CIPP line or Remove and replace pending hydro and shape considerations. Final: Drawings: Risk: Mod-High Reason: Passenger services use this section of the line and small section already broken out, high water flow through this culvert is likely to undermine the track from the broken section and lead to top of line defects and risk of derailment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121297&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000121297 | B52 -ST-GA-Jilalan-020.310km | CU200324 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 250000 | Goonyella | GA |  | 0 | KM | GA02YR20 | 0.3099 | GA02YR20 | 0.3099 | KM |  |  |  |  | 20.31 |  | 2028-06-30 | MOD-HIGH |  | CIPP |  | 4 | 4.7 | 3 | 4.4 | 1 | 17.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280606 | Defect: NCL Affected. Minor cracking in haunches and more severe in unit 16-3 Proposed: CIPP lining or Remove and replace. Reason: Under yard and main line so high risk to busy part of the network. If we can line with CIPP then will avoid large remove <(>&<)> Replace.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000130571&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000130571 | B52-ST-BW-Marmor-597.670km | CU101603 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 250000 | Blackwater | MARMOR |  | 0 | KM | BW01ML597 | 0.67 | BW01ML597 | 0.67 | KM |  |  |  |  | 597.67 |  | 2028-06-30 |  |  | REPLACE |  | 4 | 4.1 | 3 | 4.3 | 1 | 17.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20241124 | Defect: 18 Units long 600RCP. Units 5-18 mod-severe cracking horizontally in ceiling. Proposed: Remove and Replace Drawing: Risk: High Reason: High rsik of collapse and found as reactive work through a remote inspection.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135581&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000135581 | B52 -ST-BW-Westwood-036.540km | CU100488 | CIVIL | STRUCTURES | RCP-CIPP | RENEWAL | 1 | SITE | 150000 | Blackwater | WESTWOOD |  | 0 | KM | BW03ML36 | 0.54 | BW03ML36 | 0.54 | KM |  |  |  |  | 33.81 |  | 2028-06-30 |  |  | CIPP |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20250207 | CU100488 UNKNOWN - B52 -ST-BW-Westwood-036.540km Defect - units U4 horizontal severe cracks, high risk of increased deterioration. Proposed - CIPP pending hydro Final - Risk - Mod-high Reason - If not complete in FY28 risk will be lining may not be an option and a track closure will be required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124970&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000124970 | B52 -ST-BW-Callemondah-535.150km | CU101254 | CIVIL | STRUCTURES | RCP-PVC | RENEWAL | 1 | SITE | 8000000 | Blackwater | CALLEMONDAH |  | 0 | KM | BW01ML535 | 0.1499 | BW01ML535 | 0.1499 | KM |  |  |  |  | 535.15 |  | 2028-06-30 |  |  | CONCRETE LINE |  | 3.5 | 2.4 | 3 | 3.7 | 1 | 13 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270804 | CU101254 - B52 -ST-BW-Callemondah-535.150km Defect: Majority of cells have severe wear in base of RCP exposing reinf and mod cracking at base. Cell 4 has mod to severe cracks in ceiling at 12 oclock in units 11, 14, 15 Proposed: Consider PVC lining, Concrete lining or GRP lining system for this. Low speed area, so PVC similar to QAL may be good option here. Risk: Mod Reason: Low speed area, but still part of north coast line and therefore subject to customer services. Difficult to get closures on NCL, so lining options would result in good option.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074692&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000074692 | TU GA BLA-BMB DN 158.283-159.876KM MAN | GA-01ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 1.597 | KM | 1842877 | Goonyella | BROADLEA | BURTON DOWNS | 1.5949 | KM | GA01ML158 | 0.2829 | GA01ML159 | 0.877 | KM | 30 | 1330 | 3.194 | 1.597 | 158.28 | 159.877 | 2023-06-30 | DOWN | BOTH |  |  | 3.5 | 4.6 |  |  |  | 16.1 |  | 2021-03-31 |  | Track Upgrade | LIKE FOR LIKE | MEDIUM |  | LOW | MEDIUM | Notification in process | SCPR | FY23 IN | 20280630 | * 22.03.2021 12:12:54 AUSQLD Sanjna Rajagopalan (R884639) * Awaititng Tech Scope * 12.04.2021 16:20:50 AUSQLD Jeremy Stevenson (R867415) * Tech scope attached * * Start:158.28km End: 159.877km 30 Rails Sleepers: Start: 158.289km End:159.200km 1330 sleepers Scope to be pushed out due to fatigue limits not reach till 2033+ - please see attachement for section breakdown
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138915&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000138915 | C21 GA PEAK DOWNS 45.570 - 45.720 | GA-17ML | CIVIL | TRACK UPGRADE |  | RENEWAL | 0.11 | TRACK KM | 181409 | Goonyella | PEAK DOWS BALLOON | PEAK DOWNS BALLOON | 0.11 | KM | GA17ML45 | 0.5699 | GA17ML45 | 0.68 | KM | 2 | 161 | 0.22 | 0.11 | 45.57 | 45.68 | 2029-06-30 | EXIT | BOTH |  |  | 4 | 1.1 | 1 | 1.6 | 1 | 6.4 | 282 | 2024-03-28 |  | Track Upgrade | LIKE FOR LIKE |  | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20260630 | This scope starts at end of CV3311 and ends before start of CV3312 Renewal driver is significant corrosion to the foot and web with multiple layers of laminating and breaking away. Note kms on site and data differ. Located under the overpass Scope postponed to be delivered as a larger scope in future years.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124105&DY_MAB=X&~OKCODE=ONLI | FY28 |  | REACTIVE RENEWALS | COAL | 002000124105 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 3843262 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124106&DY_MAB=X&~OKCODE=ONLI | FY28 |  | REACTIVE RENEWALS | COAL | 002000124106 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4192650 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124107&DY_MAB=X&~OKCODE=ONLI | FY28 |  | REACTIVE RENEWALS | COAL | 002000124107 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 768652 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124108&DY_MAB=X&~OKCODE=ONLI | FY28 |  | REACTIVE RENEWALS | COAL | 002000124108 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 768653 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123825&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000123825 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦DA 10A/B | TO000151 | CIVIL | TURNOUTS | CONSTRUCT | CONSTRUCT | 1 | TURNOUT | 1500000 | Newlands | DURROBURRA | DA 10A/B | 0.05 | KM | NC03ML1158 | 0.4979 | NC03ML1158 | 0.448 | KM |  |  |  |  | 1158.498 |  | 2028-06-30 |  |  |  |  | 3.5 | 2.5 | 4 | 4.1 |  | 14.35 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | NWSC |  | 20280630 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦DA 12A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction (Bring it Forward to Swap with Coppabella if ideal) 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $11,900 out of $119,000 30.03.2022 Alex Rohweder (R872349) Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125857&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000125857 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦DA 12A/B | TO000119 | CIVIL | TURNOUTS | CONSTRUCT | CONSTRUCT | 1 | TURNOUT | 1500000 | Newlands | DURROBURRA | DA 12A/B | 0.0709 | KM | NL02ML0 | -0.2099 | NL02ML0 | -0.139 | KM |  |  |  |  | 0.21 |  | 2028-06-30 |  |  |  |  | 3.5 | 2.5 | 4 | 4.1 |  | 14.35 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | NWSC |  | 20280816 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦DA 12A/B 15/08/2023 Alex Rohweder (R972340) FY24 Early Design, FY26 - IFP, FY27 - IFC, FY28 - Construction (Bring it Forward to Swap with Coppabella if ideal) 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. FY24 Design budget adjusted to 10% off the total design budget = $11,900 out of $119,000 30.03.2022 Alex Rohweder (R872349) Two year design plan Early Design in FY24, detailed design for FY25 for FY27 CONSTRUCTION
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115815&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000115815 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦BL 46A | TO000919 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | BAJOOL | BL 46A | 0.0219 | KM | BW02PL605 | 0.4779 | BW02PL605 | 0.456 | KM |  |  |  |  | 605.478 | 605.456 | 2028-06-30 |  |  | POINTS & X 60KG/M 12 CS SWCMN |  | 3.5 | 4 | 3.9 | 4 |  | 13.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115840&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000115840 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ BL 9A | TO000572 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | BAJOOL | BL 9A | 0.0299 | KM | BW01ML605 | 0.5649 | BW01ML605 | 0.535 | KM |  |  |  |  | 603.078 | 603.048 | 2028-06-30 |  |  |  |  | 3.5 | 4 | 4.2 | 4 |  | 14.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115814&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000115814 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ BL 9B | TO000918 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | BAJOOL | BL 9B | 0.021 | KM | BW02PL605 | 0.4929 | BW02PL605 | 0.514 | KM |  |  |  |  | 605.493 | 605.514 | 2028-06-30 |  |  |  |  | 4 | 2 | 3.9 | 4 |  | 12.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Three TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SWCMN TGLASM MO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115828&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000115828 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ CH 273A | TO001151 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CH273A | 0.024 | KM | BW14YR534 | 0.317 | BW14YR534 | 0.341 | KM |  |  |  |  | 534.317 | 534.341 | 2028-06-30 |  |  |  |  | 3.5 | 4 | 4.1 | 5 |  | 19.8 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 8.25 CL RBM PH EO RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115829&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000115829 | TURNOUTS ¦CONSTRUCT ¦RENEWAL¦CH ER275.2F | TO001152 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CHER275.2F | 0.025 | KM | BW14YR534 | 0.343 | BW14YR534 | 0.3679 | KM |  |  |  |  | 534.343 | 534.368 | 2028-06-30 |  |  |  |  | 4.5 | 3.5 | 4.1 | 5 |  | 19.8 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 8.25 CL RBM PH EO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043319&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal GAPE Traffic | BASELOAD | COAL | 002000043319 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ LR12A | TO000135 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 500000 | Newlands | LEICHARDT RANGE | LR12A | 0.069 | KM | NL01ML153 | 0.5769 | NL01ML153 | 0.5769 | KM |  |  |  |  | 153.58 |  | 2028-06-30 |  |  |  |  | 3.5 | 2 | 3 |  |  | 12.3 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | * 04.08.2020 17:02:58 AUSQLD Lachlan Prescott (R881571) * COST UPDATED TO BRING FORWARD 8% DESIGN COST TO FY22 * 19.03.2021 12:04:51 AUSQLD Lachlan Prescott (R881571) * Deferred to FY24 due to over-allocated FY23 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043318&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal GAPE Traffic | BASELOAD | COAL | 002000043318 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ LR7A | TO000136 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 500000 | Newlands | LEICHARDT RANGE | LR7A | 0.069 | KM | NL01ML155 | 0.4789 | NL01ML155 | 0.4789 | KM |  |  |  |  | 155.48 |  | 2028-06-30 |  |  |  |  | 4 | 2.5 |  |  |  | 12.3 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | * 04.08.2020 17:01:59 AUSQLD Lachlan Prescott (R881571) * COST UPDATED TO BRING FORWARD 8% DESIGN COST TO FY22 * 19.03.2021 12:04:29 AUSQLD Lachlan Prescott (R881571) * Deferred to FY24 due to over-allocated FY23 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115844&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000115844 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ ME 11C/D | TO000840 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | MIDGEE | MIER1.2A | 0.0439 | KM | BW01ML623 | 0.137 | BW01ML623 | 0.1809 | KM |  |  |  |  | 620.653 | 620.697 | 2028-06-30 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 16.5 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115842&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | BASELOAD | COAL | 002000115842 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ ME 11A/B | TO000876 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | MIDGEE | MIER1.2A | 0.047 | KM | BW02ML623 | 0.2349 | BW02ML623 | 0.188 | KM |  |  |  |  | 621.092 | 621.045 | 2028-06-30 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 12.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | IFC due by 30 June 2025, FY26 Construction. Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043994&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000043994 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ MM1 | TO000878 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 504160 | Blackwater | MOUNT MILLER | MM1 | 0.0439 | KM | BW01FK0 | 0.1449 | BW01FK0 | 0.1449 | KM |  |  |  |  | 0.15 | [6 empty] | 3.5 | 2.5 |  |  |  | 8.75 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | * 22.03.2021 21:21:28 AUSQLD Lachlan Prescott (R881571) * FY23 overallocated - moved to FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044004&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000044004 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WA10C | TO000369 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Goonyella | WAITARA | WA10C | 0.0539 | KM | GA02PL100 | 0.452 | GA02PL100 | 0.452 | KM |  |  |  |  | 100.45 |  | 2028-06-30 |  |  |  |  | 3.5 | 5 |  |  |  | 17.5 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043322&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000043322 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WA12A | TO001028 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Goonyella | WAITARA | WA12A | 0.069 | KM | GA02PL100 | 0.4849 | GA02PL100 | 0.4849 | KM |  |  |  |  | 100.49 |  | 2028-06-30 |  |  |  |  | 3.5 | 3.5 |  |  |  | 16.7 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043323&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000043323 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WA7AB | TO000317 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Goonyella | WAITARA | WA7AB | 0.069 | KM | GA02ML98 | 0.0369 | GA02ML98 | 0.0369 | KM |  |  |  |  | 98.04 |  | 2028-06-30 |  |  |  |  | 3.5 | 5 |  | 3.5 |  | 14.4 |  | 2023-03-31 |  | Turnout Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) CONSTRUCTION reschedule to FY26 PM rejected from FY25. Move to FY26 (tunrout scope TurnOVer workshop in April 2023) Awaiting a PCR from PM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000138144&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000138144 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WA7CD | TO000367 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 200000 | Goonyella | WAITARA | WA7CD | 0.0449 | KM | GA02PL98 | 0.1449 | GA02PL98 | 0.1 | KM |  |  |  |  | 98.145 |  | 2028-06-30 |  |  |  |  | 4 | 5 |  | 3.5 |  | 14.4 |  | 2023-03-31 |  | Turnout Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290217 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (consulted with Emma-Kate and Gwenda Murphy) CONSTRUCTION reschedule to FY26 PM rejected from FY25. Move to FY26 (tunrout scope TurnOVer workshop in April 2023) Awaiting a PCR from PM
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043324&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000043324 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WA9A | TO000368 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Goonyella | WAITARA | WA9A | 0.0369 | KM | GA02PL98 | 0.168 | GA02PL98 | 0.2049 | KM |  |  |  |  | 98.17 |  | 2028-06-30 |  |  |  |  | 3 | 5 |  | 5 |  | 14.4 |  | 2023-03-31 |  | Turnout Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124175&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124175 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BFER3.3D | TO000738 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | BLUFF |  | 0.0259 | KM | BW04PL169 | 0.897 | BW04PL169 | 0.8709 | KM |  |  |  |  | 169.897 |  | 2028-05-27 |  |  |  |  | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20280527 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124178&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124178 | TURNOUTS ¦ DESIGN ¦ IFC ¦ BFER3.2E | TO000739 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | BLUFF (ON LOOP TRACK) |  | 0.0229 | KM | BW04PL169 | 0.5979 | BW04PL169 | 0.6209 | KM |  |  |  |  | 169.598 |  | 2028-05-27 |  |  |  |  | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20280527 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Remove TO000742 (169.645KM ER3.2E(SDG) TURNOUT BLUFF) as part of the renewal. Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124181&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124181 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO001155 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW17YR0 | 0.4829 | BW17YR0 | 0.511 | KM |  |  |  |  | 0.483 | [21 empty] | Outstanding notification | NWSC |  | 20280527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124172&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124172 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 214A | TO001172 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH | CH 214A | 0.029 | KM | BW08YR533 | 0.779 | BW08YR533 | 0.808 | KM |  |  |  |  | 533.779 | [21 empty] | Outstanding notification | NWSC |  | 20280527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124187&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124187 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 215B | TO001177 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | CALLEMONDAH | CH 215B | 0.028 | KM | BW21YR0 | 0.127 | BW21YR0 | 0.099 | KM |  |  |  |  | 0.127 | [21 empty] | Outstanding notification | NWSC |  | 20280527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124051&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124051 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 217A/B | TO001183 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 56800 | Blackwater | CALLEMONDAH | 217 A/B | 0.032 | KM | BW21YR2 | 0.3119 | BW21YR2 | 0.28 | KM |  |  |  |  | 534.698 |  | 2028-05-27 |  |  |  |  | 3 | 5 |  |  |  | 12.3 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280527 | TURNOUTS ¦ EARLY DESIGN ¦ RENEWAL ¦ CH 217A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 235A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over to CH217 turnout (from CH 274). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts. PCR 5349 PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124058&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124058 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 235A/B | TO001182 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 56800 | Blackwater | CALLEMONDAH | 235A/B | 0.0309 | KM | BW21YR2 | 0.199 | BW21YR2 | 0.168 | KM |  |  |  |  | 2.178 | 2.147 | 2028-05-27 |  |  |  |  | 3 | 5 |  |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280527 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 235A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over with CH 235A/B turnout (from CH 276A). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124071&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124071 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 281A/B | TO001139 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 56800 | Blackwater | CALLEMONDAH | 281A/B | 0.033 | KM | BW11BL2 | 0.4949 | BW11BL2 | 0.528 | KM |  |  |  |  | 2.495 | 2.528 | 2028-05-27 |  |  |  |  | 4.2 | 5 |  |  |  | 14.7 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280527 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CH 281A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115837&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000115837 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WA45A | TO000698 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 1000 | Blackwater | WARREN | WR45A | 0.0359 | KM | BW04ML25 | 0.541 | BW04ML25 | 0.505 | KM |  |  |  |  | 24.536 | 24.5 | 2028-05-27 |  |  |  |  | 3.5 | 3.5 | 4.1 | 3 |  | 14.35 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280227 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115836&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000115836 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WR46A | TO000697 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 59500 | Blackwater | WARREN | WR46A | 0.0379 | KM | BW04ML25 | 0.444 | BW04ML25 | 0.406 | KM |  |  |  |  | 24.439 | 24.401 | 2028-05-27 |  |  |  |  | 3.5 | 3.5 | 4.1 | 4 |  | 14.35 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280527 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction Two TOR in one project POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118509&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000118509 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WD 7B/C | TO000670 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 74950 | Blackwater | WESTWOOD | WD7B/C | 0.0369 | KM | BW03ML47 | 0.505 | BW03ML47 | 0.468 | KM |  |  |  |  | 46.507 | 46.47 | 2028-05-27 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 12.6 |  |  |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280511 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118506&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000118506 | TURNOUTS ¦ DESIGN ¦ IFC ¦ WD ER1.2A | TO000705 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 84330 | Blackwater | WESTWOOD | WDER1.2A | 0.0359 | KM | BW04ML46 | 0.767 | BW04ML46 | 0.7309 | KM |  |  |  |  | 45.774 | 45.738 | 2028-05-27 |  |  |  |  | 4 | 3 | 4.2 | 4 |  | 13.5 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280527 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO RH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124147&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000124147 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AL 7A/B | TO000854 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | ALDOGA | AL 7A/B | 0.0459 | KM | BW01ML555 | 0.9879 | BW01ML555 | 0.9419 | KM |  |  |  |  | 555.988 |  | 2028-02-27 | [19 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124144&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000124144 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AL 7C/D | TO000899 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | ALDOGA | AL 7C/D | 0.0519 | KM | BW02ML555 | 0.888 | BW02ML555 | 0.9399 | KM |  |  |  |  | 555.888 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124138&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000124138 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AL 8A/B | TO000898 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | ALDOGA | AL 8A/B | 0.047 | KM | BW02ML555 | 0.8659 | BW02ML555 | 0.8189 | KM |  |  |  |  | 555.866 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124141&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | FUTURE SCOPE | COAL | 002000124141 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AL 8C/D | TO000856 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | ALDOGA | AL 8C/D | 0.049 | KM | BW01ML555 | 0.767 | BW01ML555 | 0.8159 | KM |  |  |  |  | 555.767 |  | 2028-02-27 | [19 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124132&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124132 | TURNOUTS ¦ DESIGN ¦ IFP ¦ AR 11A/B | TO000614 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | AROONA | AR 11A/B | 0.0359 | KM | BW03ML94 | 0.542 | BW03ML94 | 0.5779 | KM |  |  |  |  | 94.542 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124135&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124135 | TURNOUTS ¦ DESIGN ¦ IFP ¦AR 11C/D | TO000719 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Blackwater | AROONA | AR 11C/D | 0.0359 | KM | BW04ML94 | 0.6129 | BW04ML94 | 0.5769 | KM |  |  |  |  | 94.613 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124162&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124162 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000497 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT |  | 0.0449 | KM | GA01BD3 | 0.083 | GA01BD3 | 0.0379 | KM |  |  |  |  | 3.083 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124153&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124153 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000496 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT |  | 0.048 | KM | GA01BA3 | 0.4109 | GA01BA3 | 0.459 | KM |  |  |  |  | 3.411 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124165&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124165 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000104 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT |  | 0.049 | KM | GA02BA3 | 0.4349 | GA02BA3 | 0.386 | KM |  |  |  |  | 3.435 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124168&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124168 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000568 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT |  | 0.047 | KM | GA02BA3 | 0.627 | GA02BA3 | 0.5799 | KM |  |  |  |  | 3.627 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124159&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124159 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HP 11C/D | TO000567 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT | HP 11C/D | 0.0369 | KM | GA02BA3 | 0.643 | GA02BA3 | 0.68 | KM |  |  |  |  | 3.643 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124156&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000124156 | TURNOUTS ¦ DESIGN ¦ IFP ¦ HP11A/B | TO000493 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | HAY POINT | HP11A/B | 0.0449 | KM | GA01BA3 | 0.8519 | GA01BA3 | 0.807 | KM |  |  |  |  | 3.852 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124150&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000124150 | TURNOUTS ¦ DESIGN ¦ IFP ¦ YN 48A/B | TO000336 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | YUKAN | YN 48A/B | 0.033 | KM | GA02ML29 | 0.398 | GA02ML29 | 0.4309 | KM |  |  |  |  | 29.398 | [21 empty] | Outstanding notification | NWSC |  | 20280227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103958&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | FUTURE SCOPE | COAL | 002000103958 | TURNOUTS ¦ DESIGN ¦ IFP ¦ MO10 | TO000823 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 0 | Blackwater | MEMOOLOO | MO 10 | 0.032 | KM | BW06ML47 | 0.8639 | BW06ML47 | 0.8319 | KM |  |  |  |  | 47.864 | 47.832 | 2028-02-27 |  |  |  |  | 4 | 1.5 |  |  |  | 13.2 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG |  | 20280227 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ MO10 Defer the Design to FY25 Maintain the turnout reliability via Maintenace Strategy and C16. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066278&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000066278 | MA HBD HWD Tech Options | MA | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 10000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | REJC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000087327&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000087327 | Main Line Pan Cam BW | BW | CONTROL SYSTEMS | ASSET PROTECTION | MAINLINE PANCAM | RENEWAL | 1 | UNIT | 1500000 | Blackwater | BW SYSTEM |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2023-06-30 | [7 empty] | 25 |  | 25 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | MEDIUM |  | LOW | HIGH | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053166&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000053166 | Wagon Scanner at Moorvale | ST007160 | CONTROL SYSTEMS | ASSET PROTECTION | WAGON SCANNER AT MOORVALE | RENEWAL | 1 | UNIT | 400000 | Goonyella | MOORVALE |  | 0 | KM | GA15ML5 | 0.4899 | GA15ML5 | 0.4899 | KM | [6 empty] | 2022-06-30 | [7 empty] | 25 |  | 25 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046850&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000046850 | CS Technology Renewal | ST005860 | CONTROL SYSTEMS | CONTROL SYS TECHNOLOGY RENEWAL |  | RENEWAL | 1 | LUMPSUM | 120000 | Goonyella | MACKAY | MACKAY | 0 | KM | GA46CR0 | 959.3999 | GA46CR0 | 959.3999 | KM | [6 empty] | 2024-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN |  | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090690&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000090690 | CS CER Relocation | ST003940 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 200000 | Goonyella | BOLINGBROKE CER | BOLINGBROKE CER | 0 | KM | GA01ML60 | 0.6199 | GA01ML60 | 0.6199 | KM |  |  |  |  | 60.491 | 60.491 | 2026-06-30 |  |  |  |  | 5 |  | 1 |  | 1 |  |  | 2024-03-28 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | HIGH | LOW | LOW | Outstanding notification | SCPR |  | 20280630 | Pushed to FY28. Scope Integrated with the SER upgrade happening at the same time. As the SER N4 is moving to FY28 we will move this one.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085336&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085336 | CSI Equipment Room Renewal | ST006150 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Blackwater | KOORILGAH CER | KOORILGAH CER | 0 | KM | BW13ML12 | 0.876 | BW13ML12 | 0.876 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085338&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085338 | CSI Equipment Room Renewal | ST006160 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Blackwater | TIKARDI CER | TIKARDI CER | 0 | KM | BW05ML5 | 0.511 | BW05ML5 | 0.511 | KM | [6 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000109711&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000109711 | CSI CER Renewal | ST004060 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML28 | 0.806 | GA01ML28 | 0.806 | KM | [6 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119603&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119603 | CSI Dehydrator Renewal FY28 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 45000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119602&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119602 | CSI Dehydrator Renewal FY28 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 45000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085421&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000085421 | CSI Generator Renewal | NL | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 170000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078694&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000078694 | CSI GENSET RENEWAL | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 180000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630 | * 10.06.2021 17:25:22 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046880&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000046880 | CSI GENSET RENEWAL | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | UNIT | 180000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | ALL |  |  |  | 4 | 2.5 |  |  |  | 10 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085428&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000085428 | CSI NMS Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085423&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000085423 | CSI NMS Renewal | ST005490-E5 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 240000 | Blackwater |  |  | 0 | KM | BW64CR638 | 0.8 | BW64CR638 | 0.8 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | REJC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085422&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000085422 | CSI NMS Renewal | ST005810-65 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 240000 | Goonyella |  |  | 0 | KM | GA46CR959 | 0.4 | GA46CR959 | 0.4 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | REJC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086527&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000086527 | CSI OF Renewal | ST008470-52 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2700 | METERS | 324000 | Blackwater | BLACKWATER TSC |  | 2.5779 | KM | BW03ML186 | 0.3709 | BW03ML188 | 0.9499 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086523&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000086523 | CSI OF Renewal | ST000050-30 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5500 | METERS | 660000 | Blackwater | BLUFF FSS |  | 5.3079 | KM | BW03ML173 | 0.2049 | BW03ML178 | 0.5 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086526&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000086526 | CSI OF Renewal | ST001850-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 600000 | Blackwater | BOONAL MIW |  | 0.667 | KM | BW03ML181 | 0.33 | BW03ML182 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086525&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000086525 | CSI OF Renewal | ST002430-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2000 | METERS | 240000 | Blackwater | BOONAL SER |  | 1.931 | KM | BW03ML179 | 0.379 | BW03ML181 | 0.33 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086588&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000086588 | CSI OF Renewal | ST006090-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 18500 | METERS | 2368000 | Blackwater | COMET CER | YAMALA CER | 18.385 | KM | BW03ML224 | 0.2089 | BW03ML242 | 0.5749 | KM | [6 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046832&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | STRATEGIC | COAL | 002000046832 | CSI OF Renewal -GLADS to CALLE CER | ST003460-17 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5226 | METERS | 1099702 | Blackwater | GLADSTONE CER | CALLEMONDAH CER | 4.87 | KM |  | 0 |  | 0 | [5 empty] | 534 | 529.13 | 2028-06-30 | ALL |  |  |  | 4 | 1 |  | 1 |  | 12 |  | 2023-09-01 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079390&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | STRATEGIC | COAL | 002000079390 | CSI OF Renewal - STH GLADS to GLADS | ST005630-08 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2805 | METERS | 619761 | Moura | GLT-CER TO SGT-CER O/FBR CABLE |  | 2.6749 | KM | NC02ML529 | 0.13 | NC02ML526 | 0.46 | KM |  |  |  |  | 529.13 | 526.46 | 2028-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086916&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000086916 | CSI OF Renewal | ST006560-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12500 | METERS | 1125000 | Goonyella | HAIL CREEK AT0 | HAIL CREEK ATN | 12.573 | KM | GA07ML18 | 0.1059 | GA07ML30 | 0.68 | KM | [6 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086917&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000086917 | CSI OF Renewal | ST006570-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 11000 | METERS | 990000 | Goonyella | HAIL CREEK ATN | HAIL CREEK SER | 11.162 | KM | GA07ML30 | 0.068 | GA07ML41 | 0.23 | KM | [6 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085521&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085521 | CSI OF Renewal | ST006070-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 7000 | METERS | 896000 | Blackwater | NOGOA CER | EMERALD MWR/CER | 2.1099 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086515&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic | STRATEGIC | COAL | 002000086515 | CSI OF Renewal - PARANA to STH GLAD | ST005640-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1509 | METERS | 620207 | Moura | SOUTH GLADSTONE |  | 2.039 | KM | NC02ML526 | 0.46 | NC02ML522 | 0.3719 | KM |  |  |  |  | 526.46 | 522.372 | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 22.5 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086584&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000086584 | CSI OF Renewal | ST006100-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 21000 | METERS | 1890000 | Blackwater | TOLMIES CER | COMET CER | 21.0199 | KM | BW03ML203 | 0.111 | BW03ML224 | 0.2089 | KM | [6 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086589&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000086589 | CSI OF Renewal | ST006050-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 20500 | METERS | 2624000 | Blackwater | YAMALA CER | NOGOA CER | 20.463 | KM | BW03ML242 | 0.5749 | BW03ML262 | 0.9599 | KM | [6 empty] | 2028-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074765&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000074765 | CSI OF Renewal | ST003260-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12000 | METERS | 1440000 | Blackwater | YAN YAN SER | GREGORY CER | 11.3469 | KM | BW08ML50 | 0.89 | BW08ML62 | 0.231 | KM |  |  |  |  | 50.89 | 62.231 | 2028-06-30 |  |  |  |  | 4.5 | 5 |  |  |  | 10 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM | LOW | LOW | MEDIUM | Notification in process | SCPR INIF |  | 20280630 | * 23.03.2021 08:10:18 AUSQLD Scott Andrews (R003573) * Renew OF at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119527&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119527 | CSI Radome Renewal FY28 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 70000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119526&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119526 | CSI Radome Renewal FY28 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 100 | SITE | 70000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 |  |  | 20 | [5 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085553&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000085553 | CSI Structure Renewal | ST006230-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | STRUCTURE | RENEWAL | 1 | SITE | 200000 | Moura | SOUTH GLADSTONE |  | 0 | KM | NC02ML529 | 0.1059 | NC02ML529 | 0.1059 | KM | [6 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046886&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000046886 | CSI Tower Guyed Refurb | ST006380-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 30000 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | HEAVY MAINTENANCE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046856&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000046856 | CSI Tower Renewal | ST005950-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 30000 | Blackwater | CAPELLA | CAPELLA | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | HEAVY MAINTENANCE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046824&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000046824 | CSI Tower Guyed Refurb | ST005280-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 30000 | Blackwater | CROCKER PEAK | CROCKER PEAK | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2028-06-30 | ALL |  |  |  | 4 | 2.5 |  |  |  | 10 |  |  |  | Transmission & Data Renewals | HEAVY MAINTENANCE | LOW | MEDIUM | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046855&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000046855 | CSI Tower Guyed Refurb | ST005510-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 30000 | Blackwater | GREGORY | GREGORY | 0 | KM | BW08ML62 | 0.2469 | BW08ML62 | 0.2469 | KM | [6 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | HEAVY MAINTENANCE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046857&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000046857 | CSI Tower Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 200000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046821&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000046821 | CSI Tower Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 200000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046858&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000046858 | CSI Tower Guyed Refurb | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 30000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2028-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | HEAVY MAINTENANCE | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124723&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000124723 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 7 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124066&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000124066 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124365&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000124365 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065470&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000065470 | SIG_Interlocking Renewal_GA_Bolingbr_Com | ST003940-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | SITE | 2500000 | Goonyella | BOLINGBROKE |  | 0 | KM | GA01ML60 | 0.6199 | GA01ML60 | 0.6199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | * 28.09.2020 09:17:34 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043583&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000043583 | SIG_Interlocking Renewal_GA_Yukan_Bld | ST004060 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | SITE | 2000000 | Goonyella | YUKAN |  | 0 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 3 | 5 |  |  |  | 15 |  | 2019-07-15 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065479&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000065479 | SIG_Interlocking Renewal_GA_Balook_Com | ST003880-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 1000000 | Goonyella | BALOOK |  | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 10 | 10 |  |  |  | 100 |  | 2022-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20280630 | * 28.09.2020 10:23:07 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108337&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000108337 | SIG_Interlocking Renewal_MA_Stirrat_Des | ST003830-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | STIRRAT | STIRRAT | 0 | KM | MA01ML39 | 0.404 | MA01ML39 | 0.404 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 |  | 25 | [5 empty] | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20260630 | Replace Stirrat VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares. Replace Stirrat-S towe(Graham) AzS600 axle counter block with another axle counter (eg Frauscher).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125119&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000125119 | SIG_Interlocking Renewal_MA_Stowe_Bld | ST003860-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1800000 | Moura | STOWE | BYELLEE | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Construction the replacement of VPI Stowe, removal of Graham and replace AzS600 axle counter in Byellee-Stowe block. Replace of Graham Interlocking with Object Controller of Stowe if required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123834&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000123834 | SIG_Interlocking Renewal - GA_JB_Des | ST006030-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | WESTLOCK REPLACEMENT | ASSESSMENT | 1 | SITE | 1500000 | Goonyella | JILALAN BYPASS | JILALAN YARD | 0 | KM | GA01ML20 | 0.0299 | GA01ML20 | 0.0299 | KM | [11 empty] | 5 | 4 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Design the replacement of Jilalan Bypass and Jilalan Yard master interlocking. Consider technology, supplier arrangement, schedule, changes to housings and power supplies, interfaces to other interlockings and maintenance, and resourcing with regards to other pro jects.Review splitting the bypass and yard into 2 separate interlockings with separate telemetry.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060015&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060015 | SIG_Replace M23A_GA_BK8A_Com | TO000212-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.4789 | GA01ML74 | 0.4789 | KM |  |  |  |  | 74.479 | 74.479 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:11:26 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060016&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060016 | SIG_Replace M23A_GA_BK8D_Com | TO000323-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BALOOK | BALOOK | 0 | KM | GA02ML74 | 0.5779 | GA02ML74 | 0.5779 | KM |  |  |  |  | 74.578 | 74.578 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:11:37 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060013&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060013 | SIG_Replace M23A_GA_BK7A_Com | TO000322-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BALOOK | BALOOK | 0 | KM | GA02ML74 | 0.5989 | GA02ML74 | 0.5989 | KM |  |  |  |  | 74.599 | 74.599 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:10:57 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060014&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060014 | SIG_Replace M23A_GA_BK7D_Com | TO000213-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BALOOK | BALOOK | 0 | KM | GA01ML74 | 0.6979 | GA01ML74 | 0.6979 | KM |  |  |  |  | 74.698 | 74.698 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:11:15 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060039&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060039 | SIG_Replace M23A_GA_BO8A_Com | TO000450-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML60 | 0.401 | GA01ML60 | 0.401 | KM |  |  |  |  | 60.401 | 60.401 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:15:22 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060040&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060040 | SIG_Replace M23A_GA_BO8D_Com | TO000326-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA02ML60 | 0.5 | GA02ML60 | 0.5 | KM |  |  |  |  | 60.5 | 60.5 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:15:33 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060037&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060037 | SIG_Replace M23A_GA_BO12A_Com | TO000325-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA02ML60 | 0.521 | GA02ML60 | 0.521 | KM |  |  |  |  | 60.521 | 60.521 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:15:05 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060038&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000060038 | SIG_Replace M23A_GA_BO12D_Com | TO000451-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | BOLINGBROKE | BOLINGBROKE | 0 | KM | GA01ML60 | 0.6199 | GA01ML60 | 0.6199 | KM |  |  |  |  | 60.62 | 60.62 | 2028-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  | LOW | LOW | LOW | Outstanding notification | SCPR INIF |  | 20280630 | * 23.06.2020 12:15:14 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126554&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000126554 | SIG_Train Detection_NL_Binbee_Des | ST008070-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | DESIGN | 6 | UNITS | 350000 | Newlands | BINBEE | ARMUNA | 8.0579 | KM | NL01ML36 | 0.1469 | NL01ML44 | 0.2089 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Design phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The 6 blocks are a block btn Binbee and Aberdeen, 4 tracks in Aberdeen and a block between Aberdeen and Armuna. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126577&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000126577 | SIG_Train Detection_NL_Armuna_Pln | ST008270-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | PLANNING | 2 | UNITS | 50000 | Newlands | ARMUNA | PRING | 0 | KM | NL01ML24 | 0.8589 | NL01ML24 | 0.8589 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Planning phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The 2 blocks are a block btn Armuna and Buckley and a block between Buckley and Pring. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104866&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000104866 | SIG_Train Detection_NL_Almoola_Com | ST008620 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 2 | UNIT | 1300000 | Newlands | ALMOOLA | BRIABA | 0 | KM | NL01ML71 | 0.921 | NL01ML71 | 0.921 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | Commissioning phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The blocks are 2 blocks btn Almoola and Briaba and a block between Briaba and Binbee. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065531&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000065531 | SIG_Train Detection_BW_Windah_CSEE_Des | ST004470 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 18 | UNIT | 990000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW03ML57 | 0.629 | BW03ML57 | 0.629 | KM | [6 empty] | 2022-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630 | * 28.09.2020 11:02:28 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065530&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000065530 | SIG_Train Detection_BW_Westwood_CSEE_Com | ST004440 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 41 | UNIT | 5500000 | Blackwater | WESTWOOD | WESTWOOD | 0 | KM | BW03ML46 | 0.6939 | BW03ML46 | 0.6939 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20280630 | * 28.09.2020 11:01:50 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085340&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000085340 | SIG_Train Detection_GA_Broadlea_ML_Des | ST000980 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 1089860 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML155 | 0.8339 | GA01ML155 | 0.8339 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  | 2022-03-31 |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20280630 | Replace all track circuits (primarily defunct ML tracks) with 20 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125898&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | BASELOAD | COAL | 002000125898 | SIG_Train Detection_GA_NthGoonyel_ML_Pln | ST004920 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | PLANNING | 1 | SITE | 66000 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0 | KM | GA01ML213 | 0.6999 | GA01ML213 | 0.6999 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Replace all track circuits (primarily defunct ML tracks) with 11 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125266&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000125266 | SIG_Train Detection_GA_Goonyella_ML_Com | ST004740-04 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 600000 | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA13ML195 | 0.4199 | GA13ML195 | 0.4199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Planning phase to replace 5 ML track circuits in the balloon loop (freq E,F) with 2 Frauscher tracks. Tracks with ML freq are 17BBT(1xF) and 17B5AT-17BA2AT(2xE,2xF). This interlocking is relay based and hence the resetting of the 2 axlecounter tracks need to be implemented with relays.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103825&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000103825 | SIG_Train Detection_GA_Moorvale_ML_Com | ST006650 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 3247000 | Goonyella | MOORVALE | MOORVALE | 0 | KM | GA03ML8 | 0.5999 | GA03ML8 | 0.5999 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20280630 | Replace all track circuits (primarily defunct ML tracks) with 17 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100908&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000100908 | CS Transmission DMR Link | ST005350-25 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 380000 | Newlands | BRIABA | SUMMER HILL | 0 | KM | NL09CR0 | 0 | NL09CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100907&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000100907 | CS Transmission DMR Link | ST005930-24 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 380000 | Goonyella | COLSTON PARK | TIERAWOOMBA | 0 | KM | GA37CR0 | 0 | GA37CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100906&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000100906 | CS Transmission DMR Link | ST005910-29 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 380000 | Goonyella | THREE SISTERS | COLSTON PARK | 0 | KM | GA47CR901 | 0 | GA47CR901 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100905&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000100905 | CS Transmission DMR Link | ST005530-26 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 380000 | Blackwater | WALLAROO | BLUFF | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100955&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000100955 | CS Transmission IOT | BW | CONTROL SYSTEMS | TRANSMISSION | IOT | EXECUTION | 1 | LUMPSUM | 100000 | Blackwater | BLACKWATER STATIONS | BLACKWATER STATIONS | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [9 empty] | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100953&DY_MAB=X&~OKCODE=ONLI | FY28 |  | STRATEGIC | COAL | 002000100953 | CS Transmission IOT | MA | CONTROL SYSTEMS | TRANSMISSION | IOT | EXECUTION | 1 | LUMPSUM | 80000 | Moura | MOURA STATIONS | MOURA STATIONS | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [9 empty] | 100 |  |  |  | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100293&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000100293 | CS Transmission Power Supply | ST008060-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | ABERDEEN SER | ABERDEEN SER | 0 | KM | NL01ML34 | 0.898 | NL01ML34 | 0.898 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101699&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101699 | CS Transmission Power Supply | ST006380-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | BLAIR ATHOL MWR | BLAIR ATHOL MWR | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101664&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101664 | CS Transmission Power Supply | ST002410-18 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | BLUFF SER | BLUFF SER | 0 | KM | BW03ML170 | 0.203 | BW03ML170 | 0.203 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101701&DY_MAB=X&~OKCODE=ONLI | FY28 | RIM Infrastructure |  | RIM | 002000101701 | CS Transmission Power Supply | ST009280-19 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | CAVAL RIDGE SER | CAVAL RIDGE SER | 0 | KM | GA24ML6 | 0.5889 | GA24ML6 | 0.5889 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101665&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101665 | CS Transmission Power Supply | ST002940-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | CLERMONT MWR | CLERMONT MWR | 0 | KM | BW03ML100 | 0.26 | BW03ML100 | 0.26 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101692&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101692 | CS Transmission Power Supply | ST005280-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | CROCKER PEAK MWR | CROCKER PEAK MWR | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101667&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101667 | CS Transmission Power Supply | ST003020-34 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | EMERALD MWR | EMERALD MWR | 0 | KM | BW57CR0 | 0 | BW57CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101690&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101690 | CS Transmission Power Supply | ST005160-30 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | GRACEMERE SER | GRACEMERE SER | 0 | KM | BW03ML8 | 0.65 | BW03ML8 | 0.65 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101693&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101693 | CS Transmission Power Supply | ST005510-39 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | GREGORY MWR | GREGORY MWR | 0 | KM | BW59CR0 | 0 | BW59CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101668&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101668 | CS Transmission Power Supply | ST003150-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | GREGORY SR1 | GREGORY SR1 | 0 | KM | BW09ML62 | 0.275 | BW09ML62 | 0.275 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101691&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101691 | CS Transmission Power Supply | ST005170-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | KABRA SER | KABRA SER | 0 | KM | BW03ML13 | 0.5799 | BW03ML13 | 0.5799 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101662&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101662 | CS Transmission Power Supply | ST002860-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Newlands | MCNAUGHTON SER | MCNAUGHTON SER | 0 | KM | NL04ML81 | 0.53 | NL04ML81 | 0.53 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101702&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101702 | CS Transmission Power Supply | ST009550-16 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | MORANBAH MWR | MORANBAH MWR | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101695&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101695 | CS Transmission Power Supply | ST004840-26 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | MORANBAH SER | MORANBAH SER | 0 | KM | GA05ML18 | 0.2939 | GA05ML18 | 0.2939 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101700&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101700 | CS Transmission Power Supply | ST009220-16 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | MORANBAH SR2 | MORANBAH SR2 | 0 | KM | GA05ML20 | 0.8359 | GA05ML20 | 0.8359 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101697&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101697 | CS Transmission Power Supply | ST005940-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | PINE MOUNTAIN MWR | PINE MOUNTAIN MWR | 0 | KM | GA43CR0 | 0 | GA43CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101236&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101236 | CS Transmission Power Supply | ST008150-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Newlands | PRING SER 1 | PRING SER 1 | 0 | KM | NL01ML3 | 0.22 | NL01ML3 | 0.22 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101663&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101663 | CS Transmission Power Supply | ST004360-24 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | ROCKLANDS SER | ROCKLANDS SER | 0 | KM | BW03ML0 | 0.25 | BW03ML0 | 0.25 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101696&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101696 | CS Transmission Power Supply | ST005900-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | SARINA MWR | SARINA MWR | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101703&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101703 | CS Transmission Power Supply | ST009410-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | WANDOO WSS | WANDOO WSS | 0 | KM | GA01ML92 | 0 | GA01ML92 | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101694&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000101694 | CS Transmission Power Supply | ST000770-38 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Goonyella | WOTONGA FSS | WOTONGA FSS | 0 | KM | GA01ML175 | 0.19 | GA01ML175 | 0.19 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078652&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000078652 | CS Transmission Power Supply | ST000020-28 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 34000 | Blackwater | WYCARBAH FS |  | 0 | KM | BW03ML33 | 0.4199 | BW03ML33 | 0.4199 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | * 10.06.2021 16:01:58 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101669&DY_MAB=X&~OKCODE=ONLI | FY28 | Dual Traffic |  | COAL | 002000101669 | CS Transmission Power Supply | ST003870-22 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37000 | Blackwater | YARWUN SER | YARWUN SER | 0 | KM | BW01ML547 | 0.275 | BW01ML547 | 0.275 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093804&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000093804 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEW | 10 | SITE | 140000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093779&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000093779 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEW | 10 | SITE | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093803&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000093803 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEW | 10 | SITE | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission & Data Renewals |  | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101625&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000101625 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 130000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101624&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000101624 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 130000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093763&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000093763 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 8 | SITE | 110000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093762&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000093762 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 8 | SITE | 110000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093761&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000093761 | CS Transmission Supervisory Card | NL | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 8 | SITE | 110000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | 4 |  | 4 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | RRIG |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101258&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000101258 | CS Transmission TDM Replacement | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101259&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  | COAL | 002000101259 | CS Transmission TDM Replacement | GA | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120134&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000120134 | CS Transmission Tele Battery Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120135&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000120135 | CS Transmission Tele Battery Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120133&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000120133 | CS Transmission Tele Battery Renewal | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Moura | TBC | TBC | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120136&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000120136 | CS Transmission Tele Battery Renewal | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102837&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000102837 | CS TETRA AP Site Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella | GOONYELLA SYSTEM | GOONYELLA SYSTEM | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 5 |  |  | 4 |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM | LOW | LOW | MEDIUM | Outstanding notification | REJC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119722&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119722 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119723&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000119723 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 500000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000093771&DY_MAB=X&~OKCODE=ONLI | FY28 |  | BASELOAD | COAL | 002000093771 | CS Transmission TSI | BW | CONTROL SYSTEMS | TRANSMISSION | TSI | RENEWAL | 1 | SITE | 180000 | Blackwater | GLADSTONE PORT | GLADSTONE PORT | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2023-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120195&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic | STRATEGIC | COAL | 002000120195 | OVERHEAD¦FW CLEARANCE¦RENEWAL¦YUKAN | GA-0201-00201C | ELECTRICAL | OVERHEAD | FW CLEARANCE IMPROVEMENT | RENEWAL | 1 | SITE | 250000 | Goonyella | YUKAN | YUKAN | 1.165 | KM | GA/28/788/TFR2 | 0 | GA/29/953/SR | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | AREQ |  | 20280630 | Commoning electrical subsections 201A, B and C to remove the FW hazard. See attached report, estimate and risk assessment.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103837&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000103837 | OVERHEAD¦GOONYELLA PORTS OHL¦RENEWAL | GA-0912 | ELECTRICAL | OVERHEAD | GOONYELLA PORTS OHL RENEWAL | RENEWAL | 1 | UNIT | 1713000 | Goonyella | DALRYMPLE BAY | HAY POINT | 9.6679 | KM | DL/-0/068/DR1 | 0 | GA/9/600/D | 0 | KM | [6 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104012&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104012 | PLACEHOLDER FY28 HEADSPANS | GA | ELECTRICAL | OVERHEAD | HEADSPANS | RENEWAL | 12 | UNITS | 1680000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for headspan renewals in FY28. Assume 12 headspans/year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074788&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000074788 | SECTION INSULATOR - JILALAN | SQ020360 | ELECTRICAL | OVERHEAD | SECTION INSULATOR | RENEWAL | 1 | UNIT | 100000 | Goonyella | JILALAN |  | 0 | KM |  | 0 |  | 0 | [18 empty] | 5334 |  |  | OH Reactive Works - Fix on Fail | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20280126 | 06/02/24 EK: Renewal date pushed out to FY28 from FY24 to align with notification 2000134889. No impact on the overall renewal strategy.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103994&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103994 | PLACEHOLDER FY28 SI/NS BW | BW | ELECTRICAL | OVERHEAD | SI/NS | RENEWAL | 2 | UNITS | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for SI/NS renewals in FY28. Assume 2 SI/NS per system per year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103993&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103993 | PLACEHOLDER FY28 SI/NS GA | GA | ELECTRICAL | OVERHEAD | SI/NS | RENEWAL | 2 | UNITS | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for SI/NS renewals in FY28. Assume 2 SI/NS per system per year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103995&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103995 | SMALL COMPONENT RENEWALS BW | BW | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | UNITS | 1000000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for small component renewals in FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103996&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103996 | SMALL COMPONENT RENEWALS GA | GA | ELECTRICAL | OVERHEAD | SMALL COMPONENTS | RENEWAL | 1 | UNITS | 1000000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for small component renewals in FY28.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136254&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136254 | AT - BLAIR ATHOL ATS - AT1 | ST001390-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | GA05ML103 | 0.5849 | GA05ML103 | 0.5849 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136307&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136307 | AT - BOONAL ATS - AT1 | ST001980-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | BOONAL ATS | BOONAL ATS | 0 | KM | BW03ML179 | 0.448 | BW03ML179 | 0.448 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136308&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136308 | AT - BOONAL ATS - AT2 | ST001980-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | BOONAL ATS | BOONAL ATS | 0 | KM | BW03ML179 | 0.448 | BW03ML179 | 0.448 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136259&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136259 | AT - MORANBAH - VILLAFRANCA ATS - AT1 | ST001290-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | MORANBAH - VILLAFRANCA ATS | MORANBAH - VILLAFRANCA ATS | 0 | KM | GA05ML37 | 0.4319 | GA05ML37 | 0.4319 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136257&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136257 | AT - VILLAFRANCA-MOUNT MCLAREN ATS - AT1 | ST001310-01 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Goonyella | VILLAFRANCA-MOUNT MCLAREN | VILLAFRANCA-MOUNT MCLAREN | 0 | KM | GA05ML55 | 0.4969 | GA05ML55 | 0.4969 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000136306&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000136306 | AT - WALTON ATS - AT2 | ST001970-02 | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 1 | UNIT | 826079 | Blackwater | WALTON ATS | WALTON ATS | 0 | KM | BW03ML162 | 0.202 | BW03ML162 | 0.202 | KM | [6 empty] | 2028-05-31 |  |  |  |  | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20280222 | 23-02-24 EK: Renewal notification for FY28 AT Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075936&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000075936 | MI Renewal 241/2 Coppabella | SQ030264 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | OC/3/776/U | 0 | OC/3/776/U | 0 | KM |  |  |  |  | 3.776 | 3.776 | 2028-06-30 |  |  |  |  | 3.44 | 2.4 | 2 | 3.2 | 1 | 11.01 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 6/3/2023 R.Licis: Moved to FY28 in the interim
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075888&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000075888 | MI Renewal 242/2 Coppabella | SQ030611 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | COPPABELLA | COPPABELLA | 0 | KM | OC/3/932/D | 0 | OC/3/932/D | 0 | KM |  |  |  |  | 3.932 | 3.932 | 2028-06-30 |  |  |  |  | 3.94 | 2.4 | 2 | 3.2 | 1 | 12.61 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20280630 | 13/2/2022 R.Licis: To be relocated to FY25 when 241B/242C is getting done once PSC5 and SER has established communication. A separate telecom design to be done for this using a separate N4 noti. 5/3/2023 R.Licis: N4 design required for FY26 and Renewal (this noti) to be done in FY28
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074291&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000074291 | MI Renewal 902J/906E Jilalan | SQ030552 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/17/634/DM | 0 | GA/17/634/DM | 0 | KM |  |  |  |  | 17.634 | 17.634 | 2028-06-30 |  |  |  |  | 3.9 | 4.6 | 2 | 4.1 | 1 | 15.99 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY23 IN | 20280630 | * 31.03.2021 19:20:30 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 17/3/2022 R.Licis: Site Inspected in March 2022. Further access query to be followed up with Net Ops. Relocation of isolator may be required however it will involve design OHW mods and including U/G recabling. In the mean time, this site which was originally FY23 will be swapped with South Walker 232H/233A. This noti will be moved to FY25 and OHW design (if required) in FY24. PCR to be submitted. Discussion with Jason and Trent on existing access to be explored first. 5/3/2023 R.Licis: To be designed in FY26 and renew (this noti in FY28). Scoping to be done in FY25.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044512&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044512 | MI Renewal 905/4 Jilalan | SQ030563 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | JILALAN | JILALAN | 0 | KM | GA/22/804/UY | 0 | GA/22/804/UY | 0 | KM |  |  |  |  | 22.804 | 22.804 | 2028-06-30 |  |  |  |  | 2.9 | 4.8 | 2 | 4.2 | 1 | 12.18 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY23 IN | 20280630 | * 06.03.2020 14:32:42 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 905/4 * 22.03.2021 14:54:02 AUSQLD Rinaldo Licis (R851602) * MI 905/4 Jilalan swapped with MI 632/6 Goonyella. 905/4 to be done in FY23 now * 12.04.2021 16:21:44 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * 5/3/2023 R.Licis: Access difficult. Recommend the following: FY26 Scope (separate noti): Optioneering for removal/relocate FY28 Scope (This noti): Relocate or Remove isolator
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075929&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000075929 | MI Renewal 622/4 Mallawa | SQ030262 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MALLAWA | MALLAWA | 0 | KM | GA/167/747/D | 0 | GA/167/747/D | 0 | KM |  |  |  |  | 167.747 | 167.747 | 2028-06-30 |  |  |  |  | 3.44 | 2.4 | 2 | 3.2 | 1 | 11.01 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20280630 | 11/3/2022 R.Licis: Scope and inspection form attached. Confirm plant access with Jason. Moved to FY25 tentatively 18/3/2022: Inspection Scope form attached. Noti moved to FY25. Optioneer and design in FY24. 6/3/2023 R.Licis: Design in FY26 (new noti to be created) and Renew in FY28 (this noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044475&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000044475 | MI Renewal 282/2 Mindi | SQ030275 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Goonyella | MINDI | MINDI | 0 | KM | GA/120/720/D | 0 | GA/120/720/D | 0 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 4.1 | 4.4 | 2 | 4 | 1 | 16.4 | 3634 | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | LOW |  | LOW | LOW | Notification in process | NWSC | FY23 IN | 20280630 | * 10.11.2020 14:48:03 AUSQLD Zane Hooton (R875021) * Pushed out of FY21 due PCR-3634 * 12.04.2021 16:21:58 AUSQLD Jeremy Stevenson (R867415) * Std Design (could be change in unit rate based on lessons learnt for FY21) * * undertaken first including estimate. 24/10/2022 PCR has been requested for this. 6/3/2023 R.Licis: Access issue. Use new MI philosophy. Require to enter Design noti for FY26. Then renewal noti in FY28 (this noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053157&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000053157 | MI Renewal 542/2 Raglan | SQ030183 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 54828 | Blackwater | RAGLAN | RAGLAN | 0 | KM | N/584/102/D | 0 | N/584/102/D | 0 | KM |  |  |  |  | 584.102 |  | 2028-06-30 |  |  |  |  | 4.1 | 4.9 | 2 | 4.2 | 1 | 17.22 |  | 2020-03-06 | 2020-11-13 | Motorised Isolator Renewal | LIKE FOR LIKE |  |  |  |  | Notification in process | NWSC |  | 20280630 | * 06.03.2020 14:39:56 AUSQLD Emma-Kate Clyburn (R870828) * Isolator Number 542/2 Robin Chen's project - 2-4 April Closure 27.1.22 - Duane , am reallocating to your Work Centre, Our Substation staff have already decommissioned this Isolator, remainder of work is OHLE by Lines Staff to occur during system closures, Luke Davey PCR5324 - pushed from FY22 to FY25 (L.Schneider 6/5/22) 6/3/2023 R.Licis: To be optioneered using new MI philosophy document. Design noti to be created for FY26 and Renewal this noti for FY28 (this noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091913&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000091913 | MI Renewal 121/6 Tunnel West | SQ030595 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | TUNNEL WEST | TUNNEL WEST | 0 | KM | CW/75/964/U | 0 | CW/75/964/U | 0 | KM |  |  |  |  | 75.964 | 75.964 | 2028-06-30 |  |  |  |  | 3.44 | 3.15 | 2 | 3.6 | 1 | 12.38 |  |  |  |  | LIKE FOR LIKE | HIGH |  | HIGH | HIGH | Notification in process | NWSC | FY24 OUT | 20280630 | 15/2/2022 R.Licis: N4 created for FY24 8/3/2022 R.Licis: Inspected Scope attached. No mentioned if there is enough room for manual isolator. Renewal to be checked if it stays in FY24 or FY25. 11/3/2022 R.Licis: Tentatively pushed out to FY25 due to access issue. 6/3/2023 R.Licis: Access issue. To be scoped. Design in FY26(ti be created). Renewal in FY28 (this noti).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074280&DY_MAB=X&~OKCODE=ONLI | FY28 | Coal Traffic |  | COAL | 002000074280 | MI Renewal 811/4 Warren | SQ030536 | ELECTRICAL | POWER SYSTEMS | MI | RENEWAL | 1 | UNIT | 42535 | Blackwater | WARREN | WARREN | 0 | KM | CW/25/152/U | 0 | CW/25/152/U | 0 | KM |  |  |  |  | 25.152 | 25.152 | 2028-06-30 |  |  |  |  | 3.4 | 3.4 | 2 | 3.7 | 1 | 12.58 |  | 2021-03-31 | 2021-10-05 | Motorised Isolator Renewal | LIKE FOR LIKE | HIGH |  | HIGH | HIGH | Notification in process | NWSC | FY23 IN | 20280630 | * 31.03.2021 19:20:58 AUSQLD Tracy Holmes (R870040) * Std Design (could be change in unit rate based on lessons learnt for FY21) 4/3/2022 R.Licis: 811/4 Warren was originaly in FY23. Inspection site with Grant Kennedy was done early March 2022. Access for plant is an issue because. Optioneering to be done for solution. Therefore moved to FY25 on the interim. It is therefore replaced with Wycarbah 822/6 in FY23 6/3/2023: R.Licis: Optioneering required. Assume design in FY26 (new ntoi to be added) and Renewal in FY28 (this noti)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104020&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000104020 | PLACEHOLDER FY28 PSC RENEWALS BW | BW | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 2 | UNITS | 300000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for PSC site renewals in FY28. Assume 2 per system per year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103999&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103999 | PLACEHOLDER FY28 PSC RENEWALS GA | GA | ELECTRICAL | POWER SYSTEMS | PSC SITE RENEWAL | RENEWAL | 2 | UNITS | 300000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2028-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20280630 | Placeholder for PSC site renewals in FY28. Assume 2 per system per year.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103881&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103881 | Traction Substation Renewals | BW | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 1 | UNIT | 20631749 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103882&DY_MAB=X&~OKCODE=ONLI | FY28 |  |  |  | 002000103882 | Traction Substation Renewals | GA | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 14 | UNIT | 40736791 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20280630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125417&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000125417 | C60-ACP-BW-km | BW | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2023-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125419&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000125419 | C60-ACP-GA-km | GA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2023-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125420&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000125420 | C60-ACP-MA-km | MA | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2023-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125421&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000125421 | C60-ACP-NL-km | NL | CIVIL | ACCESS POINTS |  | REACTIVE WORKS | 1 | SITE | 100000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 |  | 0.5 | 5 | 1 | 25 |  | 2023-03-31 |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121184&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000121184 | FY29 ACCESS POINT DESIGN - IFC | BW | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT DESIGN IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121185&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000121185 | FY29 ACCESS POINT DESIGN IFC | GA | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121186&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000121186 | FY29 ACCESS POINT DESIGN IFC | MA | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT DESIGN IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121187&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000121187 | FY29 ACCESS POINT DESIGN IFC | NL | CIVIL | ACCESS POINTS | IFC | DESIGN | 1 | SITE | 12000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT DESIGN IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103914&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000103914 | FY29 ACCESS POINT - IFP | MA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103917&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000103917 | FY29 ACCESS POINT - IFP | NL | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103908&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000103908 | FY29 ACCESS POINT IFP | BW | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125413&DY_MAB=X&~OKCODE=ONLI | FY29 |  | FUTURE SCOPE | COAL | 002000125413 | C60-ACP-GA-GA-km | GA | CIVIL | ACCESS POINTS | IFP | DESIGN | 1 | SITE | 18000 | Goonyella | GA |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2026-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 |  |  |  | Access Points & Rds | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT DESIGN- IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114139&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000114139 | FY29 ACCESS POINT RENEWAL | BW | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114145&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000114145 | FY29 ACCESS POINT RENEWAL | GA | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114143&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000114143 | FY29 ACCESS POINT RENEWAL | MA | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000114141&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000114141 | FY29 ACCESS POINT RENEWAL | NL | CIVIL | ACCESS POINTS | RENEWAL | RENEWAL | 1 | SITE | 321000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 |  | 0.5 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 ACCESS POINT RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104185&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000104185 | C13 Turnout B/U Callemondah 219A Pts | TO001160 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 140156 | Blackwater | CALLEMONDAH | GLADSTONE POWERHOUSE | 0.0269 | KM | BW17YR0 | 0.2859 | BW17YR0 | 0.259 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 3.4 | 0.9 | 2 | 2.3 | 1 | 7.8 |  |  |  | Turnout Undercutting - C13 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000080107&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000080107 | C13 Turnout B/U Kabra 110A/B | TO000744 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 138273 | Blackwater | KABRA | KABRA | 0.0459 | KM | BW03ML18 | 0.39 | BW03ML18 | 0.4359 | KM |  |  |  |  | 18.39 | 18.39 | 2029-06-30 | BW-03ML |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Highly Fouled
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104242&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000104242 | C13 Turnout B/U Kabra 112A/B | TO000584 | CIVIL | BALLAST UNDERCUTTING | TURNOUT C13 | RENEWAL | 1 | TURNOUT | 150000 | Blackwater | KABRA | STANWELL | 0.0449 | KM | BW04ML18 | 0.388 | BW04ML18 | 0.4329 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 3.4 | 3.4 | 2 | 3.6 | 1 | 12.2 | [9 empty] | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115209&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000115209 | C05-FR-GA-WAITARA-101.2km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.15 | KM | 936987 | Goonyella | WAITARA | NEBO | 0.1499 | KM | GA02ML101 | 0.2 | GA02ML101 | 0.3499 | KM |  |  |  |  | 101.2 | 101.35 | 2026-06-30 | UP |  |  |  | 2.8 | 4.4 | 3 | 4.3 | 1 | 12.2 |  | 2023-09-01 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20290630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 100.480km to 101.570km Up Rd side of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • FY23 Track upgrade 100.815km-102.558km (noti # 2000074327) • Nominated by district – to be confirmed with DCPs
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000110120&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic |  | COAL | 002000110120 | FY29 RENEWAL | LX005953 | CIVIL | LEVEL CROSSINGS |  | MAJOR RENEWAL | 1 | SITE | 659076 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML7 | 0.116 | MA01ML7 | 0.116 | KM |  |  |  |  | 7.116 | 7.116 | 2027-06-30 | WHITNEY ST |  |  | RENEWAL DESIGN |  | 1.3 | 2 |  | 1 | [10 empty] | Outstanding notification | NWSC |  | 20270630 | Deferred to FY29 for FY26 Cashflow limit.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123426&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123426 | C57-LX-BW-BW-km | BW | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | SITE | 600000 | Blackwater | BW | BW | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  | REACTIVE WORKS | 5 | 5 | 2 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123429&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123429 | C57-LX-NL-NL-km | NL | CIVIL | LEVEL CROSSINGS |  | REACTIVE WORKS | 1 | SITE | 600000 | Newlands | NL | NL | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  | REACTIVE WORKS | 5 | 5 | 2 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083393&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000083393 | C58-LX-MA-CLARKE-72.6km | LX005995 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Moura | CLARKE | FRY | 0 | KM | MA01ML72 | 0.5999 | MA01ML72 | 0.5999 | KM |  |  |  |  | 72.6 | 72.6 | 2029-06-30 | DUCKHOLE ROAD |  |  |  | 3.2 | 1 |  |  |  | 1 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY29 MAJOR RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102012&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000102012 | C58-LX-GA-DALY BAY-0.012km | LX020244 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 805800 | Goonyella | DALRYMPLE BAY | PRAGUELANDS | 0 | KM | GA04BA0 | 0.0769 | GA04BA0 | 0.0769 | KM |  |  |  |  | 0.012 |  | 2027-06-30 | MAINTENANCE ACCESS RD |  |  |  |  | 4.2 | [7 empty] | Level Crossing Renewals | [5 empty] | Outstanding notification | NWSC |  | 20270630 | Moved to FY29 Renewal due to fund limit.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000102013&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000102013 | C58-LX-GA-PRAGUELANDS-19.666km | LX007287 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 805800 | Goonyella | PRAGUELANDS | JILALAN | 0 | KM | GA01YR19 | 0.67 | GA01YR19 | 0.67 | KM |  |  |  |  | 19.666 |  | 2027-06-30 | ENTRANCE TO STATION NEW |  |  |  |  | 4.2 | [7 empty] | Level Crossing Renewals | [5 empty] | Outstanding notification | NWSC |  | 20280630 | Moved to FY27 Design (IFP) for FY29 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068842&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000068842 | C58-LX-NL-BIRALEE-103.07km | LX003315 | CIVIL | LEVEL CROSSINGS |  | RENEWAL MAJOR | 1 | SITE | 455000 | Newlands | BIRALEE | HAVILAH | 0 | KM | NL01ML103 | 0.07 | NL01ML103 | 0.07 | KM |  |  |  |  | 103.07 | 103.07 |  | PRIVATE CATTLE CROSSING | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY27 Design for FY29 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122916&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000122916 | C58-LX-NL-BIRRALEE-94.201km | LX003314 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML94 | 0.203 | NL01ML94 | 0.203 | KM |  |  |  |  | 94.201 | 94.201 | 2030-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.57 | 2.14 | 2 | 3 | 1 | 7.71 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | This crossing had a Ballast Undercut in Aug 2023. DCP's were taken at this time and low strength formation was identified on the higher km side of the crossing. Despite this issue if the Mine ceases watering the crossing (as they have agreed via the Customer team) renewal can be delayed. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing 2 years to FY28 IFP, FY29 IFC, FY30 Renewal. This crossing will continue to be monitored and bought forward if required. FY26 DESIGN. Scoped on 11 May 2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122942&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000122942 | C58-LX-BW-BLACKWATER-0.941km | LX005881 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Blackwater | BLACKWATER | KOORILGAH | 0 | KM | BW13ML0 | 0.937 | BW13ML0 | 0.937 | KM |  |  |  |  | 0.941 | 0.941 |  | PONY CLUB ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY28 Design for FY30 Delivery. FY24 DESIGN The renewal of this crossing is delayed till FY27 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123432&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000123432 | C58-LX-MA-EARLSFIELD-136.015km | LX006028 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML136 | 0.0149 | MA01ML136 | 0.0149 | KM |  |  |  |  | 136.015 | 136.015 | 2031-06-30 |  |  |  | DESIGN IFC | 3 | 1.1 | 2 | 2 | 1 | 6 | [9 empty] | Outstanding notification | NWSC |  | 20310630 | FY31 DESIGN- LEVEL CROSSINGS IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122943&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000122943 | C58-LX-MA-GLADSTONE-19.73km | LX005961 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 32000 | Moura | GLADSTONE | STOWE | 0 | KM | MA01ML19 | 0.7339 | MA01ML19 | 0.7339 | KM |  |  |  |  | 19.73 | 19.73 | 2022-06-30 | BATTERY ROAD |  |  |  | 3.08 | 1.3 |  |  |  | 4 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Pushed to FY28 Design for FY30 renewal as per the mtg on 28 July 2022 with the IM team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123434&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000123434 | C58-LX-GA-PRAUGELANDS-14.678km | LX006433 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 35692 | Goonyella | PRAUGELANDS | JILALAN | 0 | KM | GA01ML14 | 0.678 | GA01ML14 | 0.678 | KM |  |  |  |  | 14.678 | 14.678 | 2031-06-30 |  |  |  | DESIGN IFC | 1.6 | 4.6 | 2 | 5 | 1 | 15 | [9 empty] | Outstanding notification | NWSC |  | 20310630 | FY31 DESIGN- LEVEL CROSSINGS IFC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122918&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000122918 | C58-LX-BW-RANGAL-198.37km | LX003432 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Blackwater | RANGAL | BURNGROVE | 0 | KM | BW03ML198 | 0.3679 | BW03ML198 | 0.3679 | KM |  |  |  |  | 198.37 | 198.37 | 2028-06-30 | TOLMIES CREEK ROAD |  |  |  | 2.67 | 2.05 |  |  |  | 5.47 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Mtg with T Dingle, moved IFC design to FY29. AS per the mtg on 31 Aug 2022 with the IM team, the design was moved to FY26. Possible to add in FY24 DESIGN <(>&<)> FY26 DELIVERY. Scope development is required before it cab be brought forward.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122913&DY_MAB=X&~OKCODE=ONLI | FY29 | Non Coal Traffic |  | NON-COAL | 002000122913 | C58-LX-BW-TOLMIES-221.69km | LX002761 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36590 | Blackwater | TOLMIES | COMET | 0 | KM | BW03ML221 | 0.6999 | BW03ML221 | 0.6999 | KM |  |  | 221.69 | 221.69 | 221.69 | 221.69 |  | COMET RIVER ROAD |  |  |  | 1.4 | 1.4 |  |  |  | 2.31 | 4929 | 2025-06-30 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | As per the mtg on 31 Aug 2022 with the IM team in Blackwater, this crossing was requested to be upgraded to flashing lights and boom gates due to the heavy use by trucks and long vehicles. Possible to add in FY24 DESIGN COMPARING THE PRIORITY OVER OTHER CROSSINGS FOR FY26 DELIVERY. Scope development is required before b ringing in to FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122940&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000122940 | C58-LX-GA-WOTONGA-0.428km | LX005813 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 36000 | Goonyella | WOTONGA | MORANBAH | 0 | KM | GA05ML0 | 0.4289 | GA05ML0 | 0.4289 | KM |  |  |  |  | 0.428 | 0.428 | 2022-06-30 |  |  |  |  | 2.75 | 2.5 |  |  |  | 5 | 4873 | 2022-06-30 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | IV.00459.E.6.M | 20290630 | 13.03.2020 13:38:29 AUSQLD Sharbaree Biswas (R865006) I 13.03.2020 13:44:22 AUSQLD Sharbaree Biswas (R865006) ID5813.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068866&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000068866 | C58-LX-GA-WOTONGA-9.97km | LX006680 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | DESIGN | 30000 | Goonyella | WOTONGA | MORANBAH | 0 | KM | GA05ML9 | 0.9709 | GA05ML9 | 0.9709 | KM |  |  | 576.77 | 576.77 | 9.97 | 9.97 |  | EPALA LANE |  |  |  | 2.4 | 1.5 | 2 | 3 |  | 6.5 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Moved to FY29 Design for FY31 Renewal. Moved to FY25 Renewal due to low OC and due to lack of additional supporting documents. Possible to add in FY24 Design comparing the priority over other crossings for FY26 delivery. Scope development is required before adding in FY24 design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079986&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000079986 | C58-LX-BW-FAIRHILL-44.5km | LX003469 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | FAIRHILL | YAN YAN | 0 | KM | BW08ML44 | 0.5 | BW08ML44 | 0.5 | KM |  |  |  |  | 44.5 | 44.5 |  | UNNAMED ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | FY26 DESIGN <(>&<)> FY27 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123431&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000123431 | C58-LX-MA-MOUNT RAINBOW-102.565km | LX006006 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | MOUNT RAINBOW | DUMGREE | 0 | KM | MA01ML102 | 0.5669 | MA01ML102 | 0.5669 | KM |  |  |  |  | 102.565 | 102.565 | 2029-06-30 |  |  |  | DESIGN IFP | 3 | 1.3 | 2 | 5 | 1 | 15 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 DESIGN- LEVEL CROSSINGS IFP
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079995&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000079995 | C58-LX-GA-MT MCLAREN-78.1km | LX005850 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 30000 | Goonyella | MT MCLAREN | BLACKRIDGE | 0 | KM | GA05ML78 | 0.1 | GA05ML78 | 0.1 | KM |  |  |  |  | 78.1 | 78.1 |  | PRIVATE ACCESS ROAD |  |  |  | 1.4 | 1.2 |  |  |  | 1.7 | 4929 |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20290630 | Pushed out to FY29 for design and FY31 Renewal. Supported by Reagan Case. To be maintained by IM. Ballast fouling is only up to 10-20%. PCR 5124 added. FY23 DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103949&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal GAPE Traffic |  | COAL | 002000103949 | C58-LX-NL-SUTTOR CREEK-193.566km | LX007258 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Newlands | SUTTOR CREEK | EAGLEFIELD CREEK | 0 | KM | NL01ML193 | 0.5679 | NL01ML193 | 0.5679 | KM |  |  |  |  | 193.566 | 193.566 | 2031-06-30 | PRIVATE CATTLE CROSSING |  |  |  | 2.52 | 1.2 | 2 | 3 | 1 | 7.56 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | This crossing had a ballast undercut/sleepers replaced/drainage replaced/road surface repaired in FY24. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing several years to FY29 IFP, FY30 IFC, FY31 Renewal. This crossing will continue to be monitored and bought forward if required. FY26 DESIGN. SCOPED ON 11 MAY 2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068815&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000068815 | C58-LX-MA-DAKENBA-0.316km | LX006405 | CIVIL | LEVEL CROSSINGS | MAJOR | RENEWAL | 1 | SITE | 1325905 | Moura | DAKENBA | CALLIDE | 0 | KM | MA07ML0 | 0.316 | MA07ML0 | 0.316 | KM |  |  | 0.316 | 0.316 | 0.316 | 0.316 | 2029-06-30 | JAMBIN DAKENBA RD |  |  |  | 3.2 | 1 | 2 | 2 | 1 | 7.7 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | Moved further to FY29 (fund limit). Due to FY25 budget constraint, this was pushed to FY26 renewal. DD50 ADDED IN SPM. Discussed with Geoff O'Connor on 12 July 2021. This crossing has been delayed till FY25 based on the fact that ballast fouling is not as significant as ID5965 (Talaba Road) and there is already another Callide Coalfield crossing due for renewal in FY25 (ID6406), could be better to do both in the same year. Further supporting documents to be collected from the site inspection.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050539&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000050539 | C58-LX-GA-YUKAN-27.88km | LX003499 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | CONSTRUCTION (CIVIL) | 1 | SITE | 1500000 | Goonyella | YUKAN | BLACK MOUNTAIN | 0 | KM | GA01ML27 | 0.88 | GA01ML27 | 0.88 | KM |  |  | 27.88 | 27.88 | 27.88 | 27.88 | 2029-06-30 | THE GLEN ACCESS ROAD |  |  |  | 1.05 | 1 |  |  |  | 1.05 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 29.01.2020 14:24:04 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 due to funding issues (R884639) Moved from FY22 due to funding issues 8 JULY 2021 BASED ON THE discussion with Rob Love, the design of ID3499 not to occur till FY26 and the delivery to occur in FY28. SB has contacted QR for their thoughts and Simone A to contact with Cane Authority.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083377&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000083377 | C58-LX-BW-EDUNGALBA-89.33km | LX005557 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 800000 | Blackwater | EDUNGALBA | AROONA | 0 | KM | BW03ML89 | 0.33 | BW03ML89 | 0.33 | KM |  |  |  |  | 89.33 | 89.33 | 2029-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.6 | 3 | 2.38 | 4 | 1 | 10.4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | 28/3/2024- Deferred to FY29 Renewal due to FY26 cashflow and Civil design resource limitation. FY26 MAJOR RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000088580&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000088580 | C58-LX-GA-WINCESTER-45.32km | LX003230 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | RENEWAL | 1 | SITE | 859655 | Goonyella | WINCESTER | PEAK DOWNS | 0 | KM | GA03ML45 | 0.32 | GA03ML45 | 0.32 | KM |  |  | 45.32 | 45.32 | 45.32 | 45.32 | 2029-06-30 | PRIVATE ACCESS ROAD |  |  |  | 3 | 2.1 | 2 | 3 | 1 | 9 |  |  |  | Level Crossing Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240804 | 30.03.2023 Moved to FY29 due to funding constraint. It has been undercut in FY23. IM is comfortable to monitor it over the next few years. FY25 RENEWAL-DD50 ADDED IN SPM.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123427&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123427 | C57-LX-GA-GA-km | GA | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | SITE | 600000 | Goonyella | GA | GA | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  | REACTIVE WORKS | 5 | 5 | 2 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123428&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123428 | C57-LX-MA-MA-km | MA | CIVIL | LEVEL CROSSINGS | REACTIVE WORKS | REACTIVE WORKS | 1 | SITE | 600000 | Moura | MA | MA | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  | REACTIVE WORKS | 5 | 5 | 2 | 5 | 1 | 25 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | FY29 REACTIVE WORKS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044040&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044040 | C58-LX-BW-COLUMBA ACC RD-181.29km | LX005614 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 859000 | Blackwater | COLUMBA ACCESS RD |  | 0 | KM | BW03ML181 | 0.255 | BW03ML181 | 0.255 | KM |  |  |  |  | 181.29 | 181.293 | 2029-06-30 |  |  |  |  | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | The renewal of this crossing is delayed till FY27 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team and the turn out asset manager. The design of the crossing is left in FY23 as a low priority and to be completed with the design of the turnout as well.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044033&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044033 | C58-LX-GA-OAKY CREEK-136.47km | LX003636 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 659000 | Goonyella | OAKY CREEK |  | 0 | KM | GA03ML136 | 0.4729 | GA03ML136 | 0.4729 | KM |  |  |  |  | 136.47 | 136.47 | 2029-06-30 |  |  |  |  | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | PCR 5124 added. In BC <(>&<)> D program for FY23. Supported by Reagan Case.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044042&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044042 | C58-LX-GA-PRI ACC rd-127.1km | LX003632 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 455000 | Goonyella | PRIVATE ACCESS ROAD |  | 0 | KM | GA03ML127 | 0.1039 | GA03ML127 | 0.1039 | KM |  |  |  |  | 127.1 | 127.104 | [5 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044020&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044020 | C58-LX-MA-BYELLEE-13.06km | LX005956 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Moura | BYELLEE |  | 0 | KM | MA01ML13 | 0.063 | MA01ML13 | 0.063 | KM |  |  |  |  | 13.06 | 13.06 |  | SINGLE |  |  |  | 3.25 | 2.5 |  |  |  | 8.1 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 15.01.2020 12:44:09 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY23 due to low priority * 11.11.2020 13:17:00 AUSQLD Sharbaree Biswas (R865006) * Moved to FY24 due to other high priority crossings.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103582&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | BASELOAD | COAL | 002000103582 | C58-LX-MA-CALLEMONDAH-6.33km | LX000963 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 659000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML6 | 0.339 | MA01ML6 | 0.339 | KM |  |  |  |  | 6.33 |  | 2029-06-30 | MERCURY ROAD |  |  |  | 3.3 | 1.3 | 2 | 3 | 1 | 8.55 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | 15.03.2024 This crossing is holding well since FoF reactive works in 2023. Original plan was for FY26 IFP, FY27 IFC, FY28 Renewal. Due to good condition at FY26 MRSB submission time Civil Assets have pushed out by 1 year to FY27 IFP, FY28 IFC, FY29 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123433&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000123433 | C58-LX-MA-EARLSFIELD-136.015km | LX006028 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 859000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML136 | 0.0149 | MA01ML136 | 0.0149 | KM |  |  |  |  | 136.015 | 136.015 | 2032-06-30 |  |  |  | RENEWAL | 3 | 1.1 | 2 | 2 | 1 | 6 | [9 empty] | Outstanding notification | NWSC |  | 20320630 | FY32 RENEWAL- LEVEL CROSSINGS
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044070&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | BASELOAD | COAL | 002000044070 | C58-LX-BW-PORT CURTIS WAY-559.67km | LX005584 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Blackwater | PORT CURTIS WAY |  | 0 | KM | BW01ML559 | 0.6959 | BW01ML559 | 0.6959 | KM |  |  |  |  | 559.675 | 559.675 | 2029-06-30 |  |  |  |  | 3.1 | 4.5 | 2 | 4.1 | 1 | 12.71 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | March 2024 moved again to FY29 Renewal due to funding limit. Moved to FY28 Renewal (as it is a FY26 Design).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044031&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044031 | C58-LX-BW-SUBSTATION ACC RD-195.07km | LX003431 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Blackwater | SUBSTATION ACCESS ROAD |  | 0 | KM | BW03ML195 | 0.07 | BW03ML195 | 0.07 | KM |  |  |  |  | 195.06 | 195.06 | 2029-06-30 |  |  |  |  | 3.5 | 2.85 | 2 | 3 | 1 | 10.5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 15.01.2020 13:01:11 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY23 due to low priority Moved from FY22 to FY23 due to low priority 15.01.2020 13:01:11 AUSQLD Sanjna Rajagopalan (R884639) The renewal of this crossing is delayed till FY26 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068852&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000068852 | C58-LX-MA-GRAHAM-29.828km | LX005969 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL MAJOR | 1 | SITE | 455000 | Moura | GRAHAM | STIRRAT | 0 | KM | MA01ML29 | 0.8279 | MA01ML29 | 0.8279 | KM |  |  |  | 29.828 | 29.828 | 29.828 |  | HOOKE ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Moved to FY27 Design as per the consultation with the IM team. 26.07.2021 Ben Crozier (R888068) Notification 2000044022 was found to be duplicate of this notification and was closed. 26.07.2021 S.Biswas This renewal is currently scheduled in FY26 delivery. This is to be discussed and finalised on 2 Aug 2021 when an inspection has been sorted with the relevant inspector. A new N4 for the design of ID5969 in FY25 to be created.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044023&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000044023 | C58-LX-MA-BARFIELD RD-172.2km | LX006054 | CIVIL | LEVEL CROSSINGS | RENEWAL MAJOR | RENEWAL | 1 | SITE | 455000 | Moura | BARFIELD RD |  | 0 | KM | MA01ML172 | 0.203 | MA01ML172 | 0.203 | KM |  |  |  |  | 172.2 | 172.2 |  | SINGLE |  |  |  | 2 | 2.5 |  |  |  | 5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 15.01.2020 13:16:57 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY24 due to low priority Moved from FY22 to FY24 due to low priority
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068843&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000068843 | C58-LX-MA-DAKENBA-2.28km | LX006406 | CIVIL | LEVEL CROSSINGS | RENEWAL MAJOR | RENEWAL MAJOR | 1 | SITE | 455000 | Moura | DAKENBA | CALLIDE | 0 | KM | MA07ML2 | 0.28 | MA07ML2 | 0.28 | KM |  |  |  |  | 2.28 | 2.28 |  | DUDARKOS RD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | DELAYED TILL FY27 DESIGN for FY29 Delivery. As per the discussion on 28 July 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123455&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123455 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 2.4 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123456&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123456 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123458&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123458 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | DESIGN | 1 | SITE | 170000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123443&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123443 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123444&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123444 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123445&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123445 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123446&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123446 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | SIGNAL | PLANNING | 1 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 1 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL PLANNING
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123466&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123466 | C58-LX-BW--km | BW | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 2.4 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123467&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123467 | C58-LX-GA--km | GA | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123469&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123469 | C58-LX-NL--km | NL | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL UPGRADE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043441&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000043441 | B52 -ST-BW-Kenmare-012.930km | CU100944 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 58683 | Blackwater | KINROLA | KENMARE | 0 | KM | BW06ML12 | 0.93 | BW06ML12 | 0.93 | KM |  |  |  |  | 12.93 |  | 2022-06-30 |  |  |  |  | 3.5 | 2.6 |  |  |  | 9.1 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290630 | * 10.03.2020 08:17:01 AUSQLD Peter Rayner (R003851) * Defect - Full section loss in localised areas of invert - Proposed Renewal - Tunnel line * 26.05.2020 07:46:26 AUSQLD Edward Brooks (R884255) * Error in upload to SPM, as this work should be design not renewal in this financial year. * 08.09.2020 15:51:28 AUSQLD Edward Brooks (R884255) * Pushed out to FY29, as blast and paint planned in NMP work for FY21.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043785&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000043785 | B52 -ST-GA-Moorvale-008.080km | CU200404 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 497640 | Goonyella | BIDGERLEY JUNCTION | BIDGERLEY JUNCTION | 0 | KM | GA03ML8 | 0.08 | GA03ML8 | 0.08 | KM |  |  |  |  | 8.08 | [6 empty] | 3 | 5 |  |  |  | 15 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | * 20.10.2020 16:21:22 AUSQLD Edward Brooks (R884255) * Defect: Minor to moderate spalling in culvert walls and minor cracks in hauches. * Proposed: CIPP Lining or Remove and Replace
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043806&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000043806 | B52 -ST-BW-Burngrove-008.260km | CU101143 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 300000 | Blackwater | TIKARDI | TIKARDI | 0 | KM | BW08ML8 | 0.258 | BW08ML8 | 0.258 | KM |  |  |  |  | 8.26 | [6 empty] | 3 | 1 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Defect: Minor to moderate spalling in localised areas Proposed: Concrete lining TBC by hydro, otherwise remove and replace. Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043853&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000043853 | B12 -ST-NL-Cockool-124.020km | BR300533 | CIVIL | STRUCTURES | BRIDGE-STRENGTHENING | DESIGN | 1 | SITE | 100000 | Newlands | COCKOOL | HAVILAH | 0 | KM | NL01ML124 | 0.02 | NL01ML124 | 0.02 | KM |  |  |  |  | 124.02 |  | 2034-06-30 |  |  | STRENGTHEN |  | 3 | 2.5 |  |  |  | 5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20290630 | Defect: Special Defect - fine cracks on underside of girders. Design assessment found structures to shear deficient and borderline Moment capacity. Proposed: Level 3 Inspections, measurements, Strengthening for shear SMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133486&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000133486 | B52 -ST-BW-Gregory-065.450km | CU101939 | CIVIL | STRUCTURES | CMP-CONCRE LINE | RENEWAL | 1 | SITE | 960000 | Blackwater | GREGORY |  | 0 | KM | BW08ML65 | 0.45 | BW08ML65 | 0.45 | KM |  |  |  |  | 65.45 |  | 2029-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1 | 3 | 3 | 1 | 10.5 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250111 | CU101939 - B52 -ST-BW-Gregory-065.450km Defect: Localised sectionof widening is showing corrosion in the top half of the CMP, suggesting corrosio from outside in But looks to be only 3-4m long. Proposed: Concrete Line pending hydro. Final: Drawings: Risk: Mod Reason: Risk hard to assess due to corrosion appears to be coming from outside in and therefore extent could be far larger on outside of CMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091923&DY_MAB=X&~OKCODE=ONLI | FY29 | Non Coal Traffic |  | NON-COAL | 002000091923 | B52 -ST-BW-Nogoa-245.040km | CU100411 | CIVIL | STRUCTURES | NON-MRSB RCP | RENEWAL | 1 | SITE | 450000 | Blackwater |  |  | 0 | KM | BW03ML245 | 0.04 | BW03ML245 | 0.04 | KM |  |  |  |  | 245.04 |  | 2029-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 10 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON-MRSB | 20290630 | Defect: Culverts moving and gaps opening up Proposed: CIPP lining or R <(>&<)> R pending hydro results to be confirmed by consultant Risk: Moderate Reason: Misalignment and sinking can lead to track alignment and derailment risks. Gaps and joint opening up may let material fall t hrough after next wet season. Construction should be fine in FY26 Design brought forward from FY23 to FY22 to enable more accurate planning of closures to meet the E2E <(>&<)> RIG Requirements
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000113766&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic |  | COAL | 002000113766 | B52 -ST-BW-Archer-619.240km | CU101513 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 1750000 | Blackwater | BW-NCL |  | 0 | KM | BW01ML619 | 0.2399 | BW01ML619 | 0.2399 | KM |  |  |  |  | 619.24 |  | 2028-06-30 |  |  | REMOVE & REPLACE |  | 3 | 4.1 | 3 | 4.3 | 1 | 12.9 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Defect: Base slab is failing with severe cracks from units 1-6 on all cells. Looks to be subgrade issue. Proposed: Remove and Replace Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085959&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085959 | B52 -ST-BW-Aroona-086.050km | CU100581 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 535000 | Blackwater | BW-CL |  | 0.05 | KM | BW03ML86 | 0.1 | BW03ML86 | 0.05 | KM |  |  |  |  | 86.05 |  | 2029-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290802 | Defect: Insitu original, RCBC on WL. Seevere spalling in ceiling of precast units. Proposed: Check Hydro for area, however likely Remove and Replace. Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103758&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic |  | COAL | 002000103758 | B52 -ST-BW-Mount Larcom-564.830km | CU101306 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 6020800 | Blackwater | BW-NCL |  | 0 | KM | BW01ML564 | 0.8299 | BW01ML564 | 0.8299 | KM |  |  |  |  | 564.83 |  | 2029-06-30 |  |  | CIPP OR PVC LINE | REMOVE & REPLACE | 3 | 1.7 | 3 | 3.4 | 1 | 10.1 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Defect - Horizontal minor to moderate cracking in units C1-3,4,5,6, C2-4 ,5,6, C3-3,5,6, C4-3,4,5. Looking at renewal options now as Turnout above being renewed in FY26. Note Mast looks to be impacted by remove and replace Proposed - Tentative in FY26 for Remove and Replace as turnout replaced above, however first prefernce is to look at lining options for this asset so it can be held unti FY28-30 before renewal Risk - Moderate for Remove and Replace in FY26 Reason - Included in FY26 because turnout above is being renewed and to prevent damaging this in the future a remove and replace will be better for the rail over time but also more cost effective as two assets being upgraded at the same time minimised track and formation material removal at least on one occasion.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000121296&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000121296 | B52 -ST-GA-Red Mountain-026.210km | CU200396 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 40000 | Goonyella | RED MOUNTAIN | WINCHESTER | 0 | KM | GA03ML26 | 0.2099 | GA03ML26 | 0.2099 | KM |  |  |  |  | 26.21 |  | 2030-06-30 | MOD-HIGH |  | REMOVE & REPLACE |  | 3.5 | 1.7 | 3 | 3.3 | 1 | 11.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20240627 | 20.10.2020 15:56:53 AUSQLD Edward Brooks (R884255) Defect: Minor cracking in haunches and more severe in unit 16-3 Proposed: CIPP lining or Remove and replace. Defect: Minor to moderate cracking in most haunches and more severe in unit 16-3. localised severe smalling and exposed reinf. Proposed: Remove and replace. Final: Drawing: Risk: Mod-High Reason: previously repaired spalling is respalling which means maintenance techniques are not working as this structure is too under strength. The regular haunches cracks suggest the units are pumping and deteriorating more quickly. Risk at haunch the crack may be full depth and have steel corroding in the corner and spalling on the outside which will be difficult to see.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133028&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000133028 | B52 -ST-BW-Tryphinia-133.050km | CU100202 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2000000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML133 | 0.05 | BW03ML133 | 0.05 | KM |  |  |  |  | 133.05 |  | 2029-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | CU100202 - B52 -ST-BW-Tryphinia-133.050km Defect: Rollout found top of units sinking and in poor condition and concern about structural capacity Proposed: Remove and Replace with bridge or unibox on ground improvement system. Final: Drawing: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100692&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100692 | B52 -ST-BW-Fairhill-036.900km | CU101154 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | DESIGN | 1 | SITE | 40000 | Blackwater | BW-GG |  | 0 | KM | BW08ML36 | 0.9 | BW08ML36 | 0.9 | KM |  |  |  |  | 36.9 |  | 2031-06-30 | MOD |  | CONCRETE LINE |  | 3 | 1.1 | 3 | 3 | 1 | 9.2 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Defect - Moderate spalling <(>&<)> cracking in ceiling of units 9,10,11. Proposed - Possible tunnelline in future pending hydro. Risk: Mod Reason: Concrete lining will avoid track closure.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135515&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000135515 | B52 -ST-BW-Tryphinia-132.972km | CU100322 | CIVIL | STRUCTURES | RCBC-UNIBOX | RENEWAL | 1 | SITE | 1722000 | Blackwater | TRYPHINIA |  | 0 | KM | BW03ML132 | 0.9719 | BW03ML132 | 0.9719 | KM |  |  |  |  | 132.972 |  | 2029-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 3.4 | 3 | 4 | 1 | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20290630 | CU100322 BRIDGE WATER CREEK - B52 -ST-BW-Tryphinia-132.972km Defect - Rollout found top of units sinking and in poor condition and concern about structural capacity. Cell 10 25mm drop . Pumping under loaded. Proposed - Remove and Replace with bridge or unibox. Consider ground improvement system if required. Final - Risk - Mod-high Reason - Pumping will lead to top of line issues with the track and likely TSR's
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000135661&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000135661 | B52 -ST-BW-Tikardi-008.780km | CU101042 | CIVIL | STRUCTURES | RCP-CIPP | DESIGN | 1 | SITE | 578000 | Blackwater | TIKARDI |  | 0 | KM | BW05ML8 | 0.78 | BW05ML8 | 0.78 | KM |  |  |  |  | 8.78 |  | 2028-06-30 |  |  | CIPP |  | 3 | 1.7 | 3 | 3.4 | 1 | 10.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250208 | 20.10.2020 16:43:42 AUSQLD Edward Brooks (R884255) Defect: Units are separating and allowing material to fall through the joints. May lead to top of line issues. Proposed: CIPP Lining Risk: Mod Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100366&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100366 | B12 -ST-BW-Umolo-147.940km | BR100659 | CIVIL | STRUCTURES | RELEIVING SLAB | RENEWAL | 1 | SITE | 400000 | Blackwater | BW-CL |  | 0.064 | KM | BW03ML147 | 0.9399 | BW03ML147 | 1.004 | KM |  |  |  |  | 147.94 |  | 2027-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.8 | 4 | 3.8 | 1 | 11.5 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Defect: Relieving slab looks to be moving, damaged ballast wall. Joint covers at abutment moved away from girders causing them to fall down. Upgrade in next rollout Proposed: Replace Relieving slab and improve sugrade to prevent sinking. Reapir ballast wall and provide longer joint covers. Should be done with rollout Final: Drawing: Risk: Moderate Reason: deteriorated releiving slabs lead to top of line issues with the bridge and can contribute to ballast deterioration and more resurfacing requirements.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124109&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000124109 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4227589 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124110&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000124110 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4611915 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124111&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000124111 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 845518 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124112&DY_MAB=X&~OKCODE=ONLI | FY29 |  | REACTIVE RENEWALS | COAL | 002000124112 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 845518 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000141806&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000141806 | TURNOUTS ¦CONSTRUCT ¦RENEWAL ¦ BFER3.3D | TO000738 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | BLUFF |  | 0.0259 | KM | BW04PL169 | 0.897 | BW04PL169 | 0.8709 | KM |  |  |  |  | 169.897 | [6 empty] | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000141807&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000141807 | TURNOUTS ¦CONSTRUCT ¦RENEWAL ¦ BFER3.2E | TO000739 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | BLUFF (ON LOOP TRACK) |  | 0.0229 | KM | BW04PL169 | 0.5979 | BW04PL169 | 0.6209 | KM |  |  |  |  | 169.598 | [6 empty] | 3.5 | 3.5 | 3 | 4 | 1 | 14.35 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | Keep the same tunout able. Match K point. Catch Point: Review Requirements. Remove if not required. Track tie-In: Remove TO000742 (169.645KM ER3.2E(SDG) TURNOUT BLUFF) as part of the renewal. Tie-in to Station, Loop and Siding tracks. Track CL offset to adjacent track: Approx. 4.2m Composite sleepers required. OHLE stage height resticted Drainage: Poor Formation Poor: all track. Track Geometry: Rough Constraints: Bluff Station, Pedestrian overpass, OHLE, Easetment between DTMR property (Capricorn Hwy) and Rail corridor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124053&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000124053 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦CH217A/B | TO001183 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | CALLEMONDAH | 217 A/B | 0.032 | KM | BW21YR2 | 0.3119 | BW21YR2 | 0.28 | KM |  |  |  |  | 534.698 |  | 2029-05-27 |  |  |  |  | 3 | 5 |  |  |  | 12.3 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290728 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦CH217A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 235A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over to CH217 turnout (from CH 274). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts. PCR 5349 PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124059&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000124059 | TURNOUTS ¦ CONSTRUCT ¦ RENEW ¦ CH 235A/B | TO001182 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | CALLEMONDAH | 235A/B | 0.0309 | KM | BW21YR2 | 0.199 | BW21YR2 | 0.168 | KM |  |  |  |  | 2.178 | 2.147 | 2029-06-30 |  |  |  |  | 3 | 5 |  |  |  | 14.4 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | TURNOUTS ¦ CONSTRUCT ¦ RENEW ¦ CH 235A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000. 30/03/2022 Alex Rohweder (R872340) Design is to be completed in FY24 for FY26 construction. 12/05/2022 Alex Rohweder (R872340) FY24 DESIGN swap over with CH 235A/B turnout (from CH 276A). (1) to better integrate with interlocking renewal (2) to focus on a critical asset reliability at Callemondah and Golding tunrouts PCR 5349
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124072&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000124072 | TURNOUTS ¦ CONSTRUCT ¦ RENEW ¦ CH 281A/B | TO001139 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | CALLEMONDAH | 281A/B | 0.033 | KM | BW11BL2 | 0.4949 | BW11BL2 | 0.528 | KM |  |  |  |  | 2.495 | 2.528 | 2029-06-30 |  |  |  |  | 4.2 | 5 |  |  |  | 14.7 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290722 | TURNOUTS ¦ CONSTRUCT ¦ RENEW ¦ CH 281A/B 11/01/2023 Alex Rohweder (R972340) FY24 Early Design, FY25 IFP, FY27 Construction. Bundle with 217A/B and 281A/B. FY24 Design budget adjusted to 10% off the total design budget = $14,200 out of $142,000.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043320&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000043320 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WR45A | TO000698 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | WARREN | WR45A | 0.0539 | KM | BW04ML25 | 0.542 | BW04ML25 | 0.542 | KM |  |  |  |  | 25.54 |  | 2029-06-30 |  |  |  |  | 3.5 | 3.5 |  |  |  | 14.35 | 4881 | 2020-03-06 | 2020-11-13 | Turnout Renewals | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20290630 | * 14.10.2020 15:47:58 AUSQLD Lachlan Prescott (R881571) * Updated to a full renewal as part of asset strategy and to allow for smaller possession window (pre-fabricated install). This will consume fewer resources and less track time. * 10.05.2021 11:08:40 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4881 01.04/2022 Alex Rohweder Reopen PCR 4881 To design FY24 (Like for LIke option) to construct in FY26. Based on DD30 assessment, the fit for purpose renewal option is to replace the existing turnout with SNX, and improve existing track structure for better track performacne. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043321&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000043321 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WR46A | TO000697 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | WARREN | WR46A | 0.069 | KM | BW04ML25 | 0.444 | BW04ML25 | 0.444 | KM |  |  |  |  | 25.44 |  | 2029-06-30 |  |  |  |  | 3.5 | 4 |  |  |  | 14 | 4881 | 2020-03-06 | 2020-11-13 | Turnout Renewals | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20290630 | * 14.10.2020 15:49:56 AUSQLD Lachlan Prescott (R881571) * Updated to a full renewal as part of asset strategy and to allow for smaller possession window (pre-fabricated install). This will consume fewer resources and less track time. * 10.05.2021 11:08:21 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4881 ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043989&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000043989 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WDER1.2 | TO000705 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1500000 | Blackwater | WESTWOOD | WD ER1.2A | 0.0539 | KM | BW04ML46 | 0.765 | BW04ML46 | 0.765 | KM |  |  |  |  | 46.78 |  | 2029-06-30 |  |  |  |  | 3 | 4 |  |  |  | 12.6 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 22.03.2021 21:21:51 AUSQLD Lachlan Prescott (R881571) * FY23 overallocated - moved to FY24 30.03.2022 Alex Rohweder (R872340) Move construction to FY26 (FY24 design) ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115843&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000115843 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ WD 7B/C | TO000670 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1292500 | Blackwater | WESTWOOD | WD7B/C | 0.0369 | KM | BW03ML47 | 0.505 | BW03ML47 | 0.468 | KM |  |  |  |  | 46.507 | 46.47 | 2029-06-30 |  |  |  |  | 4 | 3 | 4.2 | 3 |  | 12.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 16 CS SNX TGLASM EO LH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077227&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000077227 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH 214A | TO001160 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1 | Blackwater | CALLEMONDAH | CH214A | 0.0269 | KM | BW17YR0 | 0.2859 | BW17YR0 | 0.259 | KM |  |  |  |  | 0.286 | [16 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 13.05.2021 11:16:30 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124148&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | FUTURE SCOPE | COAL | 002000124148 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AL 7A/B | TO000854 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | ALDOGA | AL 7A/B | 0.0459 | KM | BW01ML555 | 0.9879 | BW01ML555 | 0.9419 | KM |  |  |  |  | 555.988 |  | 2029-05-27 | [19 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124145&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | FUTURE SCOPE | COAL | 002000124145 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AL 7C/D | TO000899 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | ALDOGA | AL 7C/D | 0.0519 | KM | BW02ML555 | 0.888 | BW02ML555 | 0.9399 | KM |  |  |  |  | 555.888 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124139&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | FUTURE SCOPE | COAL | 002000124139 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AL 8A/B | TO000898 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | ALDOGA | AL 8A/B | 0.047 | KM | BW02ML555 | 0.8659 | BW02ML555 | 0.8189 | KM |  |  |  |  | 555.866 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124142&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | FUTURE SCOPE | COAL | 002000124142 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AL 8C/D | TO000856 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | ALDOGA | AL 8C/D | 0.049 | KM | BW01ML555 | 0.767 | BW01ML555 | 0.8159 | KM |  |  |  |  | 555.767 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124133&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000124133 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AR 11A/B | TO000614 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | AROONA | AR 11A/B | 0.0359 | KM | BW03ML94 | 0.542 | BW03ML94 | 0.5779 | KM |  |  |  |  | 94.542 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124136&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000124136 | TURNOUTS ¦ DESIGN ¦ IFC ¦ AR 11C/D | TO000719 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Blackwater | AROONA | AR 11C/D | 0.0359 | KM | BW04ML94 | 0.6129 | BW04ML94 | 0.5769 | KM |  |  |  |  | 94.613 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124163&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124163 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000497 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT |  | 0.0449 | KM | GA01BD3 | 0.083 | GA01BD3 | 0.0379 | KM |  |  |  |  | 3.083 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124154&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124154 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000496 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT |  | 0.048 | KM | GA01BA3 | 0.4109 | GA01BA3 | 0.459 | KM |  |  |  |  | 3.411 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124166&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124166 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000104 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT |  | 0.049 | KM | GA02BA3 | 0.4349 | GA02BA3 | 0.386 | KM |  |  |  |  | 3.435 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124169&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124169 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000568 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT |  | 0.047 | KM | GA02BA3 | 0.627 | GA02BA3 | 0.5799 | KM |  |  |  |  | 3.627 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124157&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124157 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HP11A/B | TO000493 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT | HP 11A/B | 0.0449 | KM | GA01BA3 | 0.8519 | GA01BA3 | 0.807 | KM |  |  |  |  | 3.852 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124160&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124160 | TURNOUTS ¦ DESIGN ¦ IFC ¦ HP 11C/D | TO000567 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | HAY POINT | HP 11C/D | 0.0369 | KM | GA02BA3 | 0.643 | GA02BA3 | 0.68 | KM |  |  |  |  | 3.643 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124151&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000124151 | TURNOUTS ¦ DESIGN ¦ IFC ¦YN 48A/B | TO000336 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | YUKAN | YN 48A/B | 0.033 | KM | GA02ML29 | 0.398 | GA02ML29 | 0.4309 | KM |  |  |  |  | 29.398 | [21 empty] | Outstanding notification | NWSC |  | 20290527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118689&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000118689 | TURNOUTS ¦ DESIGN ¦ IFC ¦ MO10 | TO000823 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 0 | Blackwater | MEMOOLOO | MO 10 | 0.032 | KM | BW06ML47 | 0.8639 | BW06ML47 | 0.8319 | KM |  |  |  |  | 47.864 | 47.832 | 2028-05-27 |  |  |  |  | 4 | 1.5 |  |  |  | 13.2 |  | 2022-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290527 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ MO10 Defer the Design to FY25 Maintain the turnout reliability via Maintenace Strategy and C16. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124201&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124201 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000482 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.0459 | KM | GA03BA7 | 0.877 | GA03BA7 | 0.923 | KM |  |  |  |  | 7.877 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124204&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124204 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000500 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.048 | KM | GA02BA7 | 0.9749 | GA02BA7 | 0.927 | KM |  |  |  |  | 7.975 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124195&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124195 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000501 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.0719 | KM | GA02BA8 | 0.069 | GA02BA8 | 0.1409 | KM |  |  |  |  | 8.069 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124198&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124198 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000553 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.0709 | KM | GA03BA8 | 0.2169 | GA03BA8 | 0.1459 | KM |  |  |  |  | 8.217 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124189&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124189 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000103 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.05 | KM | GA02BA8 | 0.33 | GA02BA8 | 0.28 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124192&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000124192 | TURNOUTS ¦ DESIGN ¦ IFP ¦ | TO000481 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | SITE | 65450 | Goonyella | DALRYMPLE BAY |  | 0.0729 | KM | GA03BA8 | 0.33 | GA03BA8 | 0.257 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20290227
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115821&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115821 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CA1 | TO001012 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 33848 | Goonyella | COPPABELLA | CA1 | 0.0309 | KM | GA44YR143 | 0.9749 | GA44YR144 | 0.01 | KM |  |  |  |  | 143.975 | 144.006 | 2029-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115822&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115822 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CA2 | TO001013 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 33848 | Goonyella | COPPABELLA | CA2 | 0.02 | KM | GA44YR144 | 0.1089 | GA44YR144 | 0.129 | KM |  |  |  |  | 144.105 | 144.125 | 2029-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115820&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115820 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CA5 | TO001200 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 31814 | Goonyella | COPPABELLA | CA5 | 0.0269 | KM | GA45YR144 | 0.4299 | GA45YR144 | 0.403 | KM |  |  |  |  | 144.43 | 144.403 | 2029-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115823&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115823 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CA6 | TO001014 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 33848 | Goonyella | COPPABELLA | CA6 | 0.0179 | KM | GA44YR144 | 0.443 | GA44YR144 | 0.4249 | KM |  |  |  |  | 144.439 | 144.421 | 2029-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 8.25 CL RBM PH HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115819&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115819 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CA7 | TO000389 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 31814 | Goonyella | COPPABELLA | CA7 | 0.025 | KM | GA09CT144 | 0.4849 | GA09CT144 | 0.46 | KM |  |  |  |  | 144.401 | 144.369 | 2029-02-25 |  |  |  |  | 4 | 3 | 3.9 | 4 |  | 15.6 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115847&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000115847 | TURNOUTS ¦ DESIGN ¦ IFP ¦ CAER2.2B | TO000284 | CIVIL | TURNOUTS | DESIGN - IFP | DESIGN | 1 | TURNOUT | 53784 | Goonyella | COPPABELLA | ER2.2B | 0.032 | KM | GA02ML143 | 0.91 | GA02ML143 | 0.9419 | KM |  |  |  |  | 143.727 | 143.759 | 2029-02-27 |  |  |  |  | 4.5 | 3 | 4 | 4 | 1 | 18.9 |  | 2023-10-13 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20290225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085757&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000085757 | Asset Protection Renewal BW | BW | CONTROL SYSTEMS | ASSET PROTECTION | ALL | RENEWAL | 1 | UNIT | 1763000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085758&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000085758 | Asset Protection Renewal GA | GA | CONTROL SYSTEMS | ASSET PROTECTION | ALL | RENEWAL | 1 | UNIT | 642000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN | LOW |  | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000066260&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000066260 | HBD Review Tech Options | BW | CONTROL SYSTEMS | ASSET PROTECTION | HBD/HWD | DESIGN | 1 | SITE | 40000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2024-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2022-03-31 |  | Safe Working Systems - Asset Protection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000053188&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000053188 | Asset Protect Weigher Renewal - not reqd | ST003130 | CONTROL SYSTEMS | ASSET PROTECTION | WEIGHBRIDGE MINOR | RENEWAL | 1 | SITE | 52899 | Blackwater | GORDONSTONE |  | 0 | KM | BW10ML13 | 0.812 | BW10ML13 | 0.812 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 | 2020-11-13 | Safe Working Systems - Minor | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090693&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000090693 | CS CER Relocation | ST003910 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | BLACK MOUNTAIN CER | BLACK MOUNTAIN CER | 0 | KM | GA01ML40 | 0.936 | GA01ML40 | 0.936 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090695&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000090695 | CS CER Relocation | ST003980 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | HATFIELD CER | HATFIELD CER | 0 | KM | GA01ML49 | 0.752 | GA01ML49 | 0.752 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119605&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119605 | CSI Dehydrator Renewal FY29 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 50000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119604&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119604 | CSI Dehydrator Renewal FY29 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 50000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085406&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000085406 | CSI Generator Renewal | ST005510-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 170000 | Blackwater | GREGORY MW | GREGORY MW | 0 | KM | BW08ML64 | 0 | BW08ML64 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078690&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000078690 | CSI GENSET RENEWAL | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 180000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | * 10.06.2021 17:20:59 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078691&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000078691 | CSI GENSET RENEWAL | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 180000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | * 10.06.2021 17:22:05 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119976&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119976 | CSI NMS Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 250000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119975&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119975 | CSI NMS Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 250000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086507&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000086507 | CSI OF Renewal Boddington Street | ST005860-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 800000 | Goonyella | MACKAY | PAGET | 954.3999 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086506&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000086506 | CSI OF Renewal - OPGW Replacement | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 37000 | METERS | 4810000 | Goonyella | OPGW BALLOONS |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119529&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119529 | CSI Radome Renewal FY29 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 75000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119528&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119528 | CSI Radome Renewal FY29 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 75000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044604&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000044604 | CSI Tower Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 220000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046853&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000046853 | CSI Tower Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 220000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124726&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000124726 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 7 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124067&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000124067 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124366&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000124366 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065457&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | FUTURE SCOPE | COAL | 002000065457 | SIG_Interlocking Renewal_GA_Mindi_Pln | ST004820-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 78960 | Goonyella | MINDI |  | 0 | KM | GA01ML120 | 0.445 | GA01ML120 | 0.445 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | RRIG | FY23 IN | 20310630 | * 28.09.2020 08:18:32 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER. 30.08.2022: Changes restricted to removing leading shunts, split detection, digital telemetry, SER building replacement and PBI upgrade, as per Goonyella Trunk Resignalling scoping document.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065493&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000065493 | SIG_Interlocking Renewal_GA_Yukan_Com | ST004060-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 1500000 | Goonyella | YUKAN |  | 0 | KM | GA01ML28 | 0.806 | GA01ML28 | 0.806 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 28.09.2020 10:33:37 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142015&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000142015 | SIG_Interlocking Renewal_MA_Clarke_Pln | ST003520-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 120000 | Moura | CLARKE | CLARKE | 0 | KM | MA01ML63 | 0.8649 | MA01ML63 | 0.8649 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Planning phase for the replacement of the VPI at Clarke. This includes axlecounters to Stirrat and any AS3000. PBI expected to be a ElectrologiX. Working components from the removed VPI are to be placed into inventory.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126115&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000126115 | SIG_Interlocking Renewal_MA_Stirrat_Bld | ST003830-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1500000 | Moura | STIRRAT | STIRRAT | 0 | KM | MA01ML39 | 0.404 | MA01ML39 | 0.404 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 |  | 25 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Replace Stirrat VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104496&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000104496 | SIG_Interlocking Renewal_MA_Stowe_Com | ST003860-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1000000 | Moura | STOWE | GRAHAM | 0 | KM | MA02PL26 | 0.3499 | MA02PL26 | 0.3499 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Construction the replacement of VPI Stowe, removal of Graham and replace AzS600 axle counter in Byellee-Stowe block. Replace of Graham Interlocking with Object Controller of Stowe if required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123835&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000123835 | SIG_Interlocking Renewal - GA_JB_Bld | ST006030-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | WESTLOCK REPLACEMENT | ASSESSMENT | 1 | SITE | 1000000 | Goonyella | JILALAN BYPASS | JILALAN YARD | 0 | KM | GA01ML20 | 0.0299 | GA01ML20 | 0.0299 | KM | [11 empty] | 5 | 4 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Commence build tasks for the replacement of Jilalan Bypass and Jilalan Yard master interlocking. Consider technology, supplier arrangement, schedule, changes to housings and power supplies, interfaces to other interlockings and maintenance, and resourcing with regards to other projects.Review splitting the bypass and yard into 2 separate interlockings with separate telemetry.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060246&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060246 | SIG_Replace_M23A_GA_YN10A_Com | TO000267-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR28 | 0.6209 | GA21YR28 | 0.6209 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290830 | * 23.06.2020 12:48:49 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060247&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060247 | SIG_Replace_M23A_GA_YN10C_Com | TO000339-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.6919 | GA02ML28 | 0.6919 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:48:58 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060248&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060248 | SIG_Replace_M23A_GA_YN11A_Com | TO000446-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML30 | 0.0389 | GA01ML30 | 0.0389 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:08 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060249&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060249 | SIG_Replace_M23A_GA_YN11D_Com | TO000333-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML30 | 0.139 | GA02ML30 | 0.139 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:17 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060250&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060250 | SIG_Replace_M23A_GA_YN12A_Com | TO000334-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML29 | 0.92 | GA02ML29 | 0.92 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:26 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060251&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060251 | SIG_Replace_M23A_GA_YN12D_Com | TO000445-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML30 | 0.02 | GA01ML30 | 0.02 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:34 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060252&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060252 | SIG_Replace_M23A_GA_YN45B_Com | TO000264-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR28 | 0.4749 | GA21YR28 | 0.4749 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:43 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060253&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060253 | SIG_Replace_M23A_GA_YN47A_Com | TO000444-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML29 | 0.3039 | GA01ML29 | 0.3039 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:49:52 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060254&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060254 | SIG_Replace_M23A_GA_YN47B_Com | TO000444-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML29 | 0.3039 | GA01ML29 | 0.3039 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:02 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060255&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060255 | SIG_Replace_M23A_GA_YN47D_Com | TO000337-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML29 | 0.376 | GA02ML29 | 0.376 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:12 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060256&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060256 | SIG_Replace_M23A_GA_YN48A_Com | TO000336-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML29 | 0.381 | GA02ML29 | 0.381 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:21 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060257&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060257 | SIG_Replace_M23A_GA_YN48C_Com | TO000269-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR29 | 0.459 | GA21YR29 | 0.459 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:31 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060258&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060258 | SIG_Replace_M23A_GA_YN49A_Com | TO000272-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR29 | 0.7089 | GA21YR29 | 0.7089 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:39 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060259&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060259 | SIG_Replace_M23A_GA_YN49C_Com | TO000335-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML29 | 0.782 | GA02ML29 | 0.782 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:50 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060260&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060260 | SIG_Replace_M23A_GA_YN50A_Com | TO000271-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR29 | 0.677 | GA21YR29 | 0.677 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:50:59 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060261&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060261 | SIG_Replace_M23A_GA_YN7A_Com | TO001222-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.7149 | GA02ML28 | 0.7149 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:08 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060262&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060262 | SIG_Replace_M23A_GA_YN7D_Com | ST001090-I4 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML28 | 0.787 | GA01ML28 | 0.787 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:18 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060263&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060263 | SIG_Replace_M23A_GA_YN8A_Com | TO000515-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA01ML27 | 0.687 | GA01ML27 | 0.687 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:26 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060264&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060264 | SIG_Replace_M23A_GA_YN8D_Com | TO000341-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML27 | 0.787 | GA02ML27 | 0.787 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:36 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060265&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060265 | SIG_Replace_M23A_GA_YN9A_Com | TO000340-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA02ML28 | 0.534 | GA02ML28 | 0.534 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:45 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060266&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000060266 | SIG_Replace_M23A_GA_YN9C_Com | TO000266-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 110000 | Goonyella | YUKAN | YUKAN | 0 | KM | GA21YR28 | 0.6039 | GA21YR28 | 0.6039 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 |  |  | 4 |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:51:54 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126578&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000126578 | SIG_Train Detection_NL_Armuna_Des | ST008270-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | DESIGN | 2 | UNITS | 200000 | Newlands | ARMUNA | PRING | 0 | KM | NL01ML24 | 0.8589 | NL01ML24 | 0.8589 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Design phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The 2 blocks are a block btn Armuna and Buckley and a block between Buckley and Pring. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126600&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000126600 | SIG_Train Detection_NL_Pring_Pln | ST002910-15 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | PLANNING | 21 | UNITS | 150000 | Newlands | PRING | PRING | 0.512 | KM | NL01PL2 | 0.9629 | NL01PL3 | 0.4779 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20310630 | Planning phase for the replacement of Siemens AzS350U axlecounter track sections with a different axlecounter. There are 21 track secytions within Pring.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126575&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000126575 | SIG_Train Detection_NL_Binbee_Com | ST008070-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 6 | UNITS | 1200000 | Newlands | BINBEE | ARMUNA | 8.0579 | KM | NL01ML36 | 0.1469 | NL01ML44 | 0.2089 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | Commissioning phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The 6 blocks are a block btn Binbee and Aberdeen, 4 tracks in Aberdeen and a block between Aberdeen and Armuna. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085827&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085827 | SIG_Train Detection_BW_CSEE_Wallaroo_Pln | ST004420 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 1 | SITE | 85000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Replace all of the track circuits at Wallaroo with Thales axlecounters.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065532&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000065532 | SIG_Train Detection BW_Windah_CSEE_Com | ST004470 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 18 | UNIT | 3438000 | Blackwater | WINDAH | WINDAH | 0 | KM | BW03ML57 | 0.629 | BW03ML57 | 0.629 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20290630 | * 28.09.2020 11:03:06 AUSQLD Peter Rayner (R003851) * Replace all TCs with Thales AC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125899&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000125899 | SIG_Train Detection_GA_NthGoonyel_ML_Des | ST004920 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | DESIGN | 1 | SITE | 605000 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0 | KM | GA01ML213 | 0.6999 | GA01ML213 | 0.6999 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Replace all track circuits (primarily defunct ML tracks) with 11 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125892&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000125892 | SIG_Train Detection_GA_Broadlea_ML_Com | ST004580 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 4080000 | Goonyella | BROADLEA | BROADLEA | 0 | KM | GA01ML156 | 0.264 | GA01ML156 | 0.264 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20290630 | Replace all track circuits (primarily defunct ML tracks) with 20 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100909&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100909 | CS Transmission DMR Link | ST005280-26 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 400000 | Blackwater | CROCKER PEAK | EMERALD | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100920&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100920 | CS Transmission DMR Link | ST003020-42 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 400000 | Blackwater | EMERALD | GREGORY | 0 | KM | BW57CR0 | 0 | BW57CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100922&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100922 | CS Transmission DMR Link | ST005740-35 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 400000 | Newlands | SUMMER HILL | MERINDA | 0 | KM | NL11CR0 | 0 | NL11CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100921&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000100921 | CS Transmission DMR Link | ST006010-23 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 400000 | Goonyella | TIERAWOOMBA | PINE MOUNTAIN | 0 | KM | GA45CR0 | 0 | GA45CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119922&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119922 | CS Transmission Power Supply | ST008540-17 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | BIDGERLEY MI | BIDGERLEY MI | 0 | KM | GA06ML6 | 0.2999 | GA06ML6 | 0.2999 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119928&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119928 | CS Transmission Power Supply | ST007490-58 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | BLACK MOUNTAIN TSC | BLACK MOUNTAIN TSC | 0 | KM | GA01ML35 | 0.4829 | GA01ML35 | 0.4829 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101963&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101963 | CS Transmission Power Supply | ST006120-37 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | BLACKWATER MWR | BLACKWATER MWR | 0 | KM | BW03ML189 | 0.259 | BW03ML189 | 0.259 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101899&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101899 | CS Transmission Power Supply | ST005520-10 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | BLUFF MWR | BLUFF MWR | 0 | KM | BW54CR0 | 0 | BW54CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101962&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101962 | CS Transmission Power Supply | ST005950-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | CAPELLA MWR | CAPELLA MWR | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119923&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119923 | CS Transmission Power Supply | ST007920-17 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | CARBOROUGH DOWNS CER | CARBOROUGH DOWNS CER | 0 | KM | GA09ML4 | 0.227 | GA09ML4 | 0.227 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119926&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119926 | CS Transmission Power Supply | ST007210-22 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | CARBOROUGH DOWNS SER | CARBOROUGH DOWNS SER | 0 | KM | GA01ML160 | 0.788 | GA01ML160 | 0.788 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119924&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119924 | CS Transmission Power Supply | ST000040-52 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | DINGO FSS | DINGO FSS | 0 | KM | BW03ML133 | 0.3099 | BW03ML133 | 0.3099 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119927&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119927 | CS Transmission Power Supply | ST004210-27 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | EDUNGALBA SER | EDUNGALBA SER | 0 | KM | BW03ML84 | 0.65 | BW03ML84 | 0.65 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101960&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101960 | CS Transmission Power Supply | ST005540-04 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | GOGANGO MWR | GOGANGO MWR | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085244&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085244 | CS Transmission Power Supply | ST009440-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | KINROLA TSY | KINROLA TSY | 0 | KM | BW06ML0 | 0.5999 | BW06ML0 | 0.5999 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119909&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119909 | CS Transmission Power Supply | ST000730-50 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | PEAK DOWNS FSS | PEAK DOWNS FSS | 0 | KM | GA03ML41 | 0.6999 | GA03ML41 | 0.6999 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119920&DY_MAB=X&~OKCODE=ONLI | FY29 | Dual Traffic | BASELOAD | COAL | 002000119920 | CS Transmission Power Supply | ST009910-02 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | RAGLAN REX | RAGLAN REX | 0 | KM | BW01ML581 | 0.2 | BW01ML581 | 0.2 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085246&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085246 | CS Transmission Power Supply | ST009450-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | STRUAN ROAD FSS | STRUAN ROAD FSS | 0 | KM | BW06ML53 | 0.266 | BW06ML53 | 0.266 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119925&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119925 | CS Transmission Power Supply | ST006660-16 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | TOOTOOLAH SER | TOOTOOLAH SER | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119921&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic | BASELOAD | COAL | 002000119921 | CS Transmission Power Supply | ST007680-14 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | TUNNEL MIE | TUNNEL MIE | 0 | KM | BW03ML73 | 0.6199 | BW03ML73 | 0.6199 | KM | [6 empty] | 2029-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101966&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101966 | CS Transmission Power Supply | ST005800-11 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | WAITARA AT | WAITARA AT | 0 | KM | GA01ML94 | 0.9599 | GA01ML94 | 0.9599 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101964&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000101964 | CS Transmission Power Supply | ST001640-14 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Goonyella | WAITARA MI | WAITARA MI | 0 | KM | GA01ML98 | 0.16 | GA01ML98 | 0.16 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085243&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085243 | CS Transmission Power Supply | ST009360-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | WIGGINS ISLAND CER | WIGGINS ISLAND CER | 0 | KM | BW16CR16 | 0.32 | BW16CR16 | 0.32 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085242&DY_MAB=X&~OKCODE=ONLI | FY29 | Coal Traffic |  | COAL | 002000085242 | BW CS Power Supply Renewal FY27 | ST009350-27 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 39000 | Blackwater | WIGGINS ISLAND SER | WIGGINS ISLAND SER | 0 | KM | BW16CR12 | 0.22 | BW16CR12 | 0.22 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101298&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000101298 | CS Transmission SDH to IP | BW | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | LUMPSUM | 140000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101297&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000101297 | CS Transmission SDH to IP | GA | CONTROL SYSTEMS | TRANSMISSION | SDH TO IP | RENEWAL | 1 | LUMPSUM | 140000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101628&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000101628 | CS Transmission Supervisory Card | BW | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 140000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101626&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000101626 | CS Transmission Supervisory Card | GA | CONTROL SYSTEMS | TRANSMISSION | SUPERVISORY CARD | RENEWAL | 1 | LUMPSUM | 140000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101322&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000101322 | CS Transmission TDM Replacement | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101390&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000101390 | CS Transmission TDM Replacement | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101391&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  | COAL | 002000101391 | CS Transmission TDM Replacement | GA | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120138&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000120138 | CS Transmission Tele Battery Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120139&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000120139 | CS Transmission Tele Battery Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120137&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000120137 | CS Transmission Tele Battery Renewal | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Moura | TBC | TBC | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120140&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000120140 | CS Transmission Tele Battery Renewal | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119724&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119724 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119726&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119726 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119725&DY_MAB=X&~OKCODE=ONLI | FY29 |  | BASELOAD | COAL | 002000119725 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124062&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000124062 | GA Ports O/H Renewal FY29-Placeholder | GA | ELECTRICAL | OVERHEAD | OVERHEAD RENEWALS | RENEWAL | 1 | UNIT | 1500000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 18/08/23 EK: The duration of the GA Ports project is still very uncertain due to the low level of scope definition, resourcing chall enges and access constraints. Based on the current limitations, it is highly likely that the estimate, program and forecast will all change in the coming years. An indicative estimate of $1.5M has been entered for FY29 (Placeholder) at this stage and will be updated as the estimating and planning is refined.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123352&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123352 | OVERHEAD RENEWAL FY29-BW-PLACEHOLDER | BW | ELECTRICAL | OVERHEAD | OVERHEAD RENEWALS | RENEWAL | 1 | UNIT | 2872938 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for Overhead Renewal at Blackwater System in FY29. Excludes Goonyella Ports OHL Renewals. Estimates based on FY25-FY28 Overhead Total Estimates (22,983,500.0) excluding Goonyella Ports OHL Renewals. Total Estimates is divided by 4 to obtain Annual Renewal Estimates (5,745,875.0). The Annual Renewal Estimates is divided further by 2 to obtain per System Annual Estimates (2,872,937.5) for FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123353&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123353 | OVERHEAD RENEWAL FY29-GA-PLACEHOLDER | GA | ELECTRICAL | OVERHEAD | OVERHEAD RENEWALS | RENEWAL | 1 | UNIT | 2872938 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for Overhead Renewal at Goonyella System in FY29. Excludes Goonyella Ports OHL Renewals. Estimates based on FY25-FY28 Overhead Total Estimates (22,983,500.0) excluding Goonyella Ports OHL Renewals. Total Estimates is divided by 4 to obtain Annual Renewal Estimates (5,745,875.0). The Annual Renewal Estimates is divided further by 2 to obtain per System Annual Estimates (2,872,937.5) for FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123273&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123273 | AT Renewals FY29-BW-Placeholder | BW | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 3 | UNIT | 2478237 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for 3 x AT in Blackwater System. Estimates based on unit rates (of approx 600k each) for Design, Procurement and Construct.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123278&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123278 | AT Renewals FY29-GA-Placeholder | GA | ELECTRICAL | POWER SYSTEMS | AT RENEWALS | RENEWAL | 3 | UNIT | 2478237 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 10 |  |  | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for 3 x AT in Goonyella System. Estimates based on unit rates (of approx 600k each) for Design, Procurement and Construct.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123279&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123279 | POWER SYSTEM RENEWAL FY29-BW-PLACEHOLDER | BW | ELECTRICAL | POWER SYSTEMS | POWER SYSTEMS RENEWAL | RENEWAL | 1 | UNIT | 878427 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for Power Systems Renewal at Blackwater System in FY29. Excludes the AT Renewals and Substation Renewals. Estimates based on FY25-FY28 Power System Total Estimates (7 ,027,417.0) excluding AT Renewals and Substation Renewals. Total Estimates is divided by 4 to obtain Annual Renewal Estimates (1 ,756,854.25). The Annual Renewal Estimates is divided further by 2 to obtain per System Annual Estimates (878,427) for FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123350&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123350 | POWER SYSTEM RENEWAL FY29-GA-PLACEHOLDER | GA | ELECTRICAL | POWER SYSTEMS | POWER SYSTEMS RENEWAL | RENEWAL | 1 | UNIT | 878427 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 10/08/23 EK: Notification is placeholder only for Power Systems Renewal at Goonyella System in FY29. Excludes the AT Renewals and Substation Renewals. Estimates based on FY25-FY28 Power System Total Estimates (7 ,027,417) excluding AT Renewals and Substation Renewals. Total Estimates is divided by 4 to obtain Annual Renewal Estimates (1,756 ,854.25). The Annual Renewal Estimates is divided further by 2 to obtain per System Annual Estimates (878,427.0) for FY29.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123280&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123280 | Traction Substation Renewals | BW | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 8 | UNIT | 5617954 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 09-08-23 EK: Placeholder only-basis of BW FY29 Estimates attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123281&DY_MAB=X&~OKCODE=ONLI | FY29 |  |  |  | 002000123281 | Traction Substation Renewals | GA | ELECTRICAL | POWER SYSTEMS | TRACTION SUBSTATION RENEWALS | RENEWAL | 14 | UNIT | 50173627 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20290630 | 09-08-23 EK: Placeholder only-basis of FY29 estimates attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084551&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084551 | C13 ADJACENT C14 ML LEAD Mt LARCOM 9AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT |  | 0.05 | KM | 25000 | Blackwater | ALDOGA | MT LARCOM | 0.0539 | KM | BW01ML566 | 0.3729 | BW01ML566 | 0.4269 | KM |  |  |  |  | 566.373 | 566.427 |  | UP |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated with Point Asset t/o 1in12 Mt Larcom 9AB (FLOC TO 000902) and linked to notification 2000074658.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084519&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084519 | C13 ADJACENT C14 ML LEAD UMOLO 12AB | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT |  | 0.05 | KM | 25000 | Blackwater | DINGO | UMOLO | 0.05 | KM | BW04ML148 | 0.4699 | BW04ML148 | 0.52 | KM |  |  |  |  | 148.47 | 148.52 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut linked to Point Asset 1in16 Umolo 12AB (FLOC TO 000580) and notification 2000074656.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084516&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084516 | C13 ADJACENT C14 ML LEAD UMOLO 12CD | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT |  | 0.05 | KM | 25000 | Blackwater | DINGO | UMOLO | 0.05 | KM | BW04ML148 | 0.5659 | BW04ML148 | 0.6159 | KM |  |  |  |  | 148.566 | 148.616 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut associated with t/o Point Asset Umolo 12CD (FLOC TO 000590) associated notification 2000074655.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084550&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084550 | C13 ADJACENT C14 ML STR UMOLO 12AB | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT |  | 0.05 | KM | 25000 | Blackwater | DINGO | UMOLO | 0.05 | KM | BW04ML148 | 0.6079 | BW04ML148 | 0.658 | KM |  |  |  |  | 148.608 | 148.658 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline u/c linked to Point Asset t/o 1in16 Umolo 12AB (FLOC TO 000580) linked to notification 2000074656.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084517&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084517 | C13 ADJACENT C14 ML STR UMOLO 12CD | BW-04ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT |  | 0.05 | KM | 25000 | Blackwater | DINGO | UMOLO | 0.05 | KM | BW04ML148 | 0.7039 | BW04ML148 | 0.754 | KM |  |  |  |  | 148.704 | 148.754 | 2023-06-30 | UP |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg on mainline undercut linked to Point Asset t/o 1in16 Umolo 12CD (FLOC TO 000590) linked to notification 2000074655.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000082778&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000082778 | C13 ADJUCENT C14 ML LEAD UMOLO 11CD | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 75000 | Blackwater |  |  | 0.05 | KM | BW03ML148 | 0.459 | BW03ML148 | 0.509 | KM |  |  |  |  | 148.459 | 148.509 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.09.2021 Tim Griffin(r8788533) Linkage to Umolo 11CD FLOC TO000734 for adjacent mainline undercut (C14) 50m. length being 10m prior to last long bearer.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084514&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084514 | C13 ADJACENT C14 ML Up RD STR UMOLO 11AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 75000 | Blackwater |  |  | 0.05 | KM | BW03ML148 | 0.554 | BW03ML148 | 0.504 | KM |  |  |  |  | 148.554 | 148.504 | 2023-06-30 |  |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) C14 mainline u/c of Straight leg to adjoining 1in16 turnout Umolo 11AB (FLOC TO 00735) and t/u undercut notification 2000074654.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084513&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084513 | C13 ADJACENT C14 ML Up RD LEAD UMOLO11AB | BW-03ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 75000 | Blackwater | 148.366 | 148.416 | 0.05 | KM | BW03ML148 | 0.3659 | BW03ML148 | 0.4159 | KM | [6 empty] | 2023-06-30 |  |  |  |  | 4 |  |  |  |  | 13.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) C14 lead ML undercut to turnout Umolo 11AB (FLOC TO 000735) and N4 reference 2000074654.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084553&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084553 | C13 ADJACENT C14 ML STR MT LARCOM 7CD | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | ALDOGA | MT LARCOM | 0.0539 | KM | BW02ML566 | 0.658 | BW02ML566 | 0.7119 | KM |  |  |  |  | 566.658 | 566.712 | 2023-06-30 | DN |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg mainline undercut for Point Asset t/o 1in16 MtLARCOM 7CD (FLOC TO 000903) linked to notification 2000074659).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084554&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084554 | C13 ADJACENT C14 ML STR MT LARCOM 7CD | BW-02ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | ALDOGA | MT LARCOM | 0.05 | KM | BW02ML566 | 0.8 | BW02ML566 | 0.8499 | KM |  |  |  |  | 566.8 | 566.85 | 2023-06-30 | DN |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT mainline undercut linked to Point Asset t/o 1in16 Mt Larcom 7CD (FLOC TO 000903) associated notification 2000074659.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084538&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084538 | C13 ADJACENT C14 ML LEAD YARWUN 11AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | YARWUN | ALDOGA | 0.05 | KM | BW01ML545 | 0.219 | BW01ML545 | 0.269 | KM |  |  |  |  | 545.219 | 545.269 | 2023-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) LEAD mainline undercut to Point Asset t/o 1in16 Yarwun 11AB (FLOC TO 000895) and associated notification 2000074618.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084540&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084540 | C13 ADJACENT C14 ML LEAD YARWUN 12CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | YARWUN | ALDOGA | 0.05 | KM | BW01ML545 | 0.2429 | BW01ML545 | 0.2929 | KM |  |  |  |  | 545.243 | 545.293 | 2023-06-30 | UP |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut linked to Point Asset t/o 1in16 Yarwun NCL (FLOC TO 000575) and reference notification 2000074619.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084539&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084539 | C13 ADJACENT C14 ML STR YARWUN 11AB | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | YARWUN | ALDOGA | 0.05 | KM | BW01ML545 | 0.3569 | BW01ML545 | 0.4069 | KM |  |  |  |  | 545.357 | 545.407 | 2023-06-30 |  |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg of mainline undercut associated with Point Asset t/o undercut 1in16 Yarwun 11AB and associated notification 2000074618.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000084541&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000084541 | C13 ADJACENT C14 ML LEAD YARWUN 12CD | BW-01ML | CIVIL | BALLAST UNDERCUTTING | C14 ADJOINING TURNOUT | RENEWAL | 0.05 | KM | 25000 | Blackwater | YARWUN | ALDOGA | 0.05 | KM | BW01ML545 | 0.381 | BW01ML545 | 0.4309 | KM |  |  |  |  | 545.381 | 545.431 |  | UP |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  | Mainline Excavator Undercutting - C14 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | 01.10.2021 Tim Griffin (r878533) STRAIGHT leg on mainline undercut for Point Asset t/o 1in16 Yarwun 12CD (FLOC TO 000575) and associated notification reference 2000074619.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052520&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052520 | CO1 Ballast Undercut | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE | RENEWAL | 0.312 | KM | 166118 | Newlands | BUCKLEY | ARMUNA | 0.3119 | KM | NL01ML15 | 0.1 | NL01ML15 | 0.4119 | KM |  |  |  |  | 15.1 | 15.412 | 2022-06-30 | SINGLE |  |  |  | 3.5 | 2.5 |  |  |  | 5.95 |  | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 25.02.2020 19:40:10 AUSQLD Allan Gough (R873345) * High fouling and resurfacing holding. RAP Civil Engineer priority No5.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052404&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000052404 | Ballast Undercut C01 ML Renew | GA-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0.906 | KM | 0 | Goonyella | BLACK MTN-HATFIELD | BLACK MTN-HATFIELD | 0.906 | KM | GA02ML45 | 0.3539 | GA02ML46 | 0.263 | KM |  |  |  |  | 45.354 | 46.263 | 2025-06-30 | UP |  |  |  | 3 | 1 |  |  |  | 3 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR |  | 20300630 | Renewal works undertaken in FY21 since originally planned in FY22 (as per fortnightly Ballast PM / RAP and AM meeting in April 2021 - Jane Livingston). 28/10/2021 Q3 <(>&<)> Q4 FY22 discussion agreed to remove notification, since completed in FY21. pushed to FY30. Sat 30.10.2021 Tim GRiffin (r878533). See attcahed file / email.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052482&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000052482 | CO1 BLACKWATER U/C. | BW-02ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 2.212 | KM | 1028922 | Blackwater | CALLEMONDAH-ROCKLANDS DN RD |  | 2.212 | KM | BW02ML610 | 0.2 | BW02ML612 | 0.4 | KM |  |  |  |  | 610.2 | 612.4 | 2022-06-30 |  |  |  |  | 3.5 | 4.9 |  |  |  | 15.75 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR |  | 20300630 | Sat 30.10.2021 Tim Griffin (r878533) agreed to move out to outer years (FY30), since completed in FY21.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052523&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052523 | CO1 NEWLANDS U/C. | NL-01ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0 | KM | 433941 | Newlands | COCKOOL | HAVILAH | 0.9989 | KM | NL01ML113 | 0.65 | NL01ML114 | 0.65 | KM |  |  |  |  | 113.65 | 114.65 | 2022-06-30 | SINGLE |  |  |  | 3.5 | 2.5 |  |  |  | 4.9 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052441&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000052441 | CO1 BLACKWATER U/C | BW-03ML | CIVIL | BALLAST UNDERCUTTING | MAINLINE C01 | RENEWAL | 0 | KM | 0 | Blackwater | ROCKLANDS-NOGOA DN RD |  | 4.1269 | KM | BW03ML118 | 0.2 | BW03ML122 | 0.2999 | KM |  |  |  |  | 118.2 | 122.3 | 2022-06-30 |  |  |  |  | 3 | 4.5 |  |  |  | 10.05 | 4748 | 2020-03-06 | 2020-11-13 | Mainline Undercutting - C01 | LIKE FOR LIKE | LOW |  | LOW | MEDIUM | Notification in process | SCPR |  | 20220630 | PCR 5076
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052756&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052756 | Formation Renewal | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 1.7 | KM | 3570000 | Newlands |  |  | 1.701 | KM | NL01ML3 | 0.4 | NL01ML5 | 0.1 | KM |  |  |  |  | 3.4 | 5.1 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052742&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052742 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.565 | KM | 1186500 | Goonyella |  |  | 0.5639 | KM | GA03ML34 | 0.7349 | GA03ML35 | 0.2999 | KM |  |  |  |  | 34.735 | 35.3 | [5 empty] | 3 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052744&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052744 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 1848000 | Goonyella |  |  | 0.4 | KM | GA03ML37 | 0.25 | GA03ML37 | 0.65 | KM |  |  |  |  | 37.25 | 37.65 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052750&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052750 | Formation Renewal | GA-05ML | CIVIL | FORMATION |  | RENEWAL | 0.5 | KM | 1050000 | Goonyella |  |  | 0.5 | KM | GA05ML38 | 0.2 | GA05ML38 | 0.6999 | KM |  |  |  |  | 38.2 | 38.7 | [5 empty] | 3 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052746&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052746 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 1848000 | Goonyella |  |  | 0.4 | KM | GA03ML38 | 0.3499 | GA03ML38 | 0.75 | KM |  |  |  |  | 38.35 | 38.75 | [5 empty] | 3 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052739&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000052739 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.7 | KM | 1470000 | Goonyella |  |  | 0.6959 | KM | GA03ML42 | 0.9 | GA03ML43 | 0.5999 | KM |  |  |  |  | 42.9 | 43.6 | 2025-06-30 |  |  |  |  | 3 | [8 empty] | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20300630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052747&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052747 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 1848000 | Goonyella |  |  | 0.394 | KM | GA03ML43 | 0.5999 | GA03ML44 | 0 | KM |  |  |  |  | 43.6 | 44 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052757&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000052757 | C05-FR-NL-BRIABA-59.000km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 1260000 | Newlands |  |  | 0.5999 | KM | NL01ML59 | 0 | NL01ML59 | 0.5999 | KM |  |  |  |  | 59 | 59.6 | 2030-06-30 |  |  |  |  | 3 | 1.5 |  |  |  | 4.5 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20300630 | 11/02/2022 R888068 Ben Crozier - issue with start/end km in location tab showing total length of 213.878km long. Updated location tab to reflect start/end km from linear data on notification tab. Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052740&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000052740 | Formation Renewal | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 2.5 | KM | 5250000 | Goonyella |  |  | 2.511 | KM | GA01ML127 | 0.75 | GA01ML130 | 0.25 | KM |  |  |  |  | 127.75 | 130.25 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052738&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000052738 | Formation Renewal | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.4 | KM | 840000 | Goonyella |  |  | 0.4 | KM | GA01ML179 | 0.4 | GA01ML179 | 0.8 | KM |  |  |  |  | 179.4 | 179.8 | 2025-06-30 |  |  |  |  | 3 | [8 empty] | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Notification in process | NWSC |  | 20300630 | Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115203&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000115203 | C05-FR-GA-BOLINGBROKE-65.85km | GA-02ML | CIVIL | FORMATION |  | RENEWAL | 0.15 | KM | 316711 | Goonyella | BOLINGBROKE | BALOOK | 0.139 | KM | GA02ML65 | 0.8499 | GA02ML66 | 0 | KM |  |  |  |  | 65.85 | 66 | 2026-06-30 | UP |  |  |  | 4.5 | 5 | 3 | 4.5 | 1 | 20.3 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defer to later years due to overlapping undercutting scope to be delivered in FY24 - will monitor for deterioration <(>&<)> performance ALEY R889072
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115208&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000115208 | C05-FR-GA-NEBO-107.2km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.365 | KM | 1557361 | Goonyella | NEBO | BRAESIDE | 0.3649 | KM | GA01ML107 | 0.2 | GA01ML107 | 0.5649 | KM |  |  |  |  | 107.2 | 107.565 | 2025-06-30 | DOWN |  |  |  | 2.8 | 4.4 | 3 | 4.3 | 1 | 12.2 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20300630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint <(>&<)> overlap with planned FY24 undercutting scope (2000094869). Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 106.880km to 108.090km Both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 108.000km to 108.250km GA-01ML (Sections adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • M3 twist defects throughout • FY24 ballast undercut 106.500km-107.650km (noti # 2000094869)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115204&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000115204 | C05-FR-GA-PRAGUELANDS-17.7km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.17 | KM | 358939 | Goonyella | PRAGUELANDS | JILALAN | 0.17 | KM | GA01ML17 | 0.6999 | GA01ML17 | 0.8699 | KM |  |  |  |  | 17.7 | 17.87 | 2026-06-30 | DOWN |  |  |  | 3.5 | 4.6 | 3 | 4.4 | 1 | 15.4 |  |  |  | Formation Renewals | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defer to later years <(>&<)> monitor - will see how area performs after turnout undercutting is completed in FY24. ALEY R889072
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043959&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043959 | 4853 Formation Renewal | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.07 | KM | 1250900 | Newlands | PRING |  | 0.069 | KM | NL01ML5 | 0.9599 | NL01ML6 | 0.0299 | KM |  |  |  |  | 5.96 | 6.03 |  | MAIN |  |  |  | 4 | 2.5 |  |  |  | 10 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Postponed to later years. Monitor <(>&<)> treat with reactive if any issues arise. 5.500 - 5.865km (2000052751 - Planned Renewal - Completed 2023) 5.858 - 5.958km (2000018672 - Reactive Renewal - Completed 2018) 6.031 - 6.134km (2000004579 - Reactive Renewal - Completed 2017) 6.054 - 6.073km (2000004181 - Shear Key - Completed 2017) 6.134 - 6.254km (2000006839 - Reactive Renewal - Completed 2017) Section missed by reactive renewals: 5.958 - 6.031km (73m) - Suggest Monitor and complete with reactive if required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078186&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000078186 | C05-FR-NL-BUCKLEY-2.790km | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.28 | KM | 750000 | Newlands | PRING | BUCKLEY | 0.28 | KM | NL01ML2 | 0.79 | NL01ML3 | 0.07 | KM |  |  |  |  | 2.79 | 3.07 | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Originally FY27 Scope, Postponed to later years as track geometry appears stable over 2021 - 2023. Monitor.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115202&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000115202 | C05-FR-BW-RAGLAN-594.3km | BW-01ML | CIVIL | FORMATION |  | RENEWAL | 0.55 | KM | 3039300 | Blackwater | RAGLAN | MARMOR | 0.752 | KM | BW01ML594 | 0.2999 | BW01ML595 | 0.05 | KM |  |  |  |  | 594.3 | 595.05 | 2026-06-30 | UP |  |  |  | 3.7 | 4.9 | 3.5 | 4.6 | 1 | 17.2 |  | 2023-09-01 |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20300630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Note FY23 Derailment Recovery site Formation Scope (550m Total): • 594.300 – 594.550km (250m) • 594.635 – 594.725km (90m) • 594.840 – 595.050km (210m) Exclude: • 594.550 – 594.635km 11C/D Turnout • 594.725 – 594.810km 12A/B Turnout • 594.810 – 594.840km ID890 Level Crossing Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 594.140km to 595.150km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Arrange additional DCP testing beyond requirements of Track Formation Capping Layer AZN.NA.SPC.12.6135.001 from 593.900km to 594.100km BW-01ML (Section adjacent to formation renewal) and provide results to Network Asset Manager representative to help inform future scoping requirements. DCP testing to be in accordance with Dynamic Cone Penetrometer Instruction AZN.NA.GDL.12.6140.006. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052717&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000052717 | Formation Renewal | GA-03ML | CIVIL | FORMATION |  | RENEWAL | 0.85 | KM | 1785000 | Goonyella | WINCHESTER | PEAK DOWNS | 0.8549 | KM | GA03ML41 | 0.75 | GA03ML42 | 0.5999 | KM |  |  |  |  | 41.75 | 42.6 | 2025-06-30 |  |  |  |  | 3 | 2.4 |  |  |  | 7.2 |  |  |  | Formation Renewals | STD DESIGN W/ BESPOKE ELEMENTS | HIGH |  | HIGH | HIGH | Notification in process | NWSC INIF |  | 20300630 | * 31.03.2021 09:51:11 AUSQLD Jane Livingston (R111275) * Push it out to FY25. Poor Access and Problem in cuttings. Ballast Undercutting is planned in FY22 which may improve the track geometry issues. Review track geometry afterwards and monitor to see if it is improved. Notification Deleted from FY25, reinstated in future years, investigation to be completed to determine requirement.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041188&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000041188 | C58-LX-MA-BOUNDARY HILL-0.72km | LX006400 | CIVIL | LEVEL CROSSINGS |  | DECOMMISSION | 1 | SITE | 15000 | Moura | BOUNDARY HILL | BOUNDARY HILL | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 0.72 | 0.72 | 2020-06-30 |  |  |  |  | 3 | 1 |  |  |  | 3 |  | 2019-03-22 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | IV.00459.E.2.M.MH.CO | 20300630 | * 07.08.2019 14:01:49 AUSQLD Jeremy Stevenson (R867415) * DECOMMISSION OF CROSSING Maintenance Access Road * 11.11.2020 13:14:11 AUSQLD Sharbaree Biswas (R865006) received from IM that the crossing is in use and cannot be de = commissioned in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041189&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000041189 | C58-LX-MA-BOUNDARY HILL-4.49km | LX006403 | CIVIL | LEVEL CROSSINGS |  | DECOMMISSION | 1 | SITE | 15000 | Moura | BOUNDARY HILL | BOUNDARY HILL | 0 |  |  | 0 |  | 0 | KM |  |  |  |  | 4.49 | 4.49 | 2020-06-30 |  |  |  |  | 3 | 1 |  |  |  | 3 |  | 2019-03-22 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 07.08.2019 14:01:55 AUSQLD Jeremy Stevenson (R867415) * DECOMMISSION OF CROSSING Mine Access Road * 11.11.2020 13:13:17 AUSQLD Sharbaree Biswas (R865006) from IM that the crossing is in use and cannot be closed in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074336&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000074336 | C58-LX-NL-HABILAH-133.919km | LX003330 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 30000 | Newlands | HABILAH | NEWLANDS | 0 | KM | NL01ML133 | 0.919 | NL01ML133 | 0.919 | KM |  |  |  |  | 133.919 | 133.919 | 2023-06-30 | PRIVATE CATTLE CROSSING | [9 empty] | 4929 | 2021-03-31 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 19.03.2021 16:57:40 AUSQLD Sharbaree Biswas (R865006) * It is a design scope as this crossing is in FY24 renewal. Sharbaree Biswas (R865006) It is a design scope as this crossing is in FY24 renewal. It is a design scope as this crossing is in FY24 renewal. FY27 renewal. 19.03.2021 16:57:40 AUSQLD Sharbaree Biswas (R865006) It is a design scope as this crossing is in FY24 renewal. Design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051962&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000051962 | C58-LX-GA-VILLAFRANCA-40.398km | LX001049 | CIVIL | LEVEL CROSSINGS |  | DESIGN | 1 | SITE | 32000 | Goonyella | VILLAFRANCA | MT MCLAREN | 0 | KM | GA05ML40 | 0.398 | GA05ML40 | 0.398 | KM |  |  |  |  | 40.398 | 40.398 | 2022-06-30 | WUTHUNG ROAD |  |  |  | 2.79 | 1.2 |  |  |  | 3.35 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | IV.00459 | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044024&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000044024 | C58-LX-MA-BATTERY rd-19.73km | LX005961 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Moura | BATTERY ROAD |  | 0 | KM | MA01ML19 | 0.7299 | MA01ML19 | 0.7299 | KM |  |  |  |  | 19.73 | 19.73 |  | SINGLE |  |  |  | 2.8 | 2.5 |  |  |  | 7 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | IV.00459.E.6.M | 20300630 | * 15.01.2020 13:18:07 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY23 due to low priority * 11.11.2020 13:17:46 AUSQLD Sharbaree Biswas (R865006) * Moved to FY24 due to other high priority crossings. Moved to FY24 due to other high priority crossings.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044064&DY_MAB=X&~OKCODE=ONLI | FY30 | Non Coal Traffic |  | NON-COAL | 002000044064 | C58-LX-BW-COME TRIVER RD-221.69km | LX002761 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Blackwater | COME TRIVER RD |  | 0 | KM | BW03ML221 | 0.6889 | BW03ML221 | 0.6889 | KM |  |  |  |  | 221.69 | [6 empty] | 2 | 1.5 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 15.01.2020 13:03:13 AUSQLD Sanjna Rajagopalan (R884639) * Moved from FY22 to FY24 due to low priority 15.01.2020 13:03:13 AUSQLD Sanjna Rajagopalan (R884639) Moved from FY22 to FY24 due to low priority 15.01.2020 13:03:13 AUSQLD Sanjna Rajagopalan (R884639) Moved from FY22 to FY24 due to low priority 15.01.2020 13:03:13 AUSQLD Sanjna Rajagopalan (R884639) Moved from FY22 to FY24 due to low priority 08 July 2021 Moved to FY25 due to limitations of fund, resources, and maintenance closure in FY24. This is due to the fact that there are already four major crossings in FY24 renewal delivery. All of these crossings are on duplicated tracks and they are major public crossings. The renewal of this crossing is delayed till FY26 as per the discussion with the Infrastructure Maintenance Team..
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044041&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000044041 | C58-LX-BW-TOLMIES-198.37km | LX003432 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Blackwater | TOLMIES |  | 0 | KM | BW03ML198 | 0.3649 | BW03ML198 | 0.3649 | KM |  |  |  |  | 198.37 | 198.365 | [5 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | Mtg with Trevor D- moved the renewal in FY30. AS per the meeting on 31 Aug, we moved this renewal out to FY28. The renewal of this crossing is delayed till FY27 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044036&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000044036 | C58-LX-GA-WOTONGA-0.43km | LX005813 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Goonyella | WOTONGA | BLAIR ATHOL | 0 | KM | GA05ML0 | 0.4279 | GA05ML0 | 0.4279 | KM |  |  |  |  | 0.43 | 0.428 | [5 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068844&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000068844 | C58-LX-BW-BLACKWATER-0.941km | LX005881 | CIVIL | LEVEL CROSSINGS |  | RENEWAL MAJOR | 1 | SITE | 455000 | Blackwater | BLACKWATER | KOORILGAH | 0 | KM | BW13ML0 | 0.9409 | BW13ML0 | 0.9409 | KM |  |  |  |  | 0.941 | 0.941 |  | PONYCLUB ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | This was pushed out of FY25 to FY27
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083392&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000083392 | C58-LX-MA-CALLE-15.79km | LX005959 | CIVIL | LEVEL CROSSINGS | DESIGN | DESIGN | 1 | SITE | 30000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML15 | 0.79 | MA01ML15 | 0.79 | KM |  |  |  |  | 15.79 | 15.79 |  | PRIVATE ACCESS ROAD |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | This crossing can be planned after FY30 Design, which the SPM does not allow us now. FY26 DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122949&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000122949 | C58-LX-GA-WOTONGA-9.97km | LX006680 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | DESIGN | 30000 | Goonyella | WOTONGA | MORANBAH | 0 | KM | GA05ML9 | 0.9699 | GA05ML9 | 0.9699 | KM |  |  | 576.77 | 576.77 | 9.97 | 9.97 |  | EPALA LANE |  |  |  | 2.4 | 1.5 | 2 | 3 |  | 6.5 |  |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Moved to FY29 Design for FY31 Renewal. Moved to FY25 Renewal due to low OC and due to lack of additional supporting documents. Possible to add in FY24 Design comparing the priority over other crossings for FY26 delivery. Scope development is required before adding in FY24 design.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122919&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000122919 | C58-LX-BW-FAIRHILL-44.5km | LX003469 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Blackwater | FAIRHILL | YAN YAN | 0 | KM | BW08ML44 | 0.512 | BW08ML44 | 0.512 | KM |  |  |  |  | 44.5 | 44.5 |  | UNNAMED ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | FY26 DESIGN <(>&<)> FY27 RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083407&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000083407 | C58-LX-MA-MT RAINBOW-102.5km | LX006006 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 35692 | Moura | MOUNT RAINBOW | DUMGREE | 0 | KM | MA01ML102 | 0.5 | MA01ML102 | 0.5 | KM |  |  |  |  | 102.5 | 102.5 |  | IVERNESS ROAD |  |  |  | 3 | 1 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Pushed to FY30 Design as per the mtg on 28 July 2022 with IM team. FY27 Design for FY29 Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122941&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000122941 | C58-LX-GA-MT MCLAREN-78.1km | LX005850 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 30000 | Goonyella | MT MCLAREN | BLACKRIDGE | 0 | KM | GA05ML78 | 0.0769 | GA05ML78 | 0.0769 | KM |  |  |  |  | 78.1 | 78.1 |  | PRIVATE ACCESS ROAD |  |  |  | 1.4 | 1.2 |  |  |  | 1.7 | 4929 |  |  | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY23 IN | 20300630 | Pushed out to FY29 for design and FY31 Renewal. Supported by Reagan Case. To be maintained by IM. Ballast fouling is only up to 10-20%. PCR 5124 added. FY23 DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122950&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal GAPE Traffic |  | COAL | 002000122950 | C58-LX-NL-SUTTOR CREEK-193.566km | LX007258 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Newlands | SUTTOR CREEK | EAGLEFIELD CREEK | 0 | KM | NL01ML193 | 0.5679 | NL01ML193 | 0.5679 | KM |  |  |  |  | 193.566 | 193.566 | 2031-06-30 | PRIVATE CATTLE CROSSING |  |  |  | 2.52 | 1.2 | 2 | 3 | 1 | 7.56 | [9 empty] | Outstanding notification | NWSC |  | 20300630 | This crossing had a ballast undercut/sleepers replaced/drainage replaced/road surface repaired in FY24. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing several years to FY29 IFP, FY30 IFC, FY31 Renewal. This crossing will continue to be monitored and bought forward if required. FY26 DESIGN. SCOPED ON 11 MAY 2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103947&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000103947 | C58-LX-MA-EARLSFIELD-136.015km | LX006028 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Moura | EARLSFIELD | BELLDEEN | 0 | KM | MA01ML136 | 0.0149 | MA01ML136 | 0.0149 | KM |  |  | 136 | 136 | 136.015 | 136.015 | 2030-06-30 | QUARRY ENTRANCE ROAD |  |  |  | 3 | 1.1 | 2 | 2 | 1 | 6 | [9 empty] | Outstanding notification | NWSC |  | 20300630 | DESIGN
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103946&DY_MAB=X&~OKCODE=ONLI | FY30 | Dual Traffic | FUTURE SCOPE | COAL | 002000103946 | C58-LX-BW-PARANA-557.267km | LX005583 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Blackwater | PARANA | MT LARCOM | 0 | KM | BW01ML557 | 0.264 | BW01ML557 | 0.264 | KM |  |  | 557.267 | 557.267 | 557.267 | 557.267 | 2026-06-30 | PORT CURTIS WAY |  |  |  | 3 | 4.5 | 2 | 4 | 1 | 12 | [9 empty] | Outstanding notification | NWSC |  | 20260630 | 12.02.2024 R888068 Ben Crozier Moved to FY30 IFP due to track upgrade through crossing during Feb. 2024 closure. FY26 IFP, FY27 IFC, FY28 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051949&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000051949 | C58-LX-GA-PRAGUELAND-14.684km | LX006433 | CIVIL | LEVEL CROSSINGS | IFP | DESIGN | 1 | SITE | 54000 | Goonyella | PRAGUELAND | JILALAN | 0 | KM | GA01ML14 | 0.675 | GA01ML14 | 0.675 | KM |  |  |  |  | 14.684 | 14.684 | 2022-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.71 | 1 |  |  |  | 2.71 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR | IV.00459 | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068849&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000068849 | C58-LX-NL-BIRRALEE-94.201km | LX003314 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | MAJOR RENEWAL | 1 | SITE | 957514 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML94 | 0.203 | NL01ML94 | 0.203 | KM |  |  |  |  | 94.201 | 94.201 | 2030-06-30 | PRIVATE ACCESS RD |  |  |  | 2.57 | 1.4 | 2 | 3 | 1 | 7.71 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | This crossing had a Ballast Undercut in Aug 2023. DCP's were taken at this time and low strength formation was identified on the higher km side of the crossing. Despite this issue if the Mine ceases watering the crossing (as they have agreed via the Customer team) renewal can be delayed. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing 2 years to FY28 IFP, FY29 IFC, FY30 Renewal. This crossing will continue to be monitored and bought forward if required. FY26 Design for FY28 Renewal. Scoped on 11 May 2023.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103945&DY_MAB=X&~OKCODE=ONLI | FY30 | Non Coal Traffic |  | NON-COAL | 002000103945 | C58-LX-BW-TOLMIES-221.69km | LX002761 | CIVIL | LEVEL CROSSINGS | UPGRADE SIGNAL | UPGRADE SIGNAL | 1 | SITE | 32000 | Blackwater | TOLMIES | COMET | 0 | KM | BW03ML221 | 0.7019 | BW03ML221 | 0.7019 | KM |  |  | 221.69 | 221.69 | 221.69 | 221.69 | 2030-06-30 | HUMBOLDT ROAD |  |  |  | 1.4 | 1.7 | 2 | 3 | 1 | 4.2 | [9 empty] | Outstanding notification | NWSC |  | 20300630 | UPGRADE SIGNAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000123468&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  |  | 002000123468 | C58-LX-MA--km | MA | CIVIL | LEVEL CROSSINGS | UPGRADE-SIGNAL | RENEWAL | 1 | SITE | 1500000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2029-06-30 |  |  |  |  | 10 | 10 | 2 | 10 | 1 | 100 | [9 empty] | Outstanding notification | NWSC |  | 20290630 | SIGNAL UPGRADE-FY30
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044277&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000044277 | 5670 Sleepers Renewal | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 157 | SLEEPERS | 96398 | Goonyella | BALOOK | WANDOO | 0.11 | KM | GA01ML74 | 0.53 | GA01ML74 | 0.64 | KM |  |  |  |  | 74.53 | 74.64 |  | DOWN | [8 empty] | 0 |  | 2019-07-15 |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044276&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000044276 | 5669 Sleepers Renewal | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 37 | SLEEPERS | 22718 | Goonyella | BALOOK | WANDOO | 0.0299 | KM | GA01ML74 | 0.7099 | GA01ML74 | 0.7399 | KM |  |  |  |  | 74.71 | 74.74 |  | DOWN | [8 empty] | 0 |  | 2019-07-15 |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043187&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000043187 | 46 Sleepers Renewal | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 3314 | SLEEPERS | 2034796 | Goonyella | BOLINGBROKE | BALOOK | 2.278 | KM | GA01ML67 | 0.7299 | GA01ML70 | 0 | KM |  |  |  |  | 67.73 | 70 |  | DOWN | [6 empty] | 25 |  | 25 |  | 2019-07-15 |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC | IV.00146 | 20300630 | * 06.09.2019 10:37:16 AUSQLD Jeremy Stevenson (R867415) * "Concrete Sleepers Goonyella Main - Jilalan Bypass * * Planned FY21 Q3. * * Cut in 17.347, roll out 3.5pair to at least 16.970. * Investigate if 2 GIJ's at 17.300 require replacement."
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044275&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000044275 | 5668 Sleepers Renewal | GA-01ML | CIVIL | SLEEPERS |  | RENEWAL | 1145 | SLEEPERS | 703030 | Goonyella | BOLINGBROKE | BALOOK | 0.794 | KM | GA01ML73 | 0.68 | GA01ML74 | 0.4699 | KM |  |  |  |  | 73.68 | 74.47 |  | DOWN | [8 empty] | 0 |  | 2019-07-15 |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052582&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  |  | 002000052582 | Structures Design | CU100254 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 0 | Blackwater |  |  | 0 | KM | BW03ML89 | 0.6129 | BW03ML89 | 0.6129 | KM |  |  |  |  | 89.61 |  | 2022-06-30 |  |  |  |  | 3.5 | 3.35 |  |  |  | 11.7 |  | 2020-03-06 |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR |  | 00000000 | * 26.02.2020 15:31:46 AUSQLD Peter Rayner (R003851) * Defect - 0 - Proposed Renewal - Remove and replace 1/1200x1200 * 16.10.2020 08:25:27 AUSQLD Edward Brooks (R884255) * Renewed in past years.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052591&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  |  | 002000052591 | Structures Design | BR101334 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 94400 | Blackwater | BOAT CREEK |  | 0 | KM | BW02ML547 | -0.8299 | BW02ML547 | -0.8299 | KM |  |  |  |  | 546.17 |  | 2022-06-30 |  |  |  |  | 3 | 4.9 |  |  |  | 14.7 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR |  | 00000000 | * 26.02.2020 15:44:53 AUSQLD Peter Rayner (R003851) * Defect - Bearing Pads deteriorated. - Proposed Renewal - Check if M220 bridge, review risk assessment and then depending on risk assessment replace bearing pads . * 25.09.2020 10:04:45 AUSQLD Edward Brooks (R884255) * Build into bridge strategy study, separate from renewal designs.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043898&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043898 | B12 -ST-NL-Durroburra-000.740km | BR300414 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 93683 | Newlands | DURROBURRA | PRING | 0 | KM | NL01ML0 | 0.7399 | NL01ML0 | 0.7399 | KM |  |  |  |  | 0.74 |  | 2022-06-30 |  |  |  |  | 3.5 | 1.7 |  |  |  | 6 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 10.03.2020 08:31:39 AUSQLD Peter Rayner (R003851) * Defect - Design assessment found structures to shear deficient and borderline Moment capacity. - Proposed Renewal - Level 3 Inspections, measurements, Strengthening for shear
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052592&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  |  | 002000052592 | Structures Design | BR101201 | CIVIL | STRUCTURES |  | DESIGN | 1 | SITE | 94400 | Blackwater | TARGINNIE ROAD |  | 0 | KM | BW02ML547 | -0.45 | BW02ML547 | -0.45 | KM |  |  |  |  | 546.55 |  | 2022-06-30 |  |  |  |  | 3 | 4.9 |  |  |  | 14.7 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR |  | 00000000 | * 26.02.2020 15:45:10 AUSQLD Peter Rayner (R003851) * Defect - Notification Bearing pads severely deteriorated. - Proposed Renewal - Check if M220 bridge, review risk assessment and then depending on risk assessment replace bearing pads . * 25.09.2020 10:03:11 AUSQLD Edward Brooks (R884255) * Build into bridge strategy works, so remove from this years scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052619&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  |  | 002000052619 | Structures Renewal | CU200875 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE |  | Goonyella |  |  | 0 | KM | GA01ML62 | 0.658 | GA01ML62 | 0.658 | KM |  |  |  |  | 62.67 |  | 2022-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  | 2020-03-06 |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Notification completed | SCPR |  | 00000000 | * 26.02.2020 15:52:23 AUSQLD Peter Rayner (R003851) * Defect - Culvert started to collape in FY16, needs replacement based on inspection notes - Proposed Renewal - Remove and Replace 3/1200x900 RCBC * 13.10.2020 13:50:58 AUSQLD Edward Brooks (R884255) * * 2020 inspection has found this culvert as replaced with 3 RCBC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052618&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052618 | B12 -ST-GA-Bolingbroke-052.570km | BR200823 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 1994400 | Goonyella | BOLINGBROKE |  | 0 | KM | GA02ML52 | 0.5699 | GA02ML52 | 0.5699 | KM |  |  |  |  | 52.57 |  | 2022-06-30 |  |  |  |  | 3 | 5 |  |  |  | 15 |  | 2020-03-06 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 26.02.2020 15:52:07 AUSQLD Peter Rayner (R003851) * Defect - SAP, Notification 2000020373 Bridge Bearing moving out - Proposed Renewal - Likely Bearing only replacement <(>&<)> monitor for shear cracking. * 12.05.2020 16:22:28 AUSQLD Edward Brooks (R884255) * Scope deferred due to budget limitation. Will need to monitor bearing due to deferred scope.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043443&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043443 | B52 -ST-BW-Kenmare-004.080km | CU100938 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 438299 | Blackwater | KINROLA | KENMARE | 0 | KM | BW06ML4 | 0.08 | BW06ML4 | 0.08 | KM |  |  |  |  | 4.08 | [6 empty] | 3 | 1.5 |  |  |  | 4.5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Section loss in invert of culvert Proposed: Concrete Line or Remove and Replace. Final: Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043786&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043786 | B12 -ST-GA-Dalrymple-009.514km | BR200652 | CIVIL | STRUCTURES | BRIDGE-STRENGTHEN | DESIGN | 1 | SITE | 100000 | Goonyella | BIDGERLEY JUNCTION | BIDGERLEY JUNCTION | 0 | KM | GA02ML10 | -0.4859 | GA02ML10 | -0.4859 | KM |  |  |  |  | 9.51 | [6 empty] | 3 | 4.6 |  |  |  | 14 |  |  |  | OVERHEAD - component replacement - Major | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043470&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043470 | B12 -ST-NL-Birralee-104.840km | BR300557 | CIVIL | STRUCTURES | BRIDGE-STRENGTHEN | DESIGN | 1 | SITE | 100000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML104 | 0.8299 | NL01ML104 | 0.8299 | KM |  |  |  |  | 104.84 |  | 2032-06-30 |  |  |  |  | 2.5 | 2.5 |  |  |  | 10.1 |  |  |  | Culvert Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Design assessment found structures to shear deficient and borderline Moment capacity. Proposed: Level 3 Inspections, measurements, Strengthening for shear Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043857&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043857 | B12 -ST-NL-Sonoma-080.430km | BR300600 | CIVIL | STRUCTURES | BRIDGE-STRENGTHEN | DESIGN | 1 | SITE | 100000 | Newlands | MCNAUGHTON | SONOMA | 0 | KM | NL01ML80 | 0.4179 | NL01ML80 | 0.4179 | KM |  |  |  |  | 80.43 |  | 2032-06-30 |  |  | STRENGTHEN |  | 2.5 | 2.5 |  |  |  | 10.1 |  |  |  | Bridges Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Design assessment found structures to shear deficient and borderline Moment capacity. Proposed: Level 3 Inspections, measurements, Strengthening for shear
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043901&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043901 | B12 -ST-NL-Aberdeen-033.020km | BR300145 | CIVIL | STRUCTURES | BRIDGE-STRENGTHENING | RENEWAL | 1 | SITE | 500000 | Newlands | ARMUNA | ABERDEEN | 0 | KM | NL01ML33 | 0.032 | NL01ML33 | 0.032 | KM |  |  |  |  | 33.02 | [6 empty] | 3.5 | 2.5 |  |  |  | 8.75 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Span 3 girders are impacting abutment and concrete concrete interface is causing cracks in the girder. " Proposed: Level 3 Inspections, measurements, Strengthening for shear, resolve moving girders.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133044&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000133044 | B52 -ST-BW-Memooloo-050.890km | CU100939 | CIVIL | STRUCTURES | CMP-CONCRETE LINE | RENEWAL | 1 | SITE | 7000000 | Blackwater | MEMOOLOO |  | 0 | KM | BW06ML50 | 0.89 | BW06ML50 | 0.89 | KM |  |  |  |  | 50.89 |  | 2030-06-30 |  |  | CONCRETE LINE S2 |  | 3.5 | 2.3 | 3 | 3.6 | 1 | 12.6 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: Corrosion in top halg of culvert suggesting corrosion from outside in. High risk of sectional loss. Proposed: "Concrete Line in Stage 2 Cells 1,2,8,9,14,15,16,18,19,20,21" Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000091922&DY_MAB=X&~OKCODE=ONLI | FY30 | Non Coal Traffic |  | NON-COAL | 002000091922 | B52 -ST-BW-Comet-229.120km | CU100174 | CIVIL | STRUCTURES | NON-MRSB RCBC | RENEWAL | 1 | SITE | 2856700 | Blackwater | BURNGROVE-NOGOA |  | 0 | KM | BW03ML229 | 0.1199 | BW03ML229 | 0.1199 | KM |  |  |  |  | 229.12 |  | 2027-06-30 |  |  |  |  | 4 | 1.65 |  |  |  | 13.3 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | NON MRSB | 20300630 | Defect - Notification 2000029936 Culvert is sinking and cracking. Servere cracking in hog and throughout - Proposed Renewal - Remove and replace as repairing haunch cracks very difficult.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086063&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000086063 | B52 -ST-BW-Tryphinia-132.820km | CU100571 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 800000 | Blackwater | BW-CL |  | 0 | KM | BW03ML132 | 0.8199 | BW03ML132 | 0.8199 | KM |  |  |  |  | 132.82 |  | 2030-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Cracks in haunches throughout Proposed: NMP to investigate depth of cracks on haunches and renewal to plan for Remove and replace assuming cracking will worsen over time which has been evident in last few years. Drawing: Risk: Mod Reason: Corrosion in Reinf is not visible from surface where the cracks are visible and some rust staining has been observed in these cracks. If wall to ceiling reinf corrodes through failure could be quite quick.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086056&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000086056 | B52 -ST-NL-Havilah-142.520km | CU300491 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 430000 | Newlands | HAVILAH |  | 0 | KM | NL01ML142 | 0.52 | NL01ML142 | 0.52 | KM |  |  |  |  | 142.52 |  | 2030-06-30 |  |  | REMOVE & REPLACE |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Cracks throughout RCP Proposed: CIPP lining or remove and replace Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000089129&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000089129 | B52 -ST-MA-Fry-086.780km | CU400449 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 850000 | Moura | MA |  | 0 | KM | MA01ML86 | 0.78 | MA01ML86 | 0.78 | KM |  |  |  |  | 86.78 |  | 2028-06-30 |  |  | R&R RCBC |  | 3 | 1.1 | 3 | 3 | 1 | 9 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Washout risk and inadequate cover. Proposed: Remove and Replace RCBC - Proposed diversion results in overtopping of rail and thus is deemed unacceptable. Currently has insufficient cover, if Aurizon wishes to remove and replace 900 x 600mm RCBC required Risk: Moderate Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044249&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000044249 | B52 -ST-NL-Binbee-050.050km | CU300404 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Newlands | NL |  | 0 | KM | NL01ML50 | 0.05 | NL01ML50 | 0.05 | KM |  |  |  |  | 50.05 |  | 2030-06-30 | MOD |  | REMOVE & REPLACE |  | 3 | 3.4 | 3 | 4 | 1 | 12 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: 29% 20-26.5TAL load intensity increase, no cover of pipe. Minor corrosion issues, but holding ok, push out Proposed: Remove <(>&<)> Replace with RCBC as cover is limited Final: Drawing: Risk: Moderate Reason: Only minor corrosion and movement in the pipe. Will renew when condition warrants, but is in long term renewal due to under strength of CMP and insufficient cover on CMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085877&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000085877 | B52 -ST-BW-Mackenzie-031.760km | CU101157 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 716095 | Blackwater | MACKENZIE | BW-GG | 0 | KM | BW08ML31 | 0.76 | BW08ML31 | 0.76 | KM |  |  |  |  | 31.76 |  | 2030-06-30 |  |  | CONCRETE LINING | CONCRETE LINING | 3.5 | 1.1 | 3 | 3 | 1 | 10.9 | 261 |  |  | Culvert Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20300630 | Defect: Severe spalling in ceiling and Cracks in roof and legs in all units Maintenance work completed in FY22 which will allow deferral of this renewal 5-10 years. Proposed: 200-250mm Concrete lining confirmed in FY22 design. Final: 1/2240x1140 Concrete Line Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124113&DY_MAB=X&~OKCODE=ONLI | FY30 |  | REACTIVE RENEWALS | COAL | 002000124113 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4016209 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124114&DY_MAB=X&~OKCODE=ONLI | FY30 |  | REACTIVE RENEWALS | COAL | 002000124114 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4381319 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124115&DY_MAB=X&~OKCODE=ONLI | FY30 |  | REACTIVE RENEWALS | COAL | 002000124115 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 930070 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124116&DY_MAB=X&~OKCODE=ONLI | FY30 |  | REACTIVE RENEWALS | COAL | 002000124116 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 930070 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124146&DY_MAB=X&~OKCODE=ONLI | FY30 | Dual Traffic | BASELOAD | COAL | 002000124146 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ AL 7C/D | TO000899 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | ALDOGA | AL 7C/D | 0.0519 | KM | BW02ML555 | 0.888 | BW02ML555 | 0.9399 | KM |  |  |  |  | 555.888 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124149&DY_MAB=X&~OKCODE=ONLI | FY30 | Dual Traffic | BASELOAD | COAL | 002000124149 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ AL 8A/B | TO000898 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | ALDOGA | AL 8A/B | 0.047 | KM | BW02ML555 | 0.8659 | BW02ML555 | 0.8189 | KM |  |  |  |  | 555.866 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124143&DY_MAB=X&~OKCODE=ONLI | FY30 | Dual Traffic | BASELOAD | COAL | 002000124143 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ AL 8C/D | TO000856 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | ALDOGA | AL 8C/D | 0.049 | KM | BW01ML555 | 0.767 | BW01ML555 | 0.8159 | KM |  |  |  |  | 555.767 |  | 2030-06-30 | [19 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124134&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000124134 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ AR 11A/B | TO000614 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | AROONA | AR 11A/B | 0.0359 | KM | BW03ML94 | 0.542 | BW03ML94 | 0.5779 | KM |  |  |  |  | 94.542 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124137&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000124137 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦AR 11C/D | TO000719 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | AROONA | AR 11C/D | 0.0359 | KM | BW04ML94 | 0.6129 | BW04ML94 | 0.5769 | KM |  |  |  |  | 94.613 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124128&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124128 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦CH210A | TO001157 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW17YR0 | 0.378 | BW17YR0 | 0.406 | KM |  |  |  |  | 0.378 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124122&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000124122 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦CH 213A | TO001174 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW20YR0 | 0.4099 | BW20YR0 | 0.438 | KM |  |  |  |  | 0.41 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124125&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124125 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦CH213B | TO001156 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.0269 | KM | BW17YR0 | 0.466 | BW17YR0 | 0.439 | KM |  |  |  |  | 0.466 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124164&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124164 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000497 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT |  | 0.0449 | KM | GA01BD3 | 0.083 | GA01BD3 | 0.0379 | KM |  |  |  |  | 3.083 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124155&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124155 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000496 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT |  | 0.048 | KM | GA01BA3 | 0.4109 | GA01BA3 | 0.459 | KM |  |  |  |  | 3.411 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124167&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124167 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000104 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT |  | 0.049 | KM | GA02BA3 | 0.4349 | GA02BA3 | 0.386 | KM |  |  |  |  | 3.435 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124170&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124170 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000568 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT |  | 0.047 | KM | GA02BA3 | 0.627 | GA02BA3 | 0.5799 | KM |  |  |  |  | 3.627 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124158&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124158 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ HP 11AB | TO000493 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT | HP 11A/B | 0.0449 | KM | GA01BA3 | 0.8519 | GA01BA3 | 0.807 | KM |  |  |  |  | 3.852 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124161&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124161 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ HP 11C/D | TO000567 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | HAY POINT | HP 11C/D | 0.0369 | KM | GA02BA3 | 0.643 | GA02BA3 | 0.68 | KM |  |  |  |  | 3.643 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124152&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000124152 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦YN 48A/B | TO000336 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Goonyella | YUKAN | YN 48A/B | 0.033 | KM | GA02ML29 | 0.398 | GA02ML29 | 0.4309 | KM |  |  |  |  | 29.398 | [21 empty] | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000073336&DY_MAB=X&~OKCODE=ONLI | FY30 | Dual Traffic | BASELOAD | COAL | 002000073336 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ AL 7A/B | TO000854 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | ALDOGA | AL 7A/B | 0.0459 | KM | BW01ML555 | 0.9879 | BW01ML555 | 0.9419 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 01.03.2021 10:11:53 AUSQLD Tracy Holmes (R870040) * See attachment for more details. Cost estimate to be firmed up * 19.03.2021 12:04:04 AUSQLD Lachlan Prescott (R881571) * Deferred to FY24 due to over-allocated FY23 * 29.04.2021 16:12:32 AUSQLD Lachlan Prescott (R881571) * Cost updated to 700k as PLACEHOLDER only. Estimate to be firmed up post inspection
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044002&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000044002 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH 233A | TO001175 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CH 233A | 0.048 | KM | BW20YR0 | 0.501 | BW20YR0 | 0.501 | KM |  |  |  |  | 0.5 |  | 2030-06-30 |  |  |  |  | 3.5 | 3.5 |  |  |  | 12.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044003&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000044003 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH 233B | TO001181 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CH 233B | 0.0539 | KM | BW21YR0 | 0.6179 | BW21YR0 | 0.6179 | KM |  |  |  |  | 0.62 |  | 2030-06-30 |  |  |  |  | 3.5 | 3.5 |  |  |  | 12.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043992&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000043992 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH212A | TO001158 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CH212A | 0 | KM | BW17YR0 | 0.326 | BW17YR0 | 0.326 | KM |  |  |  |  | 0.33 |  | 2030-06-30 |  |  |  |  | 2.5 | 3 |  |  |  | 7.5 | 4745 | 2020-03-06 |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 16.10.2020 12:42:00 AUSQLD Lachlan Prescott (R881571) * MIC process declined decommissioning. New plan is to upgrade 212A/B to SNX, leace 213A/B as is. * 23.03.2021 16:07:43 AUSQLD Lachlan Prescott (R881571) * FY23 overallocated, moved to FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043993&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000043993 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH 212B | TO001173 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 1200000 | Blackwater | CALLEMONDAH | CH212B | 0 | KM | BW20YR0 | 0.4069 | BW20YR0 | 0.4069 | KM |  |  |  |  | 0.41 |  | 2030-06-30 |  |  |  |  | 3 | 3.5 |  |  |  | 10.5 | 4745 | 2020-03-06 |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20300630 | * 16.10.2020 12:42:56 AUSQLD Lachlan Prescott (R881571) * MIC process declined decommissioning. New plan is to upgrade 212A/B to SNX, leave 213A/B as is. * 23.03.2021 16:08:10 AUSQLD Lachlan Prescott (R881571) * FY23 overallocated, moved to FY24
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115803&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000115803 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ MO10 | TO000823 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 0 | Blackwater | MEMOOLOO | MO10 | 0.032 | KM | BW06ML47 | 0.8639 | BW06ML47 | 0.8319 | KM |  |  |  |  | 47.864 | 47.832 | 2030-06-30 |  |  |  |  | 4 | 1.5 | 3.3 | 4 |  | 13.2 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27 Construction. POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM TR RH FULL RENEWAL - Same angle <(>&<)> Same no. of Points motor. Turnout renewal inabling supporting renewal within project extent Alex Rohweder (R872340) Defer the design IFP to FY26, IFC to FY27 and Construction FY28. Monitor the permanent speed reduction (25km/h) affect on the turnout. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077219&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000077219 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ ER1.2A | TO000181 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1000000 | Newlands | BINBEE | ER1.2A | 0.0259 | KM | NL05PL45 | 0.4969 | NL05PL45 | 0.523 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 13.05.2021 11:13:52 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Alex Rohweder (R872340) 12/09/2023 Defer the renewal scope to FY30 (from FY27), until customer team's Newlands Upgrade and RCS program is locked in.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077221&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000077221 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ ER2.2B | TO000177 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1000000 | Newlands | BINBEE | ER2.2B | 0.0259 | KM | NL05PL45 | 0.9549 | NL05PL45 | 0.929 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 13.05.2021 11:14:12 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Alex Rohweder (R872340) 12/09/2023 Defer the renewal scope to FY30 (from FY27), until customer team's Newlands Upgrade and RCS program is locked in.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077224&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000077224 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CH211A | TO001159 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1200000 | Blackwater | CALLEMONDAH | CH211A | 0.016 | KM | BW17YR0 | 0.2999 | BW17YR0 | 0.316 | KM | [6 empty] | 2030-06-30 | [9 empty] | 16.5 |  | 2022-03-31 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 13.05.2021 11:16:12 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077222&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000077222 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ HHER1 | TO000187 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1000000 | Newlands | HAVILAH | HHER1 | 0.0259 | KM | NL09PL130 | 0.65 | NL09PL130 | 0.676 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 13.05.2021 11:14:51 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Alex Rohweder (R872340) 12/09/2023 Defer the renewal scope to FY30 (from FY27), until customer team's Newlands Upgrade and RCS program is locked in.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000077223&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000077223 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ HHER2 | TO000188 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUTS | 1000000 | Newlands | HAVILAH | HHER2 | 0.0259 | KM | NL09PL131 | 0.07 | NL09PL131 | 0.0439 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 13.05.2021 11:15:07 AUSQLD Tracy Holmes (R870040) * Allocated to FY25, to be confirmed later. Costs TBC Alex Rohweder (R872340) 12/09/2023 Defer the renewal scope to FY30 (from FY27), until customer team's Newlands Upgrade and RCS program is locked in.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052842&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000052842 | TURNOUTS ¦ DESIGN ¦ RENEWAL ¦ MM1 | TO000878 | CIVIL | TURNOUTS | DESIGN | DESIGN | 1 | TURNOUT | 0 | Blackwater | MT MILLER | MM1 | 0.0259 | KM | BW01FK0 | 0.1449 | BW01FK0 | 0.171 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 4 | 1 |  |  |  | 4 | 5289 | 2020-03-06 | 2021-10-05 | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Notification in process | RRIG | FY23 IN | 20280107 | * 28.02.2020 13:40:30 AUSQLD Peter Rayner (R003851) * Design to be completed in FY22 for FY23 execution. Work is to upgrade turnout rail size * 10.05.2021 11:03:11 AUSQLD Lachlan Prescott (R881571) * To be moved to FY23 pending PCR4882 ALEX ROHWEDER (R872340) SWAP THE DESIGN SCOPE WITH MT. MILLER MM1 TO DESIGN IN FY23, AND TO CONSTRUCT IN FY25. REASON: ASSET CRITICALITY. PCR 5289 APPROVED. This turnout is also referred as MM145 turnout. The primary function of this turnout is for PN trains to access the siding. Mike Bray and Luke Gibbons advise to have the renewal is to be funded by PN. Alex Rohweder (R872340) The renewal of MM1 (#145) is expected to cost approximately $1.2M (require signlling installed, if to electrically operate the points). With no clear agreement from PN to renew this 3rd party asset, the TOR of MM1 (#145) is removed from TOR.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124202&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124202 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000482 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.0459 | KM | GA03BA7 | 0.877 | GA03BA7 | 0.923 | KM |  |  |  |  | 7.877 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124205&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124205 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000500 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.048 | KM | GA02BA7 | 0.9749 | GA02BA7 | 0.927 | KM |  |  |  |  | 7.975 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124196&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124196 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000501 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.0719 | KM | GA02BA8 | 0.069 | GA02BA8 | 0.1409 | KM |  |  |  |  | 8.069 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124199&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124199 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000553 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.0709 | KM | GA03BA8 | 0.2169 | GA03BA8 | 0.1459 | KM |  |  |  |  | 8.217 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124190&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124190 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000103 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.05 | KM | GA02BA8 | 0.33 | GA02BA8 | 0.28 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124193&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000124193 | TURNOUTS ¦ DESIGN ¦ IFC ¦ | TO000481 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | SITE | 53550 | Goonyella | DALRYMPLE BAY |  | 0.0729 | KM | GA03BA8 | 0.33 | GA03BA8 | 0.257 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20300527
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118688&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118688 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CA1 | TO001012 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 23625 | Goonyella | COPPABELLA | CA1 | 0.0309 | KM | GA44YR143 | 0.9749 | GA44YR144 | 0.01 | KM |  |  |  |  | 143.975 | 144.006 | 2030-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300525 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manager - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118720&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118720 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CA2 | TO001013 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 23625 | Goonyella | COPPABELLA | CA2 | 0.02 | KM | GA44YR144 | 0.1089 | GA44YR144 | 0.129 | KM |  |  |  |  | 144.105 | 144.125 | 2030-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2026-02-27 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118708&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118708 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CA5 | TO001200 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 4050 | Goonyella | COPPABELLA | CA5 | 0.0269 | KM | GA45YR144 | 0.4299 | GA45YR144 | 0.403 | KM |  |  |  |  | 144.43 | 144.403 | 2030-02-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118707&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118707 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CA6 | TO001014 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 4050 | Goonyella | COPPABELLA | CA6 | 0.0179 | KM | GA44YR144 | 0.443 | GA44YR144 | 0.4249 | KM |  |  |  |  | 144.439 | 144.421 | 2030-05-25 |  |  |  |  | 4 | 3 | 1 | 3 | 1 | 12 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300225 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 8.25 CL RBM PH HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manager - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118709&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118709 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CA7 | TO000389 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 4050 | Goonyella | COPPABELLA | CA7 | 0.025 | KM | GA09CT144 | 0.4849 | GA09CT144 | 0.46 | KM |  |  |  |  | 144.401 | 144.369 | 2030-05-25 |  |  |  |  | 4 | 3 | 3 | 3 | 1 | 12 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300525 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manager - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000118706&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000118706 | TURNOUTS ¦ DESIGN ¦ IFC ¦ CAER2.2B | TO000284 | CIVIL | TURNOUTS | DESIGN - IFC | DESIGN | 1 | TURNOUT | 118000 | Goonyella | COPPABELLA | ER2.2B | 0.032 | KM | GA02ML143 | 0.91 | GA02ML143 | 0.9419 | KM |  |  |  |  | 143.727 | 143.759 | 2030-05-25 |  |  |  |  | 5 | 4 | 4 | 4 | 1 | 18 |  | 2023-03-31 |  | Turnout Designs | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300525 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manager - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115356&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000115356 | Graham RailBAM Renewal | ST009860-20 | CONTROL SYSTEMS | ASSET PROTECTION | RAILBAM | RENEWAL | 1 | UNIT | 300000 | Moura | GRAHAM | GRAHAM | 0 | KM | MA01ML31 | 0.2999 | MA01ML31 | 0.2999 | KM |  |  |  |  | 31.3 | 31.3 | 2025-06-30 |  |  |  |  | 4 | 2 |  | 2 | 1 | 12 |  | 2023-03-31 |  | Safe Working Systems - Asset Protection | STD DESIGN W/ BESPOKE ELEMENTS |  | MEDIUM | MEDIUM | HIGH | Notification in process | SCPR |  | 20250630 | Graham RailBAM Renewal
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078674&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000078674 | CSI Equipment Room Renewal | ST005820 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | JILALAN MWR | JILALAN MWR | 0 | KM | GA39CR0 | 0 | GA39CR0 | 0 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  | 5 |  | 20 |  | 2022-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | MEDIUM | LOW | Outstanding notification | RRIG |  | 20240630 | * 10.06.2021 16:26:05 AUSQLD Peter Rayner (R003851) * Replace Equipment Room
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085305&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000085305 | CSI Equipment Room Renewal | ST005900 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | SARINA MW | SARINA MW | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085333&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000085333 | CSI Equipment Room Renewal | ST005910 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | THREE SISTERS MW | THREE SISTERS MW | 0 | KM | GA47CR901 | 0 | GA47CR901 | 0 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085334&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000085334 | CSI Equipment Room Renewal | ST005790 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | WAITARA MWR | WAITARA MWR | 0 | KM | GA01ML100 | 0.45 | GA01ML100 | 0.45 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119607&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119607 | CSI Dehydrator Renewal FY30 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 55000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119606&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119606 | CSI Dehydrator Renewal FY30 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 55000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Scope: Replacement of Dehydrators Description: Initial Assessment Step 1: Works Planning to approach Maintenance Teams and request to review proposed location and advise if this site needs replacement. There are TWO Options: Option 1 Description: Site Is correct and Need Replacement Step 2: Maintenance Teams/Works Planner place an order via IML for the required materials Step 3: Works Planning to advise Project Manger on the required cost of materials Step 4: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 5: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 6: Works Planner to advise Project Manager on when the work is completed Option 2 Description: Site Does Not need replacement Step 2: Works Planning to approach Maintenance Teams to advise on another site that requires replacement Step 3: Works Planning to advise Project Manger of the new site and receive approval to proceed. Step 4: Maintenance Teams/Works Planner place an order via IML for the required materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075281&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000075281 | CSI GENSET RENEWAL | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 200000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | LOW | MEDIUM | Outstanding notification | SCPR |  | 20300630 | * 30.03.2021 17:34:45 AUSQLD Scott Andrews (R003573) * RENEWAL OF EMERALD TELECOMMUNICATIONS GENERATOR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078695&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000078695 | CSI GENSET RENEWAL | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | SITE | 200000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 17:26:31 AUSQLD Peter Rayner (R003851) * Renew Generator including control equipment
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119978&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119978 | CSI NMS Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 260000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119977&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119977 | CSI NMS Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 260000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119601&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119601 | CSI Radome Renewal FY30 | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 80000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119600&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119600 | CSI Radome Renewal FY30 | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME REPLACEMENT | RENEWAL | 1 | SITE | 80000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300708 | Scope: Inspect and Renew RADOM Covers Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise on the type of RADOM Cover is required replacement Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120044&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000120044 | CSI Tower Renewal | ST006380-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 25000 | Goonyella | BLAIR ATHOL | BLAIR ATHOL | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120045&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000120045 | CSI Tower Renewal | ST005950-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 25000 | Blackwater | CAPELLA | CAPELLA | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120041&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000120041 | CSI Tower Renewal | ST005280-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 25000 | Blackwater | CROCKER PEAK | CROCKER PEAK | 0 | KM | BW56CR0 | 0 | BW56CR0 | 0 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120043&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000120043 | CSI Tower Renewal | ST005510-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 25000 | Blackwater | GREGORY | GREGORY | 0 | KM | BW08ML62 | 0.2469 | BW08ML62 | 0.2469 | KM | [6 empty] | 2030-06-30 | [14 empty] | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046851&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000046851 | CSI Tower Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 95000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046852&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000046852 | CSI Tower Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 220000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | ALL |  |  |  | 4 | 1.75 |  |  |  | 7 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120040&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000120040 | CSI Tower Renewal | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL | 1 | SITE | 25000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078621&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000078621 | Tele Power Supply Oonooie | ST000680-48 | CONTROL SYSTEMS | CONTROL SYTEMS TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Goonyella | OONOOIE FS |  | 0 | KM | GA01ML23 | 0.644 | GA01ML23 | 0.644 | KM | [6 empty] | 2022-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:28:54 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078620&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000078620 | Tele Power Supply Renewal Site TBD | BW | CONTROL SYSTEMS | CONTROL SYTEMS TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | TBD |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2022-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:27:46 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124727&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000124727 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124068&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000124068 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124378&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000124378 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065475&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000065475 | SIG_Interlocking Renewal_GA_Braeside_Des | ST004540-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 1274432 | Goonyella | BRAESIDE |  | 0 | KM | GA01ML107 | 0.6949 | GA01ML107 | 0.6949 | KM |  |  |  |  | 107.695 | 107.695 | 2031-06-30 |  |  |  |  | 4 | 4 |  | 4 |  | 16 |  | 2023-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20310630 | * 28.09.2020 10:20:40 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065486&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000065486 | SIG_Interlocking Renewal_GA_Mindi_Des | ST004820-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 500000 | Goonyella | MINDI |  | 0 | KM | GA01ML120 | 0.445 | GA01ML120 | 0.445 | KM | [6 empty] | 2029-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2031-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20310630 | * 28.09.2020 10:28:16 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER. 30.08.2022: Changes restricted to removing leading shunts, split detection, digital telemetry, SER building replacement and PBI upgrade, as per Goonyella Trunk Resignalling scoping document.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065483&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000065483 | SIG_Interlocking Renewal - PS_Pln | ST004030-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 78960 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA01ML14 | 0.6239 | GA01ML14 | 0.6239 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  | 2022-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | SCPR |  | 20320630 | * 28.09.2020 10:26:01 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065480&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000065480 | SIG_Interlocking Renewal_GA_Tootoola_Pln | ST001020-14 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 78960 | Goonyella | TOOTOOLAH |  | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM |  |  |  |  | 132.766 | 132.766 | 2028-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  | 2032-03-31 |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20320630 | * 28.09.2020 10:23:45 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142018&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000142018 | SIG_Interlocking Renewal_MA_Clarke_Des | ST003520-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | CLARKE | CLARKE | 0 | KM | MA01ML63 | 0.8649 | MA01ML63 | 0.8649 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Design phase for the replacement of the VPI at Clarke. To include block to Stirrat and AS3000 requirements. PBI expected to be a ElectrologiX. This should be the final VPI removal therefore remove all VPI spares from inventory and depots.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126111&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000126111 | SIG_Interlocking Renewal_MA_MouraMin_Pln | ST003780-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 100000 | Moura | MOURA MINE | MOURA MINE | 0 | KM | MA01ML180 | 0.14 | MA01ML180 | 0.14 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000108354&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000108354 | SIG_Interlocking Renewal_MA_Stirrat_Com | ST003830-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 1000000 | Moura | STIRRAT | STIRRAT | 0 | KM | MA01ML39 | 0.404 | MA01ML39 | 0.404 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 |  | 25 | [5 empty] | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20280630 | Replace Stirrat VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043416&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000043416 | SIG Interlocking Renewal_GA_JB_Ren | ST006030-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | WESTLOCK REPLACEMENT | RENEWAL | 1 | UNIT | 2000000 | Goonyella | JILALAN | JILALAN | 0 | KM | GA01ML20 | 0.0299 | GA01ML20 | 0.0299 | KM | [11 empty] | 4 | 4 |  |  |  | 16 |  | 2019-07-15 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126601&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000126601 | SIG_Train Detection_NL_Pring_Des | ST002910-15 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | DESIGN | 21 | UNITS | 1400000 | Newlands | PRING | PRING | 0.512 | KM | NL01PL2 | 0.9629 | NL01PL3 | 0.4779 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20310630 | Design phase for the replacement of Siemens AzS350U axlecounter track sections with a different axlecounter. There are 21 track secytions within Pring.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126635&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000126635 | SIG_Train Detection_NL_Durroburra_Pln | ST008200-01 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | PLANNING | 13 | UNITS | 100000 | Newlands | PRING | KAILI | 2.434 | KM | NL01ML0 | 0.2 | NL01ML2 | 0.6159 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Commissioning phase for the replacement of AzS350U axlecounter track sections with another axlecounter. There is a block between Pring and Durraburra, 6 Durraburra track sections and 6 Kaili track sections. Consider how block information between Durraburra and Pring will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126579&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000126579 | SIG_Train Detection_NL_Armuna_Com | ST008270-02 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 2 | UNITS | 400000 | Newlands | ARMUNA | PRING | 0 | KM | NL01ML24 | 0.8589 | NL01ML24 | 0.8589 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20300630 | Commissioning phase for the replacement of Siemens AzS350U axlecounter blocks with an axlecounter. The 2 blocks are a block btn Armuna and Buckley and a block between Buckley and Pring. Consider how block information between stations will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085906&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000085906 | SIG_Train Detection_BW_CSEE_Dingo_Pln | ST002550 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 1 | SITE | 131400 | Blackwater | DINGO | DINGO | 0 | KM | BW03ML141 | 0.2999 | BW03ML141 | 0.2999 | KM | [11 empty] | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Planning for replacement of all tracks in Dingo and adjacent blocks with axlecounter and replacement of any DEDs in the block with solar powered DEDs networked wirelessly back to the FCC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085891&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic |  | COAL | 002000085891 | SIG_Train Detection_BW_CSEE_Wallaroo_Des | ST004420 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 1 | SITE | 255000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Design phase for removing all the track circuits at Wallaroo and replacing them with Thales Axlecounter tracks
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125900&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000125900 | SIG_Train Detection_GA_NthGoonyel_ML_Con | ST004920 | CONTROL SYSTEMS | TRAIN DETECTION | ML TO AXLECOUNTER | RENEWAL | 1 | SITE | 2244000 | Goonyella | NORTH GOONYELLA | NORTH GOONYELLA | 0 | KM | GA01ML213 | 0.6999 | GA01ML213 | 0.6999 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 21 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Replace all track circuits (primarily defunct ML tracks) with 11 axlecounter blocks.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101042&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000101042 | CS Transmission ACOM BW Implementation | BW | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM |  | Blackwater | BLACKWATER SYSTEM CONTRIBUTION | BLACKWATER SYSTEM CONTRIBUTION | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101043&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000101043 | CS Transmission ACOM GA Implementation | GA | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM |  | Goonyella | GOONYELLA SYSTEM CONTRIBUTION | GOONYELLA SYSTEM CONTRIBUTION | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101044&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000101044 | CS Transmission ACOM MA Implementation | MA | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM |  | Moura | MOURA SYSTEM CONTRIBUTION | MOURA SYSTEM CONTRIBUTION | 192.36 | KM |  | 0 |  | 0 | [12 empty] | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000101045&DY_MAB=X&~OKCODE=ONLI | FY30 |  |  | COAL | 002000101045 | CS Transmission ACOM NL Implementation | NL | CONTROL SYSTEMS | TRANSMISSION | ACOM | RENEWAL | 1 | LUMPSUM |  | Newlands | NEWLANDS SYSTEM CONTRIBUTION | NEWLANDS SYSTEM CONTRIBUTION | 214.038 | KM |  | 0 |  | 0 | [12 empty] | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085524&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000085524 | CS Transmission DMR Renewal | ST006380-19 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | LINK | 350000 | Goonyella | BLAIR ATHOL | CLERMONT | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 5 | [8 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050917&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000050917 | CS Transmission DMR Renewal | ST005950-10 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | SYSTEM | 450000 | Blackwater | CAPELLA | NANYA | 0 | KM | BW55CR0 | 0 | BW55CR0 | 0 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050843&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000050843 | CS Transmission DMR Renewal | ST002940-13 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | SYSTEM | 450000 | Blackwater | CLERMONT | CAPELLA | 0 | KM | BW03ML100 | 0.26 | BW03ML100 | 0.26 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050865&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000050865 | CS Transmission DMR Renewal | ST005960-04 | CONTROL SYSTEMS | TRANSMISSION | DMR LINK | RENEWAL | 1 | SYSTEM | 450000 | Goonyella | NANYA | GREGORY | 0 | KM | GA42CR0 | 0 | GA42CR0 | 0 | KM | [6 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078626&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000078626 | CS Transmission Power Supply | BW | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 10 | SITE | 400000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:34:35 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078629&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000078629 | CS Transmission Power Supply | GA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 10 | SITE | 400000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:36:52 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078617&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000078617 | CS Transmission Power Supply | MA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 4 | SITE | 160000 | Moura | TBC | TBC | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:24:17 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078632&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000078632 | CS Transmission Power Supply | NL | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 4 | SITE | 160000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | * 10.06.2021 15:40:21 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043384&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000043384 | CS Transmission TDM Replacement | BW | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043385&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000043385 | CS Transmission TDM Replacement | ST003020-17 | CONTROL SYSTEMS | TRANSMISSION | TDM REPLACEMENT | RENEWAL | 1 | LUMPSUM | 200000 | Blackwater |  |  | 0 | KM | BW57CR0 | 0 | BW57CR0 | 0 | KM | [6 empty] | 2030-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120142&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000120142 | CS Transmission Tele Battery Renewal | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120143&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000120143 | CS Transmission Tele Battery Renewal | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 150000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120141&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000120141 | CS Transmission Tele Battery Renewal | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Moura | TBC | TBC | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000120144&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000120144 | CS Transmission Tele Battery Renewal | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 1 | LUMPSUM | 30000 | Newlands | TBC | TBC | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [13 empty] | Transmission and Data Network Minor | LIKE FOR LIKE | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20300630 | Scope: Inspect and Renew Telecommunication Batteries Description: Step 1: Works Planning to approach Maintenance Teams to advise on what site require replacement Step 2: Maintenance Teams to advise the numbers and type of Batteries to be replaced Step 3: Maintenance Teams/Works Planner place an order via IML for the required materials Step 4: Works Planning to advise Project Manger on the required cost of materials Step 5: Project Manager to adjust the budget and provide an element number to IML for Procurement Step 6: Works Planner to schedule the replacement work and advise Project Manager on when the replacement is going to take place Step 7: Works Planner to advise Project Manager on when the work is completed
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119727&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119727 | CS TETRA RADIO | BW | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Blackwater | TBC | TBC | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119728&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119728 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000119729&DY_MAB=X&~OKCODE=ONLI | FY30 |  | BASELOAD | COAL | 002000119729 | CS TETRA RADIO | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO | RENEWAL | 1 | SITE | 550000 | Goonyella | TBC | TBC | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2030-06-30 | [9 empty] | 100 |  |  |  | Transmission & Data Renewals | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127869&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | FUTURE SCOPE | COAL | 002000127869 | Burngrove to Nogoa – Scoping, Planning a | BW-0169 | ELECTRICAL | OVERHEAD |  | DESIGN | 1 | UNIT | 25000 | Blackwater | BURNGROVE | NOGOA | 60.524 | KM | CW/202/551/L | 0 | CW/263/075/DE1 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  | Section Insulator and Neutral Section Renewals | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Burngrove to Nogoa – Scoping, Planning and Estimating for removal of OHLE Develop a plan for the removal of all OHLE equipment on Electrical Section 169 from Burngrove to Nogoa, and estimate the cost of execution taking account of the likely scrap value of the recovered equipment. As a guide/starting point, refer to the attached estimate from Network Operations dated 7/10/2021 (attached to this N4). 07/03/24 EK: Pushed out to FY30 to confirm funding requirements for decommissioining assets. Refer to supporting document/email attached
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127881&DY_MAB=X&~OKCODE=ONLI | FY30 | Coal Traffic | BASELOAD | COAL | 002000127881 | Burngrove to Nogoa – Remove all OHLE and | BW-0169 | ELECTRICAL | OVERHEAD |  | RENEWAL | 1 | UNIT | 2700000 | Blackwater | BURNGROVE | NOGOA | 60.524 | KM | CW/202/551/L | 0 | CW/263/075/DE1 | 0 | KM | [6 empty] | 2026-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Burngrove to Nogoa – Remove all OHLE and recover scrap value This N4 has been created with a placeholder estimate of $2.7m based on the attached estimate of costs from 7/10/2021 by Network Operations (attached to this N4). It is expected that this estimate will be updated when the project is properly scoped and re-estimated.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000052759&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000052759 | Formation Renewal | NL-01ML | CIVIL | FORMATION |  | RENEWAL | 0.8 | KM | 1680000 | Newlands |  |  | 0.8 | KM | NL01ML60 | 0 | NL01ML60 | 0.8 | KM |  |  |  |  | 60 | 60.8 | [5 empty] | 3.5 | [9 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20290630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078185&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000078185 | Formation Renewal | MA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.6 | KM | 1500000 | Moura | EARLSFIELD | BELLDEEN | 0.5999 | KM | MA01ML130 | 0.2 | MA01ML130 | 0.8 | KM |  |  |  |  | 130.2 | 130.8 | 2027-06-30 | [14 empty] | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068845&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000068845 | C58-LX-BW-FAIRHILL-44.5km | LX003469 | CIVIL | LEVEL CROSSINGS |  | RENEWAL MAJOR | 1 | SITE | 455000 | Blackwater | FAIRHILL | YAN YAN | 0 | KM | BW08ML44 | 0.5 | BW08ML44 | 0.5 | KM |  |  |  |  | 44.5 | 44.5 |  | UNNAMED ROAD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | The renewal of this crossing is delayed till FY27 as per the discussion with the RAP <(>&<)> the Infrastructure Maintenance Team.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000122907&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Dual Traffic |  | COAL | 002000122907 | C58-LX-BW-PARANA-557.267km | LX005583 | CIVIL | LEVEL CROSSINGS | IFC | DESIGN | 1 | SITE | 54000 | Blackwater | PARANA | MT LARCOM | 0 | KM | BW01ML557 | 0.265 | BW01ML557 | 0.265 | KM |  |  | 557.267 | 557.267 | 557.267 | 557.267 | 2026-06-30 | PORT CURTIS WAY |  |  |  | 3 | 4.5 | 2 | 4 | 1 | 12 | [9 empty] | Outstanding notification | NWSC |  | 20270630 | 12.02.2024 moved to FY31 IFC. Rail and sleeper replacement were carried out in BW Feb 2024 closure. Asphalt and flangeways to be completed. FY26 IFP, FY27 IFC, FY28 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068818&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000068818 | C58-LX-BW-Mt Laren-78.1lm | LX005850 | CIVIL | LEVEL CROSSINGS | RENEWAL | MAJOR RENEWAL | 1 | SITE | 455000 | Goonyella | MT LCLAREN | BLACKRIDGE | 0 | KM | GA05ML78 | 0.1 | GA05ML78 | 0.1 | KM |  |  |  |  | 78.1 | 78.1 |  | PRIVATE ACCESS RD | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | PCR 5124 added. Pushed to FY28. Supported by Reagan Case.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041348&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000041348 | C58-LX-MA-Inverness Rd-102.567km | LX006006 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 659000 | Moura | MOUNT RAINBOW | DUMGREE | 0 | KM |  | 0 |  | 0 | KM |  |  |  |  | 102.5 |  | 2031-06-30 |  |  |  |  | 3.25 | 1.5 |  |  |  | 4.9 |  | 2019-03-22 |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | IV.00459.E.A.M.MB.CO | 20310630 | * 07.08.2019 14:23:42 AUSQLD Jeremy Stevenson (R867415) * FY20 Renewal Inverness Road, Moura Line
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103580&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000103580 | C58-LX-NL-SUTTOR CREEK-193.566km | LX007258 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 957514 | Newlands | SUTTOR CREEK | EAGLEFIELD CREEK | 0 | KM | NL01ML193 | 0.5679 | NL01ML193 | 0.5679 | KM |  |  |  |  | 193.566 | 193.566 | 2031-06-30 | PRIVATE ACCESS ROAD |  |  |  | 2.52 | 1.2 | 2 | 3 | 1 | 7.56 | [9 empty] | Outstanding notification | NWSC |  | 20310630 | This crossing had a ballast undercut/sleepers replaced/drainage replaced/road surface repaired in FY24. During meeting held in Oct 2023 with IM, Civil Assets agreed to delay this crossing several years to FY29 IFP, FY30 IFC, FY31 Renewal. This crossing will continue to be monitored and bought forward if required. Scoped on 11 May 2023. For FY26 design and FY28 RENEWAL.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104011&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  |  | 002000104011 | C58-LX-GA-Access Rd-9.97km | LX006680 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 32000 | Goonyella | WOTONGA | MORANBAH | 0 | KM | GA05ML9 | 0.9709 | GA05ML9 | 0.9709 | KM |  |  | 9.97 | 9.97 | 9.97 | 9.97 | 2031-06-30 | MERCURY ROAD |  |  |  | 2.4 | 1.5 | 2 | 3 | 1 | 7.2 | [9 empty] | Outstanding notification | NWSC |  | 20310630 | RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043468&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000043468 | B12 -ST-NL-Sonoma-082.720km | BR300468 | CIVIL | STRUCTURES | BRIDGE STRENGTHENING | RENEWAL | 1 | SITE | 1500000 | Newlands | COLLINSVILLE | SONOMA | 0 | KM | NL01ML82 | 0.7199 | NL01ML82 | 0.7199 | KM |  |  |  |  | 82.72 | [9 empty] | 0.1 |  | 100 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Top flange cracking in spans 1, 2 <(>&<)> 3" Proposed: Level 3 Inspections, measurements, Strengthening for cracking in girders and piers as required.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000125092&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Dual Traffic | FUTURE SCOPE | COAL | 002000125092 | Structures Renewal | BR101312 | CIVIL | STRUCTURES | BRIDGE-RELIEVING SLAB | RENEWAL | 1 | SITE | 500000 | Blackwater | ARCHER | MIDGEE | 0.048 | KM | BW01ML618 | 0.8329 | BW01ML618 | 0.881 | KM |  |  |  |  | 618.85 |  | 2031-06-30 | UP RD |  |  |  | 3.5 | 4.1 | 4 | 4.5 | 1 | 15.9 | 184 | 2022-03-31 |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310802 | Defect: Top of rail height issues, North relieving slab and supporting ballast wall failed with severe cracking in RS and ballast wall. North relieving slab had 160-200mm fall and 100mm higher than bridge surface. Lifting with teratek to have 75-80mm fall but still 100mm higher than deck and change drainage from RS to match formation with 5-10mm fall west to east. Monitor 6 monthly after injection in Nov 2020. Proposed: North relieving slab needs to be replaced in next bridge rollout. This will also need to include the re-construction of ballast wall support the relieving slab. Recommend remove all and reinstall. Eg saw cut ballast wall and dowel in required reinf and precast relieving slab. Craneage likely required. If north and south both replaced, estimate will need to be increased. Drawing: Risk: High
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043792&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000043792 | Structures Renewal | CU200396 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 2000000 | Goonyella | RED MOUNTAIN | WINCHESTER | 0 | KM | GA03ML26 | 0.1799 | GA03ML26 | 0.1799 | KM |  |  |  |  | 26.21 |  | 2030-06-30 | MOD-HIGH |  | REMOVE & REPLACE |  | 3.5 | 1.7 | 3 | 3.3 | 1 | 11.7 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | * 20.10.2020 15:56:53 AUSQLD Edward Brooks (R884255) * Defect: NCL Affected. Minor cracking in haunches and more severe in unit 16-3 * Proposed: CIPP lining or Remove and replace. unit 16-3. localised severe smalling and exposed reinf. Proposed: Remove and replace. Could go to FY28 Final: Drawing: Risk: Mod-High Reason: previously repaired spalling is respalling which means maintenance techniques are not working as this structure is too under strength. The regular haunches cracks suggest the units are pumping and deteriorating more quickly. Risk at haunch the crack may be full depth and have steel corroding in the corner and spalling on the outside which will be difficult to see.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044230&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000044230 | Structures Renewal | CU101154 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 500000 | Blackwater | BW-GG |  | 0 | KM | BW08ML36 | 0.9 | BW08ML36 | 0.9 | KM |  |  |  |  | 36.9 |  | 2031-06-30 | MOD |  | CONCRETE LINE |  | 3 | 1.1 | 3 | 3 | 1 | 9.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | * 19.10.2020 09:41:26 AUSQLD Edward Brooks (R884255) * Defect - head wall too small for ballast and failing. Units 5 to end dropped 50mm in unit 6 all spans. * Proposed - Remove and replace with 4 cells 1200x900. Defect: Moderate spalling & cracking in ceiling of units 9,10,11. Proposed: Possible tunnelline in future pending hydro. Risk: Moderate Reason: Concrete lining will avoid track closure. Already regular signs of cracking and spalling.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100370&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000100370 | Structures Renewal | CU300582 | CIVIL | STRUCTURES | RCBC-CONCRETE LINE | RENEWAL | 1 | SITE | 1113600 | Newlands | COCKOOL | HAVILAH | 0 | KM | NL01ML113 | 0.8 | NL01ML113 | 0.8 | KM |  |  |  |  | 113.8 |  | 2031-06-30 |  |  | CONCRETE LINE |  | 3.5 | 1.4 | 3 | 3.2 | 1 | 11.2 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630 | Defect: Moderate spalling and cracking, patch repair first but long term may be an issue. Proposed: Concrete line or Remove <(>&<)> Replace pending hydro Final: Drawing: Risk: Mod-high Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124117&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  |  | 002000124117 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ BW | BW | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 3815399 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124118&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  |  | 002000124118 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ GA | GA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 4162253 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124119&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  |  | 002000124119 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ MA | MA | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 763080 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124120&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  |  | 002000124120 | TURNOUTS ¦ C16 ¦ REACTIVE WORKS ¦ NL | NL | CIVIL | TURNOUTS | C16 | REACTIVE WORKS | 1 | SITE | 693709 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [27 empty] | Outstanding notification | NWSC |  | 20250630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124185&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124185 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO001184 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW11XR0 | 0.065 | BW11XR0 | 0.0929 | KM |  |  |  |  | 0.065 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124182&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124182 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO001155 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.028 | KM | BW17YR0 | 0.4829 | BW17YR0 | 0.511 | KM |  |  |  |  | 0.483 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124173&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124173 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO001172 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.029 | KM | BW08YR533 | 0.779 | BW08YR533 | 0.808 | KM |  |  |  |  | 533.779 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124179&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124179 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO001128 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.029 | KM | BW01XR533 | 0.8229 | BW01XR533 | 0.8519 | KM |  |  |  |  | 533.823 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124176&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124176 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO001115 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH |  | 0.0309 | KM | BW05YR533 | 0.936 | BW05YR533 | 0.905 | KM |  |  |  |  | 533.936 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124188&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000124188 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ CH 215B | TO001177 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1200000 | Blackwater | CALLEMONDAH | CH 215B | 0.028 | KM | BW21YR0 | 0.127 | BW21YR0 | 0.099 | KM |  |  |  |  | 0.127 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124203&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124203 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000482 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.0459 | KM | GA03BA7 | 0.877 | GA03BA7 | 0.923 | KM |  |  |  |  | 7.877 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124096&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124096 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000500 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.048 | KM | GA02BA7 | 0.9749 | GA02BA7 | 0.927 | KM |  |  |  |  | 7.975 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124197&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124197 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000501 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.0719 | KM | GA02BA8 | 0.069 | GA02BA8 | 0.1409 | KM |  |  |  |  | 8.069 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124200&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124200 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000553 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.0709 | KM | GA03BA8 | 0.2169 | GA03BA8 | 0.1459 | KM |  |  |  |  | 8.217 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124191&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124191 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000103 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.05 | KM | GA02BA8 | 0.33 | GA02BA8 | 0.28 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124194&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000124194 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL¦ | TO000481 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | SITE | 1700000 | Goonyella | DALRYMPLE BAY |  | 0.0729 | KM | GA03BA8 | 0.33 | GA03BA8 | 0.257 | KM |  |  |  |  | 8.33 | [21 empty] | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115839&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115839 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦CAER2.2B | TO000284 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 4000000 | Goonyella | COPPABELLA | CA ER2.2B | 0.032 | KM | GA02ML143 | 0.91 | GA02ML143 | 0.9419 | KM |  |  |  |  | 143.727 | 143.759 | 2031-06-30 |  |  |  |  | 4.5 | 3 | 4.2 | 5 |  | 18.9 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS SNX TGLASM EO LH FULL RENEWAL - Same angle <(>&<)> Additional Points motor. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) 22 03 2024 INCOMPLETION of IFP planned in FY24 - HATFILED HD 12C/D, HD 12A/B and HD 11A/B. RESULT to DEFFER COPPABELLA IFP from FY25 to FY27, IFC from FY26 to FY28 and CONSTRUCTION From FY27 to FY29. DUE to WORK Delivery Feasiblity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115816&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115816 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CA1 | TO001012 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 100000 | Goonyella | COPPABELLA | CA1 | 0.0309 | KM | GA44YR143 | 0.9749 | GA44YR144 | 0.01 | KM |  |  |  |  | 143.975 | 144.006 | 2031-06-30 |  |  |  |  | 4 | 3 | 3.9 | 4 |  | 15.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) 22 03 2024 INCOMPLETION of IFP planned in FY24 - HATFILED HD 12C/D, HD 12A/B and HD 11A/B. RESULT to DEFFER COPPABELLA IFP from FY25 to FY27, IFC from FY26 to FY28 and CONSTRUCTION From FY27 to FY29. DUE to WORK Delivery Feasiblity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115817&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115817 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CA2 | TO001013 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 100000 | Goonyella | COPPABELLA | CA2 | 0.02 | KM | GA44YR144 | 0.1089 | GA44YR144 | 0.129 | KM |  |  |  |  | 144.105 | 144.125 | 2031-06-30 |  |  |  |  | 4.5 | 3 | 3.9 | 4 |  | 17.55 | 5882 |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 12 CS RBM PHTGLASM HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) 22 03 2024 INCOMPLETION of IFP planned in FY24 - HATFILED HD 12C/D, HD 12A/B and HD 11A/B. RESULT to DEFFER COPPABELLA IFP from FY25 to FY27, IFC from FY26 to FY28 and CONSTRUCTION From FY27 to FY29. DUE to WORK Delivery Feasiblity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115813&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115813 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦CA5 | TO001200 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 100000 | Goonyella | COPPABELLA | CA5 | 0.0269 | KM | GA45YR144 | 0.4299 | GA45YR144 | 0.403 | KM |  |  |  |  | 144.43 | 144.403 | 2031-06-30 |  |  |  |  | 3 | 3 | 3.9 | 4 |  | 15.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115818&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115818 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CA6 | TO001014 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 100000 | Goonyella | COPPABELLA | CA6 | 0.0179 | KM | GA44YR144 | 0.443 | GA44YR144 | 0.4249 | KM |  |  |  |  | 144.439 | 144.421 | 2031-06-30 |  |  |  |  | 4 | 3 | 3.9 | 4 |  | 15.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project POINTS <(>&<)> X 60KG/M 8.25 CL RBM PH HO RH FULL RENEWAL - Upgrade - change angle. Turnout renewal inabling supporting renewal within project extent. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management) Alex Rohweder (R872340) 22 03 2024 INCOMPLETION of IFP planned in FY24 - HATFILED HD 12C/D, HD 12A/B and HD 11A/B. RESULT to DEFFER COPPABELLA IFP from FY25 to FY27, IFC from FY26 to FY28 and CONSTRUCTION From FY27 to FY29. DUE to WORK Delivery Feasiblity.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115812&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000115812 | TURNOUTS ¦ CONSTRUCT ¦ RENEWAL ¦ CA7 | TO000389 | CIVIL | TURNOUTS | CONSTRUCT | RENEWAL | 1 | TURNOUT | 100000 | Goonyella | COPPABELLA | CA7 | 0.025 | KM | GA09CT144 | 0.4849 | GA09CT144 | 0.46 | KM |  |  |  |  | 144.485 | 144.369 | 2031-06-30 |  |  |  |  | 4 | 5 | 3 |  |  | 15.6 |  |  |  | Turnout Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | IFP (DD50%) due by 30 June 2025, IFC due FY26, FY27¦FY28 Construction Six TOR in one project DECOMIMISSIONING. ALEX ROHWEDER (R872340) MULTI-YEAR DESIGN NOTIFICATIONS ARE CREATED. (1) DESIGN - EARLY DESIGN, if required (2) DESIGN - IFP, (3) DESIGN IFC, (4) CONSTRUCTION. INTENT IS TO ADD MORE CLARITY AND BUDGET FOR EACH PROJECT YEARLY MINIMUM TARGET DELIVERABLES. (agreed between Asset Business - Emma-Kate Clyburn, Project Manger - Gwenda Murphy and Alex Rohweder - Asset Management)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060043&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060043 | SIG_Replace M23A_GA_BR12A_Com | TO000313-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA02ML107 | 0.8149 | GA02ML107 | 0.8149 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:05 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060044&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060044 | SIG_Replace M23A_GA_BR12D_Com | TO000244-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA01ML107 | 0.908 | GA01ML107 | 0.908 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:13 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060045&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060045 | SIG_Replace M23A_GA_BR8A_Com | TO000463-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA01ML107 | 0.6919 | GA01ML107 | 0.6919 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:24 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060046&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060046 | SIG_Replace M23A_GA_BR8B_Com | TO000463-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA01ML107 | 0.6919 | GA01ML107 | 0.6919 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:34 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060047&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060047 | SIG_Replace M23A_GA_BR8C_Com | TO000314-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA02ML107 | 0.791 | GA02ML107 | 0.791 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:43 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060048&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060048 | SIG_Replace M23A_GA_BR8D_Com | TO000314-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | BRAESIDE | BRAESIDE | 0 | KM | GA02ML107 | 0.791 | GA02ML107 | 0.791 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:16:53 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060152&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060152 | SIG_Replace M23A_GA_MI11A_Com | TO000247-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA01ML120 | 0.5829 | GA01ML120 | 0.5829 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:34:44 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060153&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060153 | SIG_Replace M23A_GA_MI11D_Com | TO000303-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA02ML120 | 0.682 | GA02ML120 | 0.682 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:34:53 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060154&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060154 | SIG_Replace M23A_GA_MI12A_Com | TO000304-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA02ML120 | 0.461 | GA02ML120 | 0.461 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:35:01 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060155&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060155 | SIG_Replace M23A_GA_MI12B_Com | TO000304-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA02ML120 | 0.461 | GA02ML120 | 0.461 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:35:10 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060156&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060156 | SIG_Replace M23A_GA_MI12C_Com | TO000246-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA01ML120 | 0.56 | GA01ML120 | 0.56 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:35:20 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060157&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000060157 | SIG_Replace M23A_GA_MI12D_Com | TO000246-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | MINDI | MINDI | 0 | KM | GA01ML120 | 0.56 | GA01ML120 | 0.56 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20260630 | * 23.06.2020 12:35:30 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044577&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Non Coal Traffic | BASELOAD | NON-COAL | 002000044577 | CSI CER Renewal | ST005670 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 500000 | Moura | PARANA | PARANA | 0 | KM | NC02ML522 | 0.9699 | NC02ML522 | 0.9699 | KM |  |  |  |  | 15.66 | 15.66 | 2031-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM | LOW | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20310630 | * 28.03.2021 17:01:37 AUSQLD Scott Andrews (R003573) * Renew CER at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090692&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000090692 | CS CER Relocation | ST004030 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | PRAGUELANDS CER | PRAGUELANDS CER | 0 | KM | GA01ML14 | 0.6239 | GA01ML14 | 0.6239 | KM | [6 empty] | 2031-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000090691&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000090691 | CS CER Relocation | ST006660 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 250000 | Goonyella | TOOTOOLAH CER | TOOTOOLAH CER | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM | [6 empty] | 2031-06-30 | [13 empty] | Transmission & Data Renewals | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085426&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | BASELOAD | COAL | 002000085426 | CSI NMS Renewal | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2031-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085424&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | BASELOAD | COAL | 002000085424 | CSI NMS Renewal | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | NMS | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2031-06-30 |  |  |  |  | 4 |  |  | 3 |  | 12 |  | 2023-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN |  | HIGH | HIGH | HIGH | Outstanding notification | SCPR INIF |  | 20310630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124728&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | BASELOAD | COAL | 002000124728 | SIG_Diagnostic Computer_BW_Com | BW | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 7 | UNIT | 126000 | Blackwater | CALLEMONDAH | GREGORY MINE | 633.538 | KM |  | 0 |  | 0 | [7 empty] | 2031-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20310630 | Replace 7 existing Blackwater System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124069&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | BASELOAD | COAL | 002000124069 | SIG_Diagnostic Computer_NL_Com | NL | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 2 | UNIT | 36000 | Newlands | EAGLEFIELD CREEK | ABBOT POINT | 214.038 | KM |  | 0 |  | 0 | [7 empty] | 2031-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20310630 | Replace 2 existing Newlands System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000124379&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | BASELOAD | COAL | 002000124379 | SIG_Diagnostic Computer_GA_Com | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | DIAGNOSTIC COMPUTERS | RENEWAL | 4 | UNIT | 72000 | Goonyella | HAY POINT | OAKY CREEK | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2031-06-30 |  |  |  |  | 5 | 2 | 2 | 2 | 1 | 12 |  |  |  | Safe Working Systems - Minor | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20310630 | Replace 4 existing Goonyella System Maintenance PCs with local Aurizon IT PCs. PCs to be installed on site with correct software and connected to interlocking and network to enable remote monitoring and automatic security updates. Maintenance PCs to be chosen by RAPS based on condition and need.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065484&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000065484 | SIG_Interlocking Renewal - PS_Des | ST004030-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 1500000 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA01ML14 | 0.6239 | GA01ML14 | 0.6239 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20320630 | * 28.09.2020 10:26:46 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065481&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000065481 | SIG_Interlocking Renewal - TH_Des | ST001020-14 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 1500000 | Goonyella | TOOTOOLAH |  | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20320630 | * 28.09.2020 10:24:22 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085491&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | FUTURE SCOPE | COAL | 002000085491 | SIG_Interlocking Renewal_GA_BlackMtn_Pln | ST003910-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | SITE | 60000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA01ML40 | 0.936 | GA01ML40 | 0.936 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 4.5 | 3 | 3 | 3 | 1 | 13.5 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20330630 | Plan for the replacement of the Black Mountain relay interlocking with a PBI. Include the replacement of 4 M23A points machines with contactor relays. Incandescent JRIs to be replaced with LED JRIs to improve safety of maintenance. Consideration of replacing Track Circuits on Connor's Range to be done in order to reduce hazard and delays with accessing housings.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065488&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  | FUTURE SCOPE | COAL | 002000065488 | SIG_Interlocking Renewal_GA_Hatfield_Pln | ST003980-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | PLANNING | 1 | STATION | 100000 | Goonyella | HATFIELD |  | 0 | KM | GA01ML49 | 0.752 | GA01ML49 | 0.752 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20330630 | * 28.09.2020 10:29:50 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065476&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000065476 | SIG_Interlocking Renewal_GA_Braeside_Com | ST004540-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 2500000 | Goonyella | BRAESIDE |  | 0 | KM | GA01ML107 | 0.6949 | GA01ML107 | 0.6949 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | * 28.09.2020 10:21:16 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065487&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000065487 | SIG_Interlocking Renewal - MI_Com | ST004820-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 1500000 | Goonyella | MINDI |  | 0 | KM | GA01ML120 | 0.445 | GA01ML120 | 0.445 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | * 28.09.2020 10:29:02 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER. 30.08.2022: Changes restricted to removing leading shunts, split detection, digital telemetry, SER building replacement and PBI upgrade, as per Goonyella Trunk Resignalling scoping document.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126112&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000126112 | SIG_Interlocking Renewal_MA_MouraMin_Des | ST003780-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | MOURA MINE | MOURA MINE | 0 | KM | MA01ML180 | 0.14 | MA01ML180 | 0.14 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142021&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000142021 | SIG_Interlocking Renewal_MA_Fry_Pln | ST003660-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 2500000 | Moura | FRY | FRY | 0 | KM | MA01ML73 | 0.0509 | MA01ML73 | 0.0509 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20310630 | Planning phase for the replacement of the VPI at Fry. To include block to Clarke and AS3000 requirements. PBI expected to be a ElectrologiX. All working components of VPI equipment are to be returned to inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142020&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic |  | COAL | 002000142020 | SIG_Interlocking Renewal_MA_Clarke_Com | ST003520-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 2500000 | Moura | CLARKE | CLARKE | 0 | KM | MA01ML63 | 0.8649 | MA01ML63 | 0.8649 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20250418 | Construction phase for the replacement of the VPI at Belldeen. To include block to Stirrat and AS3000 requirements. PBI expected to be a ElectrologiX. Any working components from the VPI are to be returned to inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126636&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000126636 | SIG_Train Detection_NL_Durroburra_Des | ST008200-01 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | DESIGN | 13 | UNITS | 800000 | Newlands | PRING | KAILI | 2.434 | KM | NL01ML0 | 0.2 | NL01ML2 | 0.6159 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20320630 | Design phase for the replacement of AzS350U axlecounter track sections with another axlecounter. There is a block between Pring and Durraburra, 6 Durraburra track sections and 6 Kaili track sections. Consider how block information between Durraburra and Pring will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126602&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000126602 | SIG_Train Detection_NL_Pring_Com | ST002910-15 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 21 | UNITS | 4000000 | Newlands | PRING | PRING | 0.512 | KM | NL01PL2 | 0.9629 | NL01PL3 | 0.4779 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20310630 | Commissioning phase for the replacement of Siemens AzS350U axlecounter track sections with a different axlecounter. There are 21 track secytions within Pring.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085908&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000085908 | SIG_Train Detection_BW_CSEE_Dingo_Des | ST002550 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | DESIGN | 1 | SITE | 400400 | Blackwater | DINGO | DINGO | 0 | KM | BW03ML141 | 0.2999 | BW03ML141 | 0.2999 | KM | [11 empty] | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | Design Phase for replacement of all tracks in Dingo and adjacent blocks with axlecounter and replacement of any DEDs in the block with solar powered DEDs networked wirelessly back to the FCC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085892&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 |  |  | COAL | 002000085892 | SIG_Train Detection_BW_CSEE_Wallaroo_Com | ST004420 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 1 | SITE | 1717000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.6979 | BW03ML115 | 0.6979 | KM | [11 empty] | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | Commission the replacement of track circuits at Wallaroo with axlecounters.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000127882&DY_MAB=X&~OKCODE=ONLI | MAJOR-2031-000001 | Coal Traffic | BASELOAD | COAL | 002000127882 | South Gladstone – removal of permanently | BW-0512 | ELECTRICAL | OVERHEAD |  | RENEWAL | 1 | UNIT | 2500000 | Blackwater | SOUTH GLADSTONE |  | 14.996 | KM | N/522/147/M | 0 | N/537/143/D | 0 | KM | [6 empty] | 2031-06-30 |  |  |  |  | 10 |  |  | 10 | 1 | 100 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20310630 | South Gladstone – removal of permanently earthed OHLE This N4 has been created with a placeholder "pre-concept" estimate of $2.5m. It is expected that this estimate will be updated when the project is properly scoped and re-estimated.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044069&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000044069 | C58-LX-BW-PORT CURTIS WAY-557.27km | LX005583 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Blackwater | PORT CURTIS WAY |  | 0 | KM | BW01ML557 | 0.26 | BW01ML557 | 0.26 | KM |  |  |  |  | 557.27 | [6 empty] | 2 | 1.5 |  |  |  | 3 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20280630 | 12.02.2024 R888068 Ben Crozier Moved to FY32 Renewal due to track upgrade (rail and sleepers) through crossing during Feb. 2024 closure. FY26 IFP, FY27 IFC, FY28 Renewal.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044037&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000044037 | C58-LX-GA-Wuthung Rd-40.4km | LX001049 | CIVIL | LEVEL CROSSINGS |  | RENEWAL | 1 | SITE | 455000 | Goonyella | WUTHUNG ROAD |  | 0 | KM | GA05ML40 | 0.398 | GA05ML40 | 0.398 | KM |  |  |  |  | 40.4 | 40.398 | [5 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | * 08.03.2021 18:53:09 AUSQLD Sharbaree Biswas (R865006) * Renewed in FY21 on 10-11 February 2021. Thus pushed this to FY30. The reference of the work in FY21 is N72000069733 (attached in the list).
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000051927&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000051927 | C58-LX-BW-Byellee Rd-13.063km | LX005956 | CIVIL | LEVEL CROSSINGS | DESIGN | DESIGN | 1 | SITE | 32000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML13 | 0.063 | MA01ML13 | 0.063 | KM |  |  | 13.063 | 13.063 | 13.063 | 13.063 | 2022-06-30 | BYELLE ROAD |  |  |  | 3.18 | 1.3 |  |  |  | 4.13 | 4873 | 2020-03-06 | 2020-11-13 | Level Crossing Design | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20320630 | Moved to FY27 Design since the renewal is placed in FY29. Possible to add in FY24 DESIGN FOR FY26 DELIVERY. Scope development is required before bringing in FY24.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068854&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000068854 | C58-LX-MA-Priv Access Rd-15.766km | LX005959 | CIVIL | LEVEL CROSSINGS | MAJOR RENEWAL | MAJOR RENEWAL | 1 | SITE | 455000 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML15 | 0.79 | MA01ML15 | 0.79 | KM |  |  | 15.79 | 15.79 | 15.79 | 15.79 |  | PRIVATE ACCESS RD |  |  |  | 2.09 | 1.3 |  |  |  | 2.7 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | Pushed to FY30 Design as per the mtg on 28 July 2022 with the IM team. Pushed to FY27 Renewal due to priority over other crossings.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000068840&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000068840 | C58-LX-NL-Havillah-133.91km | LX003330 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 455000 | Newlands | HAVILLAH | NEWLANDS | 0 | KM | NL01ML133 | 0.919 | NL01ML133 | 0.919 | KM |  |  |  |  | 133.919 | 133.919 |  | PRIVATE CATTLE CROSSING | [13 empty] | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | * 19.03.2021 16:27:57 AUSQLD Sharbaree Biswas (R865006) * Pushed to FY24. A design N4 to be added in FY23. 19.03.2021 16:27:57 AUSQLD Sharbaree Biswas (R865006) Pushed to FY24. A design N4 to be added in FY23. Pushed to FY24. A design N4 to be added in FY23. renewal. 19.03.2021 16:27:57 AUSQLD Sharbaree Biswas (R865006) Pushed to FY24. A design N4 to be added in FY23. 19.03.2021 16:27:57 AUSQLD Sharbaree Biswas (R865006) Pushed to FY24. A design N4 to be added in FY23.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104010&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  |  | 002000104010 | C58-LX-GA-Maintenance Rd-14.678km | LX006433 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 859000 | Goonyella | PRAUGELANDS | JILALAN | 0 | KM | GA01ML14 | 0.677 | GA01ML14 | 0.677 | KM |  |  | 14.678 | 14.678 | 14.678 | 14.678 | 2032-06-30 | MAINTENANCE ACCESS ROAD |  |  |  | 1.6 | 4.6 | 2 | 4 | 1 | 5.7 | [9 empty] | Outstanding notification | NWSC |  | 20320630 | RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043471&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000043471 | B12 -ST-NL-Birralee-104.840km | BR300557 | CIVIL | STRUCTURES |  | RENEWAL | 1 | SITE | 500000 | Newlands | BIRRALEE | COCKOOL | 0 | KM | NL01ML104 | 0.8299 | NL01ML104 | 0.8299 | KM |  |  |  |  | 104.84 | [6 empty] | 2.5 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000092317&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000092317 | Structures Renewal | BR101606 | CIVIL | STRUCTURES | BRIDGE-RELIEVING SLAB | RENEWAL | 1 | SITE | 500000 | Blackwater | BW-NCL |  | 0.08 | KM | BW01ML546 | 0.132 | BW01ML546 | 0.2119 | KM |  |  |  |  | 546.17 |  | 2032-06-30 |  |  |  |  | 4 | 4.9 |  |  |  | 19 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | Defect: Relieving Slab sinking on low chainage end, fall of 220mm. Ballast drain installed as interim fix but needs to be replaced as cracked at ballast wall as well. Proposed: Remove and replace Low Chainage relieving slab. Ensure drainage is designed and improvement to subgrade. Drawing: Risk: Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000133025&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 | Coal Traffic |  | COAL | 002000133025 | B12 -ST-NL-Sonoma-080.430km | BR300600 | CIVIL | STRUCTURES | BRIDGE-STRENGTHEN | DESIGN | 1 | SITE | 3000000 | Newlands | MCNAUGHTON | SONOMA | 0.1509 | KM | NL01ML80 | 0.2449 | NL01ML80 | 0.396 | KM |  |  |  |  | 80.43 |  | 2032-06-30 |  |  | STRENGTHEN |  | 2.5 | 2.5 |  |  |  | 10.1 |  |  |  | Bridges Renewal | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20250105 | Defect: Design assessment found structures to shear deficient and borderline Moment capacity. Proposed: Level 3 Inspections, measurements, Strengthening for shear
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043787&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000043787 | B12 -ST-GA-Dalrymple-009.514km | BR200652 | CIVIL | STRUCTURES | BRIDGE-STRENGTHEN | RENEWAL | 1 | SITE | 1000000 | Goonyella | BIDGERLEY JUNCTION | BIDGERLEY JUNCTION | 0 | KM | GA02ML10 | -0.4859 | GA02ML10 | -0.4859 | KM |  |  |  |  | 9.51 | [6 empty] | 3 | 4.6 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20300630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043415&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000043415 | SIG_Interlocking Renewal_GA_BlackMtn_Des | GA | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN | 1 | SITE | 1400000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 220.507 | KM |  | 0 |  | 0 | [7 empty] | 2032-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 | 2020-11-13 | Safe Working Systems - Minor | BESPOKE DESIGN | HIGH | HIGH | MEDIUM | HIGH | Outstanding notification | SCPR |  | 20330630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065489&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000065489 | SIG_Interlocking Renewal_GA_Hatfield_Des | ST003980-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | DESIGN & ORDER | 1 | STATION | 600000 | Goonyella | HATFIELD |  | 0 | KM | GA01ML49 | 0.752 | GA01ML49 | 0.752 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20330630 | * 28.09.2020 10:30:36 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065485&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000065485 | SIG_Interlocking Renewal - PS_Com | ST004030-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 2500000 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA01ML14 | 0.6239 | GA01ML14 | 0.6239 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20320630 | * 28.09.2020 10:27:32 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065482&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000065482 | SIG_Interlocking Renewal - TH_Com | ST001020-14 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 2500000 | Goonyella | TOOTOOLAH |  | 0 | KM | GA01ML132 | 0.766 | GA01ML132 | 0.766 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20320630 | * 28.09.2020 10:25:14 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142022&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 | Coal Traffic |  | COAL | 002000142022 | SIG_Interlocking Renewal_MA_Fry_Des | ST003660-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | FRY | FRY | 0 | KM | MA01ML73 | 0.0509 | MA01ML73 | 0.0509 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20320630 | Design phase for the replacement of the VPI at Fry. To include block to Clarke and AS3000 requirements. PBI expected to be a ElectrologiX. Working components of VPI equipment are to be returned to inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104555&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000104555 | SIG_Interlocking Renewal_MA_MtRainbo_Pln | ST003760-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 100000 | Moura | MOUNT RAINBOW | MOUNT RAINBOW | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20280630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126113&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 | Coal Traffic | BASELOAD | COAL | 002000126113 | SIG_Interlocking Renewal_MA_MouraMin_Con | ST003780-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 2500000 | Moura | MOURA MINE | MOURA MINE | 0 | KM | MA01ML180 | 0.14 | MA01ML180 | 0.14 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060191&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000060191 | SIG_Replace M23A_GA_PS8A_Com | TO000442-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA01ML14 | 0.3649 | GA01ML14 | 0.3649 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:40:40 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060192&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000060192 | SIG_Replace M23A_GA_PS8D_Com | TO000470-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | PRAGUELANDS | PRAGUELANDS | 0 | KM | GA02ML14 | 0.463 | GA02ML14 | 0.463 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20290630 | * 23.06.2020 12:40:49 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000126637&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 | Coal Traffic | BASELOAD | COAL | 002000126637 | SIG_Train Detection_NL_Durroburra_Com | ST008200-01 | CONTROL SYSTEMS | TRAIN DETECTION | AZS350U REPLACEMENT | RENEWAL | 13 | UNITS | 2500000 | Newlands | PRING | KAILI | 2.434 | KM | NL01ML0 | 0.2 | NL01ML2 | 0.6159 | KM | [11 empty] | 4 | 2.5 | 4 | 4 | 1 | 16 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20320630 | Commissioning phase for the replacement of AzS350U axlecounter track sections with another axlecounter. There is a block between Pring and Durraburra, 6 Durraburra track sections and 6 Kaili track sections. Consider how block information between Durraburra and Pring will be transmitted. Consideration of using the Siemens ACM250 axlecounter and changes to maintenance.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085909&DY_MAB=X&~OKCODE=ONLI | MAJOR-2032-000001 |  |  | COAL | 002000085909 | SIG_Train Detection_BW_CSEE_Dingo_Com | ST002550 | CONTROL SYSTEMS | TRAIN DETECTION | CSEE TO AXLECOUNTER | RENEWAL | 1 | SITE | 2727000 | Blackwater | DINGO | DINGO | 0 | KM | BW03ML141 | 0.2999 | BW03ML141 | 0.2999 | KM | [11 empty] | 4.5 | 3 |  |  |  | 13.5 |  |  |  | Safe Working Systems - Train Detection | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20320630 | Commissioning Phase for replacement of all tracks in Dingo and adjacent blocks with axlecounter and replacement of any DEDs in the block with solar powered DEDs networked wirelessly back to the FCC.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000129755&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 | Coal Traffic |  | COAL | 002000129755 | B12 -ST-NL-Birralee-099.520km | BR300497 | CIVIL | STRUCTURES | BRIDGE STRENGTHENING | RENEWAL | 1 | SITE | 3000000 | Newlands | BOWEN RIVER |  | 0.4249 | KM | NL01ML99 | 0.3079 | NL01ML99 | 0.7329 | KM |  |  |  |  | 99.52 |  |  |  |  | STRENGTHEN |  | 3 | 2.5 |  |  |  | 6.25 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20330630 | Defect: "Design assessment found structures to shear deficient and borderline Moment capacity. Cracks in top flange of girders and in piers. " Proposed: Level 3 Inspections, measurements, Strengthening cracking in girders and piers. Drawing:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060108&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060108 | SIG_Replace M23A_GA_HD11B_Com | TO000328-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA02ML49 | 0.88 | GA02ML49 | 0.88 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:26:53 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060109&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060109 | SIG_Replace M23A_GA_HD12A_Com | TO000261-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA01PL49 | 0.78 | GA01PL49 | 0.78 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:02 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060110&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060110 | SIG_Replace M23A_GA_HD12B_Com | TO000261-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA01PL49 | 0.78 | GA01PL49 | 0.78 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:13 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060111&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060111 | SIG_Replace M23A_GA_HD12D_Com | TO000207-02 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA01ML49 | 0.925 | GA01ML49 | 0.925 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:23 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060112&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060112 | SIG_Replace M23A_GA_HD7A_Com | TO000330-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA02ML47 | 0.526 | GA02ML47 | 0.526 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:32 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060113&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060113 | SIG_Replace M23A_GA_HD7D_Com | TO000260-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA01PL47 | 0.625 | GA01PL47 | 0.625 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:40 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060114&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060114 | SIG_Replace M23A_GA_HD8A_Com | TO000449-01 | CONTROL SYSTEMS |  |  | RENEWAL | 1 | UNIT | 60000 | Goonyella | HATFIELD | HATFIELD | 0 | KM | GA01ML47 | 0.443 | GA01ML47 | 0.443 | KM | [11 empty] | 4 |  |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:27:49 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065398&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000065398 | SIG_Interlocking Renewal_GA_BlackMtn_Com | ST003910-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 2500000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA01ML40 | 0.936 | GA01ML40 | 0.936 | KM | [6 empty] | 2032-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | HIGH | HIGH | MEDIUM | Outstanding notification | SCPR INIF | FY23 IN | 20330630 | * 28.09.2020 09:16:46 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER. * 12.04.2021 16:21:03 AUSQLD Jeremy Stevenson (R867415) * Running change process for new technology * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000065490&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000065490 | SIG_Interlocking Renewal_GA_Hatfield_Com | ST003980-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | RELAY TO PBI RENEWAL | RENEWAL | 1 | STATION | 2000000 | Goonyella | HATFIELD |  | 0 | KM | GA01ML49 | 0.752 | GA01ML49 | 0.752 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20330630 | * 28.09.2020 10:31:21 AUSQLD Peter Rayner (R003851) * Replace Relays with PBI, Replace TCs with FAdC using quad, Digital Telem, Add VDRs, Split detection on crossovers, Upgrade Power Sup, Replace SER.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104788&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  | FUTURE SCOPE | COAL | 002000104788 | SIG_Interlocking Renewal_MA_MtRainbo_Des | ST003760 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | MOUNT RAINBOW | MOUNT RAINBOW | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2027-06-30 |  |  |  |  | 5 | 2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20260630 | Design phase for the replacement of the VPI at Mt Rainbow. PBI expected to be a Westrace MkII. Working components from the removed VPI are to be placed into inventory. The axle counter block between Mt Rainbow and Dumgree is to be replaced at the same time.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104808&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 | Coal Traffic |  | COAL | 002000104808 | SIG_Interlocking Renewal_MA_Belldeen_Pln | ST003350 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | PLANNING | 1 | SITE | 120000 | Moura | BELLDEEN | BELLDEEN | 0 | KM | MA01ML154 | 0.454 | MA01ML154 | 0.454 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20330630 | Planning phase for the replacement of the VPI at Belldeen. This includes axlecounters to Earlsfield and Moura Mine, plus any AS3000. PBI expected to be a ElectrologiX. This should be the final VPI removal therefore remove all VPI spares from inventory and depots.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000142025&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 | Coal Traffic |  | COAL | 002000142025 | SIG_Interlocking Renewal_MA_Fry_Com | ST003660-04 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 2500000 | Moura | FRY | FRY | 0 | KM | MA01ML73 | 0.0509 | MA01ML73 | 0.0509 | KM | [6 empty] | 2033-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20330630 | Design phase for the replacement of the VPI at Fry. To include block to Clarke and AS3000 requirements. PBI expected to be a ElectrologiX. All working components of VPI are to be returned to inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060017&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060017 | SIG_Replace M23A_GA_BM12A_Com | TO000331-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA02ML40 | 0.919 | GA02ML40 | 0.919 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | * 23.06.2020 12:11:45 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060018&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060018 | SIG_Replace M23A_GA_BM12D_Com | TO000448-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA01ML41 | 0.016 | GA01ML41 | 0.016 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20270630 | * 23.06.2020 12:11:55 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060019&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060019 | SIG_Replace M23A_GA_BM8A_Com | TO000447-01 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA01ML40 | 0.799 | GA01ML40 | 0.799 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | * 23.06.2020 12:12:04 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000060020&DY_MAB=X&~OKCODE=ONLI | MAJOR-2033-000001 |  |  | COAL | 002000060020 | SIG_Replace M23A_GA_BM8D_Com | TO000332-02 | CONTROL SYSTEMS | POINTS IMPROVEMENT | M23A CONTACTOR UPGRADE | RENEWAL | 1 | UNIT | 60000 | Goonyella | BLACK MOUNTAIN | BLACK MOUNTAIN | 0 | KM | GA02ML40 | 0.898 | GA02ML40 | 0.898 | KM | [11 empty] | 4 |  |  | 4 |  | 16 |  |  |  |  | BESPOKE DESIGN | LOW | MEDIUM | LOW | LOW | Outstanding notification | NWSC |  | 20280630 | * 23.06.2020 12:12:15 AUSQLD Peter Rayner (R003851) * Obsolete contactor in machine no longer supported and limited spares available.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000115214&DY_MAB=X&~OKCODE=ONLI | MAJOR-2034-000001 |  | BASELOAD | COAL | 002000115214 | C05-FR-GA-MORANBAH NORTH JCT-195.27km | GA-01ML | CIVIL | FORMATION |  | RENEWAL | 0.12 | KM | 796448 | Goonyella | MORANBAH NORTH JCT | GOONYELLA JCT | 0.1199 | KM | GA01ML195 | 0.27 | GA01ML195 | 0.39 | KM |  |  |  |  | 195.27 | 195.39 | 2025-06-30 | DOWN |  |  |  | 2.7 | 2.6 | 3 | 3.7 | 1 | 9.9 |  | 2023-09-01 |  | Formation Renewals | LIKE FOR LIKE | MEDIUM | MEDIUM | LOW | HIGH | Outstanding notification | SCPR |  | 20340630 | 06/10/2023 - Scope deferred from FY25 to later years due to capital constraint Formation Renewal requirements: • Complete Formation Renewal in accordance with Aurizon Standard Formation Reconstruction Standard Drawings AUR-S-9999-2101 <(>&<)> AUR-S-9999-2102 <(>&<)> Track Formation Capping Layer Civil Assets Specification AZN.NA.SPC.12.6135.001. • Clean, clear and reinstate drainage from 195.250km to 195.800km both sides of track in accordance with Aurizon Track Formation Standard Drawings 2763 - 2769, ensuring that the new formation is free draining. • Where track monuments are required but not present, arrange for BMF Survey and monument installation in conjunction with works in accordance with Aurizon Standard Drawings AUR-S-9999-2105 <(>&<)> AUR-S-9999-2106. • As best practice, remove spoil from corridor or where not possible consult with local depot to establish appropriate spoil disposal area prior to execution ensuring that location does not create future drainage issues or impede access. • Unsuitable subgrade material allowance 50% (Estimated). Geotech testing for unsuitable material validation is required prior to co nstruction. Recommend use results from adjacent culvert and level crossing renewals. • Adjust scope bounds to tie into previous Level Crossing <(>&<)> Culvert renewal, unable to locate QA. The below track component replacement shall be followed for all formation renewal sites (Unless otherwise specified): • Reuse existing rail • Reuse existing sleepers (Unless if fist clip in which case replace with new concrete e-clip) • Replace insulators and pads where appropriate with new (i.e. unless evidence of recent renewal) • Clip replacement as required to be confirmed by constructor during pre-construction walkouts or replacement as required in accordance with Asset notice TC017 Supporting Information: • Twist 10, Twist 3 defects (D7) as well as top defects • FY22 LX Renewal LX000800 @ 195.258km (Noti # 2000050537)
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000103948&DY_MAB=X&~OKCODE=ONLI | MAJOR-2034-000001 |  |  |  | 002000103948 | C58-LX-BW-Byellee Rd-13.063km | LX005956 | CIVIL | LEVEL CROSSINGS | RENEWAL | RENEWAL | 1 | SITE | 362980 | Moura | CALLEMONDAH | STOWE | 0 | KM | MA01ML13 | 0.0619 | MA01ML13 | 0.0619 | KM |  |  | 13.063 | 13.063 | 13.063 | 13.063 | 2034-06-30 | ROSEWOOD ROSE |  |  |  | 3 | 1.3 | 2 | 3 | 1 | 9 | [9 empty] | Outstanding notification | NWSC |  | 20340630 | RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043852&DY_MAB=X&~OKCODE=ONLI | MAJOR-2034-000001 |  |  | COAL | 002000043852 | B12 -ST-NL-Cockool-124.020km | BR300533 | CIVIL | STRUCTURES | BRIDGE-STRENGTHENING | RENEWAL | 1 | SITE | 1500000 | Newlands | COCKOOL | HAVILAH | 0 | KM | NL01ML124 | 0.02 | NL01ML124 | 0.02 | KM |  |  |  |  | 124.02 |  | 2034-06-30 |  |  | STRENGTHEN |  | 3 | 2.5 |  |  |  | 5 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Notification in process | NWSC |  | 20340630 | Defect: Special Defect - fine cracks on underside of girders. Design assessment found structures to shear deficient and borderline Moment capacity. Proposed: Level 3 Inspections, measurements, Strengthening for shear SMP.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104810&DY_MAB=X&~OKCODE=ONLI | MAJOR-2034-000001 | Coal Traffic |  | COAL | 002000104810 | SIG_Interlocking Renewal_MA_Belldeen_Des | ST003350 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | DESIGN | 1 | SITE | 1000000 | Moura | BELLDEEN | BELLDEEN | 0 | KM | MA01ML154 | 0.454 | MA01ML154 | 0.454 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Minor | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | MEDIUM | Outstanding notification | NWSC |  | 20340630 | Design phase for the replacement of the VPI at Belldeen. This includes axlecounters to Earlsfield and Moura Mine, plus any AS3000. PBI expected to be a ElectrologiX. This should be the final VPI removal therefore remove all VPI spares from inventory and depots.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000096050&DY_MAB=X&~OKCODE=ONLI | MAJOR-2034-000001 |  |  | COAL | 002000096050 | SIG_Interlocking Renewal_MA_MtRainbo_Com | ST003760-03 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 2500000 | Moura | MOUNT RAINBOW | MOUNT RAINBOW | 0 | KM | MA01ML91 | 0.7489 | MA01ML91 | 0.7489 | KM | [6 empty] | 2025-06-30 |  |  |  |  | 5 | 4 |  |  |  | 20 |  | 2024-06-30 |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | MEDIUM | MEDIUM | MEDIUM | HIGH | Outstanding notification | NWSC |  | 20300630 | Replace VPI with Westrace PBI to ensure it is supportable. VPI parts to be placed in inventory for spares.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085950&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  | BASELOAD | COAL | 002000085950 | B52 -ST-BW-Duaringa-107.410km | CU100284 | CIVIL | STRUCTURES | RCBC | DESIGN | 1 | SITE | 45000 | Blackwater | BW-CL |  | 0 | KM | BW03ML107 | 0.4099 | BW03ML107 | 0.4099 | KM |  |  |  |  | 107.41 |  | 2025-06-30 |  |  |  |  | 3.5 | 3.4 |  |  |  | 14 |  |  |  | Culvert Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20270630 | Defect: RCP into Box Culvert. Culvert undersized for creek, based on inspection reports. Hydro to check. Scoured after heavy rainfall and costing a lot in maintenance. awaiting remote inspection. Rock has been removed. Proposed: Remove and replace with larger RCBC system. Diffcult access on RHS. Risk: Mod-High Reason:
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000083451&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000083451 | B52 -ST-MA-Byellee-023.700km | CU400098 | CIVIL | STRUCTURES | RCBC | RENEWAL | 1 | SITE | 500000 | Moura | MA |  | 0 | KM | MA01ML23 | 0.6999 | MA01ML23 | 0.6999 | KM |  |  |  |  | 23.7 |  | 2036-06-30 |  |  | REMOVE & REPLACE |  | 3 | 1.3 | 3 |  |  | 8.1 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20360630 | Defect: LHS extention replaced by maintenance under access rd. Renewal will be driven by corrosion of this in future or arch showing more deterioartion. Proposed: Remove <(>&<)> Replace Risk: Mod Reason: Risk of pumping and overloading at this location as CMP is not compliant with cover over rigid pipe. Will deteriorate faster. And corosion will also increase risk of collapse.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075349&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075349 | COLLINSVILLE GENERATOR RENEWAL - Not Req | ST005730-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE |  | RENEWAL |  | SITE |  | Newlands |  |  | 0 | KM | NL01ML76 | 0.66 | NL01ML76 | 0.66 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20350630 | * 31.03.2021 12:17:58 AUSQLD Scott Andrews (R003573) * RENEWAL OF COLLINSVILLE TELECOMMUNICATIONS GENERATOR
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046567&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046567 | CSI Tower Renewal - Not Req | ST005960-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE |  | RENEWAL | 1 | SITE | 75000 | Goonyella | NANYA | NANYA | 0 | KM | GA42CR0 | 0 | GA42CR0 | 0 | KM | [6 empty] | 2035-06-30 | ALL |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  | 2020-03-06 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046566&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046566 | CSI Tower Renewal - Stephens - Not Req | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE |  | RENEWAL | 1 | SITE | 30000 | Goonyella | STEPHENS | STEPHENS | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 99.289 | 99.289 | 2035-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | HIGH | MEDIUM | Outstanding notification | SCPR INIF |  | 20350630 | * 07.11.2019 11:03:51 AUSQLD Allan Gough (R873345) * 07.11.2019 10:49:43 AUSQLD Allan Gough (R873345) * In-Gauge Action: Review the requirement for the un-used steel pole associated with the decommissioned DED site at Stephens and take appropriate action regarding the outcome of the review. * * Action Completed: * Reviewed requirement for Pole and Slab at base of Pole. Both no longer required. N4 Notification which is for Tower work in Goonyella has been created in SAP PM. N4 Notification 992000046566. This notification will manage completion of removal of the Pole and appropriate Environmental * The obsolete DED pole at Stephens at approximately the 99.289km. The pad is roughly 1.9m x 2.5m and is 9m from the closest rail. * * The pole appears to be in good condition with the antenna still attached to the top of the mast and tail cable cut off at head height. * Requirements as a birds nest is at the top of the Tower. * * Notification 2000046566 to cover Stephens site and Notification 2000047458 created to transfer Summer Hill scope details * *
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046859&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Dual Traffic |  | COAL | 002000046859 | CSI CER Renewal - Duplicate | ST006290 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 410000 | Blackwater | ARCHER CER | ARCHER CER | 0 | KM | BW01ML614 | 0.9839 | BW01ML614 | 0.9839 | KM | [7 empty] | ALL |  |  |  | 4 | 4.5 |  |  |  | 18 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044617&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000044617 | 4090 CSI CER Renewal - Duplicate | ST005820 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | JILALAN MWR | JILALAN MWR | 0 | KM | GA39CR0 | 0 | GA39CR0 | 0 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046860&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000046860 | CSI CER Renewal - Duplicate | ST006150 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 410000 | Blackwater | KOORILGAH CER | KOORILGAH CER | 0 | KM | BW13ML12 | 0.876 | BW13ML12 | 0.876 | KM | [7 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044618&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000044618 | 4091 CSI CER Renewal - Duplicate | ST006390 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Blackwater | SANDHURST MWR | SANDHURST MWR | 0 | KM | BW61CR0 | 0 | BW61CR0 | 0 | KM |  |  |  |  | 0 | 0 | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2020-03-06 |  | Transmission & Data Renewals | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046828&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000046828 | CSI CER Renewal - Duplicate | ST005900 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | SARINA MWR | SARINA MWR | 0 | KM | GA44CR0 | 0 | GA44CR0 | 0 | KM | [7 empty] | ALL |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  |  | BESPOKE DESIGN | MEDIUM |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046830&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000046830 | CSI CER Renewal - Duplicate | ST005910 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 400000 | Goonyella | THREE SISTERS MWR | THREE SISTERS MWR | 0 | KM | GA47CR901 | 0 | GA47CR901 | 0 | KM | [7 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN | MEDIUM |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046861&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 | Coal Traffic |  | COAL | 002000046861 | CSI CER Renewal - Duplicate | ST006160 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | CER | RENEWAL | 1 | SITE | 410000 | Blackwater | TIKARDI CER | TIKARDI CER | 0 | KM | BW05ML5 | 0.511 | BW05ML5 | 0.511 | KM | [7 empty] | ALL |  |  |  | 4 | 1.7 |  |  |  | 6.8 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075299&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075299 | BLAIR ATHOL DEHYDRATOR RENEWAL Not Req | ST006380-25 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL |  | SITE |  | Goonyella |  |  | 0 | KM | GA05ML110 | 0.4799 | GA05ML110 | 0.4799 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20350630 | * 31.03.2021 06:47:39 AUSQLD Scott Andrews (R003573) * RENEW DEHYDRATOR AT BLAIR ATHOL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075286&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075286 | DEHYDRATOR RENEWAL - Not Req | ST005600-29 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27300 | Moura |  |  | 0 | KM | MA13CR0 | 0 | MA13CR0 | 0 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW |  | MEDIUM | MEDIUM | Outstanding notification | SCPR | FY23 IN | 20350630 | * 30.03.2021 19:45:02 AUSQLD Scott Andrews (R003573) * DEHYDRATOR RENEWAL BANANA RANGE
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075282&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075282 | DEHYDRATOR RENEWAL pushed Not Req | ST006270-27 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 27300 | Blackwater |  |  | 0 | KM | BW63CR0 | 0 | BW63CR0 | 0 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR | FY23 OUT | 20350630 | * 30.03.2021 17:40:07 AUSQLD Scott Andrews (R003573) * TABLE MTN DEHYDRATOR RENEWAL
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078699&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078699 | Dehydrator Radome Renewal Gogango - Dupl | ST005540-31 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL |  | SITE |  | Blackwater | GOGANGO |  | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 17:31:26 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075300&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075300 | DEHYDRATOR MORANBAH RENEWAL - Not Req | ST009550-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL |  | SITE |  | Goonyella | MORANBAH |  | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20350630 | * 31.03.2021 06:51:53 AUSQLD Scott Andrews (R003573) * RENEW DEHYDRATOR AT MORANBAH
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078700&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078700 | Dehydrator Radome Renewal Wallaroo -Dupl | ST005530 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | DEHYDRATOR | RENEWAL | 1 | SITE | 25000 | Blackwater | WALLAROO |  | 0 | KM | BW03ML0 | 0 | BW03ML0 | 0 | KM | [6 empty] | 2035-06-30 |  |  |  |  | 4 | 5 |  |  |  | 20 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 17:32:41 AUSQLD Peter Rayner (R003851) * Renew Dehydrators at site
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046845&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046845 | CSI GEN Renewal - Duplicate | ST005950 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | UNIT | 90000 | Blackwater | CAPELLA | CAPELLA | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN | LOW |  | HIGH | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046844&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046844 | CSI GEN Renewal - Duplicate | ST005960 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | UNIT | 90000 | Goonyella | NANYA | NANYA | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  |  | BESPOKE DESIGN | LOW |  | HIGH | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046879&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046879 | CSI GEN Renewal - Duplicate | ST005910 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | GENERATOR | RENEWAL | 1 | UNIT | 95000 | Goonyella | THREE SISTERS | THREE SISTERS | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000045033&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000045033 | Control System Infrastructure OF Not Req | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OF | RENEWAL | 9600 | METERS | 1377055 | Goonyella | MORANBAH | VILLAFRANCA | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 21.2 | 37.4 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630 | * 18.09.2019 23:25:58 AUSQLD Emma-Kate Clyburn (R870828) * Optical Fibre Replacement Moranbah CER2 to Villafranca PSC-1 Blackwater to Tolmies
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044612&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044612 | 4083 CSI OF Renewal - Not Req | ST003260-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 11400 | METERS | 1368000 | Blackwater |  |  | 11.3469 | KM | BW08ML50 | 0.89 | BW08ML62 | 0.231 | KM |  |  |  |  | 50.89 | 62.231 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044613&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044613 | 4084 CSI OF Renewal - Not Req | ST004210-21 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 600000 | Blackwater |  |  | 4.8499 | KM | BW03ML84 | 0.676 | BW03ML89 | 0.503 | KM |  |  |  |  | 84.65 | 89.5 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044614&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044614 | OF Edungalba -Aroona dup 2000068916 | ST008130-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 600000 | Blackwater |  |  | 5.04 | KM | BW03ML89 | 0.503 | BW03ML94 | 0.538 | KM |  |  |  |  | 89.5 | 94.54 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044615&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044615 | OF Renewal dup 2000068918 | ST004120-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 9000 | METERS | 1080000 | Blackwater |  |  | 8.96 | KM | BW03ML94 | 0.538 | BW03ML103 | 0.5 | KM |  |  |  |  | 94.54 | 103.5 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079384&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079384 | CSI OF Renewal - Not Req | ST006290-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 9000 | METERS | 1152000 | Blackwater | ACH-CER TO BJQ-CER O/FBR CABLE |  | 9.6319 | KM | BW01ML614 | 0.9839 | BW01ML605 | 0.3709 | KM |  |  |  |  | 614.984 | 605.371 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046876&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046876 | CSI OF Renewal - Not Req | ST005830-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 9200 | METERS | 1196000 | Goonyella | BAL-AT0 TO WAN-SER OF CABLE |  | 9.14 | KM | GA01ML76 | 0.768 | GA01ML85 | 0.919 | KM |  |  |  |  | 76.78 | 85.92 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046875&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046875 | CSI OF Renewal - Not Req | ST003880-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2200 | METERS | 286000 | Goonyella | BAL-SER TO BAL-AT0 OF CABLE |  | 2.1299 | KM | GA01ML74 | 0.65 | GA01ML76 | 0.768 | KM |  |  |  |  | 74.65 | 76.78 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046874&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046874 | CSI OF Renewal - Not Req | ST001330-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5300 | METERS | 689000 | Goonyella | BBE-ATW TO BAL-TSC OF CABLE |  | 5.3179 | KM | GA01ML65 | 0.93 | GA01ML71 | 0.2449 | KM |  |  |  |  | 65.93 | 71.248 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046583&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046583 | CSI OF Renewal - Not Req | ST000690-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5800 | METERS | 580000 | Goonyella | BBE-FSS TO BBE-SER O/F CABLE |  | 5.75 | KM | GA01ML54 | 0.8739 | GA01ML60 | 0.6199 | KM |  |  |  |  | 54.87 | 60.62 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046584&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046584 | CSI OF Renewal - Not Req | ST003940-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Goonyella | BBE-SER TO BBE-ATW O/F CABLE |  | 5.3099 | KM | GA01ML60 | 0.6199 | GA01ML65 | 0.93 | KM |  |  |  |  | 60.62 | 65.93 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044575&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044575 | OF Renewal Blackwater-Tolmies - Not Req | BW-46YR | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Blackwater | BLACKWATER | TOLMIES | 0.2149 | KM | BW46YR189 | 0.223 | BW46YR189 | 0.447 | KM |  |  |  |  | 189.18 | 203.54 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046599&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  | STRATEGIC | COAL | 002000046599 | CSI OF Renewal - Not Req | ST004580-16 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12300 | METERS | 1160013 | Goonyella | BLA-SER TO COB-MWR O/F CABLE |  | 11.739 | KM | GA01ML156 | 0.264 | GA01ML144 | 0.52 | KM |  |  |  |  | 156.264 | 144.52 |  | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  | 2022-03-31 |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079379&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079379 | CSI OF Renewal - Not Req | ST004580-16 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2000 | METERS | 256000 | Goonyella | BLA-SER TO COB-MWR O/FBR CABLE |  | 1.556 | KM | GA01ML156 | 0.264 | GA01ML154 | 0.6999 | KM |  |  |  |  | 156.264 | 154.7 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079362&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079362 | CSI OF Renewal - Not Req | ST004540-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4000 | METERS | 512000 | Goonyella | BRA-SER TO MII-ATE O/FBR CABLE |  | 3.33 | KM | GA01ML107 | 0.6999 | GA01ML111 | 0.01 | KM |  |  |  |  | 107.7 | 111.01 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078607&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078607 | CSI OF Renewal - Not Req | ST006080-03 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 800 | METERS |  | Blackwater | BURNGROVE CER TO TOLMIES CER |  | 0.752 | KM | BW03ML202 | 0.3599 | BW03ML203 | 0.111 | KM |  |  |  |  | 202.36 | 203.111 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 14:25:25 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079383&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079383 | CSI OF Renewal - Not Req | ST005570-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 14000 | METERS |  | Moura | BYL-CER TO CAH-CER O/FBR CABLE |  | 520.1299 | KM |  | 0 |  | 0 | [5 empty] | 13.87 | 534 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046833&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046833 | CSI OF Renewal - Not Req | ST005570-06 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Moura | BYL-CER TO CAH-CER OF CABLE | BYL-CER TO CAH-CER OF CABLE | 520.1299 | KM |  | 0 |  | 0 | [5 empty] | 13.87 | 534 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046587&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046587 | CSI OF Renewal - Not Req | ST000040-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 8000 | METERS | 800000 | Blackwater | DIN-FSS TO DIN-CER O/F CABLE |  | 7.99 | KM | BW03ML133 | 0.3039 | BW03ML141 | 0.2979 | KM |  |  |  |  | 133.31 | 141.3 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046577&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046577 | OF Renewal dup 2000068920 | ST004190-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 6400 | METERS | 640000 | Blackwater | DUA-SER TO WAY-ATE O/F CABLE |  | 6.3099 | KM | BW03ML104 | 0.773 | BW03ML111 | 0.0899 | KM |  |  |  |  | 104.78 | 111.09 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044591&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044591 | 3404 CSI OF Renewal - Not Req | BW-19SD | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Blackwater | FAIRHILL | RED ROCK | 0.454 | KM | BW19SD37 | 0.4929 | BW19SD37 | 0.9429 | KM |  |  |  |  | 38.453 | 42.14 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079380&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079380 | CSI OF Renewal - Not Req | ST004740-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 640000 | Goonyella | GON-SER TO RIV-SER O/FBR CABLE |  | 4.668 | KM | GA13ML195 | 0.4 | GA13ML200 | 0.07 | KM |  |  |  |  | 195.4 | 200.07 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046582&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046582 | CSI OF Renewal - Not Req | ST003980-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Goonyella | HAT-SER TO BBE-FSS O/F CABLE |  | 5.1479 | KM | GA01ML49 | 0.7419 | GA01ML54 | 0.904 | KM |  |  |  |  | 49.752 | 54.9 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046838&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046838 | CSI OF Renewal - Not Req | ST001260-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1500 | METERS |  | Goonyella | IGD-AT0 TO IGD-MI0 OF CABLE |  | 1.4899 | KM | GA03ML11 | 0.7399 | GA03ML13 | 0.23 | KM |  |  |  |  | 11.74 | 13.23 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086898&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086898 | CSI OF Renewal | ST009490-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 14700 | METERS | 1249500 | Blackwater | KENMARE AT2 |  | 14.601 | KM | BW06ML26 | 0.5 | BW06ML41 | 0.1 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086884&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086884 | CSI OF Renewal | ST009500-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12000 | METERS | 1020000 | Blackwater | KENMARE AT3 |  | 12.0899 | KM | BW06ML41 | 0.1 | BW06ML53 | 0.19 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086897&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086897 | CSI OF Renewal | ST009480-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 14300 | METERS | 1215500 | Blackwater | KINROLA AT1 |  | 14.3989 | KM | BW06ML12 | 0.1 | BW06ML26 | 0.5 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085388&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000085388 | CSI OF Renewal | ST006370-23 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4800 | METERS | 408000 | Blackwater | KINROLA CER |  | 4.8499 | KM | BW05ML15 | 0.655 | BW05ML20 | 0.5 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086895&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086895 | CSI OF Renewal | ST009440-47 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 11500 | METERS | 977500 | Blackwater | KINROLA TSY |  | 11.505 | KM | BW06ML0 | 0.5999 | BW06ML12 | 0.1049 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000044590&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000044590 | 3403 CSI OF Renewal - Not Req | BW-08ML | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Blackwater | MACKENZIE | FAIRHILL | 15.0549 | KM | BW08ML23 | 0.4 | BW08ML38 | 0.453 | KM |  |  |  |  | 23.4 | 38.453 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086886&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086886 | CSI OF Renewal | ST009510-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 11000 | METERS | 935000 | Blackwater | MEMOOLOO AT4 |  | 11.1509 | KM | BW06ML67 | 0.5 | BW06ML78 | 0.65 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079363&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079363 | CSI OF Renewal - Not Req | ST006740-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 640000 | Goonyella | MII-ATE TO MII-FSS O/FBR CABLE |  | 5.091 | KM | GA01ML111 | 0.1 | GA01ML116 | 0.2 | KM |  |  |  |  | 111.1 | 116.2 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079374&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079374 | CSI OF Renewal - Not Req | ST006740-13 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4500 | METERS | 576000 | Goonyella | MII-ATW TO SWJ-SER O/FBR CABLE |  | 5.091 | KM | GA01ML111 | 0.1 | GA01ML116 | 0.2 | KM |  |  |  |  | 123.03 | 127.58 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079364&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079364 | CSI OF Renewal - Not Req | ST007310-53 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4500 | METERS | 576000 | Goonyella | MII-FSS TO MII-SER O/FBR CABLE |  | 4.243 | KM | GA01ML116 | 0.2 | GA01ML120 | 0.45 | KM |  |  |  |  | 116.2 | 120.45 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079365&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079365 | CSI OF Renewal - Not Req | ST004820-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3000 | METERS | 384000 | Goonyella | MII-SER TO MII-ATW O/FBR CABLE |  | 2.5769 | KM | GA01ML120 | 0.45 | GA01ML123 | 0.0299 | KM |  |  |  |  | 120.45 | 123.03 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079389&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079389 | CSI OF Renewal - Not Req | ST003730-35 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3500 | METERS |  | Blackwater | MLM-SR1 TO MLM-TSC O/FBR CABLE |  | 3.535 | KM | BW01ML565 | 0.2 | BW01ML568 | 0.81 | KM |  |  |  |  | 565.2 | 568.81 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079386&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079386 | CSI OF Renewal - Not Req | ST001880-09 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 10200 | METERS | 1305600 | Blackwater | MMQ-AT0 TO RGL-CER O/FBR CABLE |  | 10.198 | KM | BW01ML594 | 0.9 | BW01ML584 | 0.7189 | KM |  |  |  |  | 594.9 | 584.719 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079385&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079385 | CSI OF Renewal - Not Req | ST006300-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 3000 | METERS | 384000 | Blackwater | MMQ-CER TO MMQ-AT0 O/FBR CABLE |  | 2.3849 | KM | BW01ML597 | 0.276 | BW01ML594 | 0.9 | KM |  |  |  |  | 597.276 | 594.9 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046863&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046863 | CSI OF Renewal - Not Req | ST006300-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2300 | METERS |  | Blackwater | MMQ-CER TO MMQ-AT0 OF CABLE |  | 2.3759 | KM | BW01ML597 | 0.273 | BW01ML594 | 0.899 | KM |  |  |  |  | 597.276 | 594.9 |  | ALL |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000074768&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000074768 | OF Grantleigh CERGrantleigh MI - Not Req | ST006340-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Blackwater | OF GRANTLEIGH CER - GRANTLEIGH |  | 1.6319 | KM | BW03ML66 | 0.17 | BW03ML67 | 0.8 | KM |  |  |  |  | 66.17 | 67.8 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC | FY24 IN | 20350630 | * 23.03.2021 08:19:15 AUSQLD Scott Andrews (R003573) * Renew OF at Functional Location
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079378&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079378 | CSI OF Renewal - Not Req | ST006770-05 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 128000 | Goonyella | REM-AT0 TO WCH-SER O/FBR CABLE |  | 1.0329 | KM | GA03ML30 | 0.02 | GA03ML31 | 0.05 | KM |  |  |  |  | 30.02 | 31.05 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079377&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079377 | CSI OF Renewal - Not Req | ST005040-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4000 | METERS | 512000 | Goonyella | REM-SER TO REM-AT0 O/FBR CABLE |  | 6.3959 | KM | GA03ML23 | 0.6199 | GA03ML30 | 0.02 | KM |  |  |  |  | 23.62 | 30.02 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046873&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046873 | CSI OF Renewal - Not Req | ST006620-01 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5800 | METERS | 754000 | Blackwater | ROK-ACB TO RCS-SR1 OF CABLE |  | 5.8399 | KM |  | 0 |  | 0 | [5 empty] | 638.74 | 632.9 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046887&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046887 | CSI OF Renewal - Not Req | ST007790-14 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 7300 | METERS | 876000 | Blackwater | SPI-AT0 TO WWO-SER OF CABLE |  | 7.3109 | KM | BW03ML40 | 0.4229 | BW03ML47 | 0.7359 | KM |  |  |  |  | 40.425 | 47.736 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086887&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086887 | CSI OF Renewal | ST009520-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12800 | METERS | 1088000 | Blackwater | STARLEE AT5 |  | 12.849 | KM | BW06ML78 | 0.65 | BW06ML91 | 0.5 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086888&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086888 | CSI OF Renewal | ST009540-15 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 12000 | METERS | 1020000 | Blackwater | STARLEE AT6 |  | 12.15 | KM | BW06ML91 | 0.5 | BW06ML103 | 0.65 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Notification completed | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000086885&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000086885 | CSI OF Renewal | ST009450-62 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 14200 | METERS | 1207000 | Blackwater | STRUAN ROAD FSS |  | 14.2339 | KM | BW06ML53 | 0.266 | BW06ML67 | 0.5 | KM | [6 empty] | 2035-06-30 | [13 empty] | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046585&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046585 | CSI OF Renewal - Not Req | ST001950-07 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 2700 | METERS | 270000 | Blackwater | TRP-ATE TO TRP-CER O/F CABLE |  | 2.6859 | KM | BW03ML125 | 0.7139 | BW03ML128 | 0.405 | KM |  |  |  |  | 125.714 | 128.4 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046586&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046586 | CSI OF Renewal - Not Req | ST006360-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 5000 | METERS | 500000 | Blackwater | TRP-CER TO DIN-FSS O/F CABLE |  | 4.891 | KM | BW03ML128 | 0.4239 | BW03ML133 | 0.3039 | KM |  |  |  |  | 128.419 | 133.31 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046878&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046878 | CSI OF Renewal - Not Req | ST000700-46 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 4800 | METERS | 624000 | Goonyella | WAN-FSS TO WAN-WSS OF CABLE |  | 4.7809 | KM | GA01ML87 | 0.219 | GA01ML92 | -0.01 | KM |  |  |  |  | 87.219 | 92 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046877&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046877 | CSI OF Renewal - Not Req | ST004050-08 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1500 | METERS | 195000 | Goonyella | WAN-SER TO WAN-FSS OF CABLE |  | 1.3799 | KM | GA01ML85 | 0.919 | GA01ML87 | 0.2999 | KM |  |  |  |  | 85.92 | 87.3 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046588&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046588 | CSI OF Renewal - Not Req | ST008020-53 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 8400 | METERS | 840000 | Blackwater | WAY-TSC TO TRP-ATE O/F CABLE |  | 8.4 | KM | BW03ML118 | 0 | BW03ML126 | 0.4 | KM |  |  |  |  | 118 | 126.4 |  | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  | Telecommunication Asset | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078613&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078613 | CSI OF Renewal - Not Req | ST004470-22 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 1000 | METERS | 128000 | Blackwater | WINDAH SER TO GRANTLEIGH FSS |  | 0 | KM | BW03ML57 | 0.5999 | BW03ML57 | 0.5999 | KM |  |  |  |  | 57.6 | 57.6 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 14:29:57 AUSQLD Peter Rayner (R003851) * Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046580&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  | STRATEGIC | COAL | 002000046580 | CSI OF Renewal - Not Req | ST005310-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 7800 | METERS | 735618 | Goonyella | WOT-AT0 TO MNJ-SER O/F CABLE |  | 7.7599 | KM | GA01ML184 | 0.8469 | GA01ML192 | 0.5789 | KM |  |  |  |  | 184.84 | 192.6 |  | ALL |  |  |  | 0 | 10 |  | 0 |  | 100 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | LOW | LOW | LOW | MEDIUM | Outstanding notification | RRIG |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079381&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079381 | CSI OF Renewal - Not Req | ST005310-11 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 8000 | METERS | 1024000 | Goonyella | WOT-AT0 TO MNJ-SER O/FBR CABLE |  | 7.7859 | KM | GA01ML184 | 0.8399 | GA01ML192 | 0.5999 | KM |  |  |  |  | 184.84 | 192.6 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000079382&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000079382 | CSI OF Renewal - Not Req | ST000770-32 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL | 10000 | METERS | 1280000 | Goonyella | WOT-FSS TO WOT-AT0 O/FBR CABLE |  | 9.6449 | KM | GA01ML175 | 0.19 | GA01ML184 | 0.8399 | KM |  |  |  |  | 175.19 | 184.84 | [5 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350609 | Replace Optical Fibre Cable
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046889&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046889 | Obsolete OF Yukan AT0-Black Mtn TSC | ST005770-04 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Goonyella | YUK-AT0 TO BMT-TSC OF CABLE |  | 2.0099 | KM | GA01ML33 | 0.9899 | GA01ML36 | 0 | KM |  |  |  |  | 33.99 | 36 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | SCPR | FY23 IN | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046890&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046890 | obsolete OF Yukan SER-Yukan AT0 | ST004060-10 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | OPTICAL FIBRE | RENEWAL |  | METERS |  | Goonyella | YUK-SER TO YUK-AT0 OF CABLE |  | 5.19 | KM | GA01ML28 | 0.8 | GA01ML33 | 0.9899 | KM |  |  |  |  | 28.8 | 33.99 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Telecommunication Asset | BESPOKE DESIGN | MEDIUM |  | LOW | LOW | Outstanding notification | SCPR | FY23 IN | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075301&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075301 | RADOME RENEWAL GA - Not Required | GA | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME | RENEWAL |  | SITE |  | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR |  | 20350630 | * 31.03.2021 06:57:19 AUSQLD Scott Andrews (R003573) * RENEW RADOME IN GA SYSTEM. SITE TO BE DETERMINED IN MAY 2022 BASED ON CONDITION.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046847&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046847 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005950 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 60000 | Blackwater | CAPELLA | CAPELLA | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | LIKE FOR LIKE | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046882&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046882 | CSI RADOM Renewal - Not Required | ST005730 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 60000 | Newlands | COLLINSVILLE | COLLINSVILLE | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 2.5 |  |  |  | 10 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046884&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046884 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005280 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 60000 | Blackwater | CROCKER PEAK | CROCKER PEAK | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046848&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046848 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005920 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL |  | UNIT |  | Goonyella | GOONYELLA | GOONYELLA | 0 | KM | GA38CR0 | 0 | GA38CR0 | 0 | KM | [7 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046849&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046849 | CSI RADOM_DEHYDRAT Renew - Not Req | ST009550 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL |  | UNIT |  | Goonyella | MORANBAH | MORANBAH | 0 | KM | GA05ML19 | 0.9499 | GA05ML19 | 0.9499 | KM | [7 empty] | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046846&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046846 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005960 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL |  | UNIT |  | Goonyella | NANYA | NANYA | 0 | KM | GA01ML58 | 0.127 | GA01ML58 | 0.127 | KM | [7 empty] | ALL |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | MEDIUM |  | MEDIUM | MEDIUM | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046605&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046605 | CSI RADOME DEHYDRATOR Renewal - Not Req | BW | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 40000 | Blackwater | PINE MOUNTAIN MWR | PINE MOUNTAIN MWR | 633.538 | KM |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | LIKE FOR LIKE | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046883&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046883 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005900 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 60000 | Goonyella | SARINA | SARINA | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 4.6 |  |  |  | 18.4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046881&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046881 | CSI RADOM_DEHYDRAT Renew - Not Req | ST005910 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL | 2 | UNIT | 60000 | Goonyella | THREE SISTERS | THREE SISTERS | 0 | KM |  | 0 |  | 0 | [8 empty] | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046900&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046900 | Dehydrator Radome Renew Bluff - Not Req | ST005520 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL MINOR | 2 | UNIT | 63479 | Blackwater | BLUFF MWR | BLUFF MWR | 0 | KM |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  | Transmission & Data Renewals | LIKE FOR LIKE | HIGH |  | MEDIUM | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046902&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046902 | CSI RADOM_DEHYDRAT Renew - Not Req | ST002940 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | RADOME AND DEHYDRATOR | RENEWAL MINOR | 2 | UNIT | 63479 | Blackwater | CLERMONT | CLERMONT | 0 | KM |  | 0 |  | 0 | [5 empty] | 100.26 | 100.26 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | LIKE FOR LIKE | HIGH |  | MEDIUM | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046854&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046854 | CSI Tower Renewal - Not Req | ST005530-02 | CONTROL SYSTEMS | CONTROL SYSTEM INFRASTRUCTURE | TOWER | RENEWAL |  | SITE | 50000 | Blackwater | WALLAROO | WALLAROO | 0 | KM | BW03ML115 | 0.68 | BW03ML115 | 0.68 | KM | [7 empty] | ALL |  |  |  | 4 | 3.35 |  |  |  | 13.4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000104811&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000104811 | SIG_Interlocking Renewal_MA_Belldeen_Com | ST003350 | CONTROL SYSTEMS | INTERLOCKING SIGNALLING | VPI REPLACEMENT | RENEWAL | 1 | SITE | 2500000 | Moura | BELLDEEN | BELLDEEN | 0 | KM | MA01ML154 | 0.454 | MA01ML154 | 0.454 | KM | [6 empty] | 2028-06-30 |  |  |  |  | 5 | 1.2 | 5 | 4 | 1 | 20 |  |  |  | Safe Working Systems - Interlockings | BESPOKE DESIGN | HIGH | HIGH | HIGH | HIGH | Outstanding notification | NWSC |  | 20350630 | Commissioning phase for the replacement of the VPI at Belldeen. This includes axlecounters to Earlsfield and Moura Mine, plus any AS3000. PBI expected to be a ElectrologiX. This should be the final VPI removal therefore remove all VPI spares from inventory and depots.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046815&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046815 | Trans DMR NERA LINK Renew - Not Req | ST005580-22 | CONTROL SYSTEMS | TRANSMISSION |  | RENEWAL | 2 | SITES | 150000 | Moura | MAURICE HILL | GOLDING | 0 | KM | NC07CR0 | 0 | NC07CR0 | 0 | KM |  |  |  |  | 0 | 4.5 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046816&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046816 | Trans DMR NERA LINK Renew - Not Req | ST005580-41 | CONTROL SYSTEMS | TRANSMISSION |  | RENEWAL | 2 | SITES | 150000 | Moura | MAURICE HILL | GRAHAM | 0 | KM | NC07CR0 | 0 | NC07CR0 | 0 | KM |  |  |  |  | 0 | 31.3 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046790&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046790 | Trans Pushed from FY23 Dupl ACOM Replace | ST005860 | CONTROL SYSTEMS | TRANSMISSION | ACOM REPLACEMENT | RENEWAL | 1 | SITE | 400000 | Goonyella | MACKAY | MACKAY | 0 | KM | GA46CR0 | 959.3999 | GA46CR0 | 959.3999 | KM | [6 empty] | 2035-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  | 2021-03-31 |  | Transmission & Data Renewals | BESPOKE DESIGN | HIGH |  | HIGH | HIGH | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046792&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046792 | Trans ACOM Replacement Not Req | ST005490 | CONTROL SYSTEMS | TRANSMISSION | ACOM REPLACEMENT | RENEWAL | 1 | SITE | 400000 | Blackwater | ROCKHAMPTON | ROCKHAMPTON | 0 | KM |  | 0 |  | 0 | [7 empty] | 2035-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | BESPOKE DESIGN | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000050912&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000050912 | DMR Renewal - Not Required | MA | CONTROL SYSTEMS | TRANSMISSION | DMR | RENEWAL | 1 | SITE | 25000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [7 empty] | 2035-06-30 |  |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046923&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046923 | Trans DMR NERA LINK Renew - Not Req | ST005860 | CONTROL SYSTEMS | TRANSMISSION | DMR | RENEWAL | 1 | SITES | 90000 | Goonyella | BLACK MOUNTAIN SER | BLACK MOUNTAIN SER | 0 | KM | GA46CR0 | 959.3999 | GA46CR0 | 959.3999 | KM |  |  |  |  | 40.936 | 40.936 | 2035-06-30 | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  | 2020-03-06 |  | Transmission & Data Renewals | BESPOKE DESIGN | LOW |  | HIGH | LOW | Outstanding notification | SCPR INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000043390&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000043390 | Trans DMR Hawk Link Renewal - Not Req | ST005880-13 | CONTROL SYSTEMS | TRANSMISSION | DMR | RENEWAL | 2 | SITES | 240000 | Goonyella | KERLONG | COPPABELLA | 0 | KM | GA40CR0 | 0 | GA40CR0 | 0 | KM |  |  |  |  | 144.052 | 144.052 | 2035-06-30 | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  | Transmission & Data Renewals | BESPOKE DESIGN |  |  |  |  | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000100954&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  | STRATEGIC | COAL | 002000100954 | CS Transmission IOT - DUPLICATE | GA | CONTROL SYSTEMS | TRANSMISSION | IOT | RENEWAL | 1 | LUMPSUM | 100000 | Goonyella | GOONYELLA STATIONS | GOONYELLA STATIONS | 220.507 | KM |  | 0 |  | 0 | [17 empty] | 100 |  |  |  |  | BESPOKE DESIGN | LOW | LOW | LOW | LOW | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078618&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078618 | CS Transmission Renewal Double up | MA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Moura | BELLDEEN |  | 192.36 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:25:31 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046814&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046814 | Trans Pwr Supply Renewal **NOT VALID** | GA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 44000 | Goonyella | BRAESIDE-WAITARA WCM | BRAESIDE-WAITARA WCM | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 103.2 | 103.2 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW | LOW | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000041134&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000041134 | Transmission Power Supply - Not Req | ST005570 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 37676 | Moura | BYELLEE | BYELLEE | 0 | KM |  | 0 |  | 0 | [5 empty] | 13.87 | 13.87 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630 | * 07.08.2019 13:53:48 AUSQLD Jeremy Stevenson (R867415) * Power Supply Replacement Praguelands SER Byellee CER Rectifier 'Eltek'
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078619&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078619 | Transmission Power Supply Not Req | MA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Moura | CLARKE |  | 192.36 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:26:37 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078625&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078625 | Tele Power Supply Marmor - Not Req | ST006300-03 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | MARMOR CER |  | 0 | KM | BW01ML597 | 0.7259 | BW01ML597 | 0.7259 | KM | [11 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:33:25 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078630&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078630 | Tele Power Supply Mindi - Not Req | ST006740-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Goonyella | MINDI ATS 111.1KM |  | 0 | KM | GA01ML111 | 0.1 | GA01ML111 | 0.1 | KM | [11 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:38:04 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078631&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078631 | Tele Power Supply MtMcLaren - Not Req | ST000800-30 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Goonyella | MOUNT MCLAREN FS |  | 0 | KM | GA05ML76 | 0.2999 | GA05ML76 | 0.2999 | KM | [11 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:39:13 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078633&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078633 | CS Transmission Renewal - Not Req | ST005960-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL |  | SITE |  | Goonyella | NANYA MWR |  | 0 | KM | GA42CR0 | 0 | GA42CR0 | 0 | KM | [11 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:41:28 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078623&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078623 | CS Transmission Renewal - Not Req | BW | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | TBD |  | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:31:11 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078634&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078634 | CS Transmission Renewal - Not Req | BW | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | TBD |  | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:42:34 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078624&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078624 | CS Transmission Renewal - Not Req | BW | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | WINDAH ATS 55.1KM |  | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:32:18 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078622&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078622 | CS Transmission Renewal - Not Req | BW | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Blackwater | YAMALA CER |  | 633.538 | KM |  | 0 |  | 0 | [12 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:30:03 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000078627&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000078627 | CS Transmission Renewal - Not Req | ST005770-03 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITE | 28000 | Goonyella | YUKAN ATS 34KM |  | 0 | KM | GA01ML33 | 0.9899 | GA01ML33 | 0.9899 | KM | [11 empty] | 4 | 5 |  |  |  | 20 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | NWSC |  | 20350630 | * 10.06.2021 15:35:44 AUSQLD Peter Rayner (R003851) * Replace Power Supply
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046793&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046793 | Trans Pwr Supply Renewal - Not Req | ST005270-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Moura | BELLDEEN-MOURA HBD | BELLDEEN-MOURA HBD | 0 |  |  | 0 |  | 0 | [5 empty] | 160 | 160 |  | ALL |  |  |  | 4 | 1.3 |  |  |  | 5.2 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046810&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046810 | Trans Pwr Supply Renewal - Not Req | ST007660-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | COPPABELLA SR4 | COPPABELLA SR4 | 0 | KM |  | 0 |  | 0 | [5 empty] | 3.795 | 3.795 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046809&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046809 | Trans Pwr Supply Renewal - Not Req | ST007600-71 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | DALRYMPLE BAY FS | DALRYMPLE BAY FS | 0 | KM |  | 0 |  | 0 | [5 empty] | 1.69 | 1.69 |  | ALL |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046795&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046795 | Trans Pwr Supply Renewal - Not Req | ST005850-02 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | DALRYMPLE SER2 | DALRYMPLE SER2 | 0 | KM |  | 0 |  | 0 | [5 empty] | 8.12 | 8.12 |  | ALL |  |  |  | 4 | 2.6 |  |  |  | 10.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046813&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046813 | Trans Pwr Supply Renewal - Not Req | ST003660-13 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Moura | FRY | FRY | 0 | KM |  | 0 |  | 0 | [5 empty] | 73.051 | 73.051 |  | ALL |  |  |  | 4 | 1.1 |  |  |  | 4.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046805&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046805 | Trans Pwr Supply Renewal - Not Req | ST007220-05 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | ISAAC PLAINS JUNCTION SER | ISAAC PLAINS JUNCTION SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 171.9 | 171.9 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046807&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046807 | Trans Pwr Supply Renewal - Not Req | ST007530-09 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | JILALAN BYPASS NORTH SER | JILALAN BYPASS NORTH SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 17.39 | 17.39 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046806&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046806 | Trans Pwr Supply Renewal - Not Req | ST007580-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | JILALAN BYPASS SOUTH SER | JILALAN BYPASS SOUTH SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 23.2 | 23.2 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046808&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046808 | Trans Pwr Supply Renewal - Not Req | ST007590-29 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | JILALAN TSC | JILALAN TSC | 0 | KM |  | 0 |  | 0 | [5 empty] | 22.35 | 22.35 |  | ALL |  |  |  | 4 | 4.7 |  |  |  | 18.8 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046812&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046812 | Trans Pwr Supply Renewal - Not Req | ST008780-07 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | LAKE VERMONT ATS 11.3KM | LAKE VERMONT ATS 11.3KM | 0 | KM |  | 0 |  | 0 | [5 empty] | 11.3 | 11.3 |  | ALL |  |  |  | 4 | 1.1 |  |  |  | 4.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046811&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046811 | Trans Pwr Supply Renewal - Not Req | ST007550-12 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | LAKE VERMONT JUNCTION SER | LAKE VERMONT JUNCTION SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 87.017 | 87.017 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046804&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046804 | Trans Pwr Supply Renewal - Not Req | ST007050-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | MILLENNIUM JUNCTION SER | MILLENNIUM JUNCTION SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 16.57 | 16.57 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046800&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046800 | Trans Pwr Supply Renewal - Not Req | GA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | SOUTH WALKER JUNCTION CER | SOUTH WALKER JUNCTION CER | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 127.48 | 127.48 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046801&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046801 | Trans Pwr Supply Renewal - Not Req | GA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | VILLAFRANCA TSC | VILLAFRANCA TSC | 220.507 | KM |  | 0 |  | 0 | [5 empty] | 44.967 | 44.967 |  | ALL |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046799&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046799 | Trans Pwr Supply Renewal - Not Req | ST004060-42 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | SITES | 44000 | Goonyella | YUKAN SER | YUKAN SER | 0 | KM | GA01ML28 | 0.806 | GA01ML28 | 0.806 | KM |  |  |  |  | 28.8 | 28.8 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630