https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046733&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046733 | Trans Pwr Supply Renewal - Not Req | ST005260-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL |  | UNIT |  | Moura | ANNANDALE-DUMGREE | ANNANDALE-DUMGREE | 0 | KM | MA01ML112 | 0 | MA01ML112 | 0 | KM |  |  |  |  | 112 | 112 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046734&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046734 | Trans Pwr Supply Renewal - Not Req | MA | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL |  | UNIT |  | Moura | DUMGREE | DUMGREE | 192.36 | KM |  | 0 |  | 0 | [5 empty] | 108.545 | 108.545 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046756&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046756 | Trans Pwr Supply Renewal - Not Req | ST007640-48 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 42000 | Goonyella | GRASSTREE TSC | GRASSTREE TSC | 0 | KM |  | 0 |  | 0 | [5 empty] | 9.6 | 9.6 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046949&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046949 | Trans Pwr Supply Renewal - Not Req | ST006740-01 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 42000 | Goonyella | MINDI ATS 111.1KM | MINDI ATS 111.1KM | 0 | KM |  | 0 |  | 0 | [5 empty] | 123.03 | 123.03 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046738&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046738 | Trans Pwr Supply Renewal - Not Req | ST004820-08 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 42000 | Goonyella | MINDI SER | MINDI SER | 0 | KM |  | 0 |  | 0 | [5 empty] | 120.45 | 120.45 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046736&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046736 | Trans Pwr Supply Renewal - Not Req | ST001950-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 42000 | Blackwater | TRYPHINIA | TRYPHINIA | 0 | KM |  | 0 |  | 0 | [5 empty] | 125.714 | 125.714 |  | ALL |  |  |  | 4 | 3.4 |  |  |  | 13.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046763&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046763 | Trans Pwr Supply Renewal - Not Req | ST007750-42 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL | 1 | UNIT | 42000 | Blackwater | WESTWOOD TSC | WESTWOOD TSC | 0 | KM |  | 0 |  | 0 | [5 empty] | 48.069 | 48.069 | [5 empty] | 4 | 3.4 |  |  |  | 13.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | MEDIUM | LOW | Outstanding notification | NWSC INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046759&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046759 | Trans Pwr Supply Renewal - Not Req | ST008120-06 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL |  | UNIT |  | Goonyella | WOTONGA SER2 | WOTONGA SER2 | 0 | KM | GA01ML176 | 0.8 | GA01ML176 | 0.8 | KM |  |  |  |  | 176.8 | 176.8 | [5 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046909&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046909 | Trans Pwr Supply Renewal - Not Req | ST003880-20 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL MINOR | 1 | UNIT | 31923 | Goonyella | BALOOK SER | BALOOK SER | 0 | KM | GA01ML74 | 0.63 | GA01ML74 | 0.63 | KM |  |  |  |  | 74.63 | 74.63 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046908&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046908 | Trans Pwr Supply Renewal - Not Req | ST003910-24 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL MINOR | 1 | UNIT | 31923 | Goonyella | BLACK MOUNTAIN SER | BLACK MOUNTAIN SER | 0 | KM | GA01ML40 | 0.936 | GA01ML40 | 0.936 | KM |  |  |  |  | 40.936 | 40.936 |  | ALL |  |  |  | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046913&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046913 | Trans Pwr Supply Renewal - Not Req | ST006300-03 | CONTROL SYSTEMS | TRANSMISSION | POWER SUPPLY | RENEWAL MINOR | 1 | UNIT | 31739 | Blackwater | MARMOR CER | MARMOR CER | 0 | KM |  | 0 |  | 0 | [5 empty] | 597.726 | 597.726 |  | ALL |  |  |  | 4 | 4.1 |  |  |  | 16.4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | LOW | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085260&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000085260 | CS Battery Renewal BW Duplicate | BW | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 8 | SITE | 100000 | Blackwater |  |  | 633.538 | KM |  | 0 |  | 0 | [22 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085261&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000085261 | CS Battery Renewal GA Duplicate | GA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 8 | SITE | 100000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [22 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085263&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000085263 | CS Battery Renewal MA Duplicate | MA | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 2 | SITE | 25000 | Moura |  |  | 192.36 | KM |  | 0 |  | 0 | [22 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000085262&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000085262 | CS Battery Renewal NL Duplicate | NL | CONTROL SYSTEMS | TRANSMISSION | TELE BATTERY | RENEWAL | 2 | SITE | 25000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [22 empty] | LIKE FOR LIKE |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046779&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046779 | Trans Tetra Radio Cov Renew - Not Req | ST005170 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL | 1 | SITE | 90000 | Blackwater | KABRA |  | 0 | KM | BW03ML13 | 0.5799 | BW03ML13 | 0.5799 | KM | [11 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | LOW | Outstanding notification | RRIG INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046777&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046777 | Trans Tetra Radio Cov Renew - Not Req | ST004440 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL | 1 | SITE | 90000 | Blackwater | WESTWOOD |  | 0 | KM | BW03ML46 | 0.6939 | BW03ML46 | 0.6939 | KM | [11 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | MEDIUM |  | MEDIUM | LOW | Outstanding notification | RRIG INIF |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046819&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046819 | Trans Tetra Radio Cov Renew - Not Req | ST009870 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL | 1 | SITES | 95000 | Newlands | BYERWEN | BYERWEN | 0 | KM |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | ALL |  |  |  | 4 | 1.2 |  |  |  | 4.8 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046818&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | NON-COAL | 002000046818 | Trans Tetra Radio Cov Renew - Not Req | ST006090 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL | 1 | SITES | 95000 | Blackwater | COMET | COMET | 0 | KM |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | ALL |  |  |  | 4 | 1.65 |  |  |  | 6.6 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046817&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046817 | Trans Tetra Radio Cov Renew - Not Req | ST008560 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL | 1 | SITES | 95000 | Goonyella | MILLENIUM | MILLENIUM | 0 | KM |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | ALL |  |  |  | 4 | 1.5 |  |  |  | 6 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS |  |  |  |  | Outstanding notification | NWSC |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000046925&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000046925 | Trans Tetra Strengthening - Not Req | ST006170 | CONTROL SYSTEMS | TRANSMISSION | TETRA RADIO COVERAGE | RENEWAL MINOR | 1 | UNIT | 740588 | Blackwater | HAY POINT | HAY POINT | 0 | KM | BW12ML10 | -0.1799 | BW12ML10 | -0.1799 | KM |  |  |  |  | 3.147 | 3.147 |  | ALL |  |  |  | 4 | 1 |  |  |  | 4 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | LOW | MEDIUM | Outstanding notification | SCPR |  | 20350630
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075237&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075237 | GA SYSTEM TETRA WORKS - Not Req | GA | CONTROL SYSTEMS | TRANSMISSION | TETRA SYSTEM | RENEWAL | 1 | SITE | 84000 | Goonyella |  |  | 220.507 | KM |  | 0 |  | 0 | [12 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | HIGH | MEDIUM | Outstanding notification | RRIG |  | 20350630 | * 30.03.2021 09:34:51 AUSQLD Scott Andrews (R003573) * SINGLE CARRIER TETRA BASE TO ELIMINATE COGESTION. LOCATION DETERMINED IN MAY 2022.
https://is1.aurizon.com.au/sap/bc/gui/sap/its/webgui?sap-language=EN&sap-client=600&~transaction=IW28%20QMNUM-LOW=002000075219&DY_MAB=X&~OKCODE=ONLI | MAJOR-2035-000001 |  |  | COAL | 002000075219 | NL SYSTEM TETRA WORKS - Not Req | NL | CONTROL SYSTEMS | TRANSMISSION | TETRA SYSTEM | RENEWAL | 1 | SITE | 84000 | Newlands |  |  | 214.038 | KM |  | 0 |  | 0 | [12 empty] | 4 | 4 |  |  |  | 16 |  |  |  |  | STD DESIGN W/ BESPOKE ELEMENTS | LOW |  | HIGH | MEDIUM | Outstanding notification | RRIG |  | 20350630 | * 29.03.2021 21:15:11 AUSQLD Scott Andrews (R003573) * SINGLE CARRIER TETRA BASE TO ELIMINATE CONGESTION. LOCATION DETERMINED IN MAY 2022
Total | [11 empty] | 871578.907 |  | 2307678115 |  |  |  | 7399319.6569 |  |  | 2870804.5196 |  | 2379050.0225 | [12 empty] | 18077.11 | 12861.2 |  |  |  | 94694.92
No filters applied